## Sheet1
1. Time, Milestones, and Sequencing (The Core Schedul
Information Needed | Why It's Critical for Planning
Sectional Completion Dates | Buildings are often handed over in phases (e.g., Podium/Retail, Residential Floors, Amenities). Each phase requires a separate, strict schedule constraint.
"Dry-In" or "Envelope Completion" Date | This milestone dictates when internal trades (MEP, finishes) can safely start. Often linked to the roof and facade completion.
Vertical Access Plan | Specifics on when cranes, hoists, and elevators must be ready for use, and any restrictions on their operation or removal.
Commissioning & Testing Duration | Detailed time allowance for crucial activities like fire system testing, integrated building management systems (IBMS), and equipment run-in periods.
Permit & Approval Deadlines | Contractual requirements for when specific permits (e.g., Fire NOC, Occupancy Certificate) must be secured, often driven by the client or authority.
2. Logistical and Site Constraints (The Execution Plan)
Information Needed | Why It's Critical for Planning
Laydown Area / Storage Limits | Drawings or clauses defining the amount of space available for material storage and fabrication. Highly restrictive in dense urban areas.
Access Gates & Hour Restrictions | Specific routes and times for truck access/delivery. Public buildings often have restricted hours near schools or residential areas.
Noise & Vibration Limits | Clauses defining permissible construction noise levels and times. Directly impacts your ability to schedule piling, heavy machinery use, and night shifts.
Hoisting/Crane Capacity Requirements | Minimum number, type, and lifting capacity requirements for tower cranes and hoists. Must be scheduled for installation, operation, and dismantling.
Waste Management Protocols | Specifics on how and when construction debris must be removed, which affects material movement and site cleanliness activities.
3. Commercial, Risk, and Claims Management
Information Needed | Why It's Critical for Planning
Milestone Payment Triggers | The exact definition of a payment milestone (e.g., "50% of concrete complete," "Roofing substantially installed"). This links schedule progress to cash flow.
Weather Days Methodology | The specific number of typical weather days assumed per month or year (e.g., 5 days of rain in July). This is the baseline for claiming weather-related EOT.
RFI / Change Order Response Time | Contractual window for the Client/Engineer to respond to a Request for Information (RFI) or a Change Order submission (e.g., "7 working days"). This time must be added to your design and procurement activities.
Warranty/Defect Correction Period | Time allowed for the contractor to rectify minor defects found during pre-handover inspections (punch lists).
Definition of "Substantial Completion" | The precise criteria that signal the project is ready for the client to occupy (e.g., all fire systems certified, 95% of finishes complete). This is the point where LDs usually cease.