## WBS
wbs_code | wbs_name | parent_wbs_id
1.1 | Contract Mobilization & Site Establishment | 1
1.2 | Project Controls (Planning, Cost, Document Control) | 1
1.3 | Engineering Management & Design Coordination | 1
1.4 | Quality, Health, Safety & Environment (QHSE) Management | 1
2.1 | Surveys (Topographical, Geotechnical) & Investigations | 2
2.2 | Detailed Design - Viaduct & Associated Structures | 2
2.3 | Detailed Design - Elevated Stations | 2
2.4 | Detailed Design - New Depot | 2
2.5 | GFC (Good for Construction) Drawing Submissions | 2
3.1 | Long Lead Item Procurement (Bearings, Girders, etc.) | 3
3.2 | Right of Way (ROW) Support & Site Clearance | 3
3.3 | Utility Diversion & Shifting | 3
4.1 | Substructure Works (Piling, Pile Caps, Piers) | 4
4.2 | Superstructure Works (Segment Casting & Erection) | 4
4.3 | Special Spans & Ramps (Steel Girders, ROB/RUB) | 4
4.4 | Viaduct Finishing Works | 4
5.1 | Whitefield Station Construction | 5
5.2 | K.R. Puram Station Construction | 5
5.3 | Central Station Construction | 5
6.1 | Earthworks, Formation & Drainage | 6
6.2 | Depot Buildings & Workshop Structures | 6
6.3 | Internal Roads & Ancillary Works | 6
7.1 | Interface with System Contractors (Track, Power, Signaling) | 7
7.2 | Testing, Commissioning Support & Handover | 7
7.3 | As-Built Documentation & Contract Demobilization | 7

## TASK
task_code | task_name | wbs_code | target_drtn_hr_cnt | task_type
A1000 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A1010 | Receive Notice to Proceed (NTP) / Letter of Acceptance (LOA) | N/A | 0 | TT_FinMile
A1020 | Submit Contractual Guarantees (Performance Bond, Advance Payment Guarantee) | N/A | 0 | TT_FinMile
A1030 | Submit Required Insurance Policies for Approval | N/A | 5 | TT_Task
A1040 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A1050 | Project Controls - Setup & Baseline Phase** | N/A | 20 | TT_Task
A1060 | Develop and Finalise Project Controls Plan | N/A | 10 | TT_Task
A1070 | Establish Work Breakdown Structure (WBS) and Organisational Breakdown Structure (OBS) | N/A | 10 | TT_Task
A1080 | Develop and Agree on Project Calendars | N/A | 10 | TT_Task
A1090 | Set up Document Management System (e.g., Aconex, ProjectWise) | N/A | 10 | TT_Task
A1100 | Establish Document Control Procedures and Numbering System | N/A | 10 | TT_Task
A1110 | Set up Cost Management and Planning Systems (e.g., P6, Prism, SAP) | N/A | 20 | TT_Task
A1120 | Develop Detailed Level 4 Baseline Programme | N/A | 20 | TT_Task
A1130 | Resource and Cost Load the Baseline Programme | N/A | 10 | TT_Task
A1140 | Conduct Baseline Programme Review and Validation Workshop | N/A | 1 | TT_Task
A1150 | Submit Baseline Programme for Approval | N/A | 0 | TT_FinMile
A1160 | Milestone: Baseline Programme Approved** | N/A | 0 | TT_FinMile
A1170 | Establish Performance Measurement Baseline (PMB) for Cost & Schedule | N/A | 0 | TT_FinMile
A1180 | Establish Change Management and Variation Control Procedure | N/A | 10 | TT_Task
A1190 | Project Controls - Execution, Monitoring & Control Phase (Level of Effort)** | N/A | 0 | TT_LOE
A1200 | Perform Weekly Planning & Progress Update Cycle | N/A | 0 | TT_LOE
A1210 | Prepare and Issue 4-Week Lookahead Programmes | N/A | 0 | TT_LOE
A1220 | Prepare and Issue Monthly Progress Report (including S-Curves, CPI/SPI) | N/A | 0 | TT_LOE
A1230 | Conduct Monthly Progress and Commercial Review Meetings | N/A | 0 | TT_LOE
A1240 | Manage and Process Change Orders / Variations | N/A | 0 | TT_LOE
A1250 | Maintain Programme Revisions and incorporate Approved Changes | N/A | 0 | TT_LOE
A1260 | Perform Earned Value Management (EVM) Analysis | N/A | 0 | TT_LOE
A1270 | Maintain and Update Project Cost Forecast (Estimate at Completion - EAC) | N/A | 0 | TT_LOE
A1280 | Ongoing Management of Document Submittals and Transmittals | N/A | 0 | TT_LOE
A1290 | Process and Distribute Requests for Information (RFIs) and Site Instructions | N/A | 0 | TT_LOE
A1300 | Maintain Master Document Register (MDR) | N/A | 0 | TT_LOE
A1310 | Project Controls - Closeout Phase** | N/A | 0 | TT_LOE
A1320 | Develop and Manage Commissioning & Handover Programme | N/A | 0 | TT_LOE
A1330 | Compile and Submit Final As-Built Documentation | N/A | 10 | TT_Task
A1340 | Compile and Submit Final Handover Documentation (O&M Manuals) | N/A | 15 | TT_Task
A1350 | Prepare and Agree on Final Account Submission | N/A | 20 | TT_Task
A1360 | Prepare Final Project Controls Report (including Lessons Learned) | N/A | 10 | TT_Task
A1370 | Archive all Project Documentation and Data | N/A | 10 | TT_Task
A1380 | Milestone: Project Controls Closeout Complete** | N/A | 0 | TT_FinMile
A1390 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A1400 | Design Initiation & Planning** | N/A | 10 | TT_Task
A1410 | Develop and Finalise Engineering Management Plan (EMP) | N/A | 15 | TT_Task
A1420 | Establish Design Deliverables Register and Schedule | N/A | 10 | TT_Task
A1430 | Mobilise Design Management & Coordination Team | N/A | 15 | TT_Task
A1440 | Conduct Project Design Kick-Off Meeting with all Disciplines | N/A | 0 | TT_FinMile
A1450 | Finalise and Approve Basis of Design (BOD) Document | N/A | 10 | TT_Task
A1460 | Preliminary / 30% Design Stage** | N/A | 60 | TT_Task
A1470 | Prepare and Issue 30% Preliminary Design Package for Internal Review | N/A | 20 | TT_Task
A1480 | Conduct Inter-Disciplinary Coordination & Clash Review for 30% Design | N/A | 5 | TT_Task
A1490 | Submit 30% Preliminary Design Package to Client for Review & Comment | N/A | 0 | TT_FinMile
A1500 | Incorporate Client Comments into Design | N/A | 5 | TT_Task
A1510 | Achieve Milestone: Client Approval of 30% Preliminary Design | N/A | 0 | TT_FinMile
A1520 | Detailed / 60% Design Stage** | N/A | 60 | TT_Task
A1530 | Prepare and Issue 60% Detailed Design Package for Internal Review | N/A | 10 | TT_Task
A1540 | Conduct Inter-Disciplinary Coordination & Clash Review for 60% Design | N/A | 10 | TT_Task
A1550 | Submit 60% Detailed Design Package to Client for Review & Comment | N/A | 0 | TT_FinMile
A1560 | Incorporate Client Comments into Design | N/A | 5 | TT_Task
A1570 | Achieve Milestone: Client Approval of 60% Detailed Design | N/A | 0 | TT_FinMile
A1580 | Prepare and Issue 90% Pre-Final Design Package for Internal Review | N/A | 10 | TT_Task
A1590 | Conduct Final Inter-Disciplinary Coordination & Clash Detection | N/A | 10 | TT_Task
A1600 | Submit 90% Pre-Final Design Package to Client for Final Review | N/A | 0 | TT_FinMile
A1610 | Incorporate Final Client Comments into Design | N/A | 5 | TT_Task
A1620 | Achieve Milestone: Client Approval of 90% Pre-Final Design | N/A | 0 | TT_FinMile
A1630 | Prepare and Issue 100% Issued for Construction (IFC) Drawings & Specifications | N/A | 5 | TT_Task
A1640 | Perform Final Quality Assurance / Quality Control (QA/QC) on IFC Package | N/A | 10 | TT_Task
A1650 | Submit IFC Package for Statutory / Authority Approvals | N/A | 0 | TT_FinMile
A1660 | Achieve Milestone: Receive all Required Authority Approvals | N/A | 0 | TT_FinMile
A1670 | Manage and Track Design Progress & Performance | N/A | 0 | TT_LOE
A1680 | Conduct Weekly Design Coordination Meetings | N/A | 0 | TT_LOE
A1690 | Manage Design Interface between Disciplines (Arch, Struc, MEP, etc.) | N/A | 0 | TT_LOE
A1700 | Manage and Control Design Changes and Variations | N/A | 0 | TT_LOE
A1710 | Manage Document Control and Transmittals | N/A | 0 | TT_LOE
A1720 | Provide Technical Support during Procurement & Tendering Phase | N/A | 0 | TT_LOE
A1730 | Review and Approve Contractor Technical Submittals and Shop Drawings | N/A | 10 | TT_Task
A1740 | Manage and Respond to Site Technical Queries (TQs) / Requests for Information (RFIs) | N/A | 0 | TT_LOE
A1750 | Review and Incorporate Red-Line Markups for As-Built Records | N/A | 10 | TT_Task
A1760 | Prepare and Submit Final As-Built Drawings and Documentation | N/A | 30 | TT_Task
A1770 | Compile and Issue Final Design Handover and Closeout Report | N/A | 10 | TT_Task
A1780 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A1790 | Develop Overall Project QHSE Management Plan | N/A | 15 | TT_Task
A1800 | Develop Project-Specific Health & Safety (H&S) Plan | N/A | 10 | TT_Task
A1810 | Develop Project-Specific Environmental Management Plan | N/A | 15 | TT_Task
A1820 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A1830 | Develop and Finalise Scope of Work (SOW) for Survey & Investigation Package | N/A | 10 | TT_Task
A1840 | Procure and Appoint Specialist Survey Subcontractor | N/A | 30 | TT_Task
A1850 | Submit and Approve Method Statements & Risk Assessments (RAMS) for Survey Works | N/A | 10 | TT_Task
A1860 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A1870 | Design Management & Initiation** | N/A | 0 | TT_LOE
A1880 | Mobilize Detailed Design Team & Hold Kick-Off Meeting | N/A | 5 | TT_Task
A1890 | Review and Finalize Basis of Design (BOD) Document | N/A | 10 | TT_Task
A1900 | Compile and Review All Input Data (Geotechnical Reports, Surveys, Preliminary Design) | N/A | 10 | TT_Task
A1910 | Develop and Approve Detailed Design Execution Plan & Schedule | N/A | 20 | TT_Task
A1920 | Global Structural Analysis & Modeling** | N/A | 30 | TT_Task
A1930 | Develop 3D Global Structural Analysis Model (e.g., Midas, SAP2000) | N/A | 20 | TT_Task
A1940 | Define and Apply All Load Cases (Dead, Live, Wind, Seismic, Thermal) | N/A | 10 | TT_Task
A1950 | Run Global Structural Analysis and Extract Member Forces | N/A | 5 | TT_Task
A1960 | Prepare and Submit Global Structural Analysis Report for Review | N/A | 10 | TT_Task
A1970 | Detailed Substructure Design** | N/A | 60 | TT_Task
A1980 | Perform Detailed Design of Foundations (Piles / Pile Caps / Rafts) | N/A | 30 | TT_Task
A1990 | Perform Detailed Design of Viaduct Piers and Pier Caps | N/A | 30 | TT_Task
A2000 | Perform Detailed Design of Abutments and Wing Walls | N/A | 15 | TT_Task
A2010 | Perform Detailed Design of Viaduct Deck / Girders (Precast or Cast-in-Situ) | N/A | 60 | TT_Task
A2020 | Design and Specify Structural Bearings | N/A | 15 | TT_Task
A2030 | Design Pier Head Pedestals and Seismic Arrestors/Restrainers | N/A | 30 | TT_Task
A2040 | Design Expansion Joints and End-Diaphragms | N/A | 15 | TT_Task
A2050 | Design of Associated Retaining Walls and Embankments | N/A | 30 | TT_Task
A2060 | Integrate and Design Structural Elements for Drainage System | N/A | 15 | TT_Task
A2070 | Coordinate and Finalize Design for MEP/Systems Embedments (Conduits, Lighting) | N/A | 0 | TT_LOE
A2080 | Develop and Finalize Architectural Finishes and Cladding Details | N/A | 30 | TT_Task
A2090 | Produce General Arrangement (GA) Drawings | N/A | 15 | TT_Task
A2100 | Produce Formwork and Reinforcement Drawings for Foundations | N/A | 15 | TT_Task
A2110 | Produce Formwork and Reinforcement Drawings for Piers and Abutments | N/A | 30 | TT_Task
A2120 | Produce Formwork and Reinforcement Drawings for Superstructure Deck/Girders | N/A | 15 | TT_Task
A2130 | Produce Detail Drawings for Bearings, Pedestals, and Seismic Arrestors | N/A | 20 | TT_Task
A2140 | Prepare Detailed Bill of Quantities (BoQ) | N/A | 15 | TT_Task
A2150 | Prepare Technical Specifications for Materials and Workmanship | N/A | 15 | TT_Task
A2160 | Conduct Internal Structural Design Review and Verification (Checker) | N/A | 10 | TT_Task
A2170 | Issue Design Packages for Inter-Disciplinary Check (IDC) | N/A | 0 | TT_FinMile
A2180 | Incorporate Comments from IDC Review Cycle | N/A | 5 | TT_Task
A2190 | Compile and Submit Full Design Package for "Issued for Approval" (IFA) | N/A | 5 | TT_Task
A2200 | Receive and Review Comments from Client/Engineer | N/A | 5 | TT_Task
A2210 | Incorporate Final Comments and Revise Drawings & Documents | N/A | 5 | TT_Task
A2220 | Submit Final Design Package for "Issued for Construction" (IFC) Status | N/A | 0 | TT_FinMile
A2230 | Archive Final Design Deliverables | N/A | 5 | TT_Task
A2240 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A2250 | Design Initiation & Basis of Design** | N/A | 10 | TT_Task
A2260 | Conduct Detailed Design Kick-Off Meeting | N/A | 0 | TT_FinMile
A2270 | Gather and Review all Input Data (Geotechnical Reports, Topographical Surveys, Concept Design) | N/A | 10 | TT_Task
A2280 | Develop and Finalize the "Basis of Design" Document | N/A | 30 | TT_Task
A2290 | Establish BIM Execution Plan (BEP) and Common Data Environment (CDE) | N/A | 20 | TT_Task
A2300 | Architectural Detailed Design** | N/A | 60 | TT_Task
A2310 | Develop Detailed General Arrangement (GA) Plans, Sections, and Elevations | N/A | 20 | TT_Task
A2320 | Develop 3D Architectural Model | N/A | 20 | TT_Task
A2330 | Finalize Architectural Finishes Schedule and Material Selection | N/A | 10 | TT_Task
A2340 | Prepare Detailed Drawings for Facade, Roofing, and Internal Partitions | N/A | 30 | TT_Task
A2350 | Prepare Door, Window, and Hardware Schedules | N/A | 10 | TT_Task
A2360 | Structural Detailed Design** | N/A | 90 | TT_Task
A2370 | Develop Structural Framing System and 3D Structural Model | N/A | 40 | TT_Task
A2380 | Perform Detailed Structural Analysis and Calculations (Static, Dynamic, Seismic) | N/A | 20 | TT_Task
A2390 | Detailed Design of Substructure (Foundations, Piles, Pile Caps) | N/A | 30 | TT_Task
A2400 | Detailed Design of Superstructure (Columns, Beams, Slabs, Station Box) | N/A | 90 | TT_Task
A2410 | Detailed Design of Specialized Structural Components (e.g., Bearing **Pedestals, Seismic Arrestors**) | N/A | 30 | TT_Task
A2420 | Prepare Structural Reinforcement Drawings and Bar Bending Schedules | N/A | 15 | TT_Task
A2430 | Detailed Design of HVAC System, including Ducting and Plant Room Layouts | N/A | 45 | TT_Task
A2440 | Detailed Design of Electrical Systems (Power, Lighting, Cable Containment, Earthing) | N/A | 45 | TT_Task
A2450 | Detailed Design of Plumbing, Drainage, and Sanitary Systems | N/A | 30 | TT_Task
A2460 | Detailed Design of Fire Protection and Life Safety Systems (Sprinklers, Alarms, Smoke Extract) | N/A | 30 | TT_Task
A2470 | Detailed Design of Station ELV Systems (CCTV, PA, Access Control, Comms) | N/A | 45 | TT_Task
A2480 | Develop Coordinated 3D MEP Models | N/A | 30 | TT_Task
A2490 | Conduct Weekly Inter-Disciplinary Coordination (IDC) Workshops | N/A | 0 | TT_LOE
A2500 | Perform BIM Clash Detection, Analysis, and Resolution | N/A | 0 | TT_LOE
A2510 | Update and Maintain Federated BIM Model | N/A | 0 | TT_LOE
A2520 | Prepare and Consolidate 60% Detailed Design Submission Package | N/A | 20 | TT_Task
A2530 | Conduct Internal QA/QC and Peer Review of 60% Design Package | N/A | 10 | TT_Task
A2540 | Submit 60% Design Package for Client / Authority Review | N/A | 0 | TT_FinMile
A2550 | Receive and Incorporate Comments on 60% Design Submission | N/A | 1 | TT_Task
A2560 | Prepare and Consolidate 90% (Pre-Final) Design Submission Package | N/A | 5 | TT_Task
A2570 | Conduct Internal QA/QC and Peer Review of 90% Design Package | N/A | 10 | TT_Task
A2580 | Submit 90% Design Package for Client / Authority Review | N/A | 0 | TT_FinMile
A2590 | Receive and Incorporate Final Comments on 90% Design Submission | N/A | 10 | TT_Task
A2600 | Finalize all Design Calculations and Technical Specifications | N/A | 0 | TT_FinMile
A2610 | Prepare Final Bill of Quantities (BOQ) and Cost Estimates | N/A | 15 | TT_Task
A2620 | Prepare and Issue "Issued for Construction" (IFC) Drawing Package | N/A | 5 | TT_Task
A2630 | Compile and Submit Final Design Report | N/A | 5 | TT_Task
A2640 | Archive Final Design Deliverables | N/A | 10 | TT_Task
A2650 | Design Management and Progress Reporting (Level of Effort) | N/A | 0 | TT_LOE
A2660 | Analysis:** The target WBS is "2.4 Detailed Design - New Depot". This is a design-phase WBS, not a construction one. The provided context ("Pedestal & Seismic arrestors") is a specific construction activity and is therefore not relevant to the design process. As a Senior Planner, I will generate a logical sequence of design activities from scratch, covering the typical lifecycle from design kick-off to the issuance of construction documents. | N/A | 30 | TT_Task
A2670 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A2680 | Design Management & Mobilization** | N/A | 60 | TT_Task
A2690 | Detailed Design Kick-Off Meeting | N/A | 0 | TT_FinMile
A2700 | Establish Design Management Plan & Procedures | N/A | 10 | TT_Task
A2710 | Mobilize Multi-Disciplinary Design Team | N/A | 10 | TT_Task
A2720 | Review and Finalize Basis of Design (BoD) | N/A | 10 | TT_Task
A2730 | Review and Incorporate Preliminary/Concept Design Feedback | N/A | 10 | TT_Task
A2740 | Site Investigation & Data Collection** | N/A | 15 | TT_Task
A2750 | Conduct Detailed Topographical Survey of Depot Site | N/A | 13 | TT_Task
A2760 | Conduct Geotechnical Investigations & Soil Analysis | N/A | 134 | TT_Task
A2770 | Finalize Geotechnical Investigation Report | N/A | 5 | TT_Task
A2780 | Identify and Survey Existing Utilities and Services | N/A | 150 | TT_Task
A2790 | Schematic Design Development (30% Submission)** | N/A | 45 | TT_Task
A2800 | Develop 30% Architectural Design Package (Layouts, Elevations) | N/A | 30 | TT_Task
A2810 | Develop 30% Civil & Structural Design Package (Grading, Foundation Concepts) | N/A | 30 | TT_Task
A2820 | Develop 30% MEP & Utilities Design Package (System Schematics) | N/A | 30 | TT_Task
A2830 | Develop 30% Depot Specialist Systems Design (Track Layout, Maintenance Bays) | N/A | 30 | TT_Task
A2840 | Conduct Inter-Disciplinary Design Coordination & Review (30%) | N/A | 10 | TT_Task
A2850 | Submit 30% Design Package for Client Review | N/A | 0 | TT_FinMile
A2860 | Incorporate Client Feedback on 30% Design | N/A | 10 | TT_Task
A2870 | Develop 60% Architectural Design Package (Detailed Plans, Sections) | N/A | 60 | TT_Task
A2880 | Develop 60% Civil & Structural Design Package (Structural Framing, Drainage) | N/A | 30 | TT_Task
A2890 | Develop 60% MEP & Utilities Design Package (Equipment Sizing, Duct/Pipe Routing) | N/A | 40 | TT_Task
A2900 | Develop 60% Depot Specialist Systems Design (Signaling, OCS, Equipment Specs) | N/A | 40 | TT_Task
A2910 | Perform BIM Model Integration and Clash Detection | N/A | 0 | TT_LOE
A2920 | Conduct Inter-Disciplinary Design Coordination & Review (60%) | N/A | 0 | TT_LOE
A2930 | Submit 60% Design Package for Client Review | N/A | 0 | TT_FinMile
A2940 | Incorporate Client Feedback on 60% Design | N/A | 10 | TT_Task
A2950 | Develop 90% Architectural Design Package (Finishes, Detailing) | N/A | 30 | TT_Task
A2960 | Develop 90% Civil & Structural Design Package (Reinforcement Details, Calculations) | N/A | 30 | TT_Task
A2970 | Develop 90% MEP & Utilities Design Package (Final Layouts, Control Schematics) | N/A | 30 | TT_Task
A2980 | Develop 90% Depot Specialist Systems Design (Final Schematics, Interface Details) | N/A | 60 | TT_Task
A2990 | Prepare Draft Technical Specifications for all Disciplines | N/A | 30 | TT_Task
A3000 | Prepare Draft Bill of Quantities (BoQ) | N/A | 15 | TT_Task
A3010 | Submit 90% Design Package for Client and Authority for Approval (AFA) Review | N/A | 0 | TT_FinMile
A3020 | Incorporate Final Comments from Client and Authorities | N/A | 5 | TT_Task
A3030 | Finalize Architectural Issued for Construction (IFC) Drawings | N/A | 0 | TT_FinMile
A3040 | Finalize Civil & Structural IFC Drawings & Calculations | N/A | 10 | TT_Task
A3050 | Finalize MEP & Utilities IFC Drawings | N/A | 10 | TT_Task
A3060 | Finalize Depot Specialist Systems IFC Drawings | N/A | 10 | TT_Task
A3070 | Finalize all Technical Specifications | N/A | 10 | TT_Task
A3080 | Finalize Bill of Quantities (BoQ) | N/A | 10 | TT_Task
A3090 | Compile and Issue Complete IFC Design Package | N/A | 5 | TT_Task
A3100 | Provide Technical Support during Tender Period | N/A | 0 | TT_LOE
A3110 | Archive Final Design Documents | N/A | 5 | TT_Task
A3120 | Detailed Design Phase Close-Out Report | N/A | 0 | TT_FinMile
A3130 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A3140 | Commence GFC Drawing Production Phase (Milestone)** | N/A | 0 | TT_FinMile
A3150 | Establish and Maintain Master Drawing Submission Register** | N/A | 0 | TT_LOE
A3160 | Prepare & Submit Civil & Site Works GFC Drawings** | N/A | 20 | TT_Task
A3170 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A3180 | Finalize Technical Specifications & Bill of Quantities (BOQ) for all Long Lead Items | N/A | 10 | TT_Task
A3190 | Prepare and Compile Tender / Request for Quotation (RFQ) Documents | N/A | 15 | TT_Task
A3200 | Issue Tender/RFQ to Prequalified Suppliers | N/A | 0 | TT_FinMile
A3210 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A3220 | Conduct Topographical and Cadastral Surveys to Define ROW Limits** | N/A | 13 | TT_Task
A3230 | Prepare and Submit ROW Acquisition Plans and Legal Documents** | N/A | 30 | TT_Task
A3240 | Obtain Environmental Clearance and Permits for Site Activities** | N/A | 120 | TT_Task
A3250 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A3260 | WBS: 3.3 Utility Diversion & Shifting** | N/A | 150 | TT_Task
A3270 | Phase 1: Pre-Construction & Enabling Works** | N/A | 0 | TT_LOE
A3280 | Obtain and Review Existing Utility Record Drawings (As-Builts) | N/A | 10 | TT_Task
A3290 | Perform GPR (Ground Penetrating Radar) & CAT Scans to Survey for Unknown Utilities | N/A | 30 | TT_Task
A3300 | Engage and Coordinate with all Relevant Utility Authorities (Power, Water, Telecom, Gas, etc.) | N/A | 0 | TT_LOE
A3310 | Phase 2: Installation of New Utility Corridors** | N/A | 200 | TT_Task
A3320 | Phase 3: Live Diversion, Connection & Commissioning** | N/A | 150 | TT_Task
A3330 | Phase 4: Decommissioning & Reinstatement** | N/A | 34 | TT_Task
A3340 | Phase 5: Handover** | N/A | 0 | TT_FinMile
A3350 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A3360 | Mobilization & Site Preparation** | N/A | 25 | TT_Task
A3370 | Mobilize Piling Rig, Equipment, and Personnel to Work Area | N/A | 100 | TT_Task
A3380 | Survey and Set Out for Pile Locations | N/A | 100 | TT_Task
A3390 | Construct Piling Platform and Access Routes | N/A | 100 | TT_Task
A3400 | Piling Works** | N/A | 1 | TT_Task
A3410 | Bore/Drive Piles to Designed Depth | N/A | 900 | TT_Task
A3420 | Fabricate and Install Pile Reinforcement Cages | N/A | 2334 | TT_Task
A3430 | Pour Concrete for Piles | N/A | 278 | TT_Task
A3440 | Allow for Concrete Curing Time for Piles | N/A | 278 | TT_Task
A3450 | Conduct Pile Integrity Testing (PIT) and/or Static Load Tests | N/A | 2334 | TT_Task
A3460 | Trim/Break Pile Heads to Final Cut-off Level | N/A | 100 | TT_Task
A3470 | Pile Cap Construction** | N/A | 100 | TT_Task
A3480 | Excavate for Pile Caps | N/A | 100 | TT_Task
A3490 | Lay Blinding Concrete Layer | N/A | 120 | TT_Task
A3500 | Erect Formwork for Pile Caps | N/A | 200 | TT_Task
A3510 | Fix Reinforcement Steel for Pile Caps | N/A | 1400 | TT_Task
A3520 | Pour Concrete for Pile Caps | N/A | 150 | TT_Task
A3530 | Allow for Concrete Curing Time for Pile Caps | N/A | 7 | TT_Task
A3540 | Strip Formwork from Pile Caps | N/A | 200 | TT_Task
A3550 | Apply Waterproofing/Protective Coating to Pile Caps | N/A | 150 | TT_Task
A3560 | Backfill and Compact around Completed Pile Caps | N/A | 100 | TT_Task
A3570 | Fix Pier Starter Bars into Pile Cap | N/A | 150 | TT_Task
A3580 | Erect Formwork and Falsework for Piers (Lift 1) | N/A | 450 | TT_Task
A3590 | Fix Reinforcement Steel for Piers (Lift 1) | N/A | 1800 | TT_Task
A3600 | Pour Concrete for Piers (Lift 1) | N/A | 267 | TT_Task
A3610 | Cure and Strip Formwork for Pier (Lift 1) | N/A | 267 | TT_Task
A3620 | Repeat Formwork, Rebar, and Concrete Cycle for Subsequent Pier Lifts | N/A | 267 | TT_Task
A3630 | Construct Pier Head/Crosshead (Formwork, Rebar, Concrete) | N/A | 267 | TT_Task
A3640 | Cure and Strip Pier Head Formwork | N/A | 450 | TT_Task
A3650 | Grouting and Surface Preparation of Pier Head | N/A | 450 | TT_Task
A3660 | Install Bearings, Pedestals & Seismic Arrestors | N/A | 90 | TT_Task
A3670 | Final Survey, Inspection, and Handover of Substructure | N/A | 225 | TT_Task
A3680 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A3690 | WBS: 4.2 Superstructure Works (Segment Casting & Erection)** | N/A | 50 | TT_Task
A3700 | A. PREPARATION & MOBILIZATION** | N/A | 30 | TT_Task
A3710 | Submit & Approve Method Statements and Shop Drawings for Superstructure Works | N/A | 10 | TT_Task
A3720 | Establish & Commission Precast Segment Casting Yard | N/A | 3200 | TT_Task
A3730 | Procure & Deliver Raw Materials for Segment Casting (Reinforcement, Cement, PT etc.) | N/A | 90 | TT_Task
A3740 | B. PRECAST SEGMENT CASTING (CYCLICAL PROCESS)** | N/A | 1 | TT_Task
A3750 | C. ON-SITE ERECTION PREPARATION** | N/A | 300 | TT_Task
A3760 | D. SEGMENT ERECTION & INSTALLATION (CYCLICAL, PER SPAN)** | N/A | 300 | TT_Task
A3770 | E. FINISHING & COMPLETION WORKS** | N/A | 225 | TT_Task
A3780 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A3790 | WBS: 4.3 Special Spans & Ramps (Steel Girders, ROB/RUB)** | N/A | 0 | TT_LOE
A3800 | Engineering, Procurement & Fabrication** | N/A | 0 | TT_LOE
A3810 | Finalize & Approve Detailed Structural Designs & Shop Drawings | N/A | 20 | TT_Task
A3820 | Procure & Deliver Foundation Materials (Rebar, Piling Casings, Concrete) | N/A | 267 | TT_Task
A3830 | Fabricate Structural Steel Girders (Off-site) | N/A | 50 | TT_Task
A3840 | Apply Protective Coatings / Paint System to Girders at Fabrication Yard | N/A | 50 | TT_Task
A3850 | Factory Acceptance Testing (FAT) & Quality Inspection of Steel Girders | N/A | 50 | TT_Task
A3860 | Procure & Deliver Bearings, Pedestals, and Seismic Arrestors | N/A | 150 | TT_Task
A3870 | Procure & Deliver Decking Materials, Expansion Joints, and Parapets | N/A | 225 | TT_Task
A3880 | Arrange Logistics & Transportation for Oversized Girder Delivery to Site | N/A | 10 | TT_Task
A3890 | Enabling & Substructure Works** | N/A | 63 | TT_Task
A3900 | Site Survey, Setting Out, and Geotechnical Verification | N/A | 13 | TT_Task
A3910 | Implement Traffic Management Plan & Obtain Road/Rail Block Permissions | N/A | 25 | TT_Task
A3920 | Site Clearance, Grubbing, and Earthworks for Abutments & Piers | N/A | 267 | TT_Task
A3930 | Construct Piled Foundations for Abutments & Piers | N/A | 150 | TT_Task
A3940 | Construct Pile Caps for Abutments & Piers | N/A | 150 | TT_Task
A3950 | Construct Abutment Walls (Formwork, Rebar, Concrete Pour) | N/A | 125 | TT_Task
A3960 | Construct Pier Shafts (Formwork, Rebar, Concrete Pour) | N/A | 267 | TT_Task
A3970 | Construct Pier Caps / Abutment Seats (Formwork, Rebar, Concrete Pour) | N/A | 267 | TT_Task
A3980 | Cure Concrete Substructure & Strip Formwork | N/A | 120 | TT_Task
A3990 | Superstructure Erection** | N/A | 50 | TT_Task
A4000 | Prepare Girder Staging & Assembly Area | N/A | 50 | TT_Task
A4010 | Receive & Unload Steel Girders at Site | N/A | 50 | TT_Task
A4020 | Assemble Girder Segments on Ground (if required) | N/A | 50 | TT_Task
A4030 | Install Bearings, Pedestals & Seismic Arrestors on Pier Caps & Abutments | N/A | 90 | TT_Task
A4040 | Mobilize Heavy Lift Cranes / Launching Gantry | N/A | 400 | TT_Task
A4050 | Erect/Launch Main Steel Girders onto Bearings | N/A | 50 | TT_Task
A4060 | Install Diaphragms & Cross-Bracing between Girders | N/A | 50 | TT_Task
A4070 | Complete Bolting / Welding of All Steel Connections | N/A | 0 | TT_FinMile
A4080 | Conduct Survey & Alignment Checks of Erected Steel Superstructure | N/A | 50 | TT_Task
A4090 | Deck, Ramps & Finishes** | N/A | 267 | TT_Task
A4100 | Testing, Commissioning & Handover** | N/A | 225 | TT_Task
A4110 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A4120 | Mobilization & Preparatory Works** | N/A | 25 | TT_Task
A4130 | Mobilize personnel, plant, and materials to the viaduct deck. | N/A | 50 | TT_Task
A4140 | Conduct as-built survey of the viaduct deck for level and alignment control. | N/A | 50 | TT_Task
A4150 | Prepare deck surface (high-pressure water jetting, grinding, and minor concrete repairs). | N/A | 267 | TT_Task
A4160 | Permanent Bearings & Restraints** | N/A | 90 | TT_Task
A4170 | Install Permanent Bearings on pier heads. | N/A | 90 | TT_Task
A4180 | Install Pedestals and Seismic Arrestors. | N/A | 90 | TT_Task
A4190 | Grout pedestals, bearings, and arrestor base plates. | N/A | 90 | TT_Task
A4200 | Conduct post-grouting inspection and testing. | N/A | 125 | TT_Task
A4210 | Parapet Wall Construction** | N/A | 125 | TT_Task
A4220 | Survey and set out for parapet wall alignment. | N/A | 125 | TT_Task
A4230 | Install starter bars and fix reinforcement for parapet walls. | N/A | 125 | TT_Task
A4240 | Erect formwork for parapet walls (inner and outer). | N/A | 125 | TT_Task
A4250 | Pour concrete for parapet walls in sequential bays. | N/A | 125 | TT_Task
A4260 | Strip formwork and apply curing compound. | N/A | 125 | TT_Task
A4270 | Apply waterproofing membrane system to the entire deck surface. | N/A | 40 | TT_Task
A4280 | Conduct flood testing or integrity testing of the waterproofing membrane. | N/A | 40 | TT_Task
A4290 | Lay protective screed or asphaltic layer over the membrane. | N/A | 40 | TT_Task
A4300 | Survey and set out for track plinth/baseplate locations. | N/A | 1 | TT_Task
A4310 | Construct concrete track plinths. | N/A | 125 | TT_Task
A4320 | Install rails, fastenings, and sleepers/baseplates. | N/A | 90 | TT_Task
A4330 | Perform initial rail alignment and thermic welding. | N/A | 50 | TT_Task
A4340 | Final tamping, stressing, and alignment of track. | N/A | 20 | TT_Task
A4350 | Install deck drainage system (scuppers, downpipes). | N/A | 1 | TT_Task
A4360 | Install cable containment systems (ducts, troughs, and cable trays). | N/A | 300 | TT_Task
A4370 | Install walkway and maintenance handrailing. | N/A | 125 | TT_Task
A4380 | Pull and install power, signaling, and communication cables. | N/A | 1 | TT_Task
A4390 | Install viaduct lighting poles and fixtures. | N/A | 50 | TT_Task
A4400 | Install noise barriers and associated steelwork. | N/A | 225 | TT_Task
A4410 | Install expansion joints at abutments and designated piers. | N/A | 90 | TT_Task
A4420 | Apply final protective/aesthetic coating to parapet walls. | N/A | 125 | TT_Task
A4430 | Install all required signage and line marking. | N/A | 34 | TT_Task
A4440 | Conduct final cleaning and removal of all temporary works from the deck. | N/A | 34 | TT_Task
A4450 | Perform joint quality inspection with the client/engineer (Punch Listing). | N/A | 5 | TT_Task
A4460 | Rectify all identified defects/snags. | N/A | 34 | TT_Task
A4470 | Final Handover Inspection and Demobilization. | N/A | 50 | TT_Task
A4480 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A4490 | Site Establishment & Enabling Works** | N/A | 30 | TT_Task
A4500 | Obtain All Necessary Permits to Work | N/A | 0 | TT_FinMile
A4510 | Site Mobilization, Setup Site Offices, Welfare Facilities & Laydown Areas | N/A | 30 | TT_Task
A4520 | Perform Initial Site Survey and Setting Out | N/A | 1 | TT_Task
A4530 | Install Temporary Fencing, Hoarding, and Access Gates | N/A | 54 | TT_Task
A4540 | Utility Location, Diversion, and Protection Works | N/A | 150 | TT_Task
A4550 | Site Clearance, Grubbing, and Removal of Obstructions | N/A | 34 | TT_Task
A4560 | Substructure & Foundation Works** | N/A | 267 | TT_Task
A4570 | Bulk Excavation to Formation Level | N/A | 200 | TT_Task
A4580 | Piling Works (Installation of Bored/Driven Piles) | N/A | 1 | TT_Task
A4590 | Pile Trimming and Preparation | N/A | 100 | TT_Task
A4600 | Excavation for Pile Caps and Foundation Bases | N/A | 100 | TT_Task
A4610 | Install Blinding Concrete and Waterproofing | N/A | 40 | TT_Task
A4620 | Reinforcement Fixing and Formwork for Pile Caps & Foundations | N/A | 200 | TT_Task
A4630 | Concrete Pour for Pile Caps & Foundations | N/A | 1 | TT_Task
A4640 | Install Underground Drainage and Buried Services/Ducts | N/A | 150 | TT_Task
A4650 | Backfilling and Compaction up to Ground Level | N/A | 200 | TT_Task
A4660 | Superstructure Works** | N/A | 50 | TT_Task
A4670 | Construct Ground Floor/Sub-level Retaining Walls and Columns | N/A | 1 | TT_Task
A4680 | Install Formwork & Rebar for Ground Floor Slab | N/A | 120 | TT_Task
A4690 | Pour Concrete for Ground Floor Slab | N/A | 120 | TT_Task
A4700 | Erect Structural Steel or RC Columns to Concourse Level | N/A | 50 | TT_Task
A4710 | Install Pedestals & Seismic Arrestors on Support Columns** | N/A | 90 | TT_Task
A4720 | Install Formwork & Rebar for Concourse Level Beams and Slabs | N/A | 50 | TT_Task
A4730 | Pour Concrete for Concourse Level Slab | N/A | 120 | TT_Task
A4740 | Erect Structural Steel or RC Columns to Platform/Roof Level | N/A | 300 | TT_Task
A4750 | Construct Staircases and Lift/Elevator Shafts | N/A | 1 | TT_Task
A4760 | Install Main Roof Structural Steel/Concrete Frame | N/A | 225 | TT_Task
A4770 | Install Roof Decking, Waterproofing, and Cladding | N/A | 1 | TT_Task
A4780 | Building Envelope & Architectural Finishes** | N/A | 225 | TT_Task
A4790 | Install External Facade, Cladding, and Glazing Systems | N/A | 225 | TT_Task
A4800 | Install External Doors and Louvres | N/A | 225 | TT_Task
A4810 | Commence Internal Blockwork and Partitioning | N/A | 0 | TT_FinMile
A4820 | Floor Screeding and Toppings | N/A | 1 | TT_Task
A4830 | First Fix Internal Finishes (Wall Linings, Plastering) | N/A | 225 | TT_Task
A4840 | Ceiling Grid and System Installation | N/A | 1 | TT_Task
A4850 | Second Fix Internal Finishes (Painting, Tiling, Floor Coverings) | N/A | 225 | TT_Task
A4860 | Installation of Internal Doors, Glazing, and Architectural Metalwork | N/A | 225 | TT_Task
A4870 | Fit-out of Station Rooms (Ticket Office, Staff Rooms, Toilets) | N/A | 1 | TT_Task
A4880 | Installation of Station Furniture and Fixtures | N/A | 90 | TT_Task
A4890 | Mechanical, Electrical & Plumbing (MEP) and Systems Installation** | N/A | 150 | TT_Task
A4900 | MEP First Fix - Installation of Containment, Ductwork, and Pipework | N/A | 1 | TT_Task
A4910 | Installation of Major Plant (HVAC Chillers, Transformers, Switchgear) | N/A | 150 | TT_Task
A4920 | MEP Second Fix - Cable Pulling, Wiring, and Equipment Installation | N/A | 1 | TT_Task
A4930 | Installation of Lighting and Small Power Systems | N/A | 1 | TT_Task
A4940 | Installation of Fire Fighting, Alarm, and Life Safety Systems | N/A | 150 | TT_Task
A4950 | Installation of Plumbing, Drainage, and Sanitary Ware | N/A | 150 | TT_Task
A4960 | Installation of Station Specific Systems (CCTV, PA, Access Control, Ticketing) | N/A | 1 | TT_Task
A4970 | Installation of Lifts and Escalators | N/A | 1 | TT_Task
A4980 | External Works & Site Completion** | N/A | 225 | TT_Task
A4990 | Final Grading and Preparation for External Areas | N/A | 120 | TT_Task
A5000 | Construction of Access Roads, Pavements, and Kerbs | N/A | 25 | TT_Task
A5010 | Installation of External Lighting and Signage | N/A | 225 | TT_Task
A5020 | Landscaping, Planting, and Irrigation Works | N/A | 1 | TT_Task
A5030 | Final Site Cleanup and Removal of Temporary Facilities | N/A | 30 | TT_Task
A5040 | Testing, Commissioning & Handover** | N/A | 225 | TT_Task
A5050 | Pre-commissioning and Static Testing of Individual MEP Systems | N/A | 1 | TT_Task
A5060 | Commissioning and Dynamic Testing of MEP & Life Safety Systems | N/A | 1 | TT_Task
A5070 | Testing and Commissioning of Lifts and Escalators | N/A | 1 | TT_Task
A5080 | Integrated Station Systems Testing | N/A | 1 | TT_Task
A5090 | Final Inspections and Rectification of Snags (Punch List) | N/A | 1 | TT_Task
A5100 | Obtain Final Statutory Approvals and Occupancy Certificate | N/A | 0 | TT_FinMile
A5110 | Compile As-Built Drawings and O&M Manuals | N/A | 30 | TT_Task
A5120 | Final Handover of Whitefield Station to the Client/Operator | N/A | 0 | TT_FinMile
A5130 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A5140 | Pre-Construction & Enabling Works** | N/A | 34 | TT_Task
A5150 | Site Mobilization, Establishment of Site Office & Laydown Areas | N/A | 30 | TT_Task
A5160 | Initial Site Survey, Setting Out, and Geotechnical Investigations | N/A | 40 | TT_Task
A5170 | Site Clearance, Grubbing, and Demolition of Existing Structures | N/A | 34 | TT_Task
A5180 | Traffic Management Plan Implementation & Barricading | N/A | 25 | TT_Task
A5190 | Diversion of Existing Utilities (Electrical, Water, Telecom, Sewerage) | N/A | 34 | TT_Task
A5200 | Substructure & Foundation Works** | N/A | 267 | TT_Task
A5210 | Piling Works (Bored Cast-in-situ piles) | N/A | 1 | TT_Task
A5220 | Pile Breaking and Preparation for Pile Caps | N/A | 100 | TT_Task
A5230 | Excavation for Pile Caps and Foundations | N/A | 100 | TT_Task
A5240 | Pile Cap Reinforcement, Formwork, and Concreting | N/A | 200 | TT_Task
A5250 | Construction of Substructure Piers/Columns up to Ground Level | N/A | 267 | TT_Task
A5260 | Backfilling and Compaction around Foundations | N/A | 40 | TT_Task
A5270 | Superstructure Works** | N/A | 50 | TT_Task
A5280 | Erection of Scaffolding and Formwork for Concourse Level | N/A | 50 | TT_Task
A5290 | Concourse Level Slab & Beams - Reinforcement & Concreting | N/A | 120 | TT_Task
A5300 | Construction of Columns from Concourse to Platform Level | N/A | 50 | TT_Task
A5310 | Erection of Scaffolding and Formwork for Platform Level | N/A | 50 | TT_Task
A5320 | Platform Level Slab & Beams - Reinforcement & Concreting | N/A | 120 | TT_Task
A5330 | Installation of Bearings, Pedestals & Seismic Arrestors | N/A | 90 | TT_Task
A5340 | Construction of Columns from Platform to Roof Level | N/A | 150 | TT_Task
A5350 | Fabrication and Erection of Structural Steel for Roof | N/A | 300 | TT_Task
A5360 | Roof Sheeting, Cladding, and Waterproofing Installation | N/A | 1 | TT_Task
A5370 | Architectural Works & Finishes** | N/A | 225 | TT_Task
A5380 | MEP (Mechanical, Electrical, Plumbing) & Systems Installation** | N/A | 1 | TT_Task
A5390 | External Area Development** | N/A | 225 | TT_Task
A5400 | Testing, Commissioning & Handover** | N/A | 225 | TT_Task
A5410 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A5420 | WBS: 5.3 Central Station Construction** | N/A | 50 | TT_Task
A5430 | Site Establishment & Enabling Works** | N/A | 30 | TT_Task
A5440 | Mobilize Site Plant, Equipment & Personnel | N/A | 25 | TT_Task
A5450 | Establish Site Offices, Welfare Facilities & Laydown Areas | N/A | 30 | TT_Task
A5460 | Perform Topographical Survey and Setting Out | N/A | 13 | TT_Task
A5470 | Implement Traffic & Pedestrian Management Plans | N/A | 25 | TT_Task
A5480 | Isolate, Disconnect, and Divert Existing Utilities | N/A | 150 | TT_Task
A5490 | Erect Site Hoarding and Secure Site Perimeter | N/A | 54 | TT_Task
A5500 | Substructure Works** | N/A | 63 | TT_Task
A5510 | Install Piling (Secant, Contiguous, or Bearing Piles as required) | N/A | 2334 | TT_Task
A5520 | Perform Bulk Excavation to Formation Level | N/A | 200 | TT_Task
A5530 | Install Temporary Shoring and Dewatering Systems | N/A | 25 | TT_Task
A5540 | Install Blinding Concrete and Waterproofing Membrane | N/A | 40 | TT_Task
A5550 | Install Foundation Rebar Cages | N/A | 2334 | TT_Task
A5560 | Pour Foundation Concrete (Raft / Pile Caps) | N/A | 150 | TT_Task
A5570 | Construct Basement Retaining Walls and Columns | N/A | 278 | TT_Task
A5580 | Waterproof Substructure Walls | N/A | 40 | TT_Task
A5590 | Superstructure Works** | N/A | 50 | TT_Task
A5600 | Install Pedestals & Seismic Arrestors at Column Locations | N/A | 90 | TT_Task
A5610 | Erect Ground Floor Structural Frame (Columns & Core Walls) | N/A | 50 | TT_Task
A5620 | Install Formwork, Rebar, and MEP First Fix for Level 1 Slab | N/A | 120 | TT_Task
A5630 | Pour Concrete for Level 1 Slab | N/A | 120 | TT_Task
A5640 | Erect Level 1 Structural Frame (Columns & Walls) | N/A | 300 | TT_Task
A5650 | Repeat Slab & Frame Cycle for all Subsequent Floors...* | N/A | 120 | TT_Task
A5660 | Erect Main Roof Structural Steel Frame | N/A | 300 | TT_Task
A5670 | Install Roof Decking and Substrate | N/A | 1 | TT_Task
A5680 | Building Envelope & Cladding** | N/A | 225 | TT_Task
A5690 | Install Roof Weatherproofing and Insulation System | N/A | 1 | TT_Task
A5700 | Install External Façade Support System (Mullions/Transoms) | N/A | 225 | TT_Task
A5710 | Install Glazing, Cladding Panels, and Louvres | N/A | 225 | TT_Task
A5720 | Install External Doors and Entranceways | N/A | 225 | TT_Task
A5730 | Complete all External Sealant and Interface Works | N/A | 225 | TT_Task
A5740 | Internal Works & Finishes** | N/A | 1 | TT_Task
A5750 | Install Internal Blockwork and Drywall Partitions | N/A | 1 | TT_Task
A5760 | Install Main Staircases and Complete Lift Shaft Construction | N/A | 50 | TT_Task
A5770 | MEP First Fix (Containment, Ductwork, Pipework) in Walls & Ceilings | N/A | 1 | TT_Task
A5780 | Apply Plastering / Wall Finishes | N/A | 225 | TT_Task
A5790 | Install Suspended Ceilings and Access Panels | N/A | 150 | TT_Task
A5800 | Install Raised Access Flooring / Floor Screed | N/A | 120 | TT_Task
A5810 | Install Floor Finishes (Tiling, Terrazzo, Vinyl) | N/A | 1 | TT_Task
A5820 | Install Wall Finishes (Tiling, Panelling) | N/A | 225 | TT_Task
A5830 | Install Internal Doors, Frames, and Glazed Screens | N/A | 225 | TT_Task
A5840 | Final Painting and Decorating | N/A | 225 | TT_Task
A5850 | Mechanical, Electrical & Plumbing (MEP) & Systems Installation** | N/A | 150 | TT_Task
A5860 | Install Major Plant (HVAC Chillers, Air Handling Units, Switchgear) | N/A | 150 | TT_Task
A5870 | MEP Second Fix (Cabling, Sockets, Light Fixtures, Grilles, Sanitary Ware) | N/A | 1 | TT_Task
A5880 | Install Lifts and Escalators | N/A | 1 | TT_Task
A5890 | Install Fire Protection Systems (Sprinklers, Fire Alarms) | N/A | 150 | TT_Task
A5900 | Install Station Management Systems (BMS, CCTV, Public Address) | N/A | 1 | TT_Task
A5910 | Install Passenger Information and Ticketing Systems | N/A | 150 | TT_Task
A5920 | External Works & Landscaping** | N/A | 225 | TT_Task
A5930 | Backfill and Grade around Station Structure | N/A | 1 | TT_Task
A5940 | Install Site-wide Stormwater Drainage and Utilities | N/A | 1 | TT_Task
A5950 | Construct Access Roads, Pavements, and Hard Landscaping | N/A | 25 | TT_Task
A5960 | Install External Lighting, Signage, and Street Furniture | N/A | 225 | TT_Task
A5970 | Perform Topsoiling and Soft Landscaping (Planting) | N/A | 1 | TT_Task
A5980 | Testing, Commissioning & Handover** | N/A | 225 | TT_Task
A5990 | Perform MEP Systems Testing and Commissioning | N/A | 150 | TT_Task
A6000 | Conduct Integrated Systems Testing (Cause & Effect) | N/A | 150 | TT_Task
A6010 | Final Architectural Snagging and Defect Rectification | N/A | 1 | TT_Task
A6020 | Obtain Statutory Approvals and Certificate of Completion | N/A | 0 | TT_FinMile
A6030 | Final Site Clean and Demobilization | N/A | 54 | TT_Task
A6040 | Compile As-Built Drawings and Handover Documentation | N/A | 20 | TT_Task
A6050 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A6060 | Mobilize Plant, Equipment, and Labour for Earthworks Operations | N/A | 25 | TT_Task
A6070 | Survey and Set Out of Works Area, including Cut/Fill Limits and Drainage Lines | N/A | 1 | TT_Task
A6080 | Establish Environmental Controls (e.g., Silt Fencing, Settlement Ponds) | N/A | 1 | TT_Task
A6090 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A6100 | WBS: 6.2 Depot Buildings & Workshop Structures** | N/A | 0 | TT_LOE
A6110 | Pre-Construction & Mobilization** | N/A | 30 | TT_Task
A6120 | Submit & Obtain Approval for Construction Method Statements & Shop Drawings | N/A | 10 | TT_Task
A6130 | Mobilize Site Facilities, Plant & Personnel | N/A | 25 | TT_Task
A6140 | Establish Temporary Utilities (Power, Water, Site Offices) | N/A | 30 | TT_Task
A6150 | Perform Initial Site Survey & Setting Out of Building Footprints | N/A | 30 | TT_Task
A6160 | Site Clearance, Grubbing, and Removal of Obstructions | N/A | 34 | TT_Task
A6170 | Substructure & Foundations** | N/A | 63 | TT_Task
A6180 | Bulk Excavation to Formation Level | N/A | 200 | TT_Task
A6190 | Excavate for Foundations, Ground Beams & Service Trenches | N/A | 200 | TT_Task
A6200 | Install Underground Services (Drainage, Earthing, Below-Slab Conduits) | N/A | 150 | TT_Task
A6210 | Lay Blinding Concrete & Waterproofing Membrane | N/A | 40 | TT_Task
A6220 | Fabricate & Fix Rebar for Foundations & Pile Caps | N/A | 1 | TT_Task
A6230 | Install Formwork for Foundations & Ground Beams | N/A | 120 | TT_Task
A6240 | Install Cast-in Items (Holding Down Bolts, Plates for Pedestals & Seismic Arrestors)** | N/A | 90 | TT_Task
A6250 | Pour Concrete for Foundations & Plinths | N/A | 120 | TT_Task
A6260 | Strip Formwork & Apply Curing Compound | N/A | 120 | TT_Task
A6270 | Backfill, Grade, and Compact Hardcore for Ground Floor Slab | N/A | 120 | TT_Task
A6280 | Install Reinforcement & Formwork for Ground Floor Slab | N/A | 120 | TT_Task
A6290 | Pour Concrete for Ground Floor Slab & Apply Finish | N/A | 120 | TT_Task
A6300 | Superstructure** | N/A | 225 | TT_Task
A6310 | Procure, Fabricate & Deliver Structural Steel | N/A | 300 | TT_Task
A6320 | Erect Primary Structural Steel Frame (Columns & Rafters) | N/A | 300 | TT_Task
A6330 | Erect Secondary Steel (Purlins, Girts, Bracing) | N/A | 300 | TT_Task
A6340 | Install Roof Cladding, Gutters & Waterproofing System | N/A | 1 | TT_Task
A6350 | Install Wall Cladding, Louvers & Vents | N/A | 225 | TT_Task
A6360 | Construct Internal Masonry / Blockwork Walls | N/A | 1 | TT_Task
A6370 | Install External Doors, Windows & Glazing | N/A | 225 | TT_Task
A6380 | MEP & Internal Finishes (First Fix)** | N/A | 1 | TT_Task
A6390 | Workshop Equipment & MEP (Second Fix)** | N/A | 1 | TT_Task
A6400 | Architectural Finishes & Fit-Out** | N/A | 225 | TT_Task
A6410 | External Works** | N/A | 225 | TT_Task
A6420 | Testing, Commissioning & Handover** | N/A | 225 | TT_Task
A6430 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A6440 | Pre-Construction & Enabling Works** | N/A | 34 | TT_Task
A6450 | Procure and Deliver Long-Lead Items (e.g., Stormwater Pipes, Light Poles) | N/A | 90 | TT_Task
A6460 | Mobilize Site Team, Plant & Equipment for Road Works | N/A | 25 | TT_Task
A6470 | Survey, Set Out, and Peg Road Alignments, Levels, and Drainage Lines | N/A | 13 | TT_Task
A6480 | Clear and Grub Site along Road Corridors | N/A | 40 | TT_Task
A6490 | Strip and Stockpile Topsoil for Later Re-use | N/A | 100 | TT_Task
A6500 | Demolish any Existing Conflicting Pavements or Structures | N/A | 34 | TT_Task
A6510 | Earthworks & Sub-grade Preparation** | N/A | 34 | TT_Task
A6520 | Bulk Excavation (Cut) to Formation Level | N/A | 200 | TT_Task
A6530 | Import, Place, and Compact Engineered Fill to Formation Level | N/A | 240 | TT_Task
A6540 | Proof Roll and Test Sub-grade for Compaction and CBR | N/A | 20 | TT_Task
A6550 | Final Grade and Trim Sub-grade to Lines and Levels | N/A | 120 | TT_Task
A6560 | Underground Services & Drainage** | N/A | 1 | TT_Task
A6570 | Excavate Trenches for Stormwater Drainage and Utility Crossings | N/A | 200 | TT_Task
A6580 | Install Bedding Material for Pipes and Ducts | N/A | 150 | TT_Task
A6590 | Lay Stormwater Pipes and Culverts | N/A | 150 | TT_Task
A6600 | Construct Manholes, Catch Basins, and Headwalls | N/A | 150 | TT_Task
A6610 | Install Ducts for Electrical and Communication Services Crossings | N/A | 150 | TT_Task
A6620 | Backfill and Compact all Trenches and Service Crossings | N/A | 200 | TT_Task
A6630 | Pavement Construction** | N/A | 20 | TT_Task
A6640 | Place, Spread, and Compact Sub-base Course Material | N/A | 120 | TT_Task
A6650 | Place, Spread, and Compact Base Course Material | N/A | 120 | TT_Task
A6660 | Conduct Field Density Tests for Sub-base and Base Course Layers | N/A | 120 | TT_Task
A6670 | Apply Prime Coat to Base Course | N/A | 120 | TT_Task
A6680 | Apply Tack Coat | N/A | 40 | TT_Task
A6690 | Lay and Compact Asphaltic Concrete - Binder Course | N/A | 20 | TT_Task
A6700 | Lay and Compact Asphaltic Concrete - Wearing Course | N/A | 1 | TT_Task
A6710 | Ancillary Concrete & Structural Works** | N/A | 1 | TT_Task
A6720 | Install Formwork and Rebar for Kerbstones and Gutters | N/A | 1 | TT_Task
A6730 | Pour Concrete for Kerbstones and Gutters | N/A | 1 | TT_Task
A6740 | Construct Concrete Footpaths and Sidewalks | N/A | 1 | TT_Task
A6750 | Construct Foundations for Street Lighting Poles and Signage | N/A | 278 | TT_Task
A6760 | Construct Concrete Pedestals & Supports for Ancillary Structures | N/A | 90 | TT_Task
A6770 | Ancillary Finishes & MEP** | N/A | 225 | TT_Task
A6780 | Erect Street Lighting Poles and Install Luminaires | N/A | 300 | TT_Task
A6790 | Install and Terminate Electrical Cables for Street Lighting | N/A | 1 | TT_Task
A6800 | Install Roadside Guardrails and Safety Barriers | N/A | 25 | TT_Task
A6810 | Erect Permanent Road Signage | N/A | 25 | TT_Task
A6820 | Apply Thermoplastic Road Markings and Lane Delineation | N/A | 1 | TT_Task
A6830 | Install Fencing and Gates along Road Corridors | N/A | 25 | TT_Task
A6840 | Landscaping & Final Reinstatement** | N/A | 34 | TT_Task
A6850 | Spread Stockpiled Topsoil to Verges and Landscaped Areas | N/A | 1 | TT_Task
A6860 | Carry out Final Landscaping, Seeding, and Planting | N/A | 1 | TT_Task
A6870 | Final Grading and Site Clean-up | N/A | 40 | TT_Task
A6880 | Testing, Commissioning & Handover** | N/A | 225 | TT_Task
A6890 | Test and Commission Street Lighting System | N/A | 225 | TT_Task
A6900 | Conduct Joint Site Inspection and Walkdown with Engineer/Client | N/A | 1 | TT_Task
A6910 | Rectify Punch List Items | N/A | 1 | TT_Task
A6920 | Prepare and Submit As-Built Drawings and Handover Documentation | N/A | 30 | TT_Task
A6930 | Demobilize all Remaining Plant, Equipment, and Personnel | N/A | 34 | TT_Task
A6940 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A6950 | Initial Coordination & Planning** | N/A | 10 | TT_Task
A6960 | Establish and Agree on Interface Management Plan (IMP) with all System Contractors | N/A | 20 | TT_Task
A6970 | Conduct Kick-Off Interface Workshops with Track, Power, and Signaling Contractors | N/A | 5 | TT_Task
A6980 | Develop and Agree on Master Interface Control Document (ICD) Framework | N/A | 20 | TT_Task
A6990 | Establish and Agree on a Common Data Environment (CDE) for Document Exchange | N/A | 15 | TT_Task
A7000 | Design & Engineering Interface** | N/A | 0 | TT_LOE
A7010 | Receive and Review System Contractors' 'Approved for Construction' (AFC) Drawings | N/A | 10 | TT_Task
A7020 | Incorporate System Requirements into Civil/Structural Designs (e.g., duct banks, equipment rooms, cable routes) | N/A | 15 | TT_Task
A7030 | Develop and Submit Combined Services Drawings (CSD) for System Contractor Review | N/A | 10 | TT_Task
A7040 | Conduct CSD Clash Detection and Resolution Workshops | N/A | 0 | TT_LOE
A7050 | Obtain Final Approval of all Interface CSDs from relevant parties | N/A | 0 | TT_FinMile
A7060 | Pre-Construction & Mobilization Interface** | N/A | 0 | TT_FinMile
A7070 | Coordinate and Agree on Detailed Phased Installation Schedule with all System Contractors | N/A | 10 | TT_Task
A7080 | Define and Agree on Site Access Protocols, Laydown Areas, and Permit to Work Procedures | N/A | 10 | TT_Task
A7090 | Jointly Review and Approve Health, Safety & Environmental (HSE) Interface Plans | N/A | 10 | TT_Task
A7100 | Construction Interface & Area Handover** | N/A | 0 | TT_FinMile
A7110 | Survey and Set Out locations for System Contractor Equipment Foundations and Embedments | N/A | 30 | TT_Task
A7120 | Construct Foundations, Plinths, and **Pedestals** for Trackside Equipment | N/A | 90 | TT_Task
A7130 | Construct Foundations, Plinths, and **Pedestals** for Power Supply Equipment (e.g., substations, transformers) | N/A | 90 | TT_Task
A7140 | Construct Foundations, Plinths, and **Pedestals** for Signaling Equipment (e.g., signal posts, location cases) | N/A | 90 | TT_Task
A7150 | Install required embedded items (conduits, cable trays, earthing) as per approved CSDs | N/A | 300 | TT_Task
A7160 | Conduct Joint Quality Inspection and Acceptance of Civil Interface Works | N/A | 5 | TT_Task
A7170 | Formal Handover of Certified Work Area to Track Contractor | N/A | 0 | TT_FinMile
A7180 | Formal Handover of Certified Work Area to Power Contractor | N/A | 0 | TT_FinMile
A7190 | Formal Handover of Certified Work Area to Signaling Contractor | N/A | 0 | TT_FinMile
A7200 | Testing, Commissioning & Final Interface** | N/A | 225 | TT_Task
A7210 | Provide Site Support and Access during System Installation and Testing Phases (Level of Effort) | N/A | 0 | TT_LOE
A7220 | Participate in Joint Inspections during System Integration Testing (SIT) | N/A | 0 | TT_LOE
A7230 | Manage and Close-Out Interface-Related Defects and Punch List Items | N/A | 0 | TT_LOE
A7240 | Compile and Submit As-Built Records for all Physical Interface Points | N/A | 10 | TT_Task
A7250 | Achieve Final Sign-off on Interface Completion from all System Contractors | N/A | 0 | TT_FinMile
A7260 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 0 | TT_FinMile
A7270 | Preparation & Planning Phase** | N/A | 0 | TT_LOE
A7280 | Develop and Submit Overall Testing & Commissioning Strategy and Plan | N/A | 15 | TT_Task
A7290 | Prepare and Submit System-Specific Pre-Commissioning Procedures & ITPs (Inspection and Test Plans) | N/A | 15 | TT_Task
A7300 | Prepare and Submit System-Specific Commissioning and Start-up Procedures | N/A | 20 | TT_Task
A7310 | Compile and Submit Draft Operation & Maintenance (O&M) Manuals for Review | N/A | 10 | TT_Task
A7320 | Define and Agree on Handover Protocol and Documentation Requirements with Client | N/A | 10 | TT_Task
A7330 | Procure and Calibrate Specialist Testing Equipment | N/A | 30 | TT_Task
A7340 | Pre-Commissioning & Static Testing Phase** | N/A | 90 | TT_Task
A7350 | Achieve Mechanical Completion (MC) on a System-by-System Basis | N/A | 0 | TT_FinMile
A7360 | Conduct Joint Construction Punch-Listing Walkdowns with Client/Engineer | N/A | 5 | TT_Task
A7370 | Rectify all 'Category A' Punch List Items (Preventing Commissioning) | N/A | 1 | TT_Task
A7380 | Perform Static & Dead System Checks (e.g., Cable Continuity/Megger Tests, Pipe Pressure/Hydro Tests) | N/A | 150 | TT_Task
A7390 | Complete and Sign-Off all Pre-Commissioning ITPs and Checksheets | N/A | 0 | TT_FinMile
A7400 | Issue System-Specific Mechanical Completion Certificates (MCC) | N/A | 0 | TT_FinMile
A7410 | Commissioning & Dynamic Testing Phase** | N/A | 90 | TT_Task
A7420 | System Energization and First Start-up (on a System-by-System Basis) | N/A | 400 | TT_Task
A7430 | Perform Dynamic & Live System Functional Tests (e.g., Loop Tuning, Equipment Start/Stop, Sequence Checks) | N/A | 50 | TT_Task
A7440 | Conduct System Integration Testing (SIT) to Verify Interface Functionality Between Systems | N/A | 15 | TT_Task
A7450 | Conduct Performance & Endurance Testing (e.g., Trial Operations, Load Bank Testing) | N/A | 90 | TT_Task
A7460 | Identify and Log Commissioning-Related Punch List Items | N/A | 0 | TT_LOE
A7470 | Rectify all Outstanding Punch List Items | N/A | 34 | TT_Task
A7480 | Handover & Completion Phase** | N/A | 20 | TT_Task
A7490 | Post-Completion & Project Close-Out** | N/A | 30 | TT_Task
A7500 | WBS: 7.3 As-Built Documentation & Contract Demobilization** | N/A | 30 | TT_Task
A7510 | GENERATED ACTIVITY LIST (LOGICAL SEQUENCE):** | N/A | 5 | TT_Task
A7520 | As-Built & Handover Documentation** | N/A | 20 | TT_Task
A7530 | Compile all field survey data, red-line markups, and quality inspection records. | N/A | 5 | TT_Task
A7540 | Prepare and draft As-Built drawings (Civil, Structural, Architectural). | N/A | 20 | TT_Task
A7550 | Prepare and draft As-Built drawings (MEP, Utilities, and Specialist Systems). | N/A | 30 | TT_Task
A7560 | Compile all supplier/subcontractor warranties, guarantees, and material certificates. | N/A | 10 | TT_Task
A7570 | Compile all Testing and Commissioning reports into a final handover package. | N/A | 5 | TT_Task
A7580 | Prepare draft Operation & Maintenance (O&M) Manuals. | N/A | 30 | TT_Task
A7590 | Consolidate and submit the complete As-Built and O&M documentation package for Client/Engineer review. | N/A | 10 | TT_Task
A7600 | Incorporate Client/Engineer comments on all submitted documentation. | N/A | 5 | TT_Task
A7610 | Submit final, approved As-Built drawings and Handover documentation. | N/A | 0 | TT_FinMile
A7620 | Site Demobilization & Reinstatement** | N/A | 30 | TT_Task
A7630 | Prepare and submit the Site Demobilization & Reinstatement Plan for approval. | N/A | 10 | TT_Task
A7640 | Conduct final joint site inspection (walk-down) with Client/Engineer to generate a final punch list (snag list). | N/A | 1 | TT_Task
A7650 | Rectify all items on the final punch list to the satisfaction of the Engineer. | N/A | 50 | TT_Task
A7660 | Dismantle and remove all temporary site offices, welfare facilities, and storage containers. | N/A | 30 | TT_Task
A7670 | Demobilize and remove all contractor plant, equipment, and machinery from the site. | N/A | 34 | TT_Task
A7680 | Disconnect and remove all temporary utilities (power, water, drainage). | N/A | 34 | TT_Task
A7690 | Remove all surplus construction materials, scrap, and waste from the site. | N/A | 34 | TT_Task
A7700 | Complete final site grading and reinstatement as per contract requirements. | N/A | 25 | TT_Task
A7710 | Obtain formal sign-off for punch list completion and site reinstatement. | N/A | 0 | TT_FinMile
A7720 | Contract & Commercial Close-Out** | N/A | 30 | TT_Task
A7730 | Apply for and obtain the Certificate of Substantial Completion / Taking-Over Certificate. | N/A | 0 | TT_FinMile
A7740 | Prepare and submit the draft Final Account and application for final payment. | N/A | 10 | TT_Task
A7750 | Negotiate and agree on the Final Account with the Client/Commercial team. | N/A | 20 | TT_Task
A7760 | Submit all required documentation for the release of retention monies. | N/A | 10 | TT_Task
A7770 | Obtain the Final Acceptance Certificate (FAC) from the Client. | N/A | 0 | TT_FinMile
A7780 | Secure the release of all performance bonds and bank guarantees. | N/A | 0 | TT_FinMile
A7790 | Archive all project documentation, correspondence, and financial records. | N/A | 10 | TT_Task
A7800 | Final Contract Close-Out. | N/A | 30 | TT_Task

## TASKPRED
task_code | pred_task_code | pred_type | lag_hr_cnt
A1070 | A1060 | FS | 0
A1080 | A1070 | FS | 0
A1130 | A1120 | FS | 0
A1140 | A1130 | FS | 0
A1150 | A1140 | FS | 0
A1180 | A1170 | FS | 0
A1210 | A1200 | FS | 0
A1230 | A1270 | FS | 0
A1240 | A1230 | FS | 0
A1250 | A1240 | FS | 0
A1270 | A1260 | FS | 0
A1280 | A1210 | FS | 0
A1290 | A1280 | FS | 0
A1300 | A1290 | FS | 0
A1330 | A1320 | FS | 0
A1340 | A1330 | FS | 0
A1350 | A1340 | FS | 0
A1360 | A1350 | FS | 0
A1370 | A1360 | FS | 0
A1410 | A1430 | FS | 0
A1420 | A1410 | FS | 0
A1440 | A1420 | FS | 0
A1450 | A1700 | FS | 0
A1470 | A1450 | FS | 0
A1480 | A1470 | FS | 0
A1490 | A1480 | FS | 0
A1500 | A1550 | FS | 0
A1510 | A1500 | FS | 0
A1530 | A1510 | FS | 0
A1540 | A1530 | FS | 0
A1550 | A1540 | FS | 0
A1560 | A1550 | FS | 0
A1570 | A1500 | FS | 0
A1580 | A1570 | FS | 0
A1590 | A1580 | FS | 0
A1600 | A1590 | FS | 0
A1610 | A1600 | FS | 0
A1620 | A1610 | FS | 0
A1630 | A1620 | FS | 0
A1640 | A1630 | FS | 0
A1650 | A1640 | FS | 0
A1660 | A1650 | FS | 0
A1680 | A1710 | FS | 0
A1700 | A1670 | FS | 0
A1710 | A1440 | FS | 0
A1720 | A1660 | FS | 0
A1730 | A1720 | FS | 0
A1740 | A1730 | FS | 0
A1750 | A1740 | FS | 0
A1760 | A1750 | FS | 0
A1770 | A1760 | FS | 0
A1800 | A1790 | FS | 0
A1810 | A1790 | FS | 0
A1840 | A1830 | FS | 0
A1850 | A1840 | FS | 0
A1890 | A1880 | FS | 0
A1960 | A1950 | FS | 0
A1980 | A1960 | FS | 0
A1990 | A1980 | FS | 0
A2000 | A1990 | FS | 0
A2010 | A2000 | FS | 0
A2020 | A2010 | FS | 0
A2030 | A2020 | FS | 0
A2040 | A2030 | FS | 0
A2050 | A2040 | FS | 0
A2060 | A2050 | FS | 0
A2090 | A2080 | FS | 0
A2100 | A2090 | FS | 0
A2110 | A2100 | FS | 0
A2120 | A2110 | FS | 0
A2150 | A2140 | FS | 0
A2160 | A2150 | FS | 0
A2170 | A2160 | FS | 0
A2180 | A2170 | FS | 0
A2190 | A2180 | FS | 0
A2200 | A2190 | FS | 0
A2210 | A2200 | FS | 0
A2220 | A2210 | FS | 0
A2230 | A2220 | FS | 0
A2290 | A2280 | FS | 0
A2330 | A2320 | FS | 0
A2490 | A2480 | FS | 0
A2520 | A2510 | FS | 0
A2530 | A2520 | FS | 0
A2540 | A2530 | FS | 0
A2550 | A2540 | FS | 0
A2560 | A2550 | FS | 0
A2570 | A2560 | FS | 0
A2580 | A2570 | FS | 0
A2590 | A2580 | FS | 0
A2600 | A2590 | FS | 0
A2610 | A2600 | FS | 0
A2620 | A2610 | FS | 0
A2630 | A2620 | FS | 0
A2640 | A2630 | FS | 0
A2650 | A2260 | FS | 0
A2700 | A2690 | FS | 0
A2710 | A2700 | FS | 0
A2720 | A2710 | FS | 0
A2730 | A2720 | FS | 0
A2750 | A2730 | FS | 0
A2760 | A2750 | FS | 0
A2770 | A2760 | FS | 0
A2780 | A2770 | FS | 0
A2850 | A2840 | FS | 0
A2860 | A2850 | FS | 0
A2920 | A2910 | FS | 0
A2930 | A2920 | FS | 0
A2940 | A2930 | FS | 0
A3000 | A2990 | FS | 0
A3010 | A3000 | FS | 0
A3020 | A3010 | FS | 0
A3030 | A3020 | FS | 0
A3040 | A3030 | FS | 0
A3050 | A3040 | FS | 0
A3060 | A3050 | FS | 0
A3070 | A3060 | FS | 0
A3080 | A3070 | FS | 0
A3090 | A3080 | FS | 0
A3100 | A3090 | FS | 0
A3110 | A3100 | FS | 0
A3120 | A3110 | FS | 0
A3190 | A3180 | FS | 0
A3200 | A3190 | FS | 0
A3290 | A3280 | FS | 0
A3390 | A3380 | FS | 0
A3410 | A3390 | FS | 0
A3420 | A3410 | FS | 0
A3430 | A3420 | FS | 0
A3440 | A3430 | FS | 0
A3450 | A3440 | FS | 0
A3460 | A3450 | FS | 0
A3480 | A3460 | FS | 0
A3490 | A3480 | FS | 0
A3500 | A3490 | FS | 0
A3510 | A3500 | FS | 0
A3520 | A3510 | FS | 0
A3530 | A3520 | FS | 0
A3540 | A3530 | FS | 0
A3550 | A3540 | FS | 0
A3560 | A3550 | FS | 0
A3570 | A3560 | FS | 0
A3580 | A3570 | FS | 0
A3590 | A3580 | FS | 0
A3600 | A3590 | FS | 0
A3610 | A3600 | FS | 0
A3650 | A3640 | FS | 0
A3720 | A3710 | FS | 0
A3840 | A3830 | FS | 0
A3850 | A3840 | FS | 0
A3940 | A3930 | FS | 0
A4000 | A3980 | FS | 0
A4010 | A4000 | FS | 0
A4020 | A4010 | FS | 0
A4050 | A4040 | FS | 0
A4060 | A4050 | FS | 0
A4070 | A4060 | FS | 0
A4080 | A4070 | FS | 0
A4580 | A4570 | FS | 0
A4590 | A4580 | FS | 0
A4600 | A4590 | FS | 0
A4610 | A4600 | FS | 0
A4620 | A4610 | FS | 0
A4630 | A4620 | FS | 0
A4640 | A4630 | FS | 0
A4650 | A4640 | FS | 0
A4670 | A4650 | FS | 0
A4680 | A4670 | FS | 0
A4690 | A4680 | FS | 0
A4700 | A4690 | FS | 0
A4730 | A4720 | FS | 0
A4740 | A4730 | FS | 0
A4750 | A4740 | FS | 0
A4760 | A4750 | FS | 0
A4810 | A4800 | FS | 0
A4970 | A4750 | FS | 0
A5060 | A5050 | FS | 0
A5070 | A4970 | FS | 0
A5080 | A5060 | FS | 0
A5090 | A5080 | FS | 0
A5100 | A5090 | FS | 0
A5110 | A5100 | FS | 0
A5120 | A5110 | FS | 0
A5220 | A5210 | FS | 0
A5230 | A5220 | FS | 0
A5260 | A5250 | FS | 0
A5280 | A5260 | FS | 0
A5290 | A5280 | FS | 0
A5300 | A5290 | FS | 0
A5310 | A5300 | FS | 0
A5320 | A5310 | FS | 0
A5350 | A5340 | FS | 0
A5470 | A5460 | FS | 0
A5530 | A5520 | FS | 0
A5540 | A5530 | FS | 0
A5550 | A5540 | FS | 0
A5560 | A5550 | FS | 0
A5570 | A5560 | FS | 0
A5580 | A5570 | FS | 0
A5600 | A5580 | FS | 0
A5610 | A5600 | FS | 0
A5640 | A5630 | FS | 0
A5650 | A5640 | FS | 0
A5660 | A5650 | FS | 0
A5670 | A5660 | FS | 0
A5690 | A5670 | FS | 0
A5700 | A5690 | FS | 0
A5730 | A5720 | FS | 0
A5750 | A5730 | FS | 0
A5760 | A5750 | FS | 0
A5790 | A5780 | FS | 0
A5800 | A5790 | FS | 0
A5930 | A5580 | FS | 0
A5940 | A5930 | FS | 0
A5990 | A5910 | FS | 0
A6000 | A5990 | FS | 0
A6010 | A6000 | FS | 0
A6020 | A6010 | FS | 0
A6030 | A6020 | FS | 0
A6040 | A6030 | FS | 0
A6220 | A6210 | FS | 0
A6230 | A6220 | FS | 0
A6260 | A6250 | FS | 0
A6290 | A6280 | FS | 0
A6490 | A6480 | FS | 0
A6500 | A6490 | FS | 0
A6520 | A6500 | FS | 0
A6550 | A6540 | FS | 0
A6570 | A6550 | FS | 0
A6580 | A6570 | FS | 0
A6590 | A6580 | FS | 0
A6620 | A6610 | FS | 0
A6670 | A6660 | FS | 0
A6680 | A6670 | FS | 0
A6690 | A6680 | FS | 0
A6700 | A6690 | FS | 0
A6720 | A6700 | FS | 0
A6730 | A6720 | FS | 0
A6740 | A6730 | FS | 0
A6750 | A6740 | FS | 0
A6760 | A6750 | FS | 0
A6780 | A6760 | FS | 0
A6790 | A6780 | FS | 0
A6800 | A6790 | FS | 0
A6810 | A6800 | FS | 0
A6820 | A6810 | FS | 0
A6830 | A6820 | FS | 0
A6850 | A6830 | FS | 0
A6890 | A6870 | FS | 0
A6900 | A6890 | FS | 0
A6910 | A6900 | FS | 0
A6920 | A6910 | FS | 0
A6990 | A6980 | FS | 0
A7010 | A6990 | FS | 0
A7040 | A7030 | FS | 0
A7050 | A7040 | FS | 0
A7070 | A7050 | FS | 0
A7170 | A7160 | FS | 0
A7180 | A7170 | FS | 0
A7190 | A7180 | FS | 0
A7210 | A7190 | FS | 0
A7220 | A7210 | FS | 0
A7230 | A7220 | FS | 0
A7240 | A7230 | FS | 0
A7250 | A7240 | FS | 0
A7290 | A7280 | FS | 0
A7300 | A7290 | FS | 0
A7310 | A7300 | FS | 0
A7320 | A7310 | FS | 0
A7330 | A7320 | FS | 0
A7350 | A7330 | FS | 0
A7360 | A7350 | FS | 0
A7370 | A7360 | FS | 0
A7400 | A7390 | FS | 0
A7420 | A7400 | FS | 0
A7470 | A7460 | FS | 0