## Productivity_Norms
Norm_ID | Activity_Descriptor | BOQ_Code | UoM | Productivity_Rate | Time_Unit | Crew_ID
1.0 Project Mobilization & Management (WBS 1.1, 3.2, 3.3)
PN-101 | Site Boundary, Hoarding, and Fencing | 1.1.1 | m | 150 | Day | CR-FENCE-01
PN-102 | Construct Temporary Site Offices | 1.1.2 | m² | 50 | Day | CR-BLDG-01
PN-103 | Initial Site Clearance and Grubbing | 1.1.3 | ha | 0.5 | Day | CR-EARTH-01
PN-104 | Construct Temporary Site Access Roads | 1.1.4 | m² | 200 | Day | CR-ROAD-01
PN-105 | Utility Detection and Marking (GPR) | 3.2.1 | m | 500 | Day | CR-SURVEY-02
PN-106 | Demolish and Remove Existing Obstructions | 3.2.2 | m³ | 75 | Day | CR-DEMO-01
PN-107 | Excavate Trenches for New Utility Corridors | 3.3.1 | m³ | 100 | Day | CR-EARTH-02
PN-108 | Lay New Ducts, Conduits, and Pipes | 3.3.2 | m | 120 | Day | CR-UTIL-01
PN-109 | Pull New Electrical & Communication Cables | 3.3.3 | m | 400 | Day | CR-ELEC-01
2.0 Surveys & Investigations (WBS 2.1)
PN-201 | Conduct Topographical Survey Fieldwork | 2.1.1 | ha | 2 | Day | CR-SURVEY-01
PN-202 | Geotechnical Fieldwork - Borehole Drilling | 2.1.2 | m | 30 | Day | CR-GEO-01
4.0 Viaduct Civil Works (WBS 4.1, 4.2, 4.3, 4.4)
PN-401 | Bore/Drive Piles | 4.1.1 | No. | 2 | Day | CR-PILE-01
PN-402 | Fabricate and Install Pile Reinforcement Cages | 4.1.2 | ton | 1.5 | Day | CR-REBAR-01
PN-403 | Pour Concrete for Piles | 4.1.3 | m³ | 90 | Day | CR-CONC-01
PN-404 | Excavate for Pile Caps | 4.1.4 | m³ | 150 | Day | CR-EARTH-02
PN-405 | Erect Formwork for Pile Caps | 4.1.5 | m² | 50 | Day | CR-CARP-01
PN-406 | Fix Reinforcement Steel for Pile Caps | 4.1.6 | ton | 2 | Day | CR-REBAR-01
PN-407 | Pour Concrete for Pile Caps | 4.1.7 | m³ | 80 | Day | CR-CONC-01
PN-408 | Erect Formwork and Falsework for Piers | 4.1.8 | m² | 40 | Day | CR-CARP-02
PN-409 | Fix Reinforcement Steel for Piers | 4.1.9 | ton | 2.5 | Day | CR-REBAR-01
PN-410 | Pour Concrete for Piers (per lift) | 4.1.10 | m³ | 60 | Day | CR-CONC-01
PN-411 | Install Bearings, Pedestals & Seismic Arrestors | 4.1.11 | No. | 4 | Day | CR-MECH-01
PN-412 | Cast Precast Segments (per mould) | 4.2.1 | No. | 1 | Day | CR-PRECAST-01
PN-413 | Transport & Stockpile Cast Segments | 4.2.2 | No. | 10 | Day | CR-LOGIS-01
PN-414 | Lift & Place Segments (Launching Gantry) | 4.2.3 | No. | 8 | Day | CR-EREC-01
PN-415 | Erect/Launch Main Steel Girders | 4.3.1 | ton | 50 | Day | CR-EREC-02
PN-416 | Pour Concrete for Bridge Deck Slab | 4.3.2 | m³ | 100 | Day | CR-CONC-02
PN-417 | Pour concrete for parapet walls | 4.4.1 | m | 80 | Day | CR-CONC-03
PN-418 | Apply waterproofing membrane | 4.4.2 | m² | 300 | Day | CR-WATER-01
PN-419 | Install cable containment systems | 4.4.3 | m | 100 | Day | CR-ELEC-02
5.0 Station Construction (WBS 5.x) (Note: These are reusable for all 3 stations)
PN-501 | Bulk Excavation to Formation Level | 5.1.1 | m³ | 400 | Day | CR-EARTH-01
PN-502 | Piling Works (Station) | 5.1.2 | No. | 3 | Day | CR-PILE-01
PN-503 | Pour Concrete for Pile Caps & Foundations | 5.1.3 | m³ | 80 | Day | CR-CONC-S1
PN-504 | Erect Structural Steel (Medium) | 5.1.4 | ton | 5 | Day | CR-STEEL-01
PN-505 | Pour Concrete for Slabs (Slab-on-Grade) | 5.1.5 | m³ | 100 | Day | CR-CONC-S1
PN-506 | Pour Concrete for Suspended Slabs | 5.1.6 | m³ | 70 | Day | CR-CONC-S1
PN-507 | Install External Facade, Cladding, and Glazing | 5.1.7 | m² | 40 | Day | CR-FACADE-01
PN-508 | Internal Blockwork and Partitioning | 5.1.8 | m² | 35 | Day | CR-MASON-01
PN-509 | Floor Screeding and Toppings | 5.1.9 | m² | 80 | Day | CR-FLOOR-01
PN-510 | Ceiling Grid and System Installation | 5.1.10 | m² | 70 | Day | CR-CEIL-01
PN-511 | MEP First Fix - Containment | 5.1.11 | m | 150 | Day | CR-ELEC-02
PN-512 | MEP First Fix - Ductwork | 5.1.12 | m | 50 | Day | CR-MECH-02
PN-513 | MEP First Fix - Pipework | 5.1.13 | m | 80 | Day | CR-PLUMB-01
PN-514 | Installation of Lifts and Escalators | 5.1.14 | No. | 1 | Week | CR-LIFT-01
6.0 Depot Works (WBS 6.x)
PN-601 | Place and Compact General Fill | 6.1.1 | m³ | 500 | Day | CR-EARTH-01
PN-602 | Lay Drainage Pipes (Large Bore) | 6.1.2 | m | 40 | Day | CR-UTIL-02
PN-603 | Erect Primary Structural Steel Frame (Depot) | 6.2.1 | ton | 8 | Day | CR-STEEL-01
PN-604 | Install Roof Cladding | 6.2.2 | m² | 120 | Day | CR-ROOF-01
PN-605 | Construct Internal Masonry / Blockwork | 6.2.3 | m² | 50 | Day | CR-MASON-01
PN-606 | Place... Sub-base Course Material | 6.3.1 | m³ | 400 | Day | CR-ROAD-01
PN-607 | Place... Base Course Material | 6.3.2 | m³ | 350 | Day | CR-ROAD-01
PN-608 | Lay Asphaltic Concrete - Binder Course | 6.3.3 | ton | 200 | Day | CR-PAVE-01
PN-609 | Lay Asphaltic Concrete - Wearing Course | 6.3.4 | ton | 150 | Day | CR-PAVE-01
PN-610 | Pour Concrete for Kerbstones | 6.3.5 | m | 100 | Day | CR-CONC-03

## Crew_Library
Resource_Code | Resource_Name | Resource_Type | Rate_Per_Hour
Labor
R-FMN-CIVIL | Foreman (Civil) | Labor | 150
R-SKL-REBAR | Steel Fixer (Skilled) | Labor | 100
R-SKL-CARP | Carpenter (Skilled) | Labor | 100
R-SKL-MASON | Mason (Skilled) | Labor | 90
R-SKL-PAVE | Paver Operator | Labor | 110
R-GEN-LABOR | General Laborer | Labor | 60
R-OPER-HVY | Heavy Equipment Operator | Labor | 120
R-OPER-CRANE | Crane Operator | Labor | 130
R-OPER-RIG | Piling Rig Operator | Labor | 140
R-ELEC-HV | Electrician (High Voltage) | Labor | 110
R-ELEC-LV | Electrician (Low Voltage) | Labor | 90
R-MECH-FIT | Mechanical Fitter | Labor | 100
R-PLUMB | Plumber | Labor | 90
Equipment (Non-Labor)
E-EXCA-30T | Excavator (30T) | Non-Labor | 2500
E-PILE-RIG | Piling Rig (Rotary) | Non-Labor | 8000
E-CRANE-50T | Mobile Crane (50T) | Non-Labor | 4000
E-CRANE-LG | Launching Gantry | Non-Labor | 25000
E-PUMP-CONC | Concrete Pump (Boom) | Non-Labor | 2000
E-TRUCK-DUMP | Dump Truck (10-wheel) | Non-Labor | 1000
E-PAVER | Asphalt Paver | Non-Labor | 3000
E-COMP | Compactor / Roller | Non-Labor | 1200

## Resource_Library
Crew_ID | Crew_Name | Role_Code_1 | Role_Count_1 | Role_Code_2 | Role_Count_2 | Equip_Code_1 | Equip_Count_1 | Equip_Code_2 | Equip_Count_2
CR-EARTH-01 | Bulk Excavation Crew | R-FMN-CIVIL | 1 | R-OPER-HVY | 2 | E-EXCA-30T | 2 | E-TRUCK-DUMP | 4
CR-PILE-01 | Piling Crew | R-FMN-CIVIL | 1 | R-OPER-RIG | 1 | E-PILE-RIG | 1 | E-CRANE-50T | 1
CR-REBAR-01 | Rebar Crew (Foundations) | R-FMN-CIVIL | 1 | R-SKL-REBAR | 6 | - | - | - | -
CR-CARP-01 | Formwork Crew (Foundations) | R-FMN-CIVIL | 1 | R-SKL-CARP | 6 | R-GEN-LABOR | 4 | - | -
CR-CONC-01 | Concrete Crew (Viaduct) | R-FMN-CIVIL | 1 | R-GEN-LABOR | 6 | E-PUMP-CONC | 1 | - | -
CR-CONC-S1 | Concrete Crew (Station Slabs) | R-FMN-CIVIL | 1 | R-GEN-LABOR | 8 | E-PUMP-CONC | 1 | - | -
CR-EREC-01 | Segment Erection Crew | R-FMN-CIVIL | 2 | R-OPER-CRANE | 2 | E-CRANE-LG | 1 | - | -
CR-STEEL-01 | Steel Erection Crew | R-FMN-CIVIL | 1 | R-SKL-REBAR | 4 | E-CRANE-50T | 1 | - | -
CR-ROAD-01 | Road Sub-base Crew | R-FMN-CIVIL | 1 | R-OPER-HVY | 2 | E-COMP | 2 | E-TRUCK-DUMP | 3
CR-PAVE-01 | Asphalt Paving Crew | R-FMN-CIVIL | 1 | R-SKL-PAVE | 2 | E-PAVER | 1 | E-COMP | 2
CR-ELEC-02 | MEP Containment Crew | R-ELEC-LV | 2 | R-GEN-LABOR | 1 | - | - | - | -