## TASK
status_code | wbs_id | task_code | task_name | wbs_name | target_drtn_hr_cnt | delete_record_flag
Activity Status | WBS Code | Activity ID | Activity Name | (*)WBS Name | Original Duration(d) | Delete This Row
Not Started | BLP-DWP-R5-5.3.4 | ED-Sec-4-1.2 | Govt/Private Land Acquisition- Sec-4 | Section -4 Ch. 16.725 to Ch. 24.425 | 200
Not Started | BLP-DWP-R5-5.3.4 | ED-Sec-4-2 | Encumbrance Free Land handover- Sec-4 | Section -4 Ch. 16.725 to Ch. 24.425 | 200
Not Started | BLP-DWP-R5-5.3.4 | ED-Sec-4-3 | Permission for Dismantling of existing Govt / IR / Private Properties- Sec-4 | Section -4 Ch. 16.725 to Ch. 24.425 | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-1 | S&T Works | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-2 | Signalling boxes , Signalling HUT building , LC gates , existing Heigh gauges and associated obstructions at respective | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-3 | Electric Cable | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-4 | Transmission Line | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-5 | Water pipe Line | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-6 | Sewer Line | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-7 | Gail / GAS Pipe line at Ch. 18.578 & at Ch. 18.589 | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-8 | OFC Cable | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-9 | Telecom Cable | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.4.1 | ED-Sec-4-US-10 | Other Utilities (Wells, Hand pump, drain, Nallah, etc.) | Utility Shifting | 200
Not Started | BLP-DWP-R5-5.3.1 | ED-Sec-1-1.2 | Govt/Private Land Acquisition- Sec-1 | Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 | 230
Not Started | BLP-DWP-R5-5.3.1 | ED-Sec-1-2 | Encumbrance Free Land handover - Sec 1 | Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 | 230
Not Started | BLP-DWP-R5-5.3.1 | ED-Sec-1-3 | Permission for Dismantling of existing Govt / IR / Private Buildings and Properties | Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 | 230
Not Started | BLP-DWP-R5-5.3.1 | ED-Sec-1-4 | Tree Cutting Permission | Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 | 200
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-1 | S&T Works | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-2 | Electric Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-3 | Transmission Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-4 | Water pipe Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-5 | Sewer Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-6 | Gail / GAS Pipe line from Ch.(-) 0.411 to Ch. (-) 0.126 | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-7 | OFC Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-8 | Telecom Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.1.1 | ED-Sec-1-US-9 | Other Utilities (Wells, Hand pump, drain, Nallah, etc.) | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A | ED-Sec-2A-1.2 | Govt/Private Land Acquisition- Sec-2A | Section -2A Ch. (-) 0.050 to Ch. 5.700 (At Grade) | 230
Not Started | BLP-DWP-R5-5.3.2.A | ED-Sec-2A-2 | Dismantling of BBMP flyover at Ch: 3+100- Sec-2A | Section -2A Ch. (-) 0.050 to Ch. 5.700 (At Grade) | 230
Not Started | BLP-DWP-R5-5.3.2.A | ED-Sec-2A-3 | Encumbrance Free Land handover- Sec-2A | Section -2A Ch. (-) 0.050 to Ch. 5.700 (At Grade) | 230
Not Started | BLP-DWP-R5-5.3.2.A | ED-Sec-2A-4 | Permission for Dismantling of existing Govt / IR / Private Properties- Sec-2A | Section -2A Ch. (-) 0.050 to Ch. 5.700 (At Grade) | 230
Not Started | BLP-DWP-R5-5.3.2.A | ED-Sec-2A-5 | Tree Cutting Permission- Sec-2A | Section -2A Ch. (-) 0.050 to Ch. 5.700 (At Grade) | 200
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-1 | S&T Works | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-2 | Electric Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-3 | Transmission Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-4 | Water pipe Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-5 | Sewer Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-6 | Gail / GAS Pipe line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-7 | OFC Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-8 | Telecom Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.A.1 | ED-Sec-2-US-9 | Other Utilities (Wells, Hand pump, drain, Nallah, etc.) | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C | ED-Sec-2B&C-1.2 | Govt/Private Land Acquisition- Sec-2B & 2C | Section -2B & 2C Ch. 5.700 to Ch. 11.350 (At Grade) | 230
Not Started | BLP-DWP-R5-5.3.3 | ED-Sec-3-1.2 | Govt/Private Land Acquisition- Sec-3 | Section -3 Ch. 11.350 to Ch. 16.725 (Upto YPR Station) | 190
Not Started | BLP-DWP-R5-5.3.3 | ED-Sec-3-2 | Encumbrance Free Land handover- Sec-3 | Section -3 Ch. 11.350 to Ch. 16.725 (Upto YPR Station) | 190
Not Started | BLP-DWP-R5-5.3.3 | ED-Sec-3-3 | Permission for Dismantling of existing Govt / IR / Private Properties- Sec-3 | Section -3 Ch. 11.350 to Ch. 16.725 (Upto YPR Station) | 190
Not Started | BLP-DWP-R5-5.3.3 | ED-Sec-3-4 | Tree Cutting Permission- Sec-3 | Section -3 Ch. 11.350 to Ch. 16.725 (Upto YPR Station) | 145
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-1 | S&T Works | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-2 | Electric Cable | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-3 | Transmission Line | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-4 | Water pipe Line | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-5 | Sewer Line | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-6 | Gail / GAS Pipe line from Ch 12.747 to Ch. 12.785 & from Ch. 13.674 to Ch. 14.357 | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-7 | OFC Cable | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-8 | Telecom Cable | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.3.3.1 | ED-Sec-3-US-9 | Other Utilities (Wells, Hand pump, drain, Nallah, etc.) | Utility Shifting | 190
Not Started | BLP-DWP-R5-5.1 | IN-1 | Receipt of LOA | Initiation | 0
Not Started | BLP-DWP-R5-5.1 | IN-5 | Access to ROW for Pre-Construction activity | Initiation | 40
Not Started | BLP-DWP-R5-5.2.1 | CS-Aft LOI-1 | Submit Power of Attorney | After Receipt of LOA | 15
Not Started | BLP-DWP-R5-5.2.1 | CS-Aft LOI-2 | Appoint of Contractor's representative | After Receipt of LOA | 20
Not Started | BLP-DWP-R5-5.2.1 | CS-Aft LOI-3 | Appoint of Design Director | After Receipt of LOA | 20
Not Started | BLP-DWP-R5-5.2.1 | CS-Aft LOI-4 | Performance Bank Guarantee | After Receipt of LOA | 28
Not Started | BLP-DWP-R5-5.3.1 | ED-Sec-1-1.1 | Handing over of Railway land-Sec-1 | Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 | 118
Not Started | BLP-DWP-R5-5.3.2.A | ED-Sec-2A-1.1 | Handing over of Railway land-Sec-2A | Section -2A Ch. (-) 0.050 to Ch. 5.700 (At Grade) | 118
Not Started | BLP-DWP-R5-5.3.2.B&C | ED-Sec-2B&C-1.1 | Handing over of Railway land-Sec-2B & 2C | Section -2B & 2C Ch. 5.700 to Ch. 11.350 (At Grade) | 118
Not Started | BLP-DWP-R5-5.3.3 | ED-Sec-3-1.1 | Handing over of Railway land-Sec-3 | Section -3 Ch. 11.350 to Ch. 16.725 (Upto YPR Station) | 118
Not Started | BLP-DWP-R5-5.3.4 | ED-Sec-4-1.1 | Handing over of Railway land | Section -4 Ch. 16.725 to Ch. 24.425 | 118
Not Started | BLP-DWP-R5-5.3.2.B&C | ED-Sec-2B&C-3 | Permission for Dismantling of existing Govt / IR / Private Properties- Sec-2B & 2C | Section -2B & 2C Ch. 5.700 to Ch. 11.350 (At Grade) | 230
Not Started | BLP-DWP-R5-5.4.6 | PCY-1 | Finalisation of Precast Yard location/logistics | Casting Yard Setup | 15
Not Started | BLP-DWP-R5-5.3.2.B&C | ED-Sec-2B&C-2 | Encumbrance Free Land handover- Sec-2B & 2C | Section -2B & 2C Ch. 5.700 to Ch. 11.350 (At Grade) | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-1 | S&T Works | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-2 | Signalling boxes , Signalling HUT building , LC gates , existing Heigh gauges and associated obstructions at respective | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-3 | Electric Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-4 | Transmission Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-5 | Water pipe Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-6 | Sewer Line | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-7 | Gail / GAS Pipe line from Ch. 6.127 to Ch. 6.228 | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-8 | OFC Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-9 | Telecom Cable | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.2.B&C.1 | ED-Sec-2B&C-US-10 | Other Utilities (Wells, Hand pump, drain, Nallah, etc.) | Utility Shifting | 230
Not Started | BLP-DWP-R5-5.3.4 | ED-Sec-4-4 | Tree Cutting Permission- Sec-4 | Section -4 Ch. 16.725 to Ch. 24.425 | 180
Not Started | BLP-DWP-R5-5.3.2.B&C | ED-Sec-2B&C-4 | Tree Cutting Permission- Sec-2B & 2C | Section -2B & 2C Ch. 5.700 to Ch. 11.350 (At Grade) | 219
Not Started | BLP-DWP-R5-5.4.3 | GTI-Client Per. | Client - Permission for GTI Works | GTI | 1
Not Started | BLP-DWP-R5-5.4.3 | GTI-Traffic Per. | Traffic Permission | GTI | 102
Not Started | BLP-DWP-R5-5.1 | IN-2 | Client Kick-Off Meeting | Initiation | 1
Not Started | BLP-DWP-R5-5.4.3 | GTI-BH details | Submission of BH details in Alignment | GTI | 60
Not Started | BLP-DWP-R5-5.4.6.1 | PCY-2 | Identification of Casting Yard Land | Land | 180
Not Started | BLP-DWP-R5-5.4.4.1 | Des-Pre-1 | Submission of DBR | Preliminary Drawings | 45
Not Started | BLP-DWP-R5-5.4.7.5 | LG-1 | Identification of LG /Bridge Gantry (Inhouse/External) | Launching Girder | 60
Not Started | BLP-DWP-R5-5.4.2 | GPR-Client-Per | Client - Permission | GPR Survey | 1
Not Started | BLP-DWP-R5-5.4.3 | GTI-AG-Sec-2B | GTI @ AG in Ch 5.7 to 11.2 (37 Nos. BH)-Sec-2B | GTI | 40
Not Started | BLP-DWP-R5-5.4.3 | GTI-EV-Sec-3 | GTI @ EV in Ch 11.2-18.1 Hebbal (120 Nos. BH)-Sec-3 | GTI | 90
Not Started | BLP-DWP-R5-5.4.3 | GTI-AG-Sec-4 | GTI @AG in Ch 18.1-24.5 (36 Nos. BH)-Sec-4 | GTI | 50
Not Started | BLP-DWP-R5-5.4.1 | Pre-Topo-1 | Topo survey/Benchmark Establishment and Submission of Report | Topo Survey / ROW | 142
Not Started | BLP-DWP-R5-5.4.2.1 | GPR-Survey | Site Survey | GPR Site Survey | 90
Not Started | BLP-DWP-R5-5.4.4.1 | Des-Pre-2 | Approval of DBR by Client | Preliminary Drawings | 45
Not Started | BLP-DWP-R5-5.4.4.1 | Des-Pre-4 | Preliminary Alignment drawing along with P&P Submission | Preliminary Drawings | 100
Not Started | BLP-DWP-R5-5.4.7.5 | LG-2 | Preparation of Design and Fabrication Drawing by Agency | Launching Girder | 20
Not Started | BLP-DWP-R5-5.4.3 | GTI-EV-Sec-1 | GTI @ EV in Ch (-)0.964 to (-)0.05 (15 Nos. BH)-Sec-1 | GTI | 20
Not Started | BLP-DWP-R5-5.4.3 | GTI-AG-Sec-2A | GTI @ AG in Ch (-)0.05 to 5.7 (29 Nos. BH)-Sec-2A | GTI | 15
Not Started | BLP-DWP-R5-5.4.7.5 | LG-3 | Proof checking of Design / Drawing | Launching Girder | 15
Not Started | BLP-DWP-R5-5.4.4.1 | Des-Pre-5 | Preliminary Alignment drawing along with P&P Approval | Preliminary Drawings | 30
Not Started | BLP-DWP-R5-5.4.7.5 | LG-4 | Submission of Proof check Design and Drawing to Client / Engineer | Launching Girder | 5
Not Started | BLP-DWP-R5-5.4.7.5 | LG-5 | Approval of Design / Drawing of Launching Girder | Launching Girder | 7
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-15 | U-Girder GA Drawing Submission | Viaduct Design / Drawings | 7
Not Started | BLP-DWP-R5-5.4.7.5 | LG-6 | Delivery of Launching Girder | Launching Girder | 162
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-16 | Approval of U-Girder GA drawing | Viaduct Design / Drawings | 15
Not Started | BLP-DWP-R5-5.4.2.1 | GPR-Survey Rep Sub | Report Submission | GPR Site Survey | 15
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1.4 | Submission of Methodology for Pile Load Test | Viaduct Design / Drawings | 30
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1 | Identification of 1st test pile location | Viaduct Design / Drawings | 7
Not Started | BLP-DWP-R5-5.4.7.2 | Precast-UG-1 | Issue of approved U-Girder Drawing- to Agency | Precast Formwork U-Girder | 3
Not Started | BLP-DWP-R5-5.4.7.2 | Precast-UG-2 | Preparation of Design and Fabrication Drawing by Agency | Precast Formwork U-Girder | 7
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1.1 | Submission of 1st test pile design | Viaduct Design / Drawings | 10
Not Started | BLP-DWP-R5-5.4.4.2.2 | Des-Pile-App | Pile Design Approval-Overall piles | Balance Test Piles | 120
Not Started | BLP-DWP-R5-5.4.7.2 | Precast-UG-3 | Submission of fabrication Design and Drawing to Client / Engineer | Precast Formwork U-Girder | 3
Not Started | BLP-DWP-R5-5.4.4.2.2 | Des-Pile-Sub | Pile Design Submission-Overall piles | Balance Test Piles | 105
Not Started | BLP-DWP-R5-5.4.7.2 | Precast-UG-4 | Approval of Design / Drawing of U-Girder Mould | Precast Formwork U-Girder | 15
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1.3 | Approval of 1st test pile design by GC / Client | Viaduct Design / Drawings | 15
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-1 | Barricading of the area | 1st Test Pile | 2
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-2 | Pile Rig Mobilization incl tools | 1st Test Pile | 15
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1.5 | Approval of Pile load Test Methodology | Viaduct Design / Drawings | 15
Not Started | BLP-DWP-R5-5.4.7.2 | Precast-UG-5 | Delivery of Material to site - Bottom Shutter | Precast Formwork U-Girder | 50
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-3 | Cutting Bending of Reinforcement & cage tying | 1st Test Pile | 3
Not Started | BLP-DWP-R5-5.4.4.2.2 | TP-Des-Sub | Test Pile Design [ Total 10 Nos location ] Submission | Balance Test Piles | 30
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-4 | Pile boring | 1st Test Pile | 3
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-5 | Reinforcement Cage lowering with Sonic Pipes & Concreting | 1st Test Pile | 1
Not Started | BLP-DWP-R5-5.4.4.2.2 | TP-Des-App | Approval of Test pile design | Balance Test Piles | 27
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-6 | Excavation and pile head preparation | 1st Test Pile | 3
Not Started | BLP-DWP-R5-5.4.1 | Pre-Topo-2 | Joint validation of survey data with Client | Topo Survey / ROW | 57
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-8 | Test Pile-8 @ BH-119 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-9 | Test Pile-9 @ ROB-408B BH-175 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-7 | Sonic Test / Intrigity Test | 1st Test Pile | 2
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-10 | Test Pile-10 @ ROB-410A BH-177 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-8 | Clearance for pile load test from client/ Engineer | 1st Test Pile | 10
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-11 | Test Pile-11 @ MJB-560 BH-178 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.5.6.5-6.1 | CW-Sec-3-EV-1 | Tree Cutting/Transplantation | Tree cutting & Building dismantling | 130
Not Started | BLP-DWP-R5-5.5.6.5-6.1 | CW-Sec-3-EV-2 | Building Dismantling | Tree cutting & Building dismantling | 145
Not Started | BLP-DWP-R5-5.4.4.8 | Misc. Dwg-3 | Final Alignment Design / Drawing Submission along with P&P | Misc. Drawings | 60
Not Started | BLP-DWP-R5-5.4.4.8 | Misc. Dwg-5 | Submission Longitudinal Section for full alignment | Misc. Drawings | 60
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-9 | Vertical & Lateral Pile load test | 1st Test Pile | 10
Not Started | BLP-DWP-R5-5.5.7.2 | CW-Sec-4B-AG-1 | Tree Cutting/Transplantation | Section -4B Ch.18.100 to Ch. 24.425 (At Grade) - Length 6525 Meters | 75
Not Started | BLP-DWP-R5-5.5.7.2 | CW-Sec-4B-AG-2 | Building Dismantling | Section -4B Ch.18.100 to Ch. 24.425 (At Grade) - Length 6525 Meters | 75
Not Started | BLP-DWP-R5-5.5.7.2.2 | CW-Sec-4B-RUB-LH | Land handing over for RUB approaches | RUB | 152
Not Started | BLP-DWP-R5-5.4.6.1 | PCY-3 | Finalization of Casting Yard Layout | Land | 10
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-2 | Test Pile-2 @ BH-12 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-10 | Report Submission to Client / Engineer | 1st Test Pile | 7
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-3 | Test Pile-3 @ BH-56 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-4 | Test Pile-4 @ BH-67 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-5 | Test Pile-5 @ DD-1 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.8 | Misc. Dwg-4 | Approval of Final Alignment Drawing along with P&P | Misc. Drawings | 45
Not Started | BLP-DWP-R5-5.4.6.1 | PCY-4 | Approval of Casting Yard Layout | Land | 15
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-6 | Test Pile-6 @ BH-104 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.2.1 | TP-1-11 | Approval of Test pile form Client / Engineer | 1st Test Pile | 3
Not Started | BLP-DWP-R5-5.4.4.8 | Misc. Dwg-1 | Submission of Drain & Misc. design / Drawings | Misc. Drawings | 90
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-1 | MIB 6 Nos.(409,410,406,410B,410C,411) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-1 | MIB 6 Nos.(409,410,406,410B,410C,411) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-1 | Submission of GAD-408B | ROB-408B | 40
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-5 | Approval of GAD from IR-408B | ROB-408B | 120
Not Started | BLP-DWP-R5-5.4.4.2.3 | TP-7 | Test Pile-7 @ BH-113 | Balance Test Piles | 35
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1.6 | Validation of Working pile Design with 1st test Pile Report | Viaduct Design / Drawings | 10
Not Started | BLP-DWP-R5-5.4.4.3.1 | ERS-Sub-Sec-3 | ERS Design Submission - Section -4 Ch. 18.100 to Ch. 24.425 = Total 3.27Km | ERS Structure Design / Drawing Submission | 140
Not Started | BLP-DWP-R5-5.4.4.3.1 | ERS-Sub-Sec-2 | ERS Design Submission - Section -2 Ch. (-) 0.050 to Ch. 11.350 = Total 8.1Km | ERS Structure Design / Drawing Submission | 150
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-17 | U-Girder (31m) Design & Drawing Submission | Viaduct Design / Drawings | 7
Not Started | BLP-DWP-R5-5.4.7.2 | Precast-UG-6 | Delivery of Material to site - Side Shutter | Precast Formwork U-Girder | 54
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-2 | MIB 3 Nos.(405,412,407) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-2 | MIB 3 Nos.(405,412,407) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.4.4.7.3 | RUB-IR-App1 | RUB 6 Nos. (LC141, LC-143, LC144, LC-144A, 412B(RUB), LC-6 ) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.7.1 | RUB-Sub-1 | RUB 6 Nos. (LC141, LC-143, LC144, LC-144A, 412B(RUB), LC-6 ) | Submission of GAD & Structural design | 25
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-1 | Submission of GAD-410A | ROB-410A | 40
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-5 | Approval of GAD from IR-410A | ROB-410A | 120
Not Started | BLP-DWP-R5-5.4.4.3.2 | ERS-App-Sec-3 | ERS Design Approval - Section -4 Ch. 18.100 to Ch. 24.425 = Total 3.27Km | Approval of ERS Structure Drawing | 140
Not Started | BLP-DWP-R5-5.4.4.3.1 | ERS-Sub-Sec-1 | ERS Design Submission - Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 = Total 1.08 Km | ERS Structure Design / Drawing Submission | 145
Not Started | BLP-DWP-R5-5.4.4.2.9.1.2 | Des-Via-154 | I-Girder Design / Drawing Submission | PR2-PR3 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.4 | Des-Via-174 | I-Girder Design / Drawing Submission | PR3-PR4 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.3 | Des-Via-194 | I-Girder Design / Drawing Submission | PR4-PR5 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.8 | Des-Via-214 | I-Girder Design / Drawing Submission | PR5-PR6 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.7 | Des-Via-234 | I-Girder Design / Drawing Submission | PR6-PR7 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.6 | Des-Via-254 | I-Girder Design / Drawing Submission | PR7-PR8 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.5 | Des-Via-274 | I-Girder Design / Drawing Submission | PR8-PR9 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.16 | Des-Via-294 | I-Girder Design / Drawing Submission | PR9-PR10 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.15 | Des-Via-314 | I-Girder Design / Drawing Submission | PR10-PR11 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.14 | Des-Via-334 | I-Girder Design / Drawing Submission | PR11-PR12 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.13 | Des-Via-354 | I-Girder Design / Drawing Submission | PR12-PR13 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.12 | Des-Via-374 | I-Girder Design / Drawing Submission | PR13-PR14 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.1.11 | Des-Via-394 | I-Girder Design / Drawing Submission | PR14-PR15 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.13 | Des-Via-414 | I-Girder Design / Drawing Submission | P194-P195 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.29 | Des-Via-434 | I-Girder Design / Drawing Submission | P195-P196 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.38 | Des-Via-454 | I-Girder Design / Drawing Submission | P195-P197 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.39 | Des-Via-474 | I-Girder Design / Drawing Submission | P197-P198 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.40 | Des-Via-494 | I-Girder Design / Drawing Submission | P198-P199 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.41 | Des-Via-514 | I-Girder Design / Drawing Submission | P199-P200 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.42 | Des-Via-534 | I-Girder Design / Drawing Submission | P200-P201 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.43 | Des-Via-554 | I-Girder Design / Drawing Submission | P201-P202 | 14
Not Started | BLP-DWP-R5-5.4.4.2.9.2.44 | Des-Via-574 | I-Girder Design / Drawing Submission | P202-P203 | 14
Not Started | BLP-DWP-R5-5.4.4.3.2 | ERS-App-Sec-2 | ERS Design Approval - Section -2 Ch. (-) 0.050 to Ch. 11.350 = Total 8.1Km | Approval of ERS Structure Drawing | 145
Not Started | BLP-DWP-R5-5.4.6.1 | PCY-5 | Acquiring of CY land | Land | 2
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-18 | Approval of U-Girder (31m) design & drawing | Viaduct Design / Drawings | 15
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-13 | Portal Design / Drawing Submission | Viaduct Design / Drawings | 75
Not Started | BLP-DWP-R5-5.4.6.2 | PCY-6 | Checking of Bearing Capacity of CY | CY Enabling Work | 20
Not Started | BLP-DWP-R5-5.4.6.2 | PCY-9 | Initial Survey & Area demarcation | CY Enabling Work | 2
Not Started | BLP-DWP-R5-5.5.5.2 | CW-Sec-2B-1 | Tree Cutting/Transplantation-2B Ch. 5.700 to Ch. 10.700 | Section -2B Ch. 5.700 to Ch. 10.700 (At Grade) - Length 5000 Meters | 115
Not Started | BLP-DWP-R5-5.5.5.2 | CW-Sec-2B-2 | Building Dismantling-2B Ch. 5.700 to Ch. 10.700 | Section -2B Ch. 5.700 to Ch. 10.700 (At Grade) - Length 5000 Meters | 115
Not Started | BLP-DWP-R5-5.4.4.3.2 | ERS-App-Sec-1 | ERS Design Approval - Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 = Total 1.08Km | Approval of ERS Structure Drawing | 135
Not Started | BLP-DWP-R5-5.4.6.2 | PCY-10 | Area levelling and development | CY Enabling Work | 70
Not Started | BLP-DWP-R5-5.5.5.2.1.2 | CW-Sec-2B1-RUB-Pre-1 | Preliminary works ( Diversion, Approval etc.) | RUB | 75
Not Started | BLP-DWP-R5-5.5.4 | CW-Sec-1-1 | Tree Cutting/Transplantation-1A Ch. (-) 0.964 to Ch. (-) 0. 675 | Civil Works : Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 | 115
Not Started | BLP-DWP-R5-5.4.4.2.4.1 | Des-Via-34 | Steel Girder Design / Drawing Submission | P112 - P113 | 60
Not Started | BLP-DWP-R5-5.4.4.2.4.2 | Des-Via-54 | Steel Girder Design / Drawing Submission | P184R - P185R | 60
Not Started | BLP-DWP-R5-5.4.4.2.4.3 | Des-Via-74 | Steel Girder Design / Drawing Submission | P185R - P186R | 60
Not Started | BLP-DWP-R5-5.4.4.2.4.4 | Des-Via-94 | Steel Girder Design / Drawing Submission | P184L - P185L | 60
Not Started | BLP-DWP-R5-5.4.4.2.4.5 | Des-Via-114 | Steel Girder Design / Drawing Submission | P185L - P186L | 60
Not Started | BLP-DWP-R5-5.4.4.2.4.6 | Des-Via-134 | Steel Girder Design / Drawing Submission | P207 - P208 | 60
Not Started | BLP-DWP-R5-5.4.6.2 | PCY-7 | Submission of detailed design drawing including formwork to Client | CY Enabling Work | 20
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App2 | MIB 3 Nos.(405,412,407) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.4.4.5 | MJB-560-1 | GAD Submission-MJB-560 | Major Bridge- MJB 560 | 15
Not Started | BLP-DWP-R5-5.4.4.5 | MJB-560-3 | Approval of GAD from IR-MJB-560 | Major Bridge- MJB 560 | 120
Not Started | BLP-DWP-R5-5.4.6.3 | PCY-UG-11 | Gantry Pedestal | Casting Bed - U Girder | 90
Not Started | BLP-DWP-R5-5.4.4.2.9.1.2 | Des-Via-164 | Approval of I-Girder Drawing | PR2-PR3 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.4 | Des-Via-184 | Approval of I-Girder Drawing | PR3-PR4 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.3 | Des-Via-204 | Approval of I-Girder Drawing | PR4-PR5 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.8 | Des-Via-224 | Approval of I-Girder Drawing | PR5-PR6 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.7 | Des-Via-244 | Approval of I-Girder Drawing | PR6-PR7 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.6 | Des-Via-264 | Approval of I-Girder Drawing | PR7-PR8 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.5 | Des-Via-284 | Approval of I-Girder Drawing | PR8-PR9 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.16 | Des-Via-304 | Approval of I-Girder Drawing | PR9-PR10 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.15 | Des-Via-324 | Approval of I-Girder Drawing | PR10-PR11 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.14 | Des-Via-344 | Approval of I-Girder Drawing | PR11-PR12 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.13 | Des-Via-364 | Approval of I-Girder Drawing | PR12-PR13 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.12 | Des-Via-384 | Approval of I-Girder Drawing | PR13-PR14 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.1.11 | Des-Via-404 | Approval of I-Girder Drawing | PR14-PR15 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.13 | Des-Via-424 | Approval of I-Girder Drawing | P194-P195 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.29 | Des-Via-444 | Approval of I-Girder Drawing | P195-P196 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.38 | Des-Via-464 | Approval of I-Girder Drawing | P195-P197 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.39 | Des-Via-484 | Approval of I-Girder Drawing | P197-P198 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.40 | Des-Via-504 | Approval of I-Girder Drawing | P198-P199 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.41 | Des-Via-524 | Approval of I-Girder Drawing | P199-P200 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.42 | Des-Via-544 | Approval of I-Girder Drawing | P200-P201 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.43 | Des-Via-564 | Approval of I-Girder Drawing | P201-P202 | 30
Not Started | BLP-DWP-R5-5.4.4.2.9.2.44 | Des-Via-584 | Approval of I-Girder Drawing | P202-P203 | 30
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-3 | MIB 6 Nos.(547,552,558,540,553,563) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-3 | MIB 6 Nos.(547,552,558,540,553,563) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.4.4.7.3 | RUB-IR-App2 | RUB 5 Nos. (407A (RUB), LC137,23+725 (RUB) , 539 (RUB), RUB Nagawara) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.7.1 | RUB-Sub-2 | RUB 5 Nos. (407A (RUB), LC137,23+725 (RUB) , 539 (RUB), RUB Nagawara) | Submission of GAD & Structural design | 25
Not Started | BLP-DWP-R5-5.4.6.3 | PCY-UG-12 | Casting Bed | Casting Bed - U Girder | 75
Not Started | BLP-DWP-R5-5.4.7.3 | Precast-IG-1 | Issue of GA Drawing I-Girder - to Agency | Precast Formwork I-Girder | 30
Not Started | BLP-DWP-R5-5.4.4.2.4.1 | Des-Via-44 | Steel Girder Design / Drawing Approval | P112 - P113 | 100
Not Started | BLP-DWP-R5-5.4.4.2.4.2 | Des-Via-64 | Steel Girder Design / Drawing Approval | P184R - P185R | 100
Not Started | BLP-DWP-R5-5.4.4.2.4.3 | Des-Via-84 | Steel Girder Design / Drawing Approval | P185R - P186R | 100
Not Started | BLP-DWP-R5-5.4.4.2.4.4 | Des-Via-95 | Steel Girder Design / Drawing Approval | P184L - P185L | 100
Not Started | BLP-DWP-R5-5.4.4.2.4.5 | Des-Via-124 | Steel Girder Design / Drawing Approval | P185L - P186L | 100
Not Started | BLP-DWP-R5-5.4.4.2.4.6 | Des-Via-144 | Steel Girder Design / Drawing Approval | P207 - P208 | 100
Not Started | BLP-DWP-R5-5.5.5.2.1.4 | CW-Sec-2B1-ERS-1 | Outer side of Track-2B Ch. 5.700 to Ch. 10.700-P1 | Earth Retaining Structure | 250
Not Started | BLP-DWP-R5-5.5.5.2.1.4 | CW-Sec-2B1-ERS-2 | Temp. Retaining Structure-2B Ch. 5.700 to Ch. 10.700-P1 | Earth Retaining Structure | 250
Not Started | BLP-DWP-R5-5.4.4.7.2 | RUB-Client-App1 | RUB 6 Nos. (LC141, LC-143, LC144, LC-144A, 412B(RUB), LC-6 ) | Approval of GAD & Structural design from GC & KRIDE (including road authorities) | 30
Not Started | BLP-DWP-R5-5.4.6.4 | PCY-PC-16 | Gantry Pedestal | Casting Bed - Pier Cap | 45
Not Started | BLP-DWP-R5-5.4.6.3 | PCY-UG-15 | U-Girder Shutter installation and Mock-up and checking | Casting Bed - U Girder | 25
Not Started | BLP-DWP-R5-5.4.4.5 | MJB-560-2 | Approval of GAD Drawing from Client / Kride-MJB-560 | Major Bridge- MJB 560 | 30
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App3 | MIB 6 Nos.(547,552,558,540,553,563) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.4.6.4 | PCY-PC-17 | Casting Bed | Casting Bed - Pier Cap | 45
Not Started | BLP-DWP-R5-5.4.6.2 | PCY-8 | Approval of detailed design drawing including formwork by Client | CY Enabling Work | 15
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-4 | MIB 5 Nos.(404,403,402,406DN,410D) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-4 | MIB 5 Nos.(404,403,402,406DN,410D) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-19 | Balance U-Girder (28m, 25m, 22m) Design & Drawing Submission | Viaduct Design / Drawings | 28
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-3 | Approval of GAD from GC & KRIDE (including road authorities)- 408B | ROB-408B | 30
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-11 | Pier cap Design / Drawing submission | Viaduct Design / Drawings | 45
Not Started | BLP-DWP-R5-5.4.7.4 | Precast-PC-1 | Issue of GA Drawing Pier Cap - to Agency | Precast Formwork Piercap | 15
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-1 | Preliminary works ( Diversion, Methodology, Approval etc.) | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 90
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-2 | Submission of Dismantling Methodology/Scheme-408B | ROB-408B | 30
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1.9 | Pile Cap and Pier design / Drawings Submission | Viaduct Design / Drawings | 50
Not Started | BLP-DWP-R5-5.5.5.1 | CW-Sec-2A-1 | Tree Cutting/Transplantation-2A Ch. (-) 0.050 to Ch. 5.700 | Section -2A Ch. (-) 0.050 to Ch. 5.700 (At Grade) - Length 5650 Meters | 122
Not Started | BLP-DWP-R5-5.5.5.1 | CW-Sec-2A-2 | Building Dismantling-2A Ch. (-) 0.050 to Ch. 5.700 | Section -2A Ch. (-) 0.050 to Ch. 5.700 (At Grade) - Length 5650 Meters | 122
Not Started | BLP-DWP-R5-5.5.5.1.2 | CW-Sec-2A-RUB-LH | Land handing over for RUB approaches | RUB | 153
Not Started | BLP-DWP-R5-5.5.5.2.1.2 | CW-Sec-2B1-RUB-Pre-2 | Land handing over for RUB approaches | RUB | 105
Not Started | BLP-DWP-R5-5.5.5.2.1.2 | CW-Sec-2B1-RUB-Pre-3 | Signalling boxes , Signalling HUT building , LC gates , existing Heigh gauges and associated obstructions at respective | RUB | 120
Not Started | BLP-DWP-R5-5.5.4 | CW-Sec-1-2 | Building Dismantling-1A Ch. (-) 0.964 to Ch. (-) 0. 675 | Civil Works : Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 | 75
Not Started | BLP-DWP-R5-5.1 | IN-4 | Receipt of NTP | Initiation | 0
Not Started | BLP-DWP-R5-5.2.2 | CS-Aft NTP-1 | Initial work program submission | After Receipt of NTP | 15
Not Started | BLP-DWP-R5-5.2.2 | CS-Aft NTP-5 | Insurance - Works(CAR) / Third Party / Workmen / Plant etc.. | After Receipt of NTP | 20
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-5 | MIB 6 Nos.(556,557,559,561,562,564) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App4 | MIB 5 Nos.(404,403,402,406DN,410D) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-5 | MIB 6 Nos.(556,557,559,561,562,564) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-3 | Approval of GAD from GC & KRIDE (including road authorities)- 410A | ROB-410A | 30
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1.7 | Pile Design Submission | Viaduct Design / Drawings | 7
Not Started | BLP-DWP-R5-5.4.6.3 | PCY-UG-14 | U Girder Zig fabrication and fixing | Casting Bed - U Girder | 25
Not Started | BLP-DWP-R5-5.4.4.7.2 | RUB-Client-App2 | RUB 5 Nos. (407A (RUB), LC137,23+725 (RUB) , 539 (RUB), RUB Kanakanagar) | Approval of GAD & Structural design from GC & KRIDE (including road authorities) | 30
Not Started | BLP-DWP-R5-5.4.4.7.3 | RUB-IR-App3 | RUB 4 Nos. (LC140,LC142,RUB Kanaknagar,541B (RUB)) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.7.1 | RUB-Sub-3 | RUB 4 Nos. (LC140,LC142,RUB Kanaknagar,541B (RUB)) | Submission of GAD & Structural design | 25
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-10 | Approval of Pile Cap and Pier Drawings | Viaduct Design / Drawings | 30
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-2 | Submission of Dismantling Methodology/Scheme-410A | ROB-410A | 30
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-1.8 | Approval of Pile Design | Viaduct Design / Drawings | 15
Not Started | BLP-DWP-R5-5.5.7.10.3 | CW-Sec-4A-1 | Tree cutting/Transplantation Ch.16.725 to Ch. 18.100 | Tree cutting & building dismantling | 45
Not Started | BLP-DWP-R5-5.5.7.10.3 | CW-Sec-4A-2 | Building dismantling Ch.16.725 to Ch. 18.100 | Tree cutting & building dismantling | 45
Not Started | BLP-DWP-R5-5.4.7.3 | Precast-IG-2 | Preparation of Design and Fabrication Drawing by Agency | Precast Formwork I-Girder | 15
Not Started | BLP-DWP-R5-5.4.7.4 | Precast-PC-2 | Preparation of Design and Fabrication Drawing by Agency | Precast Formwork Piercap | 10
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-6 | MIB 7 Nos.(548,549,550,550A,551,554,555) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App5 | MIB 6 Nos.(556,557,559,561,562,564) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-6 | MIB 7 Nos.(548,549,550,550A,551,554,555) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.5.7.2.5 | CW-Sec-4B-ERS | Outer side of Track-4B Ch.18.100 to Ch. 24.425 | Earth Retaining Structure | 420
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-1 | Shutter cleaning (Buffing) & Oil application | 1st U-Girder Casting | 1
Not Started | BLP-DWP-R5-5.5.7.2.2.1 | CW-Sec-4B-RUB-LC-6-1 | Raft | CH. 22.975 RUB (1no x 30m) Re-construction length 22.2 LC-6 | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.2.1 | CW-Sec-2B1-RUB-143-1 | Raft | CH. 7.547 RUB (1no x 30m) Re-construction length 48.96 LC-143 | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.2 | CW-Sec-2B1-RUB-141-1 | Raft | CH. 6.675 RUB (1no x 30m) Re-construction length 41.31 LC-141 | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.3 | CW-Sec-2B1-RUB-144-1 | Raft | CH. 8.175 RUB (1no x 30m) Re-construction length 41.31 LC-144 | 25
Not Started | BLP-DWP-R5-5.4.4.5 | MJB-560-4 | Major Bridge Structural design/drawing Submission-MJB-560 | Major Bridge- MJB 560 | 45
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-20 | Balance U-Girder (28m, 25m, 22m) Design & Drawing Approval | Viaduct Design / Drawings | 15
Not Started | BLP-DWP-R5-5.2.2 | CS-Aft NTP-2 | Engineers Consent on Initial work plan | After Receipt of NTP | 21
Not Started | BLP-DWP-R5-5.5.5.1.3 | CW-Sec-2A-ERS | Outer side of Track-2A Ch. (-) 0.050 to Ch. 5.700 | Earth Retaining Structure | 183
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-1 | Submission of Agency Credentials - Steel Girder | Steel Girder for Viaduct / MJBR / ROB | 30
Not Started | BLP-DWP-R5-5.4.4.5 | MJB-560-6 | Approval of Structural design/drawing of Major Bridges from IR-MJB-560 | Major Bridge- MJB 560 | 120
Not Started | BLP-DWP-R5-5.4.7.4 | Precast-PC-3 | Proof checking of Design / Drawing | Precast Formwork Piercap | 10
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-7 | MIB 7 Nos.(565,566,567,568,569,570,571) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App6 | MIB 7 Nos.(548,549,550,550A,551,554,555) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-7 | MIB 7 Nos.(565,566,567,568,569,570,571) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App1 | MIB 6 Nos.(409,410,406,410B,410C,411) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-7 | Submission of Detailed Design & Drawing- 408B | ROB-408B | 60
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-9 | Approval of Detailed Design & Drawing by IR- 408B | ROB-408B | 120
Not Started | BLP-DWP-R5-5.1 | IN-3 | Contract Signing | Initiation | 0
Not Started | BLP-DWP-R5-5.4.7.3 | Precast-IG-3 | Proof checking of Design / Drawing | Precast Formwork I-Girder | 7
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-4 | Approval of Dismantling Methodology/Scheme by GC & KRIDE (including raod authorities)- 408B | ROB-408B | 30
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-6 | Approval of Dismantling Methodology/Scheme by IR- 408B | ROB-408B | 52
Not Started | BLP-DWP-R5-5.4.4.7.2 | RUB-Client-App3 | RUB 4 Nos. (LC140,LC142,RUB Nagawara,541B (RUB)) | Approval of GAD & Structural design from GC & KRIDE (including road authorities) | 30
Not Started | BLP-DWP-R5-5.4.7.4 | Precast-PC-4 | Submission of Proof check Design and Drawing to Client / Engineer | Precast Formwork Piercap | 3
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-8 | MIB 6 Nos.(534,535,536,537,538/1,538/2) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App7 | MIB 7 Nos.(565,566,567,568,569,570,571) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-8 | MIB 6 Nos.(534,535,536,537,538/1,538/2) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-7 | Submission of Detailed Design & Drawing- 410A | ROB-410A | 60
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-9 | Approval of Detailed Design & Drawing by IR- 410A | ROB-410A | 120
Not Started | BLP-DWP-R5-5.4.7.3 | Precast-IG-4 | Submission of Proof check Design and Drawing to Client / Engineer | Precast Formwork I-Girder | 3
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-2 | Reinforcement tying in Zig | 1st U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.1 | CW-Sec-2B1-MIB-547-1 | Raft | CH. 5.8 MIB 2X2.5 length 29.896 Br No 547 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.2 | CW-Sec-2B1-MIB-552-1 | Raft | CH. 7.4 MIB 2X2.64 length 43.72 Br No 552 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.3 | CW-Sec-2B1-MIB-558-1 | Raft | CH. 9.466 MIB 2X2.5 length 35.684 Br No 558 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.4 | CW-Sec-2B1-MIB-553-1 | Raft | CH. 8.236 MIB 2X2.5 length 43.446 Br No 553 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.5 | CW-Sec-2B1-MIB-563-1 | Raft | CH. 10.244 MIB 2X2.5 length 31.914 Br No 563 | 15
Not Started | BLP-DWP-R5-5.4.6.4 | PCY-PC-18 | Stacking Bed Concrete | Casting Bed - Pier Cap | 20
Not Started | BLP-DWP-R5-5.4.6.4 | PCY-PC-19 | Pier Cap Zig fabrication and fixing | Casting Bed - Pier Cap | 20
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-30 | Bearing Design Submission | Viaduct Design / Drawings | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.2.4 | CW-Sec-2B1-RUB-KNG-1 | Raft | CH. 8.675 RUB 1no. X 6X5.5 length 40 Kanaka nagar | 25
Not Started | BLP-DWP-R5-5.4.7.3 | Precast-IG-5 | Approval of Design / Drawing of I-Girder Mould | Precast Formwork I-Girder | 15
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-4 | Approval of Dismantling Methodology/Scheme by GC & KRIDE (including raod authorities)- 410A | ROB-410A | 30
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-6 | Approval of Dismantling Methodology/Scheme by IR- 410A | ROB-410A | 52
Not Started | BLP-DWP-R5-5.4.6.5 | PCY-IG-21 | Gantry Pedestal | Casting Bed - I Girder | 60
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-12 | Approval of Pier cap Drawings | Viaduct Design / Drawings | 30
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-2 | Area barrication | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 15
Not Started | BLP-DWP-R5-5.4.4.8 | Misc. Dwg-2 | Approval of Drain / Misc. Drawings | Misc. Drawings | 15
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-14 | Portal Design / Drawing Approval | Viaduct Design / Drawings | 30
Not Started | BLP-DWP-R5-5.2.2 | CS-Aft NTP-3 | Detailed Work Program submission | After Receipt of NTP | 60
Not Started | BLP-DWP-R5-5.4.6.5 | PCY-IG-22 | Casting Bed | Casting Bed - I Girder | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.1 | CW-Sec-2B1-RUB-143-2 | Wall | CH. 7.547 RUB (1no x 30m) Re-construction length 48.96 LC-143 | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.2 | CW-Sec-2B1-RUB-141-2 | Wall | CH. 6.675 RUB (1no x 30m) Re-construction length 41.31 LC-141 | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.3 | CW-Sec-2B1-RUB-144-2 | Wall | CH. 8.175 RUB (1no x 30m) Re-construction length 41.31 LC-144 | 25
Not Started | BLP-DWP-R5-5.4.4.6.3 | MIB-IR-App-9 | MIB 7 Nos.(541A,541C,542,543,544,545,546) | Approval from IR | 120
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App8 | MIB 6 Nos.(534,535,536,537,538/1,538/2) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.4.4.6.1 | MIB-Sub-9 | MIB 7 Nos.(541A,541C,542,543,544,545,546) | Submission of GAD & Structural design | 10
Not Started | BLP-DWP-R5-5.5.7.2.2.1 | CW-Sec-4B-RUB-LC-6-2 | Wall | CH. 22.975 RUB (1no x 30m) Re-construction length 22.2 LC-6 | 35
Not Started | BLP-DWP-R5-5.5.5.2.1.1.3 | CW-Sec-2B1-MIB-558-2 | Wall | CH. 9.466 MIB 2X2.5 length 35.684 Br No 558 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.4 | CW-Sec-2B1-MIB-553-2 | Wall | CH. 8.236 MIB 2X2.5 length 43.446 Br No 553 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.5 | CW-Sec-2B1-MIB-563-2 | Wall | CH. 10.244 MIB 2X2.5 length 31.914 Br No 563 | 15
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-2 | Approval of Agency from Client / Engineer | Steel Girder for Viaduct / MJBR / ROB | 15
Not Started | BLP-DWP-R5-5.4.7.3 | Precast-IG-6 | Delivery of Material to site - Bottom Shutter | Precast Formwork I-Girder | 30
Not Started | BLP-DWP-R5-5.4.7.3 | Precast-IG-7 | Delivery of Material to site - Side Shutter | Precast Formwork I-Girder | 60
Not Started | BLP-DWP-R5-5.4.4.6.2 | MIB-Client-App9 | MIB 7 Nos.(541A,541C,542,543,544,545,546) | Approval of GAD & Structural design from GC & KRIDE | 30
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-3 | Cage Lowering | 1st U-Girder Casting | 1
Not Started | BLP-DWP-R5-5.5.5.2.1.1.1 | CW-Sec-2B1-MIB-547-2 | Wall | CH. 5.8 MIB 2X2.5 length 29.896 Br No 547 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.2 | CW-Sec-2B1-MIB-552-2 | Wall | CH. 7.4 MIB 2X2.64 length 43.72 Br No 552 | 15
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-4 | Bulk Head Fixing and Outer shutter alingment | 1st U-Girder Casting | 2
Not Started | BLP-DWP-R5-5.5.5.2.1.1.6 | CW-Sec-2B1-MIB-548-1 | Raft | CH. 6.49 MIB 2X2.5 length 34.71 Br No 548 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11 | LG-Erec-1 | Erection of Launching Girder | Erection of Superstructure | 100
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-5 | HT Strand Threading | 1st U-Girder Casting | 1
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-6 | Stressing | 1st U-Girder Casting | 2
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-7 | Inner shutter lowering and Alingment | 1st U-Girder Casting | 2
Not Started | BLP-DWP-R5-5.4.4.8 | Misc. Dwg-6 | Approval of Longitudinal sections | Misc. Drawings | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.2.4 | CW-Sec-2B1-RUB-KNG-2 | Wall | CH. 8.675 RUB 1no. X 6X5.5 length 40 Kanaka nagar | 25
Not Started | BLP-DWP-R5-5.5.7.2.6.1 | CW-Sec-4B-EW-2 | Cutting / Filling-4B Ch. 19.100 to Ch. 20.100 | Cutting / Filling-4B Ch. 18.100 to Ch. 24.425 | 120
Not Started | BLP-DWP-R5-5.MS.7 | MS-AG1 | MS-1 At Grade: Start of Earthwork | Milestone- At Grade | 0
Not Started | BLP-DWP-R5-5.5.5.2.1.1.3 | CW-Sec-2B1-MIB-558-3 | Slab | CH. 9.466 MIB 2X2.5 length 35.684 Br No 558 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.4 | CW-Sec-2B1-MIB-553-3 | Slab | CH. 8.236 MIB 2X2.5 length 43.446 Br No 553 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.5 | CW-Sec-2B1-MIB-563-3 | Slab | CH. 10.244 MIB 2X2.5 length 31.914 Br No 563 | 20
Not Started | BLP-DWP-R5-5.4.4.5 | MJB-560-5 | Approval of Structural design/drawing of Major Bridges from Client / Engineer-MJB-560 | Major Bridge- MJB 560 | 30
Not Started | BLP-DWP-R5-5.4.6.3 | PCY-UG-13 | Stacking Bed | Casting Bed - U Girder | 60
Not Started | BLP-DWP-R5-5.4.4.2 | Des-Via-594 | Bearing Design Approval | Viaduct Design / Drawings | 15
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-3 | Submission of Proof check Design and Drawing to Client / Engineer | Steel Girder for Viaduct / MJBR / ROB | 10
Not Started | BLP-DWP-R5-5.4.6.5 | PCY-IG-23 | Stacking Bed | Casting Bed - I Girder | 75
Not Started | BLP-DWP-R5-5.4.6.5 | PCY-IG-24 | I Girder Zig fabrication and fixing | Casting Bed - I Girder | 20
Not Started | BLP-DWP-R5-5.4.6.5 | PCY-IG-25 | I Girder Side shutter mock-up and checking | Casting Bed - I Girder | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.2.1 | CW-Sec-2B1-RUB-143-3 | Slab | CH. 7.547 RUB (1no x 30m) Re-construction length 48.96 LC-143 | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.2.2 | CW-Sec-2B1-RUB-141-3 | Slab | CH. 6.675 RUB (1no x 30m) Re-construction length 41.31 LC-141 | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.2.3 | CW-Sec-2B1-RUB-144-3 | Slab | CH. 8.175 RUB (1no x 30m) Re-construction length 41.31 LC-144 | 30
Not Started | BLP-DWP-R5-5.4.7.4 | Precast-PC-5 | Approval of Design / Drawing of Pier Cap Mould | Precast Formwork Piercap | 7
Not Started | BLP-DWP-R5-5.5.5.2.1.1.1 | CW-Sec-2B1-MIB-547-3 | Slab | CH. 5.8 MIB 2X2.5 length 29.896 Br No 547 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.2 | CW-Sec-2B1-MIB-552-3 | Slab | CH. 7.4 MIB 2X2.64 length 43.72 Br No 552 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-157 | Precast portal beam casting at location | PR-39 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-164 | Precast portal beam casting at location | PR-40 | 36
Not Started | BLP-DWP-R5-5.5.5.2.1.1.6 | CW-Sec-2B1-MIB-548-2 | Wall | CH. 6.49 MIB 2X2.5 length 34.71 Br No 548 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.1 | PILE2340 | Piles | P-1 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.19 | PILE3960 | Piles | P-19 | 6
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-4 | Approval of Fabrication Design / Drawing of Steel Girder | Steel Girder for Viaduct / MJBR / ROB | 30
Not Started | BLP-DWP-R5-5.4.7.4 | Precast-PC-6 | Delivery of Material to site - Shutter | Precast Formwork Piercap | 45
Not Started | BLP-DWP-R5-5.5.7.10.4.31.188 | PILE4330 | Piles | P186-L | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.188 | PILE1950 | Piles | P186-R | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.11 | PILE1120 | Piles | P209 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.3.79 | CW-Sec-3-295.5 | Approach over nallah | Approach over nallah | 120
Not Started | BLP-DWP-R5-5.5.7.2.1.1 | CW-Sec-4B-MIB-410-1 | Raft | CH. 19.575 MIB 3X2.65 length 26.988 Br No 410 | 15
Not Started | BLP-DWP-R5-5.MS.7 | MS-AG3 | MS-3: Start of 1 MNB | Milestone- At Grade | 0
Not Started | BLP-DWP-R5-5.4.4.4.1 | ROB-408B-8 | Approval of Detailed Design & Drawing by GC and KRIDE (including road authorities)- 408B | ROB-408B | 30
Not Started | BLP-DWP-R5-5.5.5.3 | CW-Sec-2C-1 | Tree Cutting/Transplantation-2C Ch.10.700 to Ch. 11.350 | Section -2C Ch.10.700 to Ch. 11.350 (At Grade) - Length 650 Meters | 135
Not Started | BLP-DWP-R5-5.4.6.4 | PCY-PC-20 | Pier Cap Shutter Installation and Mock-up | Casting Bed - Pier Cap | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.2 | PILE3410 | Piles | P-2 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.20 | PILE3970 | Piles | P-20 | 6
Not Started | BLP-DWP-R5-5.5.7.2.6.1 | CW-Sec-4B-EW-7 | Cutting / Filling-4B Ch. 20.100 to Ch. 21.100 | Cutting / Filling-4B Ch. 18.100 to Ch. 24.425 | 120
Not Started | BLP-DWP-R5-5.5.7.2.1.2 | CW-Sec-4B-MIB-409-1 | Raft | CH. 19.65 MIB 2X2.65 length 22.203 Br No 409 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.3 | CW-Sec-4B-MIB-406-1 | Raft | CH. 21.775 MIB 3x2.65 length 18.401 Br No 406 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.189 | PILE4340 | Piles | P187-L | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.1 | CW-Sec-3-2 | Pile Cap | P-1 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.19 | CW-Sec-3-74 | Pile Cap | P-19 | 10
Not Started | BLP-DWP-R5-5.MS.6 | MS-EV1 | MS-1 Elevated: Completion of 1st Working Pile | Milestone - Elevated | 0
Not Started | BLP-DWP-R5-5.4.4.4.2 | ROB-410A-8 | Approval of Detailed Design & Drawing by GC and KRIDE (including road authorities)- 410A | ROB-410A | 30
Not Started | BLP-DWP-R5-5.5.7.10.4.1.189 | PILE1000 | Piles | P187-R | 6
Not Started | BLP-DWP-R5-5.5.7.2.2.1 | CW-Sec-4B-RUB-LC-6-3 | Slab | CH. 22.975 RUB (1no x 30m) Re-construction length 22.2 LC-6 | 40
Not Started | BLP-DWP-R5-5.5.5.3 | CW-Sec-2C-2 | Building Dismantling-2C Ch.10.700 to Ch. 11.350 | Section -2C Ch.10.700 to Ch. 11.350 (At Grade) - Length 650 Meters | 135
Not Started | BLP-DWP-R5-5.5.5.2.1.5.1 | CW-Sec-2B1-EW-1 | Cutting / Filling-2B Ch. 5.700 to Ch. 6.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P1 | 160
Not Started | BLP-DWP-R5-5.5.5.2.1.3 | CW-Sec-2B1-MJB-560-1 | Foundation | CH. 9.992 MJB 2X30.5 length Br No 560 | 70
Not Started | BLP-DWP-R5-5.5.6.9.10.204.3 | PILE2330 | Piles | P-3 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.21 | PILE3980 | Piles | P-21 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.188 | 394 | Pile Cap | P186-R | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.1.3 | CW-Sec-2B1-MIB-558-4 | Return wall | CH. 9.466 MIB 2X2.5 length 35.684 Br No 558 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.4 | CW-Sec-2B1-MIB-553-4 | Return wall | CH. 8.236 MIB 2X2.5 length 43.446 Br No 553 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.5 | CW-Sec-2B1-MIB-563-4 | Return wall | CH. 10.244 MIB 2X2.5 length 31.914 Br No 563 | 20
Not Started | BLP-DWP-R5-5.5.7.2.2.4 | CW-Sec-4B-RUB-407A-1 | Preliminary works & premission to close the traffic on ROB-407A | CH. 20.6 RUB 5.5m X 6.75m Br No 407A | 135
Not Started | BLP-DWP-R5-5.5.5.2.1.1.6 | CW-Sec-2B1-MIB-548-3 | Slab | CH. 6.49 MIB 2X2.5 length 34.71 Br No 548 | 20
Not Started | BLP-DWP-R5-5.5.4.1.1 | CW-ERS-Sec-1A | Outer side of Track-1A Ch. (-) 0.964 to Ch. (-) 0. 675 | Earth Retaining Structure | 180
Not Started | BLP-DWP-R5-5.2.2 | CS-Aft NTP-4 | Approval of Detailed Work Program | After Receipt of NTP | 21
Not Started | BLP-DWP-R5-5.5.7.10.4.31.2 | PILE4350 | Piles | P188-L | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.2 | CW-Sec-3-6 | Pile Cap | P-2 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.20 | CW-Sec-3-78 | Pile Cap | P-20 | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.2.4 | CW-Sec-2B1-RUB-KNG-3 | Slab | CH. 8.675 RUB 1no. X 6X5.5 length 40 Kanaka nagar | 30
Not Started | BLP-DWP-R5-5.5.4 | CW-Sec-1-3 | Retaining wall near Railway embankment | Civil Works : Section -1 Ch. (-) 0.964 to Ch. (-) 0.050 | 250
Not Started | BLP-DWP-R5-5.5.4.2.33.4 | PILE4360 | Piles | PR-1 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.2 | PILE1020 | Piles | P188-R | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.10 | PILE1140 | Piles | P210 | 12
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-5 | Fabrication & Delivery of Material to site for Phase 1 MJBR | Steel Girder for Viaduct / MJBR / ROB | 102
Not Started | BLP-DWP-R5-5.5.7.2.2.1 | CW-Sec-4B-RUB-LC-6-4 | Approaches & misc. work | CH. 22.975 RUB (1no x 30m) Re-construction length 22.2 LC-6 | 60
Not Started | BLP-DWP-R5-5.5.7.2.1.4 | CW-Sec-4B-MIB-410B1 | Raft | CH. 19.175 MIB 2X1.8 length 41.354 Br No 410B | 15
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-3 | Dismantalling | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 45
Not Started | BLP-DWP-R5-5.5.7.2.4 | CW-Sec-4B-ROB-410A-1 | Preliminary works ( Diversion, Methodology, Approval etc.) | CH. 19.2 ROB Re-construction (2 sapns)(35+27) length Br No 410A | 90
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-8 | Concreting / Casting of U - Girder | 1st U-Girder Casting | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.204.4 | PILE2430 | Piles | P-4 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.22 | PILE3990 | Piles | P-22 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.189 | 3126 | Pile Cap | P187-R | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.11 | 3202 | Pile Cap | P209 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.1 | CW-Sec-2B1-MIB-547-4 | Return wall | CH. 5.8 MIB 2X2.5 length 29.896 Br No 547 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.2 | CW-Sec-2B1-MIB-552-4 | Return wall | CH. 7.4 MIB 2X2.64 length 43.72 Br No 552 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | PILE2490 | Piles | PR-39 | 15
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-9 | Curing Period | 1st U-Girder Casting | 2
Not Started | BLP-DWP-R5-5.MS.6 | MS-EV2 | MS-2: Start of Casting of U Girder | Milestone - Elevated | 0
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1001 | P1-P2 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1002 | P2-P3 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1003 | P3-P4 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1004 | P4-P5 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1005 | P5-P6 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1006 | P6-P7 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1007 | P7-P8 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1008 | P8-P9 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.19 | CW-Sec-3-75 | Pier | P-19 | 12
Not Started | BLP-DWP-R5-5.5.7.2.1.1 | CW-Sec-4B-MIB-410-2 | Wall | CH. 19.575 MIB 3X2.65 length 26.988 Br No 410 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.1 | CW-Sec-3-3 | Pier | P-1 | 12
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10000 | P-1 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10010 | P-2 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10020 | P-3 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10030 | P-4 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10040 | P-5 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10050 | P-6 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10060 | P-7 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10070 | P-8 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.1 | PILE1330 | Piles | P189-L | 6
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-10 | Destressing & Strand Cutting | 1st U-Girder Casting | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.204.3 | CW-Sec-3-10 | Pile Cap | P-3 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.21 | CW-Sec-3-82 | Pile Cap | P-21 | 10
Not Started | BLP-DWP-R5-5.5.7.2.1.5 | CW-Sec-4B-MIB-410C1 | Raft | CH. 19.15 MIB 2X1.8 length 32.281 Br No 410C | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.6 | CW-Sec-4B-MIB-4111 | Raft | CH. 18.725 MIB 2X2.65 length 25.099 Br No 411 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.1 | PILE1010 | Piles | P189-R | 6
Not Started | BLP-DWP-R5-5.5.3.1 | UG-Casting-11 | Lifting of U-Girder & Stacking in Yard | 1st U-Girder Casting | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.31.188 | CW-Sec-4-2 | Pile Cap | P186-L | 10
Not Started | BLP-DWP-R5-5.5.7.2.1.2 | CW-Sec-4B-MIB-409-2 | Wall | CH. 19.65 MIB 2X2.65 length 22.203 Br No 409 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.3 | CW-Sec-4B-MIB-406-2 | Wall | CH. 21.775 MIB 3x2.65 length 18.401 Br No 406 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.188 | 395 | Pier | P186-R | 15
Not Started | BLP-DWP-R5-5.MS.6 | MS-EV3 | MS-3 Elevated: Casting of 1st Pier | Milestone - Elevated | 0
Not Started | BLP-DWP-R5-5.5.6.9.10.204.5 | PILE2520 | Piles | P-5 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.23 | PILE4000 | Piles | P-23 | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.5.1 | CW-Sec-2B1-EW-2 | Cutting / Filling-2B Ch. 6.700 to Ch. 7.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P1 | 120
Not Started | BLP-DWP-R5-5.4.7.6 | Des-Via-604 | Procurement of Bearing | Bearing | 90
Not Started | BLP-DWP-R5-5.5.6.9.10.204.2 | CW-Sec-3-7 | Pier | P-2 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.20 | CW-Sec-3-79 | Pier | P-20 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.6 | PILE1360 | Piles | P190-L | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.4 | CW-Sec-3-14 | Pile Cap | P-4 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.22 | CW-Sec-3-86 | Pile Cap | P-22 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.5 | PILE2170 | Piles | PR-2 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.6 | PILE1040 | Piles | P190-R | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.9 | PILE1130 | Piles | P211 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.2 | 3162 | Pile Cap | P188-R | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1009 | P9-P10 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.MS.7 | MS-AG2 | MS-2: Completion of 2 Km Emb/Cutting | Milestone- At Grade | 0
Not Started | BLP-DWP-R5-5.5.6.9.10.204.6 | PILE2610 | Piles | P-6 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.24 | PILE4010 | Piles | P-24 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10080 | P-9 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10090 | P-10 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10100 | P-11 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10110 | P-12 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10120 | P-13 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10130 | P-14 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10140 | P-15 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10150 | P-16 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.4 | CW-Sec-1B-PR-1-2 | Pile Cap | PR-1 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.3 | CW-Sec-2B1-MJB-560-2 | Substructure | CH. 9.992 MJB 2X30.5 length Br No 560 | 90
Not Started | BLP-DWP-R5-5.5.6.9.10.204.3 | CW-Sec-3-11 | Pier | P-3 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.21 | CW-Sec-3-83 | Pier | P-21 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.19 | CW-Sec-3-881 | Pier: Curing, De-Shuttering, De-Staging | P-19 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.1 | CW-Sec-3-13 | Pier: Curing, De-Shuttering, De-Staging | P-1 | 7
Not Started | BLP-DWP-R5-5.5.7.2.1.4 | CW-Sec-4B-MIB-410B2 | Wall | CH. 19.175 MIB 2X1.8 length 41.354 Br No 410B | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.188 | CW-Sec-4-3 | Pier | P186-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.189 | CW-Sec-4-6 | Pile Cap | P187-L | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.5 | PILE1380 | Piles | P191-L | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.5 | CW-Sec-3-18 | Pile Cap | P-5 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.23 | CW-Sec-3-90 | Pile Cap | P-23 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.5 | PILE1060 | Piles | P191-R | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.1.9 | CW-Sec-2B1-MIB-550A1 | Raft | CH. 7.125 MIB 5X3.53 length 52.602 Br No 550A | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.10 | CW-Sec-2B1-MIB-551-1 | Raft | CH. 7.192 MIB 2X2.91 length 50.138 Br No 551 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.11 | CW-Sec-2B1-MIB-554-1 | Raft | CH. 8.375 MIB 2X1.8 length 52.49 Br No 554 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | PILE2500 | Piles | PR-40 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.6 | CW-Sec-2B1-MIB-548-4 | Return wall | CH. 6.49 MIB 2X2.5 length 34.71 Br No 548 | 20
Not Started | BLP-DWP-R5-5.5.7.2.1.1 | CW-Sec-4B-MIB-410-3 | Slab | CH. 19.575 MIB 3X2.65 length 26.988 Br No 410 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-171 | Precast portal beam casting at location | PR-41 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-178 | Precast portal beam casting at location | PR-42 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-3761 | Portal Beam: Curing, De-Shuttering, De-Staging | PR-40 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-3781 | Portal Beam: Curing, De-Shuttering, De-Staging | PR-39 | 31
Not Started | BLP-DWP-R5-5.5.7.2.1.5 | CW-Sec-4B-MIB-410C2 | Wall | CH. 19.15 MIB 2X1.8 length 32.281 Br No 410C | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.6 | CW-Sec-4B-MIB-4112 | Wall | CH. 18.725 MIB 2X2.65 length 25.099 Br No 411 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.7 | PILE2720 | Piles | P-7 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.25 | PILE4020 | Piles | P-25 | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.2.1 | CW-Sec-2B1-RUB-143-4 | Approaches & misc. work | CH. 7.547 RUB (1no x 30m) Re-construction length 48.96 LC-143 | 30
Not Started | BLP-DWP-R5-5.5.5.3.2 | CW-Sec-2C-ERS-1 | Outer side of Track-2C Ch.10.700 to Ch. 11.350 | Earth Retaining Structure | 0
Not Started | BLP-DWP-R5-5.5.5.2.1.5.1 | CW-Sec-2B1-EW-3 | Cutting / Filling-2B Ch. 7.700 to Ch. 8.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P1 | 100
Not Started | BLP-DWP-R5-5.5.6.9.10.204.4 | CW-Sec-3-15 | Pier | P-4 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.22 | CW-Sec-3-87 | Pier | P-22 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.2 | CW-Sec-3-711 | Pier: Curing, De-Shuttering, De-Staging | P-2 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.20 | CW-Sec-3-891 | Pier: Curing, De-Shuttering, De-Staging | P-20 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.1 | 3158 | Pile Cap | P189-R | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.11 | 3203 | Portal Pier | P209 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.10 | 3210 | Pile Cap | P210 | 20
Not Started | BLP-DWP-R5-5.5.7.2.1.2 | CW-Sec-4B-MIB-409-3 | Slab | CH. 19.65 MIB 2X2.65 length 22.203 Br No 409 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.3 | CW-Sec-4B-MIB-406-3 | Slab | CH. 21.775 MIB 3x2.65 length 18.401 Br No 406 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.4 | PILE1370 | Piles | P192-L | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.1.7 | CW-Sec-2B1-MIB-549-1 | Raft | CH. 6.913 MIB 2X2.5 length 31.367 Br No 549 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.8 | CW-Sec-2B1-MIB-550-1 | Raft | CH. 7.025 MIB 2X2.5 length 52.604 Br No 550 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1010 | P10-P11 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1011 | P11-P12 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1012 | P12-P13 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1013 | P13-P14 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1014 | P14-P15 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1015 | P15-P16 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1016 | P16-P17 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.189 | 3127 | Pier | P187-R | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.6 | CW-Sec-3-22 | Pile Cap | P-6 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.24 | CW-Sec-3-94 | Pile Cap | P-24 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.188 | CW-Sec-4-1000 | Pier: Curing, De-Shuttering, De-Staging | P186-R | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.6 | PILE2260 | Piles | PR-3 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.4 | PILE1050 | Piles | P192-R | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.8 | PILE1110 | Piles | P212 | 12
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10160 | P-17 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10170 | P-18 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10180 | P-19 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10190 | P-20 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10200 | P-21 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10210 | P-22 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10220 | P-23 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10230 | P-24 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.2.2 | CW-Sec-2B1-RUB-141-4 | Approaches & misc.work | CH. 6.675 RUB (1no x 30m) Re-construction length 41.31 LC-141 | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.204.8 | PILE2830 | Piles | P-8 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.26 | PILE2350 | Piles | P-26 | 6
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-4 | Foundation | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 45
Not Started | BLP-DWP-R5-5.5.4.2.33.5 | CW-Sec-1B-PR-2-2 | Pile Cap | PR-2 | 20
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-10 | Fabrication & Delivery of Material to site for ROB-408B | Steel Girder for Viaduct / MJBR / ROB | 90
Not Started | BLP-DWP-R5-5.5.7.10.4.31.2 | CW-Sec-4-10 | Pile Cap | P188-L | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.1 | CW-Sec-3-4 | Pier Cap Erection | P-1 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.5 | CW-Sec-3-19 | Pier | P-5 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.23 | CW-Sec-3-91 | Pier | P-23 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.3 | CW-Sec-3-731 | Pier: Curing, De-Shuttering, De-Staging | P-3 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.21 | CW-Sec-3-901 | Pier: Curing, De-Shuttering, De-Staging | P-21 | 7
Not Started | BLP-DWP-R5-5.5.5.2.1.2.3 | CW-Sec-2B1-RUB-144-4 | Approaches & misc. work | CH. 8.175 RUB (1no x 30m) Re-construction length 41.31 LC-144 | 30
Not Started | BLP-DWP-R5-5.5.7.10.4.31.3 | PILE1350 | Piles | P193-L | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.2 | CW-Sec-3-8 | Pier Cap Erection | P-2 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.1 | CW-Sec-3-PR-5-31 | Pedestal & Seismic arrestors | P-1 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.7 | CW-Sec-3-26 | Pile Cap | P-7 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.25 | CW-Sec-3-98 | Pile Cap | P-25 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.3 | PILE1030 | Piles | P193-R | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.1.46 | PILE1890 | Piles | P194 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.2 | CW-Sec-3-PR-5-32 | Pedestal & Seismic arrestors | P-2 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.4 | CW-Sec-4B-MIB-410B3 | Slab | CH. 19.175 MIB 2X1.8 length 41.354 Br No 410B | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.189 | CW-Sec-4-7 | Pier | P187-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.188 | CW-Sec-4-1010 | Pier: Curing, De-Shuttering, De-Staging | P186-L | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.9 | PILE2940 | Piles | P-9 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.27 | PILE2360 | Piles | P-27 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.6 | 3170 | Pile Cap | P190-R | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.2.4 | CW-Sec-2B1-RUB-KNG-4 | Approaches & misc. work | CH. 8.675 RUB 1no. X 6X5.5 length 40 Kanaka nagar | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.1.9 | CW-Sec-2B1-MIB-550A2 | Wall | CH. 7.125 MIB 5X3.53 length 52.602 Br No 550A | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.10 | CW-Sec-2B1-MIB-551-2 | Wall | CH. 7.192 MIB 2X2.91 length 50.138 Br No 551 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.11 | CW-Sec-2B1-MIB-554-2 | Wall | CH. 8.375 MIB 2X1.8 length 52.49 Br No 554 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | PILE2510 | Piles | PR-41 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1017 | P17-P18 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.6 | CW-Sec-3-23 | Pier | P-6 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.24 | CW-Sec-3-95 | Pier | P-24 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.4 | CW-Sec-3-721 | Pier: Curing, De-Shuttering, De-Staging | P-4 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.22 | CW-Sec-3-911 | Pier: Curing, De-Shuttering, De-Staging | P-22 | 7
Not Started | BLP-DWP-R5-5.5.7.2.1.1 | CW-Sec-4B-MIB-410-4 | Return wall | CH. 19.575 MIB 3X2.65 length 26.988 Br No 410 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.3 | CW-Sec-3-12 | Pier Cap Erection | P-3 | 2
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10240 | P-25 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10250 | P-26 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10260 | P-27 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10270 | P-28 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10280 | P-29 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10290 | P-30 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10300 | P-31 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10310 | P-32 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.4 | CW-Sec-1B-PR-1-3 | Portal Pier | PR-1 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.14 | PILE1400 | Piles | P194-L | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.31.13 | PILE1420 | Piles | P237 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.43 | PILE2010 | Piles | P236 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.8 | CW-Sec-3-30 | Pile Cap | P-8 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.26 | CW-Sec-3-102 | Pile Cap | P-26 | 10
Not Started | BLP-DWP-R5-5.5.7.2.1.5 | CW-Sec-4B-MIB-410C3 | Slab | CH. 19.15 MIB 2X1.8 length 32.281 Br No 410C | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.6 | CW-Sec-4B-MIB-4113 | Slab | CH. 18.725 MIB 2X2.65 length 25.099 Br No 411 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.2.5 | CW-Sec-2B1-RUB-142-1 | Raft | CH. 6.944 RUB (1no x 30m) LC-142 | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.6 | CW-Sec-2B1-RUB-140-1 | Raft | CH. 6.313 RUB (1no x 30m) Re-construction length 41.31 LC-140 | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.7 | CW-Sec-2B1-RUB-144A1 | Raft | CH. 8.775 RUB (1no x 30m) Re-construction length 62.73 LC-144A | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.8 | CW-Sec-2B1-RUB-NAG-1 | Raft | CH. 7.075 RUB (1no x 30m) Re-construction length 40 Nagawara | 25
Not Started | BLP-DWP-R5-5.5.7.2.2.3 | CW-Sec-4B-RUB@18.6-1 | Raft | CH. 23.725 RUB 1no. X 4mX4 length 18.655 - | 30
Not Started | BLP-DWP-R5-5.5.4.2.33.7 | PILE2270 | Piles | PR-4 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.7 | PILE1070 | Piles | P213 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-161 | Pile Cap | PR-40 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.3 | CW-Sec-3-PR-5-33 | Pedestal & Seismic arrestors | P-3 | 15
Not Started | BLP-DWP-R5-5.5.7.2.6.2 | CW-Sec-4B-Blan-2 | Blanketing-4B Ch. 19.100 to Ch. 20.100 | Blanketing-4B Ch. 18.100 to Ch. 24.425 | 60
Not Started | BLP-DWP-R5-5.5.7.10.4.31.1 | 3286 | Pile Cap | P189-L | 10
Not Started | BLP-DWP-R5-5.5.7.2.1.2 | CW-Sec-4B-MIB-409-4 | Return wall | CH. 19.65 MIB 2X2.65 length 22.203 Br No 409 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.3 | CW-Sec-4B-MIB-406-4 | Return wall | CH. 21.775 MIB 3x2.65 length 18.401 Br No 406 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.7 | CW-Sec-2B1-MIB-549-2 | Wall | CH. 6.913 MIB 2X2.5 length 31.367 Br No 549 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.8 | CW-Sec-2B1-MIB-550-2 | Wall | CH. 7.025 MIB 2X2.5 length 52.604 Br No 550 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.2 | 3163 | Pier | P188-R | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.189 | CW-Sec-4-1020 | Pier: Curing, De-Shuttering, De-Staging | P187-R | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.10 | PILE3050 | Piles | P-10 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.28 | PILE2370 | Piles | P-28 | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.1.12 | CW-Sec-2B1-MIB-555-1 | Raft | CH. 8.6 MIB 2X2.5 length 46.642 Br No 555 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.6 | CW-Sec-1B-PR-3-2 | Pile Cap | PR-3 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.11 | CW-Sec-4-1030 | Portal Pier: Curing, De-Shuttering, De-Staging | P209 | 7
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-5 | Substructure | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 60
Not Started | BLP-DWP-R5-5.5.6.9.10.204.7 | CW-Sec-3-27 | Pier | P-7 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.25 | CW-Sec-3-99 | Pier | P-25 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.5 | CW-Sec-3-741 | Pier: Curing, De-Shuttering, De-Staging | P-5 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.23 | CW-Sec-3-921 | Pier: Curing, De-Shuttering, De-Staging | P-23 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.4 | CW-Sec-3-16 | Pier Cap Erection | P-4 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-162 | Portal Pier | PR-40 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.12 | PILE1410 | Piles | P238 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.9 | CW-Sec-3-34 | Pile Cap | P-9 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.27 | CW-Sec-3-106 | Pile Cap | P-27 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.45 | PILE1900 | Piles | P195 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.4 | CW-Sec-3-PR-5-34 | Pedestal & Seismic arrestors | P-4 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.5 | 3178 | Pile Cap | P191-R | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.10 | 3211 | Portal Pier | P210 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.9 | 3206 | Pile Cap | P211 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1018 | P18-P19 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1019 | P19-P20 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1020 | P20-P21 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1021 | P21-P22 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1022 | P22-P23 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1023 | P23-P24 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1024 | P24-P25 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.11 | PILE3160 | Piles | P-11 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.29 | PILE2380 | Piles | P-29 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10320 | P-33 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10330 | P-34 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10340 | P-35 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10350 | P-36 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10360 | P-37 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10370 | P-38 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10380 | P-44 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10390 | P-45 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.8 | CW-Sec-3-31 | Pier | P-8 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.26 | CW-Sec-3-103 | Pier | P-26 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.6 | CW-Sec-3-751 | Pier: Curing, De-Shuttering, De-Staging | P-6 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.24 | CW-Sec-3-931 | Pier: Curing, De-Shuttering, De-Staging | P-24 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.5 | CW-Sec-3-20 | Pier Cap Erection | P-5 | 2
Not Started | BLP-DWP-R5-5.5.7.2.1.4 | CW-Sec-4B-MIB-410B4 | Return wall | CH. 19.175 MIB 2X1.8 length 41.354 Br No 410B | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.5 | CW-Sec-1B-PR-2-3 | Portal Pier | PR-2 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.2 | CW-Sec-4-11 | Pier | P188-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.6 | 3298 | Pile Cap | P190-L | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.189 | CW-Sec-4-1040 | Pier: Curing, De-Shuttering, De-Staging | P187-L | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.11 | PILE1440 | Piles | P239 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.10 | CW-Sec-3-38 | Pile Cap | P-10 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.28 | CW-Sec-3-110 | Pile Cap | P-28 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.8 | PILE2280 | Piles | PR-5 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.30 | PILE1160 | Piles | P214 | 12
Not Started | BLP-DWP-R5-5.5.5.2.1.1.9 | CW-Sec-2B1-MIB-550A3 | Slab | CH. 7.125 MIB 5X3.53 length 52.602 Br No 550A | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.10 | CW-Sec-2B1-MIB-551-3 | Slab | CH. 7.192 MIB 2X2.91 length 50.138 Br No 551 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.11 | CW-Sec-2B1-MIB-554-3 | Slab | CH. 8.375 MIB 2X1.8 length 52.49 Br No 554 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | PILE2530 | Piles | PR-42 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.5 | CW-Sec-3-PR-5-35 | Pedestal & Seismic arrestors | P-5 | 15
Not Started | BLP-DWP-R5-5.5.5.3.3 | CW-Sec-2C-EW | Cutting / Filling-2C Ch.10.700 to Ch. 11.350 | Formation | 210
Not Started | BLP-DWP-R5-5.5.7.2.1.5 | CW-Sec-4B-MIB-410C4 | Return wall | CH. 19.15 MIB 2X1.8 length 32.281 Br No 410C | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.6 | CW-Sec-4B-MIB-4114 | Return wall | CH. 18.725 MIB 2X2.65 length 25.099 Br No 411 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.12 | PILE3270 | Piles | P-12 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.30 | PILE2390 | Piles | P-30 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.7 | CW-Sec-1B-PR-4-2 | Pile Cap | PR-4 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.4 | CW-Sec-1B-PR-1-6 | Portal Pier: Curing,De-shuttering,De-Staging | PR-1 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-168 | Pile Cap | PR-41 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.9 | CW-Sec-3-35 | Pier | P-9 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.27 | CW-Sec-3-107 | Pier | P-27 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.7 | CW-Sec-3-761 | Pier: Curing, De-Shuttering, De-Staging | P-7 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.25 | CW-Sec-3-941 | Pier: Curing, De-Shuttering, De-Staging | P-25 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.6 | CW-Sec-3-24 | Pier Cap Erection | P-6 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.4 | 3174 | Pile Cap | P192-R | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.10 | PILE1460 | Piles | P240 | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.1.7 | CW-Sec-2B1-MIB-549-3 | Slab | CH. 6.913 MIB 2X2.5 length 31.367 Br No 549 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.8 | CW-Sec-2B1-MIB-550-3 | Slab | CH. 7.025 MIB 2X2.5 length 52.604 Br No 550 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1025 | P25-P26 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.1 | 3159 | Pier | P189-R | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.11 | CW-Sec-3-42 | Pile Cap | P-11 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.29 | CW-Sec-3-114 | Pile Cap | P-29 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.2 | CW-Sec-4-1050 | Pier: Curing, De-Shuttering, De-Staging | P188-R | 7
Not Started | BLP-DWP-R5-5.5.5.2.1.1.12 | CW-Sec-2B1-MIB-555-2 | Wall | CH. 8.6 MIB 2X2.5 length 46.642 Br No 555 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.44 | PILE1920 | Piles | P196 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.6 | CW-Sec-3-PR-5-36 | Pedestal & Seismic arrestors | P-6 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10400 | P-46 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10410 | P-47 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10420 | P-48 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10430 | P-49 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10440 | P-50 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10450 | P-51 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10460 | P186-R | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10470 | P-52 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-169 | Portal Pier | PR-41 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-185 | Precast portal beam casting at location | PR-43 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-3801 | Portal Beam: Curing, De-Shuttering, De-Staging | PR-41 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-3821 | Portal Beam: Curing, De-Shuttering, De-Staging | PR-42 | 31
Not Started | BLP-DWP-R5-5.5.5.2.1.5.1 | CW-Sec-2B1-EW-4 | Cutting / Filling-2B Ch. 8.700 to Ch. 9.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P1 | 120
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-3751 | Portal Pier: Curing, De-Shuttering, De-Staging | PR-40 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.13 | PILE3380 | Piles | P-13 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.31 | PILE2400 | Piles | P-31 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.5 | 3306 | Pile Cap | P191-L | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.10 | CW-Sec-3-39 | Pier | P-10 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.28 | CW-Sec-3-111 | Pier | P-28 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.8 | CW-Sec-3-781 | Pier: Curing, De-Shuttering, De-Staging | P-8 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.26 | CW-Sec-3-961 | Pier: Curing, De-Shuttering, De-Staging | P-26 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.4 | CW-Sec-1B-PR-1-4 | Portal Beam Cast In Situ | PR-1 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.204.7 | CW-Sec-3-28 | Pier Cap Erection | P-7 | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.6 | CW-Sec-1B-PR-3-3 | Portal Pier | PR-3 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.10 | CW-Sec-4-1060 | Portal Pier: Curing, De-Shuttering, De-Staging | P210 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.9 | PILE1450 | Piles | P241 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.12 | CW-Sec-3-46 | Pile Cap | P-12 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.30 | CW-Sec-3-118 | Pile Cap | P-30 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.9 | PILE2290 | Piles | PR-6 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.29 | PILE1180 | Piles | P215 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.7 | CW-Sec-3-PR-5-37 | Pedestal & Seismic arrestors | P-7 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.2.5 | CW-Sec-2B1-RUB-142-2 | Wall | CH. 6.944 RUB (1no x 30m) LC-142 | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.6 | CW-Sec-2B1-RUB-140-2 | Wall | CH. 6.313 RUB (1no x 30m) Re-construction length 41.31 LC-140 | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.7 | CW-Sec-2B1-RUB-144A2 | Wall | CH. 8.775 RUB (1no x 30m) Re-construction length 62.73 LC-144A | 25
Not Started | BLP-DWP-R5-5.5.5.2.1.2.8 | CW-Sec-2B1-RUB-NAG-2 | Wall | CH. 7.075 RUB (1no x 30m) Re-construction length 40 Nagawara | 25
Not Started | BLP-DWP-R5-5.5.7.2.1.7 | CW-Sec-4B-MIB-407-1 | Raft | CH. 20.975 MIB 4X2.65 length 13.182 Br No 407 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.1 | 3287 | Pier | P189-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.2 | CW-Sec-4-1070 | Pier: Curing, De-Shuttering, De-Staging | P188-L | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.14 | PILE3500 | Piles | P-14 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.32 | PILE2410 | Piles | P-32 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.8 | CW-Sec-1B-PR-5-2 | Pile Cap | PR-5 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.5 | CW-Sec-1B-PR-1-17 | Portal Pier: Curing,De-shuttering,De-Staging | PR-2 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.3 | 3166 | Pile Cap | P193-R | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.1.7 | 3182 | Pile Cap | P213 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.9 | 3207 | Portal Pier | P211 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.8 | 3198 | Pile Cap | P212 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.30 | 3218 | Pile Cap | P214 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.46 | 3734 | Pile Cap | P194 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | PILE2540 | Piles | PR-43 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1026 | P26-P27 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1027 | P27-P28 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1028 | P28-P29 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1029 | P29-P30 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1030 | P30-P31 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1031 | P31-P32 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1032 | P32-P33 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.11 | CW-Sec-3-43 | Pier | P-11 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.29 | CW-Sec-3-115 | Pier | P-29 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-163 | Portal cap & pedestal | PR-40 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.9 | CW-Sec-3-771 | Pier: Curing, De-Shuttering, De-Staging | P-9 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.27 | CW-Sec-3-951 | Pier: Curing, De-Shuttering, De-Staging | P-27 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.8 | CW-Sec-3-32 | Pier Cap Erection | P-8 | 2
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10480 | P-53 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10490 | P-54 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10500 | P-55 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10510 | P-56 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10520 | P-57 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10530 | P-58 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10540 | P-59 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10550 | P-60 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.8 | PILE1430 | Piles | P242 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.13 | CW-Sec-3-50 | Pile Cap | P-13 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.31 | CW-Sec-3-122 | Pile Cap | P-31 | 10
Not Started | BLP-DWP-R5-5.5.7.2.1.8 | CW-Sec-4B-MIB-405-1 | Raft | CH. 22.625 MIB 8.1X7.20 length 12.574 Br No 405 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.9 | CW-Sec-4B-MIB-404-1 | Raft | CH. 23.65 MIB 8.4X5.35 length 20.241 Br No 404 | 15
Not Started | BLP-DWP-R5-5.5.7.2.2.3 | CW-Sec-4B-RUB@18.6-2 | Wall | CH. 23.725 RUB 1no. X 4mX4 length 18.655 - | 35
Not Started | BLP-DWP-R5-5.5.7.10.4.1.43 | PILE1910 | Piles | P197 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-175 | Pile Cap | PR-42 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.8 | CW-Sec-3-PR-5-38 | Pedestal & Seismic arrestors | P-8 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.4 | 3302 | Pile Cap | P192-L | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03150 | PR1-PR2-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03160 | PR1-PR2-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03170 | PR1-PR2-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03180 | PR1-PR2-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03190 | PR1-PR2-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03200 | PR1-PR2-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03210 | PR1-PR2-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03220 | PR1-PR2-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.1.9 | CW-Sec-2B1-MIB-550A4 | Return wall | CH. 7.125 MIB 5X3.53 length 52.602 Br No 550A | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.10 | CW-Sec-2B1-MIB-551-4 | Return wall | CH. 7.192 MIB 2X2.91 length 50.138 Br No 551 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.11 | CW-Sec-2B1-MIB-554-4 | Return wall | CH. 8.375 MIB 2X1.8 length 52.49 Br No 554 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.6 | 3171 | Pier | P190-R | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.1 | CW-Sec-4-1080 | Pier: Curing, De-Shuttering, De-Staging | P189-R | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.15 | PILE3610 | Piles | P-15 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.33 | PILE2420 | Piles | P-33 | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.1.12 | CW-Sec-2B1-MIB-555-3 | Slab | CH. 8.6 MIB 2X2.5 length 46.642 Br No 555 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.12 | CW-Sec-3-47 | Pier | P-12 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.30 | CW-Sec-3-119 | Pier | P-30 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.10 | CW-Sec-3-791 | Pier: Curing, De-Shuttering, De-Staging | P-10 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.28 | CW-Sec-3-971 | Pier: Curing, De-Shuttering, De-Staging | P-28 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.5 | CW-Sec-1B-PR-2-4 | Portal Beam Cast In Situ | PR-2 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.204.9 | CW-Sec-3-36 | Pier Cap Erection | P-9 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-176 | Portal Pier | PR-42 | 16
Not Started | BLP-DWP-R5-5.5.4.2.33.7 | CW-Sec-1B-PR-4-3 | Portal Pier | PR-4 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.7 | PILE1390 | Piles | P243 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.10.39 | UGE12730 | U-Girder | P1-P2 by LG | 2
Not Started | BLP-DWP-R5-5.MS.6 | MS-EV4 | MS-4 Elevated: Start of Erection of U Girder | Milestone - Elevated | 0
Not Started | BLP-DWP-R5-5.5.5.2.1.5.1 | CW-Sec-2B1-EW-5 | Cutting / Filling-2B Ch. 9.700 to Ch. 10.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P1 | 120
Not Started | BLP-DWP-R5-5.5.6.9.10.204.14 | CW-Sec-3-54 | Pile Cap | P-14 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.32 | CW-Sec-3-126 | Pile Cap | P-32 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-3791 | Portal Pier: Curing, De-Shuttering, De-Staging | PR-41 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.10 | PILE2300 | Piles | PR-7 | 12
Not Started | BLP-DWP-R5-5.5.7.2.6.1 | CW-Sec-4B-EW-3 | Cutting / Filling-4B Ch. 21.100 to Ch. 22.100 | Cutting / Filling-4B Ch. 18.100 to Ch. 24.425 | 120
Not Started | BLP-DWP-R5-5.5.7.10.4.1.28 | PILE1170 | Piles | P216 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.9 | CW-Sec-3-PR-5-39 | Pedestal & Seismic arrestors | P-9 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.10.2 | UGE11060 | U-Girder | P2-P3 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.1.1.7 | CW-Sec-2B1-MIB-549-4 | Return wall | CH. 6.913 MIB 2X2.5 length 31.367 Br No 549 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.8 | CW-Sec-2B1-MIB-550-4 | Return wall | CH. 7.025 MIB 2X2.5 length 52.604 Br No 550 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1033 | P33-P34 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.10 | CW-Sec-3-40 | Pier Cap Erection | P-10 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.16 | PILE3720 | Piles | P-16 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.34 | PILE2440 | Piles | P-34 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10560 | P-61 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10570 | P-62 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10580 | P-63 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10590 | P-64 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10600 | P-65 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10610 | P-66 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10620 | P-67 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10630 | P-68 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.9 | CW-Sec-1B-PR-6-2 | Pile Cap | PR-6 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.6 | CW-Sec-1B-PR-1-37 | Portal Pier: Curing,De-shuttering,De-Staging | PR-3 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.29 | 3226 | Pile Cap | P215 | 20
Not Started | BLP-DWP-R5-5.5.6.9.11.10.4 | UGE12640 | U-Girder | P3-P4 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.13 | CW-Sec-3-51 | Pier | P-13 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.31 | CW-Sec-3-123 | Pier | P-31 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.11 | CW-Sec-3-801 | Pier: Curing, De-Shuttering, De-Staging | P-11 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.29 | CW-Sec-3-981 | Pier: Curing, De-Shuttering, De-Staging | P-29 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.10 | CW-Sec-3-PR-5-40 | Pedestal & Seismic arrestors | P-10 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.7 | CW-Sec-4B-MIB-407-2 | Wall | CH. 20.975 MIB 4X2.65 length 13.182 Br No 407 | 15
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-7 | Land handing over for ROB approaches | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.31.6 | 3299 | Pier | P190-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.3 | 3294 | Pile Cap | P193-L | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.1 | CW-Sec-4-1090 | Pier: Curing, De-Shuttering, De-Staging | P189-L | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.188 | 396 | Pier Cap Erection | P186-R | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.30 | PILE1480 | Piles | P244 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.10.3 | UGE12520 | U-Girder | P4-P5 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.15 | CW-Sec-3-58 | Pile Cap | P-15 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.33 | CW-Sec-3-130 | Pile Cap | P-33 | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10000 | PR2-PR3-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10010 | PR2-PR3-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10020 | PR2-PR3-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10030 | PR2-PR3-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10040 | PR2-PR3-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10050 | PR2-PR3-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10060 | PR2-PR3-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10070 | PR2-PR3-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC03230 | PR2-PR3-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.42 | PILE1940 | Piles | P198 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.44 | PILE2550 | Piles | P-44 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-170 | Portal cap & pedestal | PR-41 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.9 | CW-Sec-4-1100 | Portal Pier: Curing, De-Shuttering, De-Staging | P211 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.10.8 | UGE11220 | U-Girder | P5-P6 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.188 | CW-Sec-4-PR-5-231 | Pedestal & Seismic arrestors | P186-R | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.8 | CW-Sec-4B-MIB-405-2 | Wall | CH. 22.625 MIB 8.1X7.20 length 12.574 Br No 405 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.9 | CW-Sec-4B-MIB-404-2 | Wall | CH. 23.65 MIB 8.4X5.35 length 20.241 Br No 404 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.17 | PILE3830 | Piles | P-17 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.35 | PILE2450 | Piles | P-35 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.43 | 3814 | Pile Cap | P197 | 20
Not Started | BLP-DWP-R5-5.5.6.9.11.10.7 | UGE11460 | U-Girder | P6-P7 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-182 | Pile Cap | PR-43 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.14 | CW-Sec-3-55 | Pier | P-14 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.32 | CW-Sec-3-127 | Pier | P-32 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.12 | CW-Sec-3-811 | Pier: Curing, De-Shuttering, De-Staging | P-12 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.30 | CW-Sec-3-991 | Pier: Curing, De-Shuttering, De-Staging | P-30 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.6 | CW-Sec-1B-PR-3-4 | Portal Beam Cast In Situ | PR-3 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.204.11 | CW-Sec-3-44 | Pier Cap Erection | P-11 | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.8 | CW-Sec-1B-PR-5-3 | Portal Pier | PR-5 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.7 | 3183 | Portal Pier | P213 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.8 | 3199 | Portal Pier | P212 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.30 | 3219 | Portal Pier | P214 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.45 | 3774 | Pile Cap | P195 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.29 | PILE1500 | Piles | P245 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.10.6 | UGE11340 | U-Girder | P7-P8 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1034 | P34-P35 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1035 | P35-P36 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1036 | P36-P37 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1037 | P37-P38 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1038 | PR38-PR39 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1039 | PR39-PR40 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1040 | PR40-PR41 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.5 | 3179 | Pier | P191-R | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.16 | CW-Sec-3-62 | Pile Cap | P-16 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.34 | CW-Sec-3-134 | Pile Cap | P-34 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.6 | CW-Sec-4-1110 | Pier: Curing, De-Shuttering, De-Staging | P190-R | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.11 | PILE2310 | Piles | PR-8 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.27 | PILE1200 | Piles | P217 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.45 | PILE2560 | Piles | P-45 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.11 | CW-Sec-3-PR-5-41 | Pedestal & Seismic arrestors | P-11 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10640 | P-69 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10650 | P-70 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10660 | P-71 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10670 | P187-R | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10680 | P188-R | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10690 | P189-R | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10700 | P190-R | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10710 | P-72 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-183 | Portal Pier | PR-43 | 16
Not Started | BLP-DWP-R5-5.5.5.2.1.2.5 | CW-Sec-2B1-RUB-142-3 | Slab | CH. 6.944 RUB (1no x 30m) LC-142 | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.2.6 | CW-Sec-2B1-RUB-140-3 | Slab | CH. 6.313 RUB (1no x 30m) Re-construction length 41.31 LC-140 | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.2.7 | CW-Sec-2B1-RUB-144A3 | Slab | CH. 8.775 RUB (1no x 30m) Re-construction length 62.73 LC-144A | 30
Not Started | BLP-DWP-R5-5.5.5.2.1.2.8 | CW-Sec-2B1-RUB-NAG-3 | Slab | CH. 7.075 RUB (1no x 30m) Re-construction length 40 Nagawara | 30
Not Started | BLP-DWP-R5-5.5.7.2.4 | CW-Sec-4B-ROB-410A-7 | Land handing over for ROB approaches | CH. 19.2 ROB Re-construction (2 sapns)(35+27) length Br No 410A | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-3811 | Portal Pier: Curing, De-Shuttering, De-Staging | PR-42 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.18 | PILE3930 | Piles | P-18 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.36 | PILE2460 | Piles | P-36 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.10 | CW-Sec-1B-PR-7-2 | Pile Cap | PR-7 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.7 | CW-Sec-1B-PR-1-57 | Portal Pier: Curing,De-shuttering,De-Staging | PR-4 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.28 | 3222 | Pile Cap | P216 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.14 | 3314 | Pile Cap | P194-L | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.31.43 | 4174 | Pile Cap | P236 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.44 | CW-Sec-3-189 | Pile Cap | P-44 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.15 | CW-Sec-3-59 | Pier | P-15 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.33 | CW-Sec-3-131 | Pier | P-33 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.5 | UGE11100 | U-Girder | P8-P9 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.13 | CW-Sec-3-821 | Pier: Curing, De-Shuttering, De-Staging | P-13 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.31 | CW-Sec-3-1001 | Pier: Curing, De-Shuttering, De-Staging | P-31 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10080 | PR2-PR3-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10090 | PR3-PR4-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10100 | PR3-PR4-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10110 | PR3-PR4-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10120 | PR3-PR4-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10130 | PR3-PR4-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10140 | PR3-PR4-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10150 | PR3-PR4-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.1.15 | CW-Sec-2B1-MIB-559-1 | Raft | CH. 9.9 MIB 2X1.80 length 38.518 Br No 559 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.16 | CW-Sec-2B1-MIB-561-1 | Raft | CH. 10.059 MIB 2X1.8 length 38.893 Br No 561 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.17 | CW-Sec-2B1-MIB-562-1 | Raft | CH. 10.15 MIB 2X2.5 length 35.356 Br No 562 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.12 | CW-Sec-3-48 | Pier Cap Erection | P-12 | 2
Not Started | BLP-DWP-R5-5.5.5.2.1.1.12 | CW-Sec-2B1-MIB-555-4 | Return wall | CH. 8.6 MIB 2X2.5 length 46.642 Br No 555 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.28 | PILE1490 | Piles | P246 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.17 | CW-Sec-3-66 | Pile Cap | P-17 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.35 | CW-Sec-3-138 | Pile Cap | P-35 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.41 | PILE1960 | Piles | P199 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.47 | PILE2570 | Piles | P-46 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.12 | CW-Sec-3-PR-5-42 | Pedestal & Seismic arrestors | P-12 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.10.14 | UGE11850 | U-Girder | P9-P10 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.2.1.7 | CW-Sec-4B-MIB-407-3 | Slab | CH. 20.975 MIB 4X2.65 length 13.182 Br No 407 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-3841 | Portal Beam: Curing, De-Shuttering, De-Staging | PR-43 | 31
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-7 | Fabrication & Delivery of Material to site for Viaduct | Steel Girder for Viaduct / MJBR / ROB | 250
Not Started | BLP-DWP-R5-5.5.7.10.4.31.5 | 3307 | Pier | P191-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.6 | CW-Sec-4-1120 | Pier: Curing, De-Shuttering, De-Staging | P190-L | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.37 | PILE2470 | Piles | P-37 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.2.45 | CW-Sec-3-193 | Pile Cap | P-45 | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.1.13 | CW-Sec-2B1-MIB-556-1 | Raft | CH. 8.75 MIB 2X2.5 length 49.474 Br No 556 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.14 | CW-Sec-2B1-MIB-557-1 | Raft | CH. 9.2 MIB 2X2.5 length 30.593 Br No 557 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1041 | PR41-PR42 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.16 | CW-Sec-3-63 | Pier | P-16 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.34 | CW-Sec-3-135 | Pier | P-34 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-177 | Portal cap & pedestal | PR-42 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.14 | CW-Sec-3-831 | Pier: Curing, De-Shuttering, De-Staging | P-14 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.32 | CW-Sec-3-1011 | Pier: Curing, De-Shuttering, De-Staging | P-32 | 7
Not Started | BLP-DWP-R5-5.5.7.2.2.3 | CW-Sec-4B-RUB@18.6-4 | Approaches & misc. work | CH. 23.725 RUB 1no. X 4mX4 length 18.655 - | 60
Not Started | BLP-DWP-R5-5.5.4.2.33.7 | CW-Sec-1B-PR-4-4 | Portal Beam Cast In Situ | PR-4 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.4 | CW-Sec-1B-PR-1-7 | Portal Beam: Curing,De-shuttering,De-Staging | PR-1 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.204.13 | CW-Sec-3-52 | Pier Cap Erection | P-13 | 2
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10720 | P191-R | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10730 | P192-R | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10740 | P-73 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10750 | P193-R | Pier Cap Casting | 0
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10760 | P194 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10770 | P-74 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10780 | P-75 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10790 | P-76 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10830 | P195 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.9 | CW-Sec-1B-PR-6-3 | Portal Pier | PR-6 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.29 | 3227 | Portal Pier | P215 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.27 | PILE1520 | Piles | P247 | 6
Not Started | BLP-DWP-R5-5.5.5.3.3 | CW-Sec-2C-Blan | Blanketing-2C Ch.10.700 to Ch. 11.350 | Formation | 177
Not Started | BLP-DWP-R5-5.5.6.9.10.204.18 | CW-Sec-3-70 | Pile Cap | P-18 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.36 | CW-Sec-3-142 | Pile Cap | P-36 | 10
Not Started | BLP-DWP-R5-5.5.7.2.1.8 | CW-Sec-4B-MIB-405-3 | Slab | CH. 22.625 MIB 8.1X7.20 length 12.574 Br No 405 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.9 | CW-Sec-4B-MIB-404-3 | Slab | CH. 23.65 MIB 8.4X5.35 length 20.241 Br No 404 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.12 | PILE2320 | Piles | PR-9 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.26 | PILE1220 | Piles | P218 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.46 | PILE2580 | Piles | P-47 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.13 | CW-Sec-3-PR-5-43 | Pedestal & Seismic arrestors | P-13 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.10 | CW-Sec-4B-MIB-403-1 | Raft | CH. 24.025 MIB 2X2.65 length 29.635 Br No 403 | 15
Not Started | BLP-DWP-R5-5.5.7.2.6.1 | CW-Sec-4B-EW-4 | Cutting / Filling-4B Ch. 22.100 to Ch. 23.100 | Cutting / Filling-4B Ch. 18.100 to Ch. 24.425 | 120
Not Started | BLP-DWP-R5-5.5.7.2.6.2 | CW-Sec-4B-Blan-3 | Blanketing-4B Ch. 20.100 to Ch. 21.100 | Blanketing-4B Ch. 18.100 to Ch. 24.425 | 105
Not Started | BLP-DWP-R5-5.5.7.10.4.31.13 | 3322 | Pile Cap | P237 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.44 | CW-Sec-3-190 | Pier | P-44 | 12
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10160 | PR3-PR4-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10170 | PR3-PR4-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10180 | PR4-PR5-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10190 | PR4-PR5-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10200 | PR4-PR5-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10210 | PR4-PR5-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10220 | PR4-PR5-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10230 | PR4-PR5-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.4 | 3175 | Pier | P192-R | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.5 | CW-Sec-4-1130 | Pier: Curing, De-Shuttering, De-Staging | P191-R | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.38 | PILE2480 | Piles | P-38 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.11 | CW-Sec-1B-PR-8-2 | Pile Cap | PR-8 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.8 | CW-Sec-1B-PR-1-77 | Portal Pier: Curing,De-shuttering,De-Staging | PR-5 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.27 | 3234 | Pile Cap | P217 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.8 | CW-Sec-4-1140 | Portal Pier: Curing, De-Shuttering, De-Staging | P212 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.7 | CW-Sec-4-1150 | Portal Pier: Curing, De-Shuttering, De-Staging | P213 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.30 | CW-Sec-4-1160 | Portal Pier: Curing, De-Shuttering, De-Staging | P214 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.47 | CW-Sec-3-197 | Pile Cap | P-46 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.17 | CW-Sec-3-67 | Pier | P-17 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.35 | CW-Sec-3-139 | Pier | P-35 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.13 | UGE11700 | U-Girder | P10-P11 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.15 | CW-Sec-3-841 | Pier: Curing, De-Shuttering, De-Staging | P-15 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.33 | CW-Sec-3-1021 | Pier: Curing, De-Shuttering, De-Staging | P-33 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.14 | CW-Sec-3-56 | Pier Cap Erection | P-14 | 2
Not Started | BLP-DWP-R5-5.5.7.2.2.3 | CW-Sec-4B-RUB@18.6-3 | Slab | CH. 23.725 RUB 1no. X 4mX4 length 18.655 - | 40
Not Started | BLP-DWP-R5-5.5.7.10.4.1.42 | 3934 | Pile Cap | P198 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.26 | PILE1540 | Piles | P248 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.37 | CW-Sec-3-146 | Pile Cap | P-37 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-3831 | Portal Pier: Curing, De-Shuttering, De-Staging | PR-43 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.40 | PILE1970 | Piles | P200 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.51 | PILE2590 | Piles | P-48 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.14 | CW-Sec-3-PR-5-44 | Pedestal & Seismic arrestors | P-14 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.44 | 3854 | Pile Cap | P196 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.2.45 | CW-Sec-3-194 | Pier | P-45 | 12
Not Started | BLP-DWP-R5-5.5.5.2.1.1.15 | CW-Sec-2B1-MIB-559-2 | Wall | CH. 9.9 MIB 2X1.80 length 38.518 Br No 559 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.16 | CW-Sec-2B1-MIB-561-2 | Wall | CH. 10.059 MIB 2X1.8 length 38.893 Br No 561 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.17 | CW-Sec-2B1-MIB-562-2 | Wall | CH. 10.15 MIB 2X2.5 length 35.356 Br No 562 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1042 | PR42-PR43 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1043 | P43-P44 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1044 | P44-P45 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1045 | P45-P46 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1046 | P46-P47 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1047 | P47-P48 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1048 | P48-P49 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.73 | PILE2920 | Piles | P-78 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.151 | PILE3760 | Piles | P-153 | 9
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10800 | P-77 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10810 | P-78 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10820 | P-79 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10850 | P-80 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10860 | P196 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10870 | P197 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.3 | CW-Sec-2B1-MJB-560-3 | Super Structure Assemby & Erection | CH. 9.992 MJB 2X30.5 length Br No 560 | 40
Not Started | BLP-DWP-R5-5.5.6.9.10.2.46 | CW-Sec-3-201 | Pile Cap | P-47 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.18 | CW-Sec-3-71 | Pier | P-18 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.36 | CW-Sec-3-143 | Pier | P-36 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.12 | UGE11890 | U-Girder | P11-P12 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.16 | CW-Sec-3-851 | Pier: Curing, De-Shuttering, De-Staging | P-16 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.34 | CW-Sec-3-1031 | Pier: Curing, De-Shuttering, De-Staging | P-34 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.8 | CW-Sec-1B-PR-5-4 | Portal Beam Cast In Situ | PR-5 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.5 | CW-Sec-1B-PR-1-27 | Portal Beam: Curing,De-shuttering,De-Staging | PR-2 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.204.15 | CW-Sec-3-60 | Pier Cap Erection | P-15 | 2
Not Started | BLP-DWP-R5-5.5.7.2.1.7 | CW-Sec-4B-MIB-407-4 | Return wall | CH. 20.975 MIB 4X2.65 length 13.182 Br No 407 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.10 | CW-Sec-1B-PR-7-3 | Portal Pier | PR-7 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.28 | 3223 | Portal Pier | P216 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.4 | 3303 | Pier | P192-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.12 | 3318 | Pile Cap | P238 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.5 | CW-Sec-4-1170 | Pier: Curing, De-Shuttering, De-Staging | P191-L | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.189 | 3128 | Pier Cap Erection | P187-R | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.25 | PILE1530 | Piles | P249 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.38 | CW-Sec-3-150 | Pile Cap | P-38 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.13 | PILE2070 | Piles | PR-10 | 12
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10240 | PR4-PR5-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10250 | PR4-PR5-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10260 | PR4-PR5-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10270 | PR5-PR6-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10280 | PR5-PR6-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10290 | PR5-PR6-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10300 | PR5-PR6-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10310 | PR5-PR6-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.25 | PILE1210 | Piles | P219 | 12
Not Started | BLP-DWP-R5-5.5.5.2.1.1.13 | CW-Sec-2B1-MIB-556-2 | Wall | CH. 8.75 MIB 2X2.5 length 49.474 Br No 556 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.14 | CW-Sec-2B1-MIB-557-2 | Wall | CH. 9.2 MIB 2X2.5 length 30.593 Br No 557 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.50 | PILE2600 | Piles | P-49 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-184 | Portal cap & pedestal | PR-43 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.15 | CW-Sec-3-PR-5-45 | Pedestal & Seismic arrestors | P-15 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.1.18 | CW-Sec-2B1-MIB-564-1 | Raft | CH. 10.564 MIB 2X2.5 length 27.018 Br No 564 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.2 | 3164 | Pier Cap Erection | P188-R | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.189 | CW-Sec-4-PR-5-232 | Pedestal & Seismic arrestors | P187-R | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.47 | CW-Sec-3-198 | Pier | P-46 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.44 | CW-Sec-3-1081 | Pier: Curing, De-Shuttering, De-Staging | P-44 | 7
Not Started | BLP-DWP-R5-5.5.7.2.1.8 | CW-Sec-4B-MIB-405-4 | Return wall | CH. 22.625 MIB 8.1X7.20 length 12.574 Br No 405 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.9 | CW-Sec-4B-MIB-404-4 | Return wall | CH. 23.65 MIB 8.4X5.35 length 20.241 Br No 404 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.80 | PILE2930 | Piles | P-79 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.12 | CW-Sec-1B-PR-9-2 | Pile Cap | PR-9 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.9 | CW-Sec-1B-PR-1-97 | Portal Pier: Curing,De-shuttering,De-Staging | PR-6 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.26 | 3242 | Pile Cap | P218 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.29 | CW-Sec-4-1180 | Portal Pier: Curing, De-Shuttering, De-Staging | P215 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.1 | 3160 | Pier Cap Erection | P189-R | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.2 | CW-Sec-4-PR-5-233 | Pedestal & Seismic arrestors | P188-R | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.51 | CW-Sec-3-205 | Pile Cap | P-48 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.37 | CW-Sec-3-147 | Pier | P-37 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.11 | UGE12130 | U-Girder | P12-P13 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.17 | CW-Sec-3-861 | Pier: Curing, De-Shuttering, De-Staging | P-17 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.35 | CW-Sec-3-1041 | Pier: Curing, De-Shuttering, De-Staging | P-35 | 7
Not Started | BLP-DWP-R5-5.5.7.2.1.10 | CW-Sec-4B-MIB-403-2 | Wall | CH. 24.025 MIB 2X2.65 length 29.635 Br No 403 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.16 | CW-Sec-3-64 | Pier Cap Erection | P-16 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.6 | 3172 | Pier Cap Erection | P190-R | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.24 | PILE1510 | Piles | P250 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.1 | CW-Sec-4-PR-5-234 | Pedestal & Seismic arrestors | P189-R | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1049 | P49-P50 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.3 | 3167 | Pier | P193-R | 0
Not Started | BLP-DWP-R5-5.5.6.9.10.4.73 | CW-Sec-3-325 | Pile Cap | P-78 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.46 | 3744 | Pier | P194 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.4 | CW-Sec-4-1190 | Pier: Curing, De-Shuttering, De-Staging | P192-R | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.3 | CW-Sec-4-1200 | Pier: Curing, De-Shuttering, De-Staging | P193-R | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.6.155 | PILE3770 | Piles | P-154 | 9
Not Started | BLP-DWP-R5-5.5.7.10.4.1.39 | PILE1930 | Piles | P201 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.49 | PILE2620 | Piles | P-50 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.16 | CW-Sec-3-PR-5-46 | Pedestal & Seismic arrestors | P-16 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10840 | P186-L | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10880 | P187-L | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10890 | P-81 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10900 | P188-L | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10910 | P-82 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10930 | P-84 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.6 | CW-Sec-4-PR-5-235 | Pedestal & Seismic arrestors | P190-R | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.46 | CW-Sec-3-202 | Pier | P-47 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.45 | CW-Sec-3-1091 | Pier: Curing, De-Shuttering, De-Staging | P-45 | 7
Not Started | BLP-DWP-R5-5.5.5.1.2.1 | CW-Sec-2A-RUB-137-1 | Raft | CH. 2.6 RUB (1no x 30m)Re-construction length 27.85 LC-137 | 35
Not Started | BLP-DWP-R5-5.5.5.1.2.2 | CW-Sec-2A-RUB-539-1 | Raft | CH. 4.137 RUB 1no. X 6.1mX3 length 27.18 Br No 539 | 35
Not Started | BLP-DWP-R5-5.5.5.1.2.3 | CW-Sec-2A-RUB-541A-1 | Raft | CH. 4.709 RUB 1no. X 7.5 mX5 length 12.225 Br No 541B | 35
Not Started | BLP-DWP-R5-5.5.5.2.1.2.5 | CW-Sec-2B1-RUB-142-4 | Approaches & misc. work | CH. 6.944 RUB (1no x 30m) LC-142 | 30
Not Started | BLP-DWP-R5-5.5.7.10.4.31.25 | 3366 | Pile Cap | P249 | 10
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-6 | Super Structure | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 60
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-8 | Fabrication & Delivery of Material to site for Viaduct at BEL ROB | Steel Girder for Viaduct / MJBR / ROB | 102
Not Started | BLP-DWP-R5-5.5.6.9.10.6.151 | CW-Sec-3-625 | Pile Cap | P-153 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.82 | PILE2950 | Piles | P-80 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.11 | 3330 | Pile Cap | P239 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.5 | 3180 | Pier Cap Erection | P191-R | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.50 | CW-Sec-3-209 | Pile Cap | P-49 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.38 | CW-Sec-3-151 | Pier | P-38 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-154 | Pile Cap | PR-39 | 20
Not Started | BLP-DWP-R5-5.5.6.9.11.10.10 | UGE12010 | U-Girder | P13-P14 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.18 | CW-Sec-3-871 | Pier: Curing, De-Shuttering, De-Staging | P-18 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.36 | CW-Sec-3-1051 | Pier: Curing, De-Shuttering, De-Staging | P-36 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.9 | CW-Sec-1B-PR-6-4 | Portal Beam Cast In Situ | PR-6 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.6 | CW-Sec-1B-PR-1-47 | Portal Beam: Curing,De-shuttering,De-Staging | PR-3 | 31
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10320 | PR5-PR6-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10330 | PR5-PR6-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10340 | PR5-PR6-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10350 | PR5-PR6-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10360 | PR6-PR7-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10370 | PR6-PR7-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10380 | PR6-PR7-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10390 | PR6-PR7-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.1.15 | CW-Sec-2B1-MIB-559-3 | Slab | CH. 9.9 MIB 2X1.80 length 38.518 Br No 559 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.16 | CW-Sec-2B1-MIB-561-3 | Slab | CH. 10.059 MIB 2X1.8 length 38.893 Br No 561 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.17 | CW-Sec-2B1-MIB-562-3 | Slab | CH. 10.15 MIB 2X2.5 length 35.356 Br No 562 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.204.17 | CW-Sec-3-68 | Pier Cap Erection | P-17 | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.11 | CW-Sec-1B-PR-8-3 | Portal Pier | PR-8 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.27 | 3235 | Portal Pier | P217 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.23 | PILE1560 | Piles | P251 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.5 | CW-Sec-4-PR-5-236 | Pedestal & Seismic arrestors | P191-R | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.80 | CW-Sec-3-329 | Pile Cap | P-79 | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.2.6 | CW-Sec-2B1-RUB-140-4 | Approaches & misc. work | CH. 6.313 RUB (1no x 30m) Re-construction length 41.31 LC-140 | 30
Not Started | BLP-DWP-R5-5.5.4.2.33.14 | PILE2080 | Piles | PR-11 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.24 | PILE1190 | Piles | P220 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.48 | PILE2630 | Piles | P-51 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.4 | 3176 | Pier Cap Erection | P192-R | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.17 | CW-Sec-3-PR-5-47 | Pedestal & Seismic arrestors | P-17 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.41 | 3974 | Pile Cap | P199 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.2.51 | CW-Sec-3-206 | Pier | P-48 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.47 | CW-Sec-3-1101 | Pier: Curing, De-Shuttering, De-Staging | P-46 | 7
Not Started | BLP-DWP-R5-5.5.7.2.1.11 | CW-Sec-4B-MIB-412-1 | Raft | CH. 18.65 MIB 2X2.65 length 23.757 Br No 412 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-155 | Portal Pier | PR-39 | 16
Not Started | BLP-DWP-R5-5.5.7.2.6.1 | CW-Sec-4B-EW-5 | Cutting / Filling-4B Ch. 23.100 to Ch. 24.100 | Cutting / Filling-4B Ch. 18.100 to Ch. 24.425 | 120
Not Started | BLP-DWP-R5-5.5.7.10.4.31.3 | 3295 | Pier | P193-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.4 | CW-Sec-4-1210 | Pier: Curing, De-Shuttering, De-Staging | P192-L | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.3 | 3168 | Pier Cap Erection | P193-R | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.1.4 | CW-Sec-4-PR-5-237 | Pedestal & Seismic arrestors | P192-R | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.3 | CW-Sec-4-PR-5-238 | Pedestal & Seismic arrestors | P193-R | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.81 | PILE2960 | Piles | P-81 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.157 | PILE3780 | Piles | P-155 | 9
Not Started | BLP-DWP-R5-5.5.4.2.33.13 | CW-Sec-1B-PR-10-2 | Pile Cap | PR-10 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.10 | CW-Sec-1B-PR-1-117 | Portal Pier: Curing,De-shuttering,De-Staging | PR-7 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.28 | CW-Sec-4-1220 | Portal Pier: Curing, De-Shuttering, De-Staging | P216 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.49 | CW-Sec-3-213 | Pile Cap | P-50 | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.1.13 | CW-Sec-2B1-MIB-556-3 | Slab | CH. 8.75 MIB 2X2.5 length 49.474 Br No 556 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.14 | CW-Sec-2B1-MIB-557-3 | Slab | CH. 9.2 MIB 2X2.5 length 30.593 Br No 557 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1050 | P50-P51 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1051 | P51-P52 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1052 | P52-P53 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1053 | P53-P54 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1054 | P54-P55 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1055 | P55-P56 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1056 | P56-P57 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.73 | CW-Sec-3-326 | Pier | P-78 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.9 | UGE11290 | U-Girder | P14-P15 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.37 | CW-Sec-3-1061 | Pier: Curing, De-Shuttering, De-Staging | P-37 | 7
Not Started | BLP-DWP-R5-5.5.5.2.1.1.18 | CW-Sec-2B1-MIB-564-2 | Wall | CH. 10.564 MIB 2X2.5 length 27.018 Br No 564 | 15
Not Started | BLP-DWP-R5-5.5.5.2.1.2.7 | CW-Sec-2B1-RUB-144A4 | Approaches & misc.work | CH. 8.775 RUB (1no x 30m) Re-construction length 62.73 LC-144A | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.204.18 | CW-Sec-3-72 | Pier Cap Erection | P-18 | 2
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10920 | P-83 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10940 | P-85 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10950 | P-86 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10960 | P198 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10970 | P-87 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10980 | P-88 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC10990 | P-89 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11010 | P189-L | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.4 | CW-Sec-1B-PR-1-5 | Pedestal & Seismic arrestors | PR-1 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.22 | PILE1580 | Piles | P252 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.82 | CW-Sec-3-333 | Pile Cap | P-80 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.155 | CW-Sec-3-629 | Pile Cap | P-154 | 10
Not Started | BLP-DWP-R5-5.5.7.2.1.12 | CW-Sec-4B-MIB-410D1 | Raft | CH. 19.1 MIB 2X2.65 length 31.103 Br No 410D | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.13 | CW-Sec-4B-MIB-406UP1 | Raft | CH. 21.775 MIB 3X2.65 length 18.681 Br No 406UP | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.14 | CW-Sec-4B-MIB-402-1 | Raft | CH. 24.475 MIB 4X4 length 30 Br No 402 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.25 | 3367 | Pier | P249 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.24 | 3358 | Pile Cap | P250 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.36 | PILE1980 | Piles | P202 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.57 | PILE2640 | Piles | P-52 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.19 | CW-Sec-3-76 | Pier Cap Erection | P-19 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.151 | CW-Sec-3-626 | Pier | P-153 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.18 | CW-Sec-3-PR-5-48 | Pedestal & Seismic arrestors | P-18 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.10 | 3338 | Pile Cap | P240 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.50 | CW-Sec-3-210 | Pier | P-49 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.46 | CW-Sec-3-1111 | Pier: Curing, De-Shuttering, De-Staging | P-47 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10400 | PR6-PR7-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10410 | PR6-PR7-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10420 | PR6-PR7-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10430 | PR6-PR7-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10440 | PR6-PR7-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10450 | PR7-PR8-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10460 | PR7-PR8-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10470 | PR7-PR8-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.2.1.2.8 | CW-Sec-2B1-RUB-NAG-4 | Approaches & misc. work | CH. 7.075 RUB (1no x 30m) Re-construction length 40 Nagawara | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.204.20 | CW-Sec-3-80 | Pier Cap Erection | P-20 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.19 | CW-Sec-3-PR-5-49 | Pedestal & Seismic arrestors | P-19 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.45 | 3784 | Pier | P195 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.46 | CW-Sec-4-1230 | Pier: Curing, De-Shuttering, De-Staging | P194 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.86 | PILE2970 | Piles | P-82 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.2.48 | CW-Sec-3-217 | Pile Cap | P-51 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.80 | CW-Sec-3-330 | Pier | P-79 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.1 | UGE11580 | U-Girder | P15-P16 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.38 | CW-Sec-3-1071 | Pier: Curing, De-Shuttering, De-Staging | P-38 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.7 | CW-Sec-1B-PR-1-67 | Portal Beam: Curing,De-shuttering,De-Staging | PR-4 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.204.21 | CW-Sec-3-84 | Pier Cap Erection | P-21 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.20 | CW-Sec-3-PR-5-50 | Pedestal & Seismic arrestors | P-20 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.12 | CW-Sec-1B-PR-9-3 | Portal Pier | PR-9 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.26 | 3243 | Portal Pier | P218 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.25 | 3238 | Pile Cap | P219 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.21 | PILE1570 | Piles | P253 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.81 | CW-Sec-3-337 | Pile Cap | P-81 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.156 | PILE3790 | Piles | P-156 | 9
Not Started | BLP-DWP-R5-5.5.4.2.33.15 | PILE2090 | Piles | PR-12 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.23 | PILE1240 | Piles | P221 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.58 | PILE2650 | Piles | P-53 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.22 | CW-Sec-3-88 | Pier Cap Erection | P-22 | 2
Not Started | BLP-DWP-R5-5.5.5.2.1.5.2 | CW-Sec-2B1-Blan-1 | Blanketing-2B Ch. 5.700 to Ch. 6.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P1 | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.204.21 | CW-Sec-3-PR-5-51 | Pedestal & Seismic arrestors | P-21 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.49 | CW-Sec-3-214 | Pier | P-50 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.51 | CW-Sec-3-1121 | Pier: Curing, De-Shuttering, De-Staging | P-48 | 7
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1057 | P57-P58 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.7.2.2.4 | CW-Sec-4B-RUB-407A-2 | Raft | CH. 20.6 RUB 5.5m X 6.75m Br No 407A | 30
Not Started | BLP-DWP-R5-5.5.7.2.1.10 | CW-Sec-4B-MIB-403-3 | Slab | CH. 24.025 MIB 2X2.65 length 29.635 Br No 403 | 15
Not Started | BLP-DWP-R5-5.5.4.2.29 | CW-Sec-1B-DS | Deck Slab | Deck slab | 340
Not Started | BLP-DWP-R5-5.5.7.2.6.1 | CW-Sec-4B-EW-6 | Cutting / Filling-4B Ch. 24.100 to Ch. 24.425 | Cutting / Filling-4B Ch. 18.100 to Ch. 24.425 | 120
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-8 | Approaches and misc Works | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 50
Not Started | BLP-DWP-R5-5.5.6.9.10.204.23 | CW-Sec-3-92 | Pier Cap Erection | P-23 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.157 | CW-Sec-3-633 | Pile Cap | P-155 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.22 | CW-Sec-3-PR-5-52 | Pedestal & Seismic arrestors | P-22 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.85 | PILE2980 | Piles | P-83 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11000 | P-90 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11020 | P-91 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11030 | P-92 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11050 | P-93 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11060 | P-94 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11070 | P-95 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11090 | P-97 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.14 | CW-Sec-1B-PR-11-2 | Pile Cap | PR-11 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.11 | CW-Sec-1B-PR-1-137 | Portal Pier: Curing,De-shuttering,De-Staging | PR-8 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.24 | 3230 | Pile Cap | P220 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.27 | CW-Sec-4-1240 | Portal Pier: Curing, De-Shuttering, De-Staging | P217 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.57 | CW-Sec-3-221 | Pile Cap | P-52 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.82 | CW-Sec-3-334 | Pier | P-80 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.28 | UGE12450 | U-Girder | P16-P17 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.46 | 3754 | Pier Cap Erection | P194 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.73 | CW-Sec-3-1421 | Pier: Curing, De-Shuttering, De-Staging | P-78 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.23 | 3378 | Pile Cap | P251 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.24 | CW-Sec-3-96 | Pier Cap Erection | P-24 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.23 | CW-Sec-3-PR-5-53 | Pedestal & Seismic arrestors | P-23 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.11 | CW-Sec-4B-MIB-412-2 | Wall | CH. 18.65 MIB 2X2.65 length 23.757 Br No 412 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.14 | 3315 | Pier | P194-L | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.31.9 | 3334 | Pile Cap | P241 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.43 | 4184 | Pier | P236 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.3 | CW-Sec-4-1250 | Pier: Curing, De-Shuttering, De-Staging | P193-L | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.14 | CW-Sec-4-1260 | Pier: Curing, De-Shuttering, De-Staging | P194-L | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.20 | PILE1600 | Piles | P254 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.86 | CW-Sec-3-341 | Pile Cap | P-82 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.46 | CW-Sec-4-PR-5-345 | Pedestal & Seismic arrestors | P194 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-3771 | Portal Pier: Curing, De-Shuttering, De-Staging | PR-39 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10480 | PR7-PR8-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10490 | PR7-PR8-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10500 | PR7-PR8-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10510 | PR7-PR8-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10520 | PR7-PR8-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10530 | PR7-PR8-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10540 | PR8-PR9-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10550 | PR8-PR9-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.35 | PILE1990 | Piles | P203 | 12
Not Started | BLP-DWP-R5-5.5.5.2.1.1.15 | CW-Sec-2B1-MIB-559-4 | Return wall | CH. 9.9 MIB 2X1.80 length 38.518 Br No 559 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.16 | CW-Sec-2B1-MIB-561-4 | Return wall | CH. 10.059 MIB 2X1.8 length 38.893 Br No 561 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.17 | CW-Sec-2B1-MIB-562-4 | Return wall | CH. 10.15 MIB 2X2.5 length 35.356 Br No 562 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.2.59 | PILE2660 | Piles | P-54 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.25 | CW-Sec-3-100 | Pier Cap Erection | P-25 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.155 | CW-Sec-3-630 | Pier | P-154 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.24 | CW-Sec-3-PR-5-54 | Pedestal & Seismic arrestors | P-24 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.6.151 | CW-Sec-3-2181 | Pier: Curing, De-Shuttering, De-Staging | P-153 | 7
Not Started | BLP-DWP-R5-5.5.5.2.1.1.18 | CW-Sec-2B1-MIB-564-3 | Slab | CH. 10.564 MIB 2X2.5 length 27.018 Br No 564 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.2.48 | CW-Sec-3-218 | Pier | P-51 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.50 | CW-Sec-3-1131 | Pier: Curing, De-Shuttering, De-Staging | P-49 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.5 | CW-Sec-1B-PR-2-5 | Pedestal & Seismic arrestors | PR-2 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.204.26 | CW-Sec-3-104 | Pier Cap Erection | P-26 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.25 | CW-Sec-3-PR-5-55 | Pedestal & Seismic arrestors | P-25 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.12 | CW-Sec-4B-MIB-410D2 | Wall | CH. 19.1 MIB 2X2.65 length 31.103 Br No 410D | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.13 | CW-Sec-4B-MIB-406UP2 | Wall | CH. 21.775 MIB 3X2.65 length 18.681 Br No 406UP | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.14 | CW-Sec-4B-MIB-402-2 | Wall | CH. 24.475 MIB 4X4 length 30 Br No 402 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.84 | PILE2990 | Piles | P-84 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.161 | PILE3800 | Piles | P-157 | 9
Not Started | BLP-DWP-R5-5.5.7.10.4.31.24 | 3359 | Pier | P250 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.40 | 4014 | Pile Cap | P200 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.25 | CW-Sec-4-1270 | Pier: Curing, De-Shuttering, De-Staging | P249 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.58 | CW-Sec-3-225 | Pile Cap | P-53 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.81 | CW-Sec-3-338 | Pier | P-81 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.27 | UGE12370 | U-Girder | P17-P18 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.80 | CW-Sec-3-1431 | Pier: Curing, De-Shuttering, De-Staging | P-79 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.8 | CW-Sec-1B-PR-1-87 | Portal Beam: Curing,De-shuttering,De-Staging | PR-5 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.204.27 | CW-Sec-3-108 | Pier Cap Erection | P-27 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.26 | CW-Sec-3-PR-5-56 | Pedestal & Seismic arrestors | P-26 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.13 | CW-Sec-1B-PR-10-3 | Portal Pier | PR-10 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.19 | PILE1620 | Piles | P255 | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.1.13 | CW-Sec-2B1-MIB-556-4 | Return wall | CH. 8.75 MIB 2X2.5 length 49.474 Br No 556 | 20
Not Started | BLP-DWP-R5-5.5.5.2.1.1.14 | CW-Sec-2B1-MIB-557-4 | Return wall | CH. 9.2 MIB 2X2.5 length 30.593 Br No 557 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1058 | P58-P59 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1059 | P59-P60 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1060 | P60-P61 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1061 | P61-P62 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1062 | P62-P63 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1063 | P186-P187 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1064 | P187-P188 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.85 | CW-Sec-3-345 | Pile Cap | P-83 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.156 | CW-Sec-3-637 | Pile Cap | P-156 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.10.26 | UGE12500 | U-Girder | P18-P19 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.44 | 3864 | Pier | P196 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.45 | CW-Sec-4-1280 | Pier: Curing, De-Shuttering, De-Staging | P195 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.16 | PILE2100 | Piles | PR-13 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.22 | PILE1260 | Piles | P222 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.56 | PILE2670 | Piles | P-55 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.28 | CW-Sec-3-112 | Pier Cap Erection | P-28 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.27 | CW-Sec-3-PR-5-57 | Pedestal & Seismic arrestors | P-27 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11040 | P190-L | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11080 | P-96 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11100 | P-98 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11110 | P199 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11130 | P-100 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11140 | P-101 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11150 | P-102 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11170 | P-104 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-156 | Portal cap & pedestal | PR-39 | 15
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-6 | Fabrication & Delivery of Material to site for Phase 2 MJBR | Steel Girder for Viaduct / MJBR / ROB | 102
Not Started | BLP-DWP-R5-5.5.6.9.10.2.57 | CW-Sec-3-222 | Pier | P-52 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.49 | CW-Sec-3-1141 | Pier: Curing, De-Shuttering, De-Staging | P-50 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.10.25 | UGE12540 | U-Girder | P19-P20 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.22 | 3386 | Pile Cap | P252 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.29 | CW-Sec-3-116 | Pier Cap Erection | P-29 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.28 | CW-Sec-3-PR-5-58 | Pedestal & Seismic arrestors | P-28 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.83 | PILE3000 | Piles | P-85 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.15 | CW-Sec-1B-PR-12-2 | Pile Cap | PR-12 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.12 | CW-Sec-1B-PR-1-157 | Portal Pier: Curing,De-shuttering,De-Staging | PR-9 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.23 | 3250 | Pile Cap | P221 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.8 | 3326 | Pile Cap | P242 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.26 | CW-Sec-4-1290 | Portal Pier: Curing, De-Shuttering, De-Staging | P218 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.59 | CW-Sec-3-229 | Pile Cap | P-54 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.86 | CW-Sec-3-342 | Pier | P-82 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.24 | UGE12530 | U-Girder | P20-P21 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.82 | CW-Sec-3-1441 | Pier: Curing, De-Shuttering, De-Staging | P-80 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10560 | PR8-PR9-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10570 | PR8-PR9-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10580 | PR8-PR9-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10590 | PR8-PR9-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10600 | PR8-PR9-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10610 | PR8-PR9-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10620 | PR8-PR9-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10630 | PR9-PR10-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.30 | CW-Sec-3-120 | Pier Cap Erection | P-30 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.29 | CW-Sec-3-PR-5-59 | Pedestal & Seismic arrestors | P-29 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.10 | CW-Sec-4B-MIB-403-4 | Return wall | CH. 24.025 MIB 2X2.65 length 29.635 Br No 403 | 15
Not Started | BLP-DWP-R5-5.MS.7 | MS-AG4 | MS-4: Completion of 15 Minor Bridges | Milestone- At Grade | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.31.18 | PILE1610 | Piles | P256 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.84 | CW-Sec-3-349 | Pile Cap | P-84 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.10.23 | UGE12460 | U-Girder | P21-P22 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.160 | PILE3810 | Piles | P-158 | 9
Not Started | BLP-DWP-R5-5.5.7.10.4.1.47 | PILE2000 | Piles | P204 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.2.55 | PILE2680 | Piles | P-56 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.31 | CW-Sec-3-124 | Pier Cap Erection | P-31 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.157 | CW-Sec-3-634 | Pier | P-155 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.204.30 | CW-Sec-3-PR-5-60 | Pedestal & Seismic arrestors | P-30 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.45 | 3794 | Pier Cap Erection | P195 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.155 | CW-Sec-3-2191 | Pier: Curing, De-Shuttering, De-Staging | P-154 | 7
Not Started | BLP-DWP-R5-5.5.5.1.2.1 | CW-Sec-2A-RUB-137-2 | Wall | CH. 2.6 RUB (1no x 30m)Re-construction length 27.85 LC-137 | 40
Not Started | BLP-DWP-R5-5.5.5.1.2.2 | CW-Sec-2A-RUB-539-2 | Wall | CH. 4.137 RUB 1no. X 6.1mX3 length 27.18 Br No 539 | 40
Not Started | BLP-DWP-R5-5.5.5.1.2.3 | CW-Sec-2A-RUB-541A-2 | Wall | CH. 4.709 RUB 1no. X 7.5 mX5 length 12.225 Br No 541B | 35
Not Started | BLP-DWP-R5-5.5.7.10.4.1.25 | 3239 | Portal Pier | P219 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.2.58 | CW-Sec-3-226 | Pier | P-53 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.48 | CW-Sec-3-1151 | Pier: Curing, De-Shuttering, De-Staging | P-51 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.10.22 | UGE12570 | U-Girder | P22-P23 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.2.1.11 | CW-Sec-4B-MIB-412-3 | Slab | CH. 18.65 MIB 2X2.65 length 23.757 Br No 412 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.13 | 3323 | Pier | P237 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.43 | CW-Sec-4-1300 | Pier: Curing, De-Shuttering, De-Staging | P236 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.32 | CW-Sec-3-128 | Pier Cap Erection | P-32 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.161 | CW-Sec-3-641 | Pile Cap | P-157 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.31 | CW-Sec-3-PR-5-61 | Pedestal & Seismic arrestors | P-31 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.45 | CW-Sec-4-PR-5-355 | Pedestal & Seismic arrestors | P195 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.92 | PILE3010 | Piles | P-86 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.2.56 | CW-Sec-3-233 | Pile Cap | P-55 | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1065 | P63-P64 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1071 | P191-P192 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1072 | P66-P67 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.85 | CW-Sec-3-346 | Pier | P-83 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.21 | UGE12560 | U-Girder | P23-P24 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.81 | CW-Sec-3-1451 | Pier: Curing, De-Shuttering, De-Staging | P-81 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.11 | CW-Sec-1B-PR-8-4 | Portal Beam Cast In Situ | PR-8 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.10 | CW-Sec-1B-PR-7-4 | Portal Beam Cast In Situ | PR-7 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.12 | CW-Sec-1B-PR-9-4 | Portal Beam Cast In Situ | PR-9 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.9 | CW-Sec-1B-PR-1-107 | Portal Beam: Curing,De-shuttering,De-Staging | PR-6 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.204.33 | CW-Sec-3-132 | Pier Cap Erection | P-33 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.32 | CW-Sec-3-PR-5-62 | Pedestal & Seismic arrestors | P-32 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11120 | P-99 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11160 | P-103 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11180 | P-105 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11210 | P-107 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11220 | P-108 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11230 | P-109 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11250 | P191-L | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.14 | CW-Sec-1B-PR-11-3 | Portal Pier | PR-11 | 16
Not Started | BLP-DWP-R5-5.5.4.2.33.6 | CW-Sec-1B-PR-3-5 | Pedestal & Seismic arrestors | PR-3 | 15
Not Started | BLP-DWP-R5-5.5.4.2.4.1 | IGE10380 | I-Girder | PR1-PR2 | 4
Not Started | BLP-DWP-R5-5.5.7.10.4.1.24 | 3231 | Portal Pier | P220 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.17 | PILE1590 | Piles | P257 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.83 | CW-Sec-3-353 | Pile Cap | P-85 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.10.20 | UGE12590 | U-Girder | P24-P25 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.2.1.12 | CW-Sec-4B-MIB-410D3 | Slab | CH. 19.1 MIB 2X2.65 length 31.103 Br No 410D | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.13 | CW-Sec-4B-MIB-406UP3 | Slab | CH. 21.775 MIB 3X2.65 length 18.681 Br No 406UP | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.14 | CW-Sec-4B-MIB-402-3 | Slab | CH. 24.475 MIB 4X4 length 30 Br No 402 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.17 | PILE2110 | Piles | PR-14 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.23 | 3379 | Pier | P251 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.21 | 3382 | Pile Cap | P253 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.24 | CW-Sec-4-1310 | Pier: Curing, De-Shuttering, De-Staging | P250 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.14 | PILE1080 | Piles | P205 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.21 | PILE1250 | Piles | P223 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.54 | PILE2690 | Piles | P-57 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.34 | CW-Sec-3-136 | Pier Cap Erection | P-34 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.33 | CW-Sec-3-PR-5-63 | Pedestal & Seismic arrestors | P-33 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.7 | 3310 | Pile Cap | P243 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.59 | CW-Sec-3-230 | Pier | P-54 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.57 | CW-Sec-3-1161 | Pier: Curing, De-Shuttering, De-Staging | P-52 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.10.19 | UGE12610 | U-Girder | P25-P26 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10640 | PR9-PR10-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10650 | PR9-PR10-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10660 | PR9-PR10-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10670 | PR9-PR10-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10680 | PR9-PR10-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10690 | PR9-PR10-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10700 | PR9-PR10-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10710 | PR9-PR10-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.4 | CW-Sec-2C-MIB-568-1 | Raft | CH. 11.145 MIB 2X2.65 length 13.925 Br No 568 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.5 | CW-Sec-2C-MIB-569-1 | Raft | CH. 11.202 MIB 2X1.8 length 25.779 Br No 569 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.6 | CW-Sec-2C-MIB-570-1 | Raft | CH. 11.37 MIB 2X2.5 length 30.531 Br No 570 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.35 | CW-Sec-3-140 | Pier Cap Erection | P-35 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.34 | CW-Sec-3-PR-5-64 | Pedestal & Seismic arrestors | P-34 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.43 | 3824 | Pier | P197 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.44 | CW-Sec-4-1320 | Pier: Curing, De-Shuttering, De-Staging | P196 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.93 | PILE3020 | Piles | P-87 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.159 | PILE3820 | Piles | P-159 | 9
Not Started | BLP-DWP-R5-5.5.5.2.1.1.18 | CW-Sec-2B1-MIB-564-4 | Return wall | CH. 10.564 MIB 2X2.5 length 27.018 Br No 564 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.16 | CW-Sec-1B-PR-13-2 | Pile Cap | PR-13 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.13 | CW-Sec-1B-PR-1-177 | Portal Pier: Curing,De-shuttering,De-Staging | PR-10 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.22 | 3258 | Pile Cap | P222 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.2.55 | CW-Sec-3-237 | Pile Cap | P-56 | 10
Not Started | BLP-DWP-R5-5.5.7.2.6.1 | CW-Sec-4B-EW-1 | Cutting / Filling-4B Ch. 18.100 to Ch. 19.100 | Cutting / Filling-4B Ch. 18.100 to Ch. 24.425 | 120
Not Started | BLP-DWP-R5-5.5.6.9.10.4.84 | CW-Sec-3-350 | Pier | P-84 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.18 | UGE12600 | U-Girder | P26-P27 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.86 | CW-Sec-3-1461 | Pier: Curing, De-Shuttering, De-Staging | P-82 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.204.36 | CW-Sec-3-144 | Pier Cap Erection | P-36 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-158 | Railway/ Power block as required | PR-39 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.204.35 | CW-Sec-3-PR-5-65 | Pedestal & Seismic arrestors | P-35 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.7 | CW-Sec-1B-PR-4-6 | Pedestal & Seismic arrestors | PR-4 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.39 | 3894 | Pile Cap | P201 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.16 | PILE1550 | Piles | P258 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.92 | CW-Sec-3-357 | Pile Cap | P-86 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.160 | CW-Sec-3-645 | Pile Cap | P-158 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.10.17 | UGE12550 | U-Girder | P27-P28 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.48 | PILE2020 | Piles | P206 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.2.53 | PILE2700 | Piles | P-58 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.204.37 | CW-Sec-3-148 | Pier Cap Erection | P-37 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.156 | CW-Sec-3-638 | Pier | P-156 | 12
Not Started | BLP-DWP-R5-5.5.5.2.1.5.2 | CW-Sec-2B1-Blan-2 | Blanketing-2B Ch. 6.700 to Ch. 7.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P1 | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.204.36 | CW-Sec-3-PR-5-66 | Pedestal & Seismic arrestors | P-36 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.6.157 | CW-Sec-3-2201 | Pier: Curing, De-Shuttering, De-Staging | P-155 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.56 | CW-Sec-3-234 | Pier | P-55 | 12
Not Started | BLP-DWP-R5-5.5.5.3.1.1 | CW-Sec-2C-MIB-565-1 | Raft | CH. 10.75 MIB 2X2.65 length 13.195 Br No 565 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.2 | CW-Sec-2C-MIB-566-1 | Raft | CH. 10.965 MIB 2X2.65 length 11.545 Br No 566 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.3 | CW-Sec-2C-MIB-567-1 | Raft | CH. 11.075 MIB 2X2.65 length 11.555 Br No 567 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.58 | CW-Sec-3-1171 | Pier: Curing, De-Shuttering, De-Staging | P-53 | 7
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1066 | P188-P189 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1067 | P64-P65 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1068 | P189-P190 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1069 | P190-P191 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1070 | P65-P66 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1079 | P72-P73 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.11.10.16 | UGE12580 | U-Girder | P28-P29 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.2.2.4 | CW-Sec-4B-RUB-407A-3 | Wall | CH. 20.6 RUB 5.5m X 6.75m Br No 407A | 35
Not Started | BLP-DWP-R5-5.5.6.9.10.204.38 | CW-Sec-3-152 | Pier Cap Erection | P-38 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.204.37 | CW-Sec-3-PR-5-67 | Pedestal & Seismic arrestors | P-37 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.94 | PILE3030 | Piles | P-88 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11190 | P236 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11200 | P-106 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11240 | P-110 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11260 | P-111 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11290 | P-113 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11300 | P200 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11310 | P-114 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11330 | P-115 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.54 | CW-Sec-3-241 | Pile Cap | P-57 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.83 | CW-Sec-3-354 | Pier | P-85 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.15 | UGE12250 | U-Girder | P29-P30 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.44 | 3874 | Pier Cap Erection | P196 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.85 | CW-Sec-3-1471 | Pier: Curing, De-Shuttering, De-Staging | P-83 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.13 | CW-Sec-1B-PR-10-4 | Portal Beam Cast In Situ | PR-10 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.31.20 | 3394 | Pile Cap | P254 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-159 | Portal beam erection | PR-39 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.204.38 | CW-Sec-3-PR-5-68 | Pedestal & Seismic arrestors | P-38 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.11 | CW-Sec-4B-MIB-412-4 | Return wall | CH. 18.65 MIB 2X2.65 length 23.757 Br No 412 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.15 | CW-Sec-1B-PR-12-3 | Portal Pier | PR-12 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.23 | 3251 | Portal Pier | P221 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.12 | 3319 | Pier | P238 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.30 | 3346 | Pile Cap | P244 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.13 | CW-Sec-4-1330 | Pier: Curing, De-Shuttering, De-Staging | P237 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.25 | CW-Sec-4-1340 | Portal Pier: Curing, De-Shuttering, De-Staging | P219 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.15 | PILE1470 | Piles | P259 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.93 | CW-Sec-3-361 | Pile Cap | P-87 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.10.37 | UGE12650 | U-Girder | P30-P31 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.44 | CW-Sec-4-PR-5-365 | Pedestal & Seismic arrestors | P196 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.6.158 | PILE3840 | Piles | P-160 | 9
Not Started | BLP-DWP-R5-5.5.4.2.33.18 | PILE2120 | Piles | PR-15 | 12
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10720 | PR10-PR11-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10730 | PR10-PR11-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10740 | PR10-PR11-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10750 | PR10-PR11-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10760 | PR10-PR11-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10770 | PR10-PR11-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10780 | PR10-PR11-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10790 | PR10-PR11-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.13 | PILE1100 | Piles | P207 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.20 | PILE1280 | Piles | P224 | 12
Not Started | BLP-DWP-R5-5.5.5.3.1.4 | CW-Sec-2C-MIB-568-2 | Wall | CH. 11.145 MIB 2X2.65 length 13.925 Br No 568 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.5 | CW-Sec-2C-MIB-569-2 | Wall | CH. 11.202 MIB 2X1.8 length 25.779 Br No 569 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.6 | CW-Sec-2C-MIB-570-2 | Wall | CH. 11.37 MIB 2X2.5 length 30.531 Br No 570 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.52 | PILE2710 | Piles | P-59 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.2.55 | CW-Sec-3-238 | Pier | P-56 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.59 | CW-Sec-3-1191 | Pier: Curing, De-Shuttering, De-Staging | P-54 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.10.36 | UGE12680 | U-Girder | P31-P32 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.4.2 | IGE10370 | I-Girder | PR2-PR3 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-165 | Railway/ Power block as required | PR-40 | 5
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-166 | Portal beam erection | PR-40 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.6.159 | CW-Sec-3-649 | Pile Cap | P-159 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.1.39 | CW-Sec-3-PR-5-69 | Pedestal & Seismic arrestors | PR-39 | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.12 | CW-Sec-4B-MIB-410D4 | Return wall | CH. 19.1 MIB 2X2.65 length 31.103 Br No 410D | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.13 | CW-Sec-4B-MIB-406UP4 | Return wall | CH. 21.775 MIB 3X2.65 length 18.681 Br No 406UP | 15
Not Started | BLP-DWP-R5-5.5.7.2.1.14 | CW-Sec-4B-MIB-402-4 | Return wall | CH. 24.475 MIB 4X4 length 30 Br No 402 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.91 | PILE3040 | Piles | P-89 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.17 | CW-Sec-1B-PR-14-2 | Pile Cap | PR-14 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.14 | CW-Sec-1B-PR-1-197 | Portal Pier: Curing,De-shuttering,De-Staging | PR-11 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.21 | 3254 | Pile Cap | P223 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.22 | 3387 | Pier | P252 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.23 | CW-Sec-4-1360 | Pier: Curing, De-Shuttering, De-Staging | P251 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.24 | CW-Sec-4-1350 | Portal Pier: Curing, De-Shuttering, De-Staging | P220 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.53 | CW-Sec-3-245 | Pile Cap | P-58 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.92 | CW-Sec-3-358 | Pier | P-86 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.35 | UGE12670 | U-Girder | P32-P33 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.84 | CW-Sec-3-1481 | Pier: Curing, De-Shuttering, De-Staging | P-84 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.8 | CW-Sec-1B-PR-5-7 | Pedestal & Seismic arrestors | PR-5 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.42 | PILE1650 | Piles | P260 | 6
Not Started | BLP-DWP-R5-5.5.5.3.1.1 | CW-Sec-2C-MIB-565-2 | Wall | CH. 10.75 MIB 2X2.65 length 13.195 Br No 565 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.2 | CW-Sec-2C-MIB-566-2 | Wall | CH. 10.965 MIB 2X2.65 length 11.545 Br No 566 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.3 | CW-Sec-2C-MIB-567-2 | Wall | CH. 11.075 MIB 2X2.65 length 11.555 Br No 567 | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1073 | P192-P193 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1074 | P67-P68 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1076 | P69-P70 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1077 | P70-P71 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1080 | P73-P74 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.94 | CW-Sec-3-365 | Pile Cap | P-88 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.10.34 | UGE12700 | U-Girder | P33-P34 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.42 | 3944 | Pier | P198 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.43 | CW-Sec-4-1370 | Pier: Curing, De-Shuttering, De-Staging | P197 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.65 | PILE2730 | Piles | P-60 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-173 | Portal beam erection | PR-41 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.6.161 | CW-Sec-3-642 | Pier | P-157 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.1.40 | CW-Sec-3-PR-5-70 | Pedestal & Seismic arrestors | PR-40 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.6.156 | CW-Sec-3-2211 | Pier: Curing, De-Shuttering, De-Staging | P-156 | 7
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11270 | P-112 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11280 | P192-L | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11320 | P193-L | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11340 | P-116 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11370 | P-118 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11390 | P-120 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11410 | P-121 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-172 | Railway/ Power block as required | PR-41 | 5
Not Started | BLP-DWP-R5-5.5.6.9.10.2.54 | CW-Sec-3-242 | Pier | P-57 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.56 | CW-Sec-3-1181 | Pier: Curing, De-Shuttering, De-Staging | P-55 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.10.33 | UGE12720 | U-Girder | P34-P35 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.4.4 | IGE10010 | I-Girder | PR3-PR4 | 4
Not Started | BLP-DWP-R5-5.5.7.10.4.31.19 | 3402 | Pile Cap | P255 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.90 | PILE3060 | Piles | P-90 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.167 | PILE3850 | Piles | P-161 | 9
Not Started | BLP-DWP-R5-5.5.7.10.4.31.29 | 3354 | Pile Cap | P245 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.52 | CW-Sec-3-249 | Pile Cap | P-59 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.93 | CW-Sec-3-362 | Pier | P-87 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.10.32 | UGE12710 | U-Girder | P35-P36 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.83 | CW-Sec-3-1491 | Pier: Curing, De-Shuttering, De-Staging | P-85 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.14 | CW-Sec-1B-PR-11-4 | Portal Beam Cast In Situ | PR-11 | 36
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10800 | PR10-PR11-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10810 | PR11-PR12-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10820 | PR11-PR12-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10830 | PR11-PR12-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10840 | PR11-PR12-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10850 | PR11-PR12-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10860 | PR11-PR12-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10870 | PR11-PR12-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.4 | CW-Sec-2C-MIB-568-3 | Slab | CH. 11.145 MIB 2X2.65 length 13.925 Br No 568 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.5 | CW-Sec-2C-MIB-569-3 | Slab | CH. 11.202 MIB 2X1.8 length 25.779 Br No 569 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.6 | CW-Sec-2C-MIB-570-3 | Slab | CH. 11.37 MIB 2X2.5 length 30.531 Br No 570 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-180 | Portal beam erection | PR-42 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.1.41 | CW-Sec-3-PR-5-71 | Pedestal & Seismic arrestors | PR-41 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.7 | CW-Sec-2C-MIB-571-1 | Raft | CH. 11.47 MIB 2X2.5 length 38.029 Br No 571 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.16 | CW-Sec-1B-PR-13-3 | Portal Pier | PR-13 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.22 | 3259 | Portal Pier | P222 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.41 | PILE1640 | Piles | P261 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.91 | CW-Sec-3-369 | Pile Cap | P-89 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.158 | CW-Sec-3-653 | Pile Cap | P-160 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.10.31 | UGE12660 | U-Girder | P36-P37 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-179 | Railway/ Power block as required | PR-42 | 4
Not Started | BLP-DWP-R5-5.5.4.2.33.19 | PILE2130 | Piles | PR-16 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.12 | PILE1090 | Piles | P208 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.19 | PILE1300 | Piles | P225 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.66 | PILE2740 | Piles | P-61 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.43 | 3834 | Pier Cap Erection | P197 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.36 | 4054 | Pile Cap | P202 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.2.53 | CW-Sec-3-246 | Pier | P-58 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.55 | CW-Sec-3-1201 | Pier: Curing, De-Shuttering, De-Staging | P-56 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.10.30 | UGE12690 | U-Girder | P37-P38 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.11 | 3331 | Pier | P239 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.12 | CW-Sec-4-1380 | Pier: Curing, De-Shuttering, De-Staging | P238 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.1.42 | CW-Sec-3-PR-5-72 | Pedestal & Seismic arrestors | PR-42 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.43 | CW-Sec-4-PR-5-375 | Pedestal & Seismic arrestors | P197 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.89 | PILE3070 | Piles | P-91 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.18 | CW-Sec-1B-PR-15-2 | Pile Cap | PR-15 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.15 | CW-Sec-1B-PR-1-217 | Portal Pier: Curing,De-shuttering,De-Staging | PR-12 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.20 | 3266 | Pile Cap | P224 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.23 | CW-Sec-4-1390 | Portal Pier: Curing, De-Shuttering, De-Staging | P221 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.65 | CW-Sec-3-253 | Pile Cap | P-60 | 10
Not Started | BLP-DWP-R5-5.5.5.3.1.1 | CW-Sec-2C-MIB-565-3 | Slab | CH. 10.75 MIB 2X2.65 length 13.195 Br No 565 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.2 | CW-Sec-2C-MIB-566-3 | Slab | CH. 10.965 MIB 2X2.65 length 11.545 Br No 566 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.3 | CW-Sec-2C-MIB-567-3 | Slab | CH. 11.075 MIB 2X2.65 length 11.555 Br No 567 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1075 | P68-P69 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1078 | P71-P72 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1081 | P74-P75 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1087 | P79-P80 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.94 | CW-Sec-3-366 | Pier | P-88 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.92 | CW-Sec-3-1501 | Pier: Curing, De-Shuttering, De-Staging | P-86 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-186 | Railway/ Power block as required | PR-43 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-187 | Portal beam erection | PR-43 | 4
Not Started | BLP-DWP-R5-5.5.7.2.3 | CW-Sec-4B-ROB-408B-9 | Diversion of Traffic | CH. 19.85 ROB Re-construction (1no x 30m) length Br No 408B | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11350 | P194-L | Pier Cap Casting | 0
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11360 | P-117 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11380 | P-119 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11400 | P237 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11420 | P-122 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11430 | P238 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11450 | P-124 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11470 | P-125 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11490 | P241 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.9 | CW-Sec-1B-PR-5-8 | Pedestal & Seismic arrestors | PR-6 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.44 | PILE4370 | Piles | P262 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.90 | CW-Sec-3-373 | Pile Cap | P-90 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.29.2 | UGE12630 | U-Girder | PR38-PR39 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.168 | PILE3860 | Piles | P-162 | 9
Not Started | BLP-DWP-R5-5.5.5.1.2.3 | CW-Sec-2A-RUB-541A-3 | Slab | CH. 4.709 RUB 1no. X 7.5 mX5 length 12.225 Br No 541B | 35
Not Started | BLP-DWP-R5-5.5.7.10.4.31.21 | 3383 | Pier | P253 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.18 | 3398 | Pile Cap | P256 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.22 | CW-Sec-4-1400 | Pier: Curing, De-Shuttering, De-Staging | P252 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.67 | PILE2750 | Piles | P-62 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.160 | CW-Sec-3-646 | Pier | P-158 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.6.161 | CW-Sec-3-2221 | Pier: Curing, De-Shuttering, De-Staging | P-157 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.28 | 3350 | Pile Cap | P246 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.43 | 4194 | Pier Cap Erection | P236 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.52 | CW-Sec-3-250 | Pier | P-59 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.54 | CW-Sec-3-1211 | Pier: Curing, De-Shuttering, De-Staging | P-57 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.44 | CW-Sec-3-191 | Pier Cap Erection | P-44 | 2
Not Started | BLP-DWP-R5-5.5.4.2.4.3 | IGE10000 | I-Girder | PR4-PR5 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.1.43 | CW-Sec-3-PR-5-73 | Pedestal & Seismic arrestors | PR-43 | 15
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10880 | PR11-PR12-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10890 | PR11-PR12-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10900 | PR12-PR13-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10910 | PR12-PR13-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10920 | PR12-PR13-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10930 | PR12-PR13-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10940 | PR12-PR13-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10950 | PR12-PR13-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.167 | CW-Sec-3-657 | Pile Cap | P-161 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.41 | 3984 | Pier | P199 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.42 | CW-Sec-4-1410 | Pier: Curing, De-Shuttering, De-Staging | P198 | 7
Not Started | BLP-DWP-R5-5.5.7.2.4 | CW-Sec-4B-ROB-410A-2 | Area barrication | CH. 19.2 ROB Re-construction (2 sapns)(35+27) length Br No 410A | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.88 | PILE3080 | Piles | P-92 | 6
Not Started | BLP-DWP-R5-5.5.5.3.1.7 | CW-Sec-2C-MIB-571-2 | Wall | CH. 11.47 MIB 2X2.5 length 38.029 Br No 571 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.43 | CW-Sec-4-PR-5-455 | Pedestal & Seismic arrestors | P236 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.66 | CW-Sec-3-257 | Pile Cap | P-61 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.91 | CW-Sec-3-370 | Pier | P-89 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.29.4 | UGE11090 | U-Girder | PR39-PR40 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.93 | CW-Sec-3-1511 | Pier: Curing, De-Shuttering, De-Staging | P-87 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.188 | CW-Sec-4-4 | Pier Cap Erection | P186-L | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.45 | CW-Sec-3-195 | Pier Cap Erection | P-45 | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.15 | CW-Sec-1B-PR-12-4 | Portal Beam Cast In Situ | PR-12 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.2.44 | CW-Sec-3-PR-5-74 | Pedestal & Seismic arrestors | P-44 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.10 | CW-Sec-1B-PR-1-127 | Portal Beam: Curing,De-shuttering,De-Staging | PR-7 | 31
Not Started | BLP-DWP-R5-5.5.4.2.33.11 | CW-Sec-1B-PR-1-147 | Portal Beam: Curing,De-shuttering,De-Staging | PR-8 | 31
Not Started | BLP-DWP-R5-5.5.4.2.33.12 | CW-Sec-1B-PR-1-167 | Portal Beam: Curing,De-shuttering,De-Staging | PR-9 | 31
Not Started | BLP-DWP-R5-5.5.5.1.2.1 | CW-Sec-2A-RUB-137-3 | Slab | CH. 2.6 RUB (1no x 30m)Re-construction length 27.85 LC-137 | 40
Not Started | BLP-DWP-R5-5.5.5.1.2.2 | CW-Sec-2A-RUB-539-3 | Slab | CH. 4.137 RUB 1no. X 6.1mX3 length 27.18 Br No 539 | 40
Not Started | BLP-DWP-R5-5.5.4.2.33.17 | CW-Sec-1B-PR-14-3 | Portal Pier | PR-14 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.21 | 3255 | Portal Pier | P223 | 16
Not Started | BLP-DWP-R5-5.5.7.2.2.4 | CW-Sec-4B-RUB-407A-5 | Approaches & misc. work | CH. 20.6 RUB 5.5m X 6.75m Br No 407A | 60
Not Started | BLP-DWP-R5-5.5.6.9.10.4.89 | CW-Sec-3-377 | Pile Cap | P-91 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.47 | CW-Sec-3-199 | Pier Cap Erection | P-46 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.45 | CW-Sec-3-PR-5-75 | Pedestal & Seismic arrestors | P-45 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.188 | CW-Sec-4-PR-5-292 | Pedestal & Seismic arrestors | P186-L | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.20 | PILE2140 | Piles | PR-17 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.18 | PILE1290 | Piles | P226 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.68 | PILE2760 | Piles | P-63 | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.5.2 | CW-Sec-2B1-Blan-3 | Blanketing-2B Ch. 7.700 to Ch. 8.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P1 | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.2.65 | CW-Sec-3-254 | Pier | P-60 | 12
Not Started | BLP-DWP-R5-5.5.5.3.1.4 | CW-Sec-2C-MIB-568-4 | Return wall | CH. 11.145 MIB 2X2.65 length 13.925 Br No 568 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.5 | CW-Sec-2C-MIB-569-4 | Return wall | CH. 11.202 MIB 2X1.8 length 25.779 Br No 569 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.6 | CW-Sec-2C-MIB-570-4 | Return wall | CH. 11.37 MIB 2X2.5 length 30.531 Br No 570 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.53 | CW-Sec-3-1221 | Pier: Curing, De-Shuttering, De-Staging | P-58 | 7
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1082 | P75-P76 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1084 | P186-P187 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1085 | P77-P78 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1088 | P80-P81 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.11.29.3 | UGE11080 | U-Girder | PR40-PR41 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.46 | CW-Sec-3-203 | Pier Cap Erection | P-47 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.47 | CW-Sec-3-PR-5-76 | Pedestal & Seismic arrestors | P-46 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.87 | PILE3090 | Piles | P-93 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.166 | PILE3870 | Piles | P-163 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11440 | P-123 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11460 | P239 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11480 | P240 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11500 | P201 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11510 | P-126 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11530 | P-127 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11550 | P-129 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11570 | P244 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.19 | CW-Sec-1B-PR-16-2 | Pile Cap | PR-16 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.16 | CW-Sec-1B-PR-1-237 | Portal Pier: Curing,De-shuttering,De-Staging | PR-13 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.22 | CW-Sec-4-1420 | Portal Pier: Curing, De-Shuttering, De-Staging | P222 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.67 | CW-Sec-3-261 | Pile Cap | P-62 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.90 | CW-Sec-3-374 | Pier | P-90 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.42 | 3954 | Pier Cap Erection | P198 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.94 | CW-Sec-3-1521 | Pier: Curing, De-Shuttering, De-Staging | P-88 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.51 | CW-Sec-3-207 | Pier Cap Erection | P-48 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.46 | CW-Sec-3-PR-5-77 | Pedestal & Seismic arrestors | P-47 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.17 | 3390 | Pile Cap | P257 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.10 | 3339 | Pier | P240 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.28 | 3351 | Pier | P246 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.27 | 3362 | Pile Cap | P247 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.11 | CW-Sec-4-1430 | Pier: Curing, De-Shuttering, De-Staging | P239 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.40 | PILE1680 | Piles | P263 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.88 | CW-Sec-3-381 | Pile Cap | P-92 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.168 | CW-Sec-3-661 | Pile Cap | P-162 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.29.8 | UGE11120 | U-Girder | PR41-PR42 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.42 | CW-Sec-4-PR-5-385 | Pedestal & Seismic arrestors | P198 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.50 | CW-Sec-3-211 | Pier Cap Erection | P-49 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.51 | CW-Sec-3-PR-5-78 | Pedestal & Seismic arrestors | P-48 | 15
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10960 | PR12-PR13-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10970 | PR12-PR13-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10980 | PR12-PR13-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC10990 | PR12-PR13-10 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11000 | PR12-PR13-11 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11010 | PR13-PR14-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11020 | PR13-PR14-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11030 | PR13-PR14-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.1.2.1 | CW-Sec-2A-RUB-137-4 | Approaches & misc. work | CH. 2.6 RUB (1no x 30m)Re-construction length 27.85 LC-137 | 45
Not Started | BLP-DWP-R5-5.5.5.3.1.1 | CW-Sec-2C-MIB-565-4 | Return wall | CH. 10.75 MIB 2X2.65 length 13.195 Br No 565 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.2 | CW-Sec-2C-MIB-566-4 | Return wall | CH. 10.965 MIB 2X2.65 length 11.545 Br No 566 | 15
Not Started | BLP-DWP-R5-5.5.5.3.1.3 | CW-Sec-2C-MIB-567-4 | Return wall | CH. 11.075 MIB 2X2.65 length 11.555 Br No 567 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.69 | PILE2770 | Piles | P-64 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.159 | CW-Sec-3-650 | Pier | P-159 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.6.160 | CW-Sec-3-2231 | Pier: Curing, De-Shuttering, De-Staging | P-158 | 7
Not Started | BLP-DWP-R5-5.5.7.2.2.4 | CW-Sec-4B-RUB-407A-4 | Slab | CH. 20.6 RUB 5.5m X 6.75m Br No 407A | 40
Not Started | BLP-DWP-R5-5.5.5.3.1.7 | CW-Sec-2C-MIB-571-3 | Slab | CH. 11.47 MIB 2X2.5 length 38.029 Br No 571 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.66 | CW-Sec-3-258 | Pier | P-61 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.52 | CW-Sec-3-1231 | Pier: Curing, De-Shuttering, De-Staging | P-59 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.49 | CW-Sec-3-215 | Pier Cap Erection | P-50 | 2
Not Started | BLP-DWP-R5-5.5.4.2.4.8 | IGE10020 | I-Girder | PR5-PR6 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.2.50 | CW-Sec-3-PR-5-79 | Pedestal & Seismic arrestors | P-49 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.44 | 4244 | Pile Cap | P262 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.100 | PILE3100 | Piles | P-94 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.165 | PILE3880 | Piles | P-164 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.20 | 3395 | Pier | P254 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.35 | 4094 | Pile Cap | P203 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.21 | CW-Sec-4-1440 | Pier: Curing, De-Shuttering, De-Staging | P253 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.68 | CW-Sec-3-265 | Pile Cap | P-63 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.89 | CW-Sec-3-378 | Pier | P-91 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.91 | CW-Sec-3-1541 | Pier: Curing, De-Shuttering, De-Staging | P-89 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.48 | CW-Sec-3-219 | Pier Cap Erection | P-51 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.49 | CW-Sec-3-PR-5-80 | Pedestal & Seismic arrestors | P-50 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.13 | CW-Sec-1B-PR-1-187 | Portal Beam: Curing,De-shuttering,De-Staging | PR-10 | 31
Not Started | BLP-DWP-R5-5.5.7.2.6.2 | CW-Sec-4B-Blan-1 | Blanketing-4B Ch. 18.100 to Ch. 19.100 | Blanketing-4B Ch. 18.100 to Ch. 24.425 | 90
Not Started | BLP-DWP-R5-5.5.7.2.6.2 | CW-Sec-4B-Blan-4 | Blanketing-4B Ch. 21.100 to Ch. 22.100 | Blanketing-4B Ch. 18.100 to Ch. 24.425 | 95
Not Started | BLP-DWP-R5-5.5.7.10.4.31.189 | CW-Sec-4-8 | Pier Cap Erection | P187-L | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.29.1 | UGE11110 | U-Girder | PR42-PR43 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.18 | CW-Sec-1B-PR-15-3 | Portal Pier | PR-15 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.20 | 3267 | Portal Pier | P224 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.19 | 3274 | Pile Cap | P225 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.39 | PILE1700 | Piles | P264 | 6
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1083 | P76-P77 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1086 | P78-P79 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1089 | P81-P82 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1092 | P84-P85 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1095 | P204-P205 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.87 | CW-Sec-3-385 | Pile Cap | P-93 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.166 | CW-Sec-3-665 | Pile Cap | P-163 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.40 | 4024 | Pier | P200 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.41 | CW-Sec-4-1450 | Pier: Curing, De-Shuttering, De-Staging | P199 | 7
Not Started | BLP-DWP-R5-5.5.7.2.4 | CW-Sec-4B-ROB-410A-3 | Dismantalling | CH. 19.2 ROB Re-construction (2 sapns)(35+27) length Br No 410A | 45
Not Started | BLP-DWP-R5-5.5.6.9.10.2.57 | CW-Sec-3-223 | Pier Cap Erection | P-52 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.48 | CW-Sec-3-PR-5-81 | Pedestal & Seismic arrestors | P-51 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.21 | PILE2150 | Piles | PR-18 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.17 | PILE1270 | Piles | P227 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.2 | CW-Sec-4-12 | Pier Cap Erection | P188-L | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.64 | PILE2780 | Piles | P-65 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11520 | P242 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11540 | P-128 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11560 | P243 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11590 | P-130 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11610 | P-131 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11630 | P-132 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11650 | P-133 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.1.2 | UGE11130 | U-Girder | P43-P44 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.67 | CW-Sec-3-262 | Pier | P-62 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.65 | CW-Sec-3-1241 | Pier: Curing, De-Shuttering, De-Staging | P-60 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.58 | CW-Sec-3-227 | Pier Cap Erection | P-53 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.57 | CW-Sec-3-PR-5-82 | Pedestal & Seismic arrestors | P-52 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.16 | 3374 | Pile Cap | P258 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.1 | 3288 | Pier Cap Erection | P189-L | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.2 | CW-Sec-4-PR-5-294 | Pedestal & Seismic arrestors | P188-L | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.101 | PILE3110 | Piles | P-95 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.164 | PILE3890 | Piles | P-165 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.1.4 | UGE11150 | U-Girder | P44-P45 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.20 | CW-Sec-1B-PR-17-2 | Pile Cap | PR-17 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.189 | CW-Sec-4-PR-5-293 | Pedestal & Seismic arrestors | P187-L | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.17 | CW-Sec-1B-PR-1-257 | Portal Pier: Curing,De-shuttering,De-Staging | PR-14 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.18 | 3270 | Pile Cap | P226 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.26 | 3370 | Pile Cap | P248 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.21 | CW-Sec-4-1460 | Portal Pier: Curing, De-Shuttering, De-Staging | P223 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.69 | CW-Sec-3-269 | Pile Cap | P-64 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.88 | CW-Sec-3-382 | Pier | P-92 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.90 | CW-Sec-3-1551 | Pier: Curing, De-Shuttering, De-Staging | P-90 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.59 | CW-Sec-3-231 | Pier Cap Erection | P-54 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.58 | CW-Sec-3-PR-5-83 | Pedestal & Seismic arrestors | P-53 | 15
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11040 | PR13-PR14-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11050 | PR13-PR14-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11060 | PR13-PR14-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11070 | PR13-PR14-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11080 | PR13-PR14-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11090 | PR13-PR14-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11100 | PR13-PR14-10 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11110 | PR13-PR14-11 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.6 | 3300 | Pier Cap Erection | P190-L | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.1 | CW-Sec-4-PR-5-295 | Pedestal & Seismic arrestors | P189-L | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.3 | CW-Sec-2A-MIB-536-1 | Raft | CH. 1.667 MIB 4X2.65 length 13.678 Br No 536 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.4 | CW-Sec-2A-MIB-540-1 | Raft | CH. 4.275 MIB 2X2.65 length 6.646 Br No 540 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.5 | CW-Sec-2A-MIB-537-1 | Raft | CH. 1.822 MIB 2X2.65 length 14.178 Br No 537 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.1.3 | UGE11140 | U-Girder | P45-P46 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.38 | PILE1690 | Piles | P265 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.100 | CW-Sec-3-389 | Pile Cap | P-94 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.165 | CW-Sec-3-669 | Pile Cap | P-164 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.56 | CW-Sec-3-235 | Pier Cap Erection | P-55 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.59 | CW-Sec-3-PR-5-84 | Pedestal & Seismic arrestors | P-54 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.5 | 3308 | Pier Cap Erection | P191-L | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.6 | CW-Sec-4-PR-5-296 | Pedestal & Seismic arrestors | P190-L | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.63 | PILE2790 | Piles | P-66 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.158 | CW-Sec-3-654 | Pier | P-160 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.41 | 3994 | Pier Cap Erection | P199 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.159 | CW-Sec-3-2241 | Pier: Curing, De-Shuttering, De-Staging | P-159 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.1.8 | UGE11170 | U-Girder | P46-P47 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.68 | CW-Sec-3-266 | Pier | P-63 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.66 | CW-Sec-3-1251 | Pier: Curing, De-Shuttering, De-Staging | P-61 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.55 | CW-Sec-3-239 | Pier Cap Erection | P-56 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.56 | CW-Sec-3-PR-5-85 | Pedestal & Seismic arrestors | P-55 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.9 | 3335 | Pier | P241 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.27 | 3363 | Pier | P247 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.10 | CW-Sec-4-1470 | Pier: Curing, De-Shuttering, De-Staging | P240 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.28 | CW-Sec-4-1480 | Pier: Curing, De-Shuttering, De-Staging | P246 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.4 | 3304 | Pier Cap Erection | P192-L | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.5 | CW-Sec-4-PR-5-297 | Pedestal & Seismic arrestors | P191-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.41 | CW-Sec-4-PR-5-395 | Pedestal & Seismic arrestors | P199 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.102 | PILE3120 | Piles | P-96 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.163 | PILE3900 | Piles | P-166 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.1.7 | UGE11200 | U-Girder | P47-P48 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.64 | CW-Sec-3-273 | Pile Cap | P-65 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.1 | CW-Sec-2A-MIB-534-1 | Raft | CH. 0.22 MIB 3X1.8 length 27.415 Br No 534 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.2 | CW-Sec-2A-MIB-535-1 | Raft | CH. 0.947 MIB 4X2.65 length 29.245 Br No 535 | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1090 | P82-P83 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1093 | P85-P86 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1096 | P87-P88 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1103 | P92-P93 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.87 | CW-Sec-3-386 | Pier | P-93 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.6.166 | CW-Sec-3-666 | Pier | P-163 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.89 | CW-Sec-3-1561 | Pier: Curing, De-Shuttering, De-Staging | P-91 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.54 | CW-Sec-3-243 | Pier Cap Erection | P-57 | 2
Not Started | BLP-DWP-R5-5.5.5.3.1.7 | CW-Sec-2C-MIB-571-4 | Return wall | CH. 11.47 MIB 2X2.5 length 38.029 Br No 571 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.55 | CW-Sec-3-PR-5-86 | Pedestal & Seismic arrestors | P-56 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.14 | CW-Sec-1B-PR-1-207 | Portal Beam: Curing,De-shuttering,De-Staging | PR-11 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.31.3 | 3296 | Pier Cap Erection | P193-L | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.4 | CW-Sec-4-PR-5-298 | Pedestal & Seismic arrestors | P192-L | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11580 | P202 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11600 | P245 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11620 | P246 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11640 | P247 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11670 | P-134 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11690 | P-136 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11710 | P204 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11730 | P-139 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.1.6 | UGE11190 | U-Girder | P48-P49 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.19 | CW-Sec-1B-PR-16-3 | Portal Pier | PR-16 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.37 | PILE1720 | Piles | P266 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.101 | CW-Sec-3-393 | Pile Cap | P-95 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.164 | CW-Sec-3-673 | Pile Cap | P-165 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.53 | CW-Sec-3-247 | Pier Cap Erection | P-58 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.54 | CW-Sec-3-PR-5-87 | Pedestal & Seismic arrestors | P-57 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.22 | PILE2160 | Piles | PR-19 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.19 | 3403 | Pier | P255 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.15 | 3342 | Pile Cap | P259 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.20 | CW-Sec-4-1490 | Pier: Curing, De-Shuttering, De-Staging | P254 | 7
Not Started | BLP-DWP-R5-5.5.7.2.4 | CW-Sec-4B-ROB-410A-4 | Foundation | CH. 19.2 ROB Re-construction (2 sapns)(35+27) length Br No 410A | 65
Not Started | BLP-DWP-R5-5.5.7.10.4.1.16 | PILE1230 | Piles | P228 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.14 | 3316 | Pier Cap Erection | P194-L | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.31.13 | 3324 | Pier Cap Erection | P237 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.3 | CW-Sec-4-PR-5-299 | Pedestal & Seismic arrestors | P193-L | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.14 | CW-Sec-4-PR-5-300 | Pedestal & Seismic arrestors | P194-L | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.62 | PILE2800 | Piles | P-67 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.1.5 | UGE11160 | U-Girder | P49-P50 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.69 | CW-Sec-3-270 | Pier | P-64 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.67 | CW-Sec-3-1261 | Pier: Curing, De-Shuttering, De-Staging | P-62 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.52 | CW-Sec-3-251 | Pier Cap Erection | P-59 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.53 | CW-Sec-3-PR-5-88 | Pedestal & Seismic arrestors | P-58 | 15
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11120 | PR14-PR15-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11130 | PR14-PR15-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11140 | PR14-PR15-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11150 | PR14-PR15-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11160 | PR14-PR15-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11170 | PR14-PR15-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11180 | PR14-PR15-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11190 | PR14-PR15-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.12 | 3320 | Pier Cap Erection | P238 | 2
Not Started | BLP-DWP-R5-5.4.7.1 | SG Via-9 | Fabrication & Delivery of Material to site for ROB-410A | Steel Girder for Viaduct / MJBR / ROB | 102
Not Started | BLP-DWP-R5-5.5.7.10.4.31.13 | CW-Sec-4-PR-5-301 | Pedestal & Seismic arrestors | P237 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.3 | CW-Sec-2A-MIB-536-2 | Wall | CH. 1.667 MIB 4X2.65 length 13.678 Br No 536 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.4 | CW-Sec-2A-MIB-540-2 | Wall | CH. 4.275 MIB 2X2.65 length 6.646 Br No 540 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.5 | CW-Sec-2A-MIB-537-2 | Wall | CH. 1.822 MIB 2X2.65 length 14.178 Br No 537 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.39 | 3904 | Pier | P201 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.40 | CW-Sec-4-1500 | Pier: Curing, De-Shuttering, De-Staging | P200 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.103 | PILE3130 | Piles | P-97 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.162 | PILE3910 | Piles | P-167 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.1.14 | UGE11240 | U-Girder | P50-P51 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.21 | CW-Sec-1B-PR-18-2 | Pile Cap | PR-18 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.18 | CW-Sec-1B-PR-1-277 | Portal Pier: Curing,De-shuttering,De-Staging | PR-15 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.20 | CW-Sec-4-1510 | Portal Pier: Curing, De-Shuttering, De-Staging | P224 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.63 | CW-Sec-3-277 | Pile Cap | P-66 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.100 | CW-Sec-3-390 | Pier | P-94 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.88 | CW-Sec-3-1571 | Pier: Curing, De-Shuttering, De-Staging | P-92 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.65 | CW-Sec-3-255 | Pier Cap Erection | P-60 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.52 | CW-Sec-3-PR-5-89 | Pedestal & Seismic arrestors | P-59 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.44 | 4254 | Portal Pier | P262 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.11 | 3332 | Pier Cap Erection | P239 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.12 | CW-Sec-4-PR-5-302 | Pedestal & Seismic arrestors | P238 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.1.13 | UGE11230 | U-Girder | P51-P52 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.10 | CW-Sec-1B-PR-5-9 | Pedestal & Seismic arrestors | PR-7 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.47 | 4134 | Pile Cap | P204 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.36 | PILE1740 | Piles | P267 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.102 | CW-Sec-3-397 | Pile Cap | P-96 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.163 | CW-Sec-3-677 | Pile Cap | P-166 | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.4 | UGE10640 | U-Girder | P186-P187 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.2.66 | CW-Sec-3-259 | Pier Cap Erection | P-61 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.65 | CW-Sec-3-PR-5-90 | Pedestal & Seismic arrestors | P-60 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.10 | 3340 | Pier Cap Erection | P240 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.11 | CW-Sec-4-PR-5-303 | Pedestal & Seismic arrestors | P239 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.61 | PILE2810 | Piles | P-68 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.167 | CW-Sec-3-658 | Pier | P-161 | 12
Not Started | BLP-DWP-R5-5.5.5.2.1.5.2 | CW-Sec-2B1-Blan-4 | Blanketing-2B Ch. 8.700 to Ch. 9.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P1 | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.6.158 | CW-Sec-3-2251 | Pier: Curing, De-Shuttering, De-Staging | P-160 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.1.12 | UGE11260 | U-Girder | P52-P53 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.19 | 3275 | Portal Pier | P225 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.2.64 | CW-Sec-3-274 | Pier | P-65 | 12
Not Started | BLP-DWP-R5-5.5.5.1.1.1 | CW-Sec-2A-MIB-534-2 | Wall | CH. 0.22 MIB 3X1.8 length 27.415 Br No 534 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.2 | CW-Sec-2A-MIB-535-2 | Wall | CH. 0.947 MIB 4X2.65 length 29.245 Br No 535 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.68 | CW-Sec-3-1271 | Pier: Curing, De-Shuttering, De-Staging | P-63 | 7
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1091 | P83-P84 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1094 | P86-P87 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1097 | P88-P89 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1100 | P207-P208 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.66 | CW-Sec-3-PR-5-91 | Pedestal & Seismic arrestors | P-61 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.10 | CW-Sec-4-PR-5-304 | Pedestal & Seismic arrestors | P240 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.67 | CW-Sec-3-263 | Pier Cap Erection | P-62 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.104 | PILE3140 | Piles | P-98 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11680 | P-135 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11700 | P-137 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11720 | P-138 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11750 | P-141 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11770 | P205 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11790 | P248 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11810 | P-172-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.1.11 | UGE11280 | U-Girder | P53-P54 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.62 | CW-Sec-3-281 | Pile Cap | P-67 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.101 | CW-Sec-3-394 | Pier | P-95 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.6.165 | CW-Sec-3-670 | Pier | P-164 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.40 | 4034 | Pier Cap Erection | P200 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.87 | CW-Sec-3-1581 | Pier: Curing, De-Shuttering, De-Staging | P-93 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.6.166 | CW-Sec-3-2281 | Pier: Curing, De-Shuttering, De-Staging | P-163 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.18 | CW-Sec-1B-PR-15-4 | Portal Beam Cast In Situ | PR-15 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.17 | CW-Sec-1B-PR-14-4 | Portal Beam Cast In Situ | PR-14 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.16 | CW-Sec-1B-PR-13-4 | Portal Beam Cast In Situ | PR-13 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.15 | CW-Sec-1B-PR-1-227 | Portal Beam: Curing,De-shuttering,De-Staging | PR-12 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.31.42 | 3414 | Pile Cap | P260 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.67 | CW-Sec-3-PR-5-92 | Pedestal & Seismic arrestors | P-62 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.1.10 | UGE11270 | U-Girder | P54-P55 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.20 | CW-Sec-1B-PR-17-3 | Portal Pier | PR-17 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.18 | 3271 | Portal Pier | P226 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.17 | 3262 | Pile Cap | P227 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.8 | 3327 | Pier | P242 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.26 | 3371 | Pier | P248 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.9 | CW-Sec-4-1520 | Pier: Curing, De-Shuttering, De-Staging | P241 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.27 | CW-Sec-4-1530 | Pier: Curing, De-Shuttering, De-Staging | P247 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.35 | PILE1730 | Piles | P268 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.103 | CW-Sec-3-401 | Pile Cap | P-97 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.162 | CW-Sec-3-681 | Pile Cap | P-167 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.40 | CW-Sec-4-PR-5-405 | Pedestal & Seismic arrestors | P200 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.23 | PILE2180 | Piles | PR-20 | 12
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11200 | PR14-PR15-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11210 | PR11-PR12-10 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11220 | PR11-PR12-11 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11230 | PR15-PR16-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11240 | PR15-PR16-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11250 | PR15-PR16-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11260 | PR15-PR16-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11270 | PR15-PR16-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.15 | PILE1150 | Piles | P229 | 12
Not Started | BLP-DWP-R5-5.5.5.1.1.3 | CW-Sec-2A-MIB-536-3 | Slab | CH. 1.667 MIB 4X2.65 length 13.678 Br No 536 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.4 | CW-Sec-2A-MIB-540-3 | Slab | CH. 4.275 MIB 2X2.65 length 6.646 Br No 540 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.5 | CW-Sec-2A-MIB-537-3 | Slab | CH. 1.822 MIB 2X2.65 length 14.178 Br No 537 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.60 | PILE2820 | Piles | P-69 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.1.9 | UGE11250 | U-Girder | P55-P56 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.1.1.6 | CW-Sec-2A-MIB-5381-1 | Raft | CH. 3.64 MIB 2X5.45 length 6.425 Br No 538 (1) | 10
Not Started | BLP-DWP-R5-5.5.7.2.4 | CW-Sec-4B-ROB-410A-5 | Substructure | CH. 19.2 ROB Re-construction (2 sapns)(35+27) length Br No 410A | 75
Not Started | BLP-DWP-R5-5.5.6.9.10.2.63 | CW-Sec-3-278 | Pier | P-66 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.69 | CW-Sec-3-1281 | Pier: Curing, De-Shuttering, De-Staging | P-64 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.68 | CW-Sec-3-267 | Pier Cap Erection | P-63 | 2
Not Started | BLP-DWP-R5-5.5.7.2.2.2 | CW-Sec-4B-RUB-412B-1 | Raft | CH. 18.425 RUB 1no. X 6X5.5 length 8.525 Br No 412B | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.4.105 | PILE3150 | Piles | P-99 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.1.1 | UGE11210 | U-Girder | P56-P57 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.22 | CW-Sec-1B-PR-19-2 | Pile Cap | PR-19 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.19 | CW-Sec-1B-PR-1-297 | Portal Pier: Curing,De-shuttering,De-Staging | PR-16 | 7
Not Started | BLP-DWP-R5-5.5.5.1.4.1 | CW-Sec-2A-EW-1 | Cutting / Filling-2A Ch. (-) 0.050 to Ch. 0.950 | Cutting / Filling-2A Ch. (-) 0.050 to Ch. 5.700 | 45
Not Started | BLP-DWP-R5-5.5.7.10.4.1.14 | 3186 | Pile Cap | P205 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.18 | 3399 | Pier | P256 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.19 | CW-Sec-4-1540 | Pier: Curing, De-Shuttering, De-Staging | P255 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.61 | CW-Sec-3-285 | Pile Cap | P-68 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.102 | CW-Sec-3-398 | Pier | P-96 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.100 | CW-Sec-3-1591 | Pier: Curing, De-Shuttering, De-Staging | P-94 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.44 | CW-Sec-4-1550 | Portal Pier: Curing, De-Shuttering, De-Staging | P262 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.68 | CW-Sec-3-PR-5-93 | Pedestal & Seismic arrestors | P-63 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.1.28 | UGE11320 | U-Girder | P57-P58 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.34 | PILE1710 | Piles | P269 | 6
Not Started | BLP-DWP-R5-5.5.5.1.1.1 | CW-Sec-2A-MIB-534-3 | Slab | CH. 0.22 MIB 3X1.8 length 27.415 Br No 534 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.2 | CW-Sec-2A-MIB-535-3 | Slab | CH. 0.947 MIB 4X2.65 length 29.245 Br No 535 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1098 | P89-P90 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1101 | P187-P188 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1104 | P93-P94 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1108 | P97-P98 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1111 | P100-P101 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.104 | CW-Sec-3-405 | Pile Cap | P-98 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.36 | 4064 | Pier | P202 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.39 | CW-Sec-4-1560 | Pier: Curing, De-Shuttering, De-Staging | P201 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.9 | 3336 | Pier Cap Erection | P241 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.70 | PILE2840 | Piles | P-70 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.168 | CW-Sec-3-662 | Pier | P-162 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.6.167 | CW-Sec-3-2261 | Pier: Curing, De-Shuttering, De-Staging | P-161 | 7
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11660 | P203 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11760 | P-171-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11780 | P-142 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11800 | P-143 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11830 | P-144 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11850 | P-145 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11870 | P251 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11890 | P-147 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.1.27 | UGE11310 | U-Girder | P58-P59 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.62 | CW-Sec-3-282 | Pier | P-67 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.2.64 | CW-Sec-3-1291 | Pier: Curing, De-Shuttering, De-Staging | P-65 | 7
Not Started | BLP-DWP-R5-5.5.4.2.4.7 | IGE10030 | I-Girder | PR6-PR7 | 4
Not Started | BLP-DWP-R5-5.5.4.2.33.11 | CW-Sec-1B-PR-5-10 | Pedestal & Seismic arrestors | PR-8 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.12 | CW-Sec-1B-PR-5-11 | Pedestal & Seismic arrestors | PR-9 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.13 | CW-Sec-1B-PR-5-12 | Pedestal & Seismic arrestors | PR-10 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.41 | 3410 | Pile Cap | P261 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.9 | CW-Sec-4-PR-5-305 | Pedestal & Seismic arrestors | P241 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.69 | CW-Sec-3-271 | Pier Cap Erection | P-64 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.106 | PILE3170 | Piles | P-100 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.1.26 | UGE11350 | U-Girder | P59-P60 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.60 | CW-Sec-3-289 | Pile Cap | P-69 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.103 | CW-Sec-3-402 | Pier | P-97 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.6.164 | CW-Sec-3-674 | Pier | P-165 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.101 | CW-Sec-3-1601 | Pier: Curing, De-Shuttering, De-Staging | P-95 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.6.165 | CW-Sec-3-2291 | Pier: Curing, De-Shuttering, De-Staging | P-164 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.19 | CW-Sec-1B-PR-16-4 | Portal Beam Cast In Situ | PR-16 | 36
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11280 | PR15-PR16-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11290 | PR15-PR16-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11300 | PR15-PR16-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11310 | PR15-PR16-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11320 | PR16-PR17-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11330 | PR16-PR17-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11340 | PR16-PR17-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11350 | PR16-PR17-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.69 | CW-Sec-3-PR-5-94 | Pedestal & Seismic arrestors | P-64 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.1.25 | UGE11370 | U-Girder | P60-P61 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.1.1.6 | CW-Sec-2A-MIB-5381-2 | Wall | CH. 3.64 MIB 2X5.45 length 6.425 Br No 538 (1) | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.21 | CW-Sec-1B-PR-18-3 | Portal Pier | PR-18 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.44 | 4264 | Portal Beam Erection | P262 | 4
Not Started | BLP-DWP-R5-5.5.7.10.4.1.19 | CW-Sec-4-1570 | Portal Pier: Curing, De-Shuttering, De-Staging | P225 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.33 | PILE1670 | Piles | P270 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.105 | CW-Sec-3-409 | Pile Cap | P-99 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.24 | PILE2190 | Piles | PR-21 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.31 | PILE1310 | Piles | P230 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.3.71 | PILE2850 | Piles | P-71 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.39 | 3914 | Pier Cap Erection | P201 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.48 | 4214 | Pile Cap | P206 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.61 | CW-Sec-3-286 | Pier | P-68 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.24 | UGE11360 | U-Girder | P61-P62 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.63 | CW-Sec-3-1301 | Pier: Curing, De-Shuttering, De-Staging | P-66 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.7 | 3311 | Pier | P243 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.8 | CW-Sec-4-1580 | Pier: Curing, De-Shuttering, De-Staging | P242 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.26 | CW-Sec-4-1590 | Pier: Curing, De-Shuttering, De-Staging | P248 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.64 | CW-Sec-3-275 | Pier Cap Erection | P-65 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.39 | CW-Sec-4-PR-5-415 | Pedestal & Seismic arrestors | P201 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.107 | PILE3180 | Piles | P-101 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.23 | CW-Sec-1B-PR-20-2 | Pile Cap | PR-20 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.20 | CW-Sec-1B-PR-1-317 | Portal Pier: Curing,De-shuttering,De-Staging | PR-17 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.18 | CW-Sec-4-1600 | Portal Pier: Curing, De-Shuttering, De-Staging | P226 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.44 | CW-Sec-4-1610 | Portal Beam: Curing, De-Shuttering, De-Staging | P262 | 31
Not Started | BLP-DWP-R5-5.5.5.1.2.2 | CW-Sec-2A-RUB-539-4 | Approaches & misc. work | CH. 4.137 RUB 1no. X 6.1mX3 length 27.18 Br No 539 | 45
Not Started | BLP-DWP-R5-5.5.6.9.10.2.70 | CW-Sec-3-293 | Pile Cap | P-70 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.3 | CW-Sec-2A-MIB-536-4 | Return wall | CH. 1.667 MIB 4X2.65 length 13.678 Br No 536 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.4 | CW-Sec-2A-MIB-540-4 | Return wall | CH. 4.275 MIB 2X2.65 length 6.646 Br No 540 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.5 | CW-Sec-2A-MIB-537-4 | Return wall | CH. 1.822 MIB 2X2.65 length 14.178 Br No 537 | 15
Not Started | BLP-DWP-R5-5.5.5.1.4.2 | CW-Sec-2A-Blan-1 | Blanketing-2A Ch. (-) 0.050 to Ch. 0.950 | Blanketing-2A Ch. (-) 0.050 to Ch. 5.700 | 45
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1099 | P90-P91 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1102 | P91-P92 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1105 | P94-P95 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1109 | P98-P99 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.104 | CW-Sec-3-406 | Pier | P-98 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.102 | CW-Sec-3-1611 | Pier: Curing, De-Shuttering, De-Staging | P-96 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.64 | CW-Sec-3-PR-5-95 | Pedestal & Seismic arrestors | P-65 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11840 | P250 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11860 | P-146 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11880 | P-173-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11910 | P-148 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11930 | P253 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11950 | P-150 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11970 | P-151 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.14 | CW-Sec-1B-PR-5-31 | Pedestal & Seismic arrestors | PR-11 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.32 | PILE1630 | Piles | P271 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.106 | CW-Sec-3-413 | Pile Cap | P-100 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.17 | 3391 | Pier | P257 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.40 | 3426 | Pile Cap | P263 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.18 | CW-Sec-4-1620 | Pier: Curing, De-Shuttering, De-Staging | P256 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.3.72 | PILE2860 | Piles | P-72 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.6.168 | CW-Sec-3-2271 | Pier: Curing, De-Shuttering, De-Staging | P-162 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.17 | 3263 | Portal Pier | P227 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.16 | 3246 | Pile Cap | P228 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.2.60 | CW-Sec-3-290 | Pier | P-69 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.23 | UGE11330 | U-Girder | P62-P63 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.62 | CW-Sec-3-1311 | Pier: Curing, De-Shuttering, De-Staging | P-67 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11360 | PR16-PR17-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11370 | PR16-PR17-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11380 | PR16-PR17-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11390 | PR16-PR17-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11400 | PR16-PR17-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11410 | PR17-PR18-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11420 | PR17-PR18-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11430 | PR17-PR18-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.63 | CW-Sec-3-279 | Pier Cap Erection | P-66 | 2
Not Started | BLP-DWP-R5-5.5.5.1.1.1 | CW-Sec-2A-MIB-534-4 | Return wall | CH. 0.22 MIB 3X1.8 length 27.415 Br No 534 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.2 | CW-Sec-2A-MIB-535-4 | Return wall | CH. 0.947 MIB 4X2.65 length 29.245 Br No 535 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.35 | 4104 | Pier | P203 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.36 | CW-Sec-4-1630 | Pier: Curing, De-Shuttering, De-Staging | P202 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.108 | PILE3190 | Piles | P-102 | 6
Not Started | BLP-DWP-R5-5.5.5.1.1.6 | CW-Sec-2A-MIB-5381-3 | Slab | CH. 3.64 MIB 2X5.45 length 6.425 Br No 538 (1) | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.8 | 3328 | Pier Cap Erection | P242 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.71 | CW-Sec-3-297 | Pile Cap | P-71 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.105 | CW-Sec-3-410 | Pier | P-99 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.6.163 | CW-Sec-3-678 | Pier | P-166 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.103 | CW-Sec-3-1621 | Pier: Curing, De-Shuttering, De-Staging | P-97 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.6.164 | CW-Sec-3-2301 | Pier: Curing, De-Shuttering, De-Staging | P-165 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.20 | CW-Sec-1B-PR-17-4 | Portal Beam Cast In Situ | PR-17 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.2.63 | CW-Sec-3-PR-5-96 | Pedestal & Seismic arrestors | P-66 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.22 | CW-Sec-1B-PR-19-3 | Portal Pier | PR-19 | 16
Not Started | BLP-DWP-R5-5.5.4.2.4.6 | IGE10050 | I-Girder | PR7-PR8 | 4
Not Started | BLP-DWP-R5-5.5.7.10.4.1.13 | 3194 | Pile Cap | P207 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.8 | CW-Sec-4-PR-5-306 | Pedestal & Seismic arrestors | P242 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.38 | A1000 | Open Web Truss | P240-P241 | 5
Not Started | BLP-DWP-R5-5.5.7.10.4.31.31 | PILE1660 | Piles | P272 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.107 | CW-Sec-3-417 | Pile Cap | P-101 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.25 | PILE2200 | Piles | PR-22 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.32 | PILE1320 | Piles | P231 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.3.78 | PILE2870 | Piles | P-73 | 6
Not Started | BLP-DWP-R5-5.5.5.2.1.5.2 | CW-Sec-2B1-Blan-5 | Blanketing-2B Ch. 9.700 to Ch. 10.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P1 | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.2.70 | CW-Sec-3-294 | Pier | P-70 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.22 | UGE11410 | U-Girder | P63-P64 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.61 | CW-Sec-3-1321 | Pier: Curing, De-Shuttering, De-Staging | P-68 | 7
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1106 | P95-P96 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1112 | P208-P209 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1116 | P104-P105 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1119 | P189-P190 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.62 | CW-Sec-3-283 | Pier Cap Erection | P-67 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.109 | PILE3200 | Piles | P-103 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11740 | P-140 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11920 | P-149 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11940 | P-174-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11960 | P254 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11990 | P-152 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12010 | P-153 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12030 | P-175-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12050 | P257 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.24 | CW-Sec-1B-PR-21-2 | Pile Cap | PR-21 | 20
Not Started | BLP-DWP-R5-5.5.4.2.4.5 | IGE10040 | I-Girder | PR8-PR9 | 4
Not Started | BLP-DWP-R5-5.5.4.2.33.21 | CW-Sec-1B-PR-1-337 | Portal Pier: Curing,De-shuttering,De-Staging | PR-18 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.3.72 | CW-Sec-3-301 | Pile Cap | P-72 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.106 | CW-Sec-3-414 | Pier | P-100 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.36 | 4074 | Pier Cap Erection | P202 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.104 | CW-Sec-3-1631 | Pier: Curing, De-Shuttering, De-Staging | P-98 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.39 | 3434 | Pile Cap | P264 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.62 | CW-Sec-3-PR-5-97 | Pedestal & Seismic arrestors | P-67 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.15 | CW-Sec-1B-PR-5-13 | Pedestal & Seismic arrestors | PR-12 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.30 | 3347 | Pier | P244 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.7 | CW-Sec-4-1640 | Pier: Curing, De-Shuttering, De-Staging | P243 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.108 | CW-Sec-3-421 | Pile Cap | P-102 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.36 | CW-Sec-4-PR-5-425 | Pedestal & Seismic arrestors | P202 | 15
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11440 | PR17-PR18-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11450 | PR17-PR18-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11460 | PR17-PR18-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11470 | PR17-PR18-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11480 | PR17-PR18-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11490 | PR17-PR18-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11500 | PR18-PR19-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11510 | PR18-PR19-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.3 | UGE10630 | U-Girder | P187-P188 | 1
Not Started | BLP-DWP-R5-5.5.5.1.1.9 | CW-Sec-2A-MIB-541C-1 | Raft | CH. 4.722 MIB 2nosx3x1.8 length 30.238 (Barrel length is inclusive of both cells) Br No 541C | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.10 | CW-Sec-2A-MIB-542-1 | Raft | CH. 4.8 MIB 2X2.65 length 15.334 Br No 542 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.11 | CW-Sec-2A-MIB-543-1 | Raft | CH. 4.974 MIB 2X2.65 length 22.258 Br No 543 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.3.77 | PILE2880 | Piles | P-74 | 6
Not Started | BLP-DWP-R5-5.5.4.2.4.16 | IGE10060 | I-Girder | PR9-PR10 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.3.71 | CW-Sec-3-298 | Pier | P-71 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.21 | UGE11390 | U-Girder | P64-P65 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.60 | CW-Sec-3-1331 | Pier: Curing, De-Shuttering, De-Staging | P-69 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.61 | CW-Sec-3-287 | Pier Cap Erection | P-68 | 2
Not Started | BLP-DWP-R5-5.5.7.2.2.2 | CW-Sec-4B-RUB-412B-2 | Wall | CH. 18.425 RUB 1no. X 6X5.5 length 8.525 Br No 412B | 35
Not Started | BLP-DWP-R5-5.5.6.9.10.4.110 | PILE3210 | Piles | P-104 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.16 | 3375 | Pier | P258 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.17 | CW-Sec-4-1650 | Pier: Curing, De-Shuttering, De-Staging | P257 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.3.78 | CW-Sec-3-305 | Pile Cap | P-73 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.107 | CW-Sec-3-418 | Pier | P-101 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.6.162 | CW-Sec-3-682 | Pier | P-167 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.105 | CW-Sec-3-1641 | Pier: Curing, De-Shuttering, De-Staging | P-99 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.6.163 | CW-Sec-3-2311 | Pier: Curing, De-Shuttering, De-Staging | P-166 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.16 | CW-Sec-1B-PR-1-247 | Portal Beam: Curing,De-shuttering,De-Staging | PR-13 | 31
Not Started | BLP-DWP-R5-5.5.4.2.33.17 | CW-Sec-1B-PR-1-267 | Portal Beam: Curing,De-shuttering,De-Staging | PR-14 | 31
Not Started | BLP-DWP-R5-5.5.4.2.33.18 | CW-Sec-1B-PR-1-287 | Portal Beam: Curing,De-shuttering,De-Staging | PR-15 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.2.61 | CW-Sec-3-PR-5-98 | Pedestal & Seismic arrestors | P-68 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.23 | CW-Sec-1B-PR-20-3 | Portal Pier | PR-20 | 16
Not Started | BLP-DWP-R5-5.5.4.2.4.15 | IGE10070 | I-Girder | PR10-PR11 | 4
Not Started | BLP-DWP-R5-5.5.7.10.4.1.17 | CW-Sec-4-1660 | Portal Pier: Curing, De-Shuttering, De-Staging | P227 | 7
Not Started | BLP-DWP-R5-5.5.5.1.1.7 | CW-Sec-2A-MIB-5382-1 | Raft | CH. 3.816 MIB 2X2.65 length 14.025 Br No 538 (2) | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.8 | CW-Sec-2A-MIB-541A-1 | Raft | CH. 4.722 MIB 2nosx3x2.65 length 29.85 (Barrel length is inclusive of both cells) Br No 541A | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1107 | P96-P97 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1110 | P99-P100 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1113 | P101-P102 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1117 | P188-P189 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1120 | P106-P107 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1127 | P192-P193 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.109 | CW-Sec-3-425 | Pile Cap | P-103 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.47 | 4144 | Pier | P204 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.35 | CW-Sec-4-1670 | Pier: Curing, De-Shuttering, De-Staging | P203 | 7
Not Started | BLP-DWP-R5-5.5.5.1.1.6 | CW-Sec-2A-MIB-5381-4 | Return wall | CH. 3.64 MIB 2X5.45 length 6.425 Br No 538 (1) | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.26 | PILE2210 | Piles | PR-23 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.7 | 3312 | Pier Cap Erection | P243 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.34 | PILE1750 | Piles | P232 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.3.76 | PILE2890 | Piles | P-75 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11820 | P249 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12000 | P255 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12020 | P256 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12040 | P-154 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12070 | P258 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12090 | P-156 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12110 | P-157 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12130 | P-158 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.3.72 | CW-Sec-3-302 | Pier | P-72 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.20 | UGE11430 | U-Girder | P65-P66 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.2.70 | CW-Sec-3-1341 | Pier: Curing, De-Shuttering, De-Staging | P-70 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.38 | 3430 | Pile Cap | P265 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.7 | CW-Sec-4-PR-5-307 | Pedestal & Seismic arrestors | P243 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.60 | CW-Sec-3-291 | Pier Cap Erection | P-69 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.99 | PILE3220 | Piles | P-105 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.25 | CW-Sec-1B-PR-22-2 | Pile Cap | PR-22 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.22 | CW-Sec-1B-PR-1-357 | Portal Pier: Curing,De-shuttering,De-Staging | PR-19 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.15 | 3214 | Pile Cap | P229 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.16 | 3247 | Portal Pier | P228 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.3.77 | CW-Sec-3-309 | Pile Cap | P-74 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.108 | CW-Sec-3-422 | Pier | P-102 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.106 | CW-Sec-3-1651 | Pier: Curing, De-Shuttering, De-Staging | P-100 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11520 | PR18-PR19-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11530 | PR18-PR19-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11540 | PR18-PR19-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11550 | PR18-PR19-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11560 | PR18-PR19-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11570 | PR18-PR19-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11580 | PR18-PR19-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11590 | PR19-PR20-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.9 | CW-Sec-2A-MIB-541C-2 | Wall | CH. 4.722 MIB 2nosx3x1.8 length 30.238 (Barrel length is inclusive of both cells) Br No 541C | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.10 | CW-Sec-2A-MIB-542-2 | Wall | CH. 4.8 MIB 2X2.65 length 15.334 Br No 542 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.11 | CW-Sec-2A-MIB-543-2 | Wall | CH. 4.974 MIB 2X2.65 length 22.258 Br No 543 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.2.60 | CW-Sec-3-PR-5-99 | Pedestal & Seismic arrestors | P-69 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.110 | CW-Sec-3-429 | Pile Cap | P-104 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.3.75 | PILE2900 | Piles | P-76 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.35 | 4114 | Pier Cap Erection | P203 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.13 | 3195 | Portal Pier | P207 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.12 | 3190 | Pile Cap | P208 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.3.78 | CW-Sec-3-306 | Pier | P-73 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.19 | UGE11450 | U-Girder | P66-P67 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.71 | CW-Sec-3-1351 | Pier: Curing, De-Shuttering, De-Staging | P-71 | 7
Not Started | BLP-DWP-R5-5.5.4.2.4.14 | IGE10090 | I-Girder | PR11-PR12 | 5
Not Started | BLP-DWP-R5-5.5.7.10.4.31.29 | 3355 | Pier | P245 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.30 | CW-Sec-4-1680 | Pier: Curing, De-Shuttering, De-Staging | P244 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.2.70 | CW-Sec-3-295 | Pier Cap Erection | P-70 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.35 | CW-Sec-4-PR-5-435 | Pedestal & Seismic arrestors | P203 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.98 | PILE3230 | Piles | P-106 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.3.76 | CW-Sec-3-313 | Pile Cap | P-75 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.7 | CW-Sec-2A-MIB-5382-2 | Wall | CH. 3.816 MIB 2X2.65 length 14.025 Br No 538 (2) | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.8 | CW-Sec-2A-MIB-541A-2 | Wall | CH. 4.722 MIB 2nosx3x2.65 length 29.85 (Barrel length is inclusive of both cells) Br No 541A | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1114 | P102-P103 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1124 | P209-P210 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1125 | P191-P192 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1135 | P111-P112 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.109 | CW-Sec-3-426 | Pier | P-103 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.107 | CW-Sec-3-1661 | Pier: Curing, De-Shuttering, De-Staging | P-101 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.6.162 | CW-Sec-3-2321 | Pier: Curing, De-Shuttering, De-Staging | P-167 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.19 | CW-Sec-1B-PR-1-307 | Portal Beam: Curing,De-shuttering,De-Staging | PR-16 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.31.44 | CW-Sec-4-PR-5-475 | Pedestal & Seismic arrestors | P262 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.2.70 | CW-Sec-3-PR-5-100 | Pedestal & Seismic arrestors | P-70 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11900 | P252 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12080 | P-176-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12100 | P259 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12120 | P260 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12150 | P-177-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12170 | P263 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12190 | P264 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12210 | P-161 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.24 | CW-Sec-1B-PR-21-3 | Portal Pier | PR-21 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.4.99 | CW-Sec-3-433 | Pile Cap | P-105 | 10
Not Started | BLP-DWP-R5-5.5.5.1.4.1 | CW-Sec-2A-EW-2 | Cutting / Filling-2A Ch. 0.950 to Ch. 1.950 | Cutting / Filling-2A Ch. (-) 0.050 to Ch. 5.700 | 45
Not Started | BLP-DWP-R5-5.5.4.2.33.27 | PILE2220 | Piles | PR-24 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.15 | 3343 | Pier | P259 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.37 | 3442 | Pile Cap | P266 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.16 | CW-Sec-4-1690 | Pier: Curing, De-Shuttering, De-Staging | P258 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.33 | PILE1340 | Piles | P233 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.3.74 | PILE2910 | Piles | P-77 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.3.77 | CW-Sec-3-310 | Pier | P-74 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.18 | UGE11440 | U-Girder | P67-P68 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.72 | CW-Sec-3-1361 | Pier: Curing, De-Shuttering, De-Staging | P-72 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11600 | PR19-PR20-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11610 | PR19-PR20-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11620 | PR19-PR20-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11630 | PR19-PR20-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11640 | PR19-PR20-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11650 | PR19-PR20-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11660 | PR19-PR20-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11670 | PR19-PR20-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.3.71 | CW-Sec-3-299 | Pier Cap Erection | P-71 | 2
Not Started | BLP-DWP-R5-5.5.5.1.1.9 | CW-Sec-2A-MIB-541C-3 | Slab | CH. 4.722 MIB 2nosx3x1.8 length 30.238 (Barrel length is inclusive of both cells) Br No 541C | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.10 | CW-Sec-2A-MIB-542-3 | Slab | CH. 4.8 MIB 2X2.65 length 15.334 Br No 542 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.11 | CW-Sec-2A-MIB-543-3 | Slab | CH. 4.974 MIB 2X2.65 length 22.258 Br No 543 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.14 | 3187 | Pier | P205 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.47 | CW-Sec-4-1700 | Pier: Curing, De-Shuttering, De-Staging | P204 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.97 | PILE3240 | Piles | P-107 | 6
Not Started | BLP-DWP-R5-5.5.5.1.1.12 | CW-Sec-2A-MIB-544-1 | Raft | CH. 5.102 MIB 2X1.8 length 8.745 Br No 544 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.26 | CW-Sec-1B-PR-23-2 | Pile Cap | PR-23 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.23 | CW-Sec-1B-PR-1-377 | Portal Pier: Curing,De-shuttering,De-Staging | PR-20 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.30 | 3348 | Pier Cap Erection | P244 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.75 | CW-Sec-3-317 | Pile Cap | P-76 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.110 | CW-Sec-3-430 | Pier | P-104 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.108 | CW-Sec-3-1671 | Pier: Curing, De-Shuttering, De-Staging | P-102 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.3.71 | CW-Sec-3-PR-5-101 | Pedestal & Seismic arrestors | P-71 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.30 | CW-Sec-4-PR-5-308 | Pedestal & Seismic arrestors | P244 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.98 | CW-Sec-3-437 | Pile Cap | P-106 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.193 | PILE4160 | Piles | P-184-DN | 6
Not Started | BLP-DWP-R5-5.5.5.2.2 | CW-Interface-1 | Handover to KRIDE/ track laying contractor | Interface works by K-RIDE/ Track laying contractor | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.1.16 | CW-Sec-4-1710 | Portal Pier: Curing, De-Shuttering, De-Staging | P228 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.3.76 | CW-Sec-3-314 | Pier | P-75 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.17 | UGE11380 | U-Girder | P68-P69 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.1.1.7 | CW-Sec-2A-MIB-5382-3 | Slab | CH. 3.816 MIB 2X2.65 length 14.025 Br No 538 (2) | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.8 | CW-Sec-2A-MIB-541A-3 | Slab | CH. 4.722 MIB 2nosx3x2.65 length 29.85 (Barrel length is inclusive of both cells) Br No 541A | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.3.78 | CW-Sec-3-1371 | Pier: Curing, De-Shuttering, De-Staging | P-73 | 7
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1115 | P103-P104 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1118 | P105-P106 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1121 | P190-P191 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1128 | P109-P110 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1132 | P213-P214 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1133 | P236-P237 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.2.2 | CW-Interface-2 | Track laying & divert the IR traffic to newly laid BSRP track | Interface works by K-RIDE/ Track laying contractor | 28
Not Started | BLP-DWP-R5-5.5.6.9.10.3.72 | CW-Sec-3-303 | Pier Cap Erection | P-72 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.96 | PILE3250 | Piles | P-108 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC11980 | P206 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12160 | P-159 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12180 | P-160 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12200 | P-178-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12230 | P234 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12250 | P267 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12270 | P-162 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12290 | P-163 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.3.74 | CW-Sec-3-321 | Pile Cap | P-77 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.99 | CW-Sec-3-434 | Pier | P-105 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.47 | 4154 | Pier Cap Erection | P204 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.109 | CW-Sec-3-1681 | Pier: Curing, De-Shuttering, De-Staging | P-103 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.23 | CW-Sec-1B-PR-20-4 | Portal Beam Cast In Situ | PR-20 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.22 | CW-Sec-1B-PR-19-4 | Portal Beam Cast In Situ | PR-19 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.21 | CW-Sec-1B-PR-18-4 | Portal Beam Cast In Situ | PR-18 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.20 | CW-Sec-1B-PR-1-327 | Portal Beam: Curing,De-shuttering,De-Staging | PR-17 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.31.36 | 3450 | Pile Cap | P267 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.3.72 | CW-Sec-3-PR-5-102 | Pedestal & Seismic arrestors | P-72 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.25 | CW-Sec-1B-PR-22-3 | Portal Pier | PR-22 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.15 | 3215 | Portal Pier | P229 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.31 | 3278 | Pile Cap | P230 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.13 | CW-Sec-4-1720 | Portal Pier: Curing, De-Shuttering, De-Staging | P207 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.29 | CW-Sec-4-1730 | Pier: Curing, De-Shuttering, De-Staging | P245 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.97 | CW-Sec-3-441 | Pile Cap | P-107 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.47 | CW-Sec-4-PR-5-445 | Pedestal & Seismic arrestors | P204 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.28 | PILE2230 | Piles | PR-25 | 12
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11680 | PR20-PR21-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11690 | PR20-PR21-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11700 | PR20-PR21-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11710 | PR20-PR21-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11720 | PR20-PR21-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11730 | PR20-PR21-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11740 | PR20-PR21-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11750 | PR20-PR21-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.8 | UGE10660 | U-Girder | P188-P189 | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.1.38 | PILE1760 | Piles | P234 | 6
Not Started | BLP-DWP-R5-5.5.5.1.2.3 | CW-Sec-2A-RUB-541A-4 | Approaches & misc. work | CH. 4.709 RUB 1no. X 7.5 mX5 length 12.225 Br No 541B | 45
Not Started | BLP-DWP-R5-5.5.5.1.4.2 | CW-Sec-2A-Blan-2 | Blanketing-2A Ch. 0.950 to Ch. 1.950 | Blanketing-2A Ch. (-) 0.050 to Ch. 5.700 | 45
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.192 | PILE4170 | Piles | P-185-DN | 6
Not Started | BLP-DWP-R5-5.5.7.2.2.2 | CW-Sec-4B-RUB-412B-4 | Approaches & misc. work | CH. 18.425 RUB 1no. X 6X5.5 length 8.525 Br No 412B | 60
Not Started | BLP-DWP-R5-5.5.5.1.1.12 | CW-Sec-2A-MIB-544-2 | Wall | CH. 5.102 MIB 2X1.8 length 8.745 Br No 544 | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.7 | UGE10680 | U-Girder | P189-P190 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.3.75 | CW-Sec-3-318 | Pier | P-76 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.1.16 | UGE11420 | U-Girder | P69-P70 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.77 | CW-Sec-3-1381 | Pier: Curing, De-Shuttering, De-Staging | P-74 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.3.78 | CW-Sec-3-307 | Pier Cap Erection | P-73 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.95 | PILE3260 | Piles | P-109 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.27 | CW-Sec-1B-PR-24-2 | Pile Cap | PR-24 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.24 | CW-Sec-1B-PR-1-397 | Portal Pier: Curing,De-shuttering,De-Staging | PR-21 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.12 | 3191 | Portal Pier | P208 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.42 | 3415 | Pier | P260 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.15 | CW-Sec-4-1740 | Pier: Curing, De-Shuttering, De-Staging | P259 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.193 | CW-Sec-3-DN-807 | Pile Cap | P-184-DN | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.98 | CW-Sec-3-438 | Pier | P-106 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.110 | CW-Sec-3-1691 | Pier: Curing, De-Shuttering, De-Staging | P-104 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.3.78 | CW-Sec-3-PR-5-103 | Pedestal & Seismic arrestors | P-73 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.17 | CW-Sec-1B-PR-5-14 | Pedestal & Seismic arrestors | PR-14 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.16 | CW-Sec-1B-PR-5-15 | Pedestal & Seismic arrestors | PR-13 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.18 | CW-Sec-1B-PR-5-16 | Pedestal & Seismic arrestors | PR-15 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.9 | CW-Sec-2A-MIB-541C-4 | Return wall | CH. 4.722 MIB 2nosx3x1.8 length 30.238 (Barrel length is inclusive of both cells) Br No 541C | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.10 | CW-Sec-2A-MIB-542-4 | Return wall | CH. 4.8 MIB 2X2.65 length 15.334 Br No 542 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.11 | CW-Sec-2A-MIB-543-4 | Return wall | CH. 4.974 MIB 2X2.65 length 22.258 Br No 543 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1122 | P107-P108 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1129 | P212-P213 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1140 | P216-P217 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1141 | P241-P242 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1143 | P217-P218 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.96 | CW-Sec-3-445 | Pile Cap | P-108 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.48 | 4224 | Pier | P206 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.14 | CW-Sec-4-1750 | Pier: Curing, De-Shuttering, De-Staging | P205 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.13 | 3196 | Portal beam cast in situ | P207 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.31.29 | 3356 | Pier Cap Erection | P245 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.37 | PILE1770 | Piles | P235 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.191 | PILE4180 | Piles | P-184-UP | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12060 | P-155 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12240 | P266 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12260 | P-179-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12280 | P268 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12310 | P-164 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12330 | P270 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12350 | P271 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12370 | P272 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.3.74 | CW-Sec-3-322 | Pier | P-77 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.15.2 | UGE11300 | U-Girder | P70-P71 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.76 | CW-Sec-3-1391 | Pier: Curing, De-Shuttering, De-Staging | P-75 | 7
Not Started | BLP-DWP-R5-5.5.7.2.2.2 | CW-Sec-4B-RUB-412B-3 | Slab | CH. 18.425 RUB 1no. X 6X5.5 length 8.525 Br No 412B | 40
Not Started | BLP-DWP-R5-5.5.7.10.4.31.28 | 3352 | Pier Cap Erection | P246 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.35 | 3446 | Pile Cap | P268 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.29 | CW-Sec-4-PR-5-309 | Pedestal & Seismic arrestors | P245 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.3.77 | CW-Sec-3-311 | Pier Cap Erection | P-74 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.116 | PILE3280 | Piles | P-110 | 6
Not Started | BLP-DWP-R5-5.5.7.2.6.2 | CW-Sec-4B-Blan-5 | Blanketing-4B Ch. 22.100 to Ch. 23.100 | Blanketing-4B Ch. 18.100 to Ch. 24.425 | 95
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.192 | CW-Sec-3-DN-811 | Pile Cap | P-185-DN | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.97 | CW-Sec-3-442 | Pier | P-107 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.99 | CW-Sec-3-1701 | Pier: Curing, De-Shuttering, De-Staging | P-105 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.24 | CW-Sec-1B-PR-21-4 | Portal Beam Cast In Situ | PR-21 | 36
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11760 | PR20-PR21-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11770 | PR21-PR22-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11780 | PR21-PR22-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11790 | PR21-PR22-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11800 | PR21-PR22-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11810 | PR21-PR22-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11820 | PR21-PR22-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11830 | PR21-PR22-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.27 | 3364 | Pier Cap Erection | P247 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.28 | CW-Sec-4-PR-5-310 | Pedestal & Seismic arrestors | P246 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.7 | CW-Sec-2A-MIB-5382-4 | Return wall | CH. 3.816 MIB 2X2.65 length 14.025 Br No 538 (2) | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.8 | CW-Sec-2A-MIB-541A-4 | Return wall | CH. 4.722 MIB 2nosx3x2.65 length 29.85 (Barrel length is inclusive of both cells) Br No 541A | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.3.77 | CW-Sec-3-PR-5-104 | Pedestal & Seismic arrestors | P-74 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.12 | CW-Sec-2A-MIB-544-3 | Slab | CH. 5.102 MIB 2X1.8 length 8.745 Br No 544 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.26 | CW-Sec-1B-PR-23-3 | Portal Pier | PR-23 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.4.95 | CW-Sec-3-449 | Pile Cap | P-109 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.29 | PILE2240 | Piles | PR-26 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.26 | 3372 | Pier Cap Erection | P248 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.27 | CW-Sec-4-PR-5-311 | Pedestal & Seismic arrestors | P247 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.190 | PILE4320 | Piles | P-185-UP | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.14 | 3188 | Pier Cap Erection | P205 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.193 | CW-Sec-3-DN-808 | Pier | P-184-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.15.4 | UGE11480 | U-Girder | P71-P72 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.75 | CW-Sec-3-1401 | Pier: Curing, De-Shuttering, De-Staging | P-76 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.25 | 3368 | Pier Cap Erection | P249 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.26 | CW-Sec-4-PR-5-312 | Pedestal & Seismic arrestors | P248 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.3.76 | CW-Sec-3-315 | Pier Cap Erection | P-75 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.14 | CW-Sec-4-PR-5-239 | Pedestal & Seismic arrestors | P205 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.117 | PILE3290 | Piles | P-111 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.28 | CW-Sec-1B-PR-25-2 | Pile Cap | PR-25 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.25 | CW-Sec-1B-PR-1-417 | Portal Pier: Curing,De-shuttering,De-Staging | PR-22 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.15 | CW-Sec-4-1760 | Portal Pier: Curing, De-Shuttering, De-Staging | P229 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.191 | CW-Sec-3-DN-815 | Pile Cap | P-184-UP | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1123 | P108-P109 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1126 | P210-P211 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1136 | P214-P215 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1137 | P238-P239 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1148 | P115-P116 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1149 | P245-P246 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1151 | P246-P247 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.96 | CW-Sec-3-446 | Pier | P-108 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.98 | CW-Sec-3-1711 | Pier: Curing, De-Shuttering, De-Staging | P-106 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.24 | 3360 | Pier Cap Erection | P250 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.25 | CW-Sec-4-PR-5-313 | Pedestal & Seismic arrestors | P249 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.3.76 | CW-Sec-3-PR-5-105 | Pedestal & Seismic arrestors | P-75 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12140 | P261 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12320 | P-180-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12340 | P-165 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12360 | P-166 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12390 | P-167 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12410 | P-185-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12430 | P-184-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12450 | P-1 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.116 | CW-Sec-3-453 | Pile Cap | P-110 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.23 | 3380 | Pier Cap Erection | P251 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.41 | 3411 | Pier | P261 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.34 | 3438 | Pile Cap | P269 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.24 | CW-Sec-4-PR-5-314 | Pedestal & Seismic arrestors | P250 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.42 | CW-Sec-4-1770 | Pier: Curing, De-Shuttering, De-Staging | P260 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.43.188 | PILE1780 | Piles | P-1 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.31 | 3279 | Portal Pier | P230 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.32 | 3282 | Pile Cap | P231 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.12 | CW-Sec-4-1780 | Portal Pier: Curing, De-Shuttering, De-Staging | P208 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.192 | CW-Sec-3-DN-812 | Pier | P-185-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.15.3 | UGE11470 | U-Girder | P72-P73 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.74 | CW-Sec-3-1411 | Pier: Curing, De-Shuttering, De-Staging | P-77 | 7
Not Started | BLP-DWP-R5-5.5.4.2.4.13 | IGE10080 | I-Girder | PR12-PR13 | 5
Not Started | BLP-DWP-R5-5.5.4.2.33.19 | CW-Sec-1B-PR-5-17 | Pedestal & Seismic arrestors | PR-16 | 15
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11840 | PR21-PR22-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11850 | PR21-PR22-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11860 | PR22-PR23-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11870 | PR22-PR23-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11880 | PR22-PR23-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11890 | PR22-PR23-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11900 | PR22-PR23-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11910 | PR22-PR23-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.22 | 3388 | Pier Cap Erection | P252 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.23 | CW-Sec-4-PR-5-315 | Pedestal & Seismic arrestors | P251 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.6 | UGE10670 | U-Girder | P190-P191 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.3.75 | CW-Sec-3-319 | Pier Cap Erection | P-76 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.48 | CW-Sec-4-1790 | Pier: Curing, De-Shuttering, De-Staging | P206 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.132 | PILE3460 | Piles | P-126 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.118 | PILE3300 | Piles | P-112 | 6
Not Started | BLP-DWP-R5-5.5.7.10.1.29.5 | UGE10650 | U-Girder | P191-P192 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.190 | CW-Sec-3-UP-819 | Pile Cap | P-185-UP | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.95 | CW-Sec-3-450 | Pier | P-109 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.97 | CW-Sec-3-1721 | Pier: Curing, De-Shuttering, De-Staging | P-107 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.25 | CW-Sec-1B-PR-22-4 | Portal Beam Cast In Situ | PR-22 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.31.21 | 3384 | Pier Cap Erection | P253 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.22 | CW-Sec-4-PR-5-316 | Pedestal & Seismic arrestors | P252 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.14 | UGE10710 | U-Girder | P192-P193 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.3.75 | CW-Sec-3-PR-5-106 | Pedestal & Seismic arrestors | P-76 | 15
Not Started | BLP-DWP-R5-5.5.5.2.2 | CW-Interface-3 | Removal / Dismentalling of Existing IR track including Ballast | Interface works by K-RIDE/ Track laying contractor | 28
Not Started | BLP-DWP-R5-5.5.4.2.33.27 | CW-Sec-1B-PR-24-3 | Portal Pier | PR-24 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.4.117 | CW-Sec-3-457 | Pile Cap | P-111 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.30 | PILE2250 | Piles | PR-27 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.20 | 3396 | Pier Cap Erection | P254 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.21 | CW-Sec-4-PR-5-317 | Pedestal & Seismic arrestors | P253 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.189 | PILE1790 | Piles | P-2 | 9
Not Started | BLP-DWP-R5-5.5.4.2.4.12 | IGE10100 | I-Girder | PR13-PR14 | 5
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.191 | CW-Sec-3-DN-816 | Pier | P-184-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.15.8 | UGE11500 | U-Girder | P73-P74 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.1.1.13 | CW-Sec-2A-MIB-545-1 | Raft | CH. 5.398 MIB 2X2.65 length 22.17 Br No 545 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.14 | CW-Sec-2A-MIB-546-1 | Raft | CH. 5.566 MIB 2X2.65 length 27.51 Br No 546 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.193 | CW-Sec-3-2371 | Pier: Curing, De-Shuttering, De-Staging | P-184-DN | 7
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1130 | P193-P194 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1134 | P237-P238 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1144 | P242-P243 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1145 | P114-P115 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1157 | P249-P250 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1159 | P250-P251 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.12 | CW-Sec-2A-MIB-544-4 | Return wall | CH. 5.102 MIB 2X1.8 length 8.745 Br No 544 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.7 | 3184 | Portal beam cast in situ | P213 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.12 | 3192 | Portal beam cast in situ | P208 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.11 | 3204 | Portal beam cast in situ | P209 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.10 | 3212 | Portal beam cast in situ | P210 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.9 | 3208 | Portal beam cast in situ | P211 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.8 | 3200 | Portal beam cast in situ | P212 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.31.19 | 3404 | Pier Cap Erection | P255 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.20 | CW-Sec-4-PR-5-318 | Pedestal & Seismic arrestors | P254 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.3.74 | CW-Sec-3-323 | Pier Cap Erection | P-77 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.133 | PILE3470 | Piles | P-127 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.119 | PILE3310 | Piles | P-113 | 9
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12220 | P265 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12400 | P-184-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12420 | P-182-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12440 | P235 | Pier Cap Casting | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12470 | P-183-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12490 | P-3 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12510 | P-4 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12530 | P-5 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.26 | CW-Sec-1B-PR-1-437 | Portal Pier: Curing,De-shuttering,De-Staging | PR-23 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.29 | CW-Sec-1B-PR-26-2 | Pile Cap | PR-26 | 20
Not Started | BLP-DWP-R5-5.5.7.2.4 | CW-Sec-4B-ROB-410A-6 | Super Structure | CH. 19.2 ROB Re-construction (2 sapns)(35+27) length Br No 410A | 60
Not Started | BLP-DWP-R5-5.5.6.9.10.4.116 | CW-Sec-3-454 | Pier | P-110 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.48 | 4234 | Pier Cap Erection | P206 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.96 | CW-Sec-3-1731 | Pier: Curing, De-Shuttering, De-Staging | P-108 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.18 | 3400 | Pier Cap Erection | P256 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.33 | 3422 | Pile Cap | P270 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.19 | CW-Sec-4-PR-5-319 | Pedestal & Seismic arrestors | P255 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.73 | CW-Sec-3-327 | Pier Cap Erection | P-78 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.3.74 | CW-Sec-3-PR-5-107 | Pedestal & Seismic arrestors | P-77 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.20 | CW-Sec-1B-PR-5-18 | Pedestal & Seismic arrestors | PR-17 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.132 | CW-Sec-3-517 | Pile Cap | P-126 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.118 | CW-Sec-3-461 | Pile Cap | P-112 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.48 | CW-Sec-4-PR-5-465 | Pedestal & Seismic arrestors | P206 | 15
Not Started | BLP-DWP-R5-5.5.4.2.4.11 | IGE10110 | I-Girder | PR14-PR15 | 4
Not Started | BLP-DWP-R5-5.5.4.2.33.31 | PILE2030 | Piles | PR-28 | 18
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11920 | PR22-PR23-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11930 | PR22-PR23-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11940 | PR22-PR23-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11950 | PR23-PR24-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11960 | PR23-PR24-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11970 | PR23-PR24-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11980 | PR23-PR24-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC11990 | PR23-PR24-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.17 | 3392 | Pier Cap Erection | P257 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.18 | CW-Sec-4-PR-5-320 | Pedestal & Seismic arrestors | P256 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.80 | CW-Sec-3-331 | Pier Cap Erection | P-79 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.73 | CW-Sec-3-PR-5-108 | Pedestal & Seismic arrestors | P-78 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.190 | CW-Sec-3-UP-820 | Pier | P-185-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.15.7 | UGE11530 | U-Girder | P74-P75 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.192 | CW-Sec-3-2381 | Pier: Curing, De-Shuttering, De-Staging | P-185-DN | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.16 | 3376 | Pier Cap Erection | P258 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.17 | CW-Sec-4-PR-5-321 | Pedestal & Seismic arrestors | P257 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.82 | CW-Sec-3-335 | Pier Cap Erection | P-80 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.80 | CW-Sec-3-PR-5-109 | Pedestal & Seismic arrestors | P-79 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.134 | PILE3480 | Piles | P-128 | 6
Not Started | BLP-DWP-R5-5.5.5.1.4.1 | CW-Sec-2A-EW-3 | Cutting / Filling-2A Ch. 1.950 to Ch. 2.950 | Cutting / Filling-2A Ch. (-) 0.050 to Ch. 5.700 | 40
Not Started | BLP-DWP-R5-5.5.7.10.4.31.40 | 3427 | Pier | P263 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.41 | CW-Sec-4-1800 | Pier: Curing, De-Shuttering, De-Staging | P261 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.43.2 | PILE1810 | Piles | P-3 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.117 | CW-Sec-3-458 | Pier | P-111 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.95 | CW-Sec-3-1741 | Pier: Curing, De-Shuttering, De-Staging | P-109 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.21 | CW-Sec-1B-PR-1-347 | Portal Beam: Curing,De-shuttering,De-Staging | PR-18 | 31
Not Started | BLP-DWP-R5-5.5.4.2.33.22 | CW-Sec-1B-PR-1-367 | Portal Beam: Curing,De-shuttering,De-Staging | PR-19 | 31
Not Started | BLP-DWP-R5-5.5.4.2.33.23 | CW-Sec-1B-PR-1-387 | Portal Beam: Curing,De-shuttering,De-Staging | PR-20 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.31.15 | 3344 | Pier Cap Erection | P259 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.16 | CW-Sec-4-PR-5-322 | Pedestal & Seismic arrestors | P258 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.81 | CW-Sec-3-339 | Pier Cap Erection | P-81 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.82 | CW-Sec-3-PR-5-110 | Pedestal & Seismic arrestors | P-80 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.28 | CW-Sec-1B-PR-25-3 | Portal Pier | PR-25 | 16
Not Started | BLP-DWP-R5-5.5.4.2.4.10 | IGE10130 | I-Girder | PR15-PR16 | 4
Not Started | BLP-DWP-R5-5.5.7.10.4.1.31 | CW-Sec-4-1810 | Portal Pier: Curing, De-Shuttering, De-Staging | P230 | 7
Not Started | BLP-DWP-R5-5.5.5.1.1.13 | CW-Sec-2A-MIB-545-2 | Wall | CH. 5.398 MIB 2X2.65 length 22.17 Br No 545 | 10
Not Started | BLP-DWP-R5-5.5.5.1.1.14 | CW-Sec-2A-MIB-546-2 | Wall | CH. 5.566 MIB 2X2.65 length 27.51 Br No 546 | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1131 | P110-P111 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1138 | P215-P216 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1142 | P113-P114 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1152 | P117-P118 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1156 | P119-P120 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1165 | P122-P123 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1167 | P256-P257 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.133 | CW-Sec-3-521 | Pile Cap | P-127 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.120 | PILE3320 | Piles | P-114 | 9
Not Started | BLP-DWP-R5-5.5.7.10.4.31.42 | 3416 | Pier Cap Erection | P260 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.15 | CW-Sec-4-PR-5-323 | Pedestal & Seismic arrestors | P259 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.86 | CW-Sec-3-343 | Pier Cap Erection | P-82 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.81 | CW-Sec-3-PR-5-111 | Pedestal & Seismic arrestors | P-81 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.2 | CW-Sec-2B2-RUB-Pre | Preliminary works ( Diversion, Approval etc.) | RUB | 41
Not Started | BLP-DWP-R5-5.5.5.2.3.3 | CW-Sec-2B2-MJB-560-1 | Dismantling | CH. 9.992 MJB 2X30.5 length Br No 560 | 40
Not Started | BLP-DWP-R5-5.5.5.2.3.1.1 | CW-Sec-2B2-MIB-547-1 | Raft | CH. 5.8 MIB 2X2.5 length 29.896 Br No 547 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.2 | CW-Sec-2B2-MIB-552-1 | Raft | CH. 7.4 MIB 2X2.64 length 43.72 Br No 552 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.3 | CW-Sec-2B2-MIB-558-1 | Raft | CH. 9.466 MIB 2X2.5 length 35.684 Br No 558 | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12300 | P269 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12480 | P-2 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12500 | P-171-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12550 | P-6 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12570 | P-7 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12600 | P-9 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.15.6 | UGE11520 | U-Girder | P75-P76 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.191 | CW-Sec-3-2391 | Pier: Curing, De-Shuttering, De-Staging | P-184-UP | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.32 | 3406 | Pile Cap | P271 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.42 | CW-Sec-4-PR-5-324 | Pedestal & Seismic arrestors | P260 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.85 | CW-Sec-3-347 | Pier Cap Erection | P-83 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.86 | CW-Sec-3-PR-5-112 | Pedestal & Seismic arrestors | P-82 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.30 | 3220 | Portal beam cast in situ | P214 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.29 | 3228 | Portal beam cast in situ | P215 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.28 | 3224 | Portal beam cast in situ | P216 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.27 | 3236 | Portal beam cast in situ | P217 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.26 | 3244 | Portal beam cast in situ | P218 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.25 | 3240 | Portal beam cast in situ | P219 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.24 | 3232 | Portal beam cast in situ | P220 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.4.119 | CW-Sec-3-465 | Pile Cap | P-113 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.135 | PILE3490 | Piles | P-129 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.27 | CW-Sec-1B-PR-1-457 | Portal Pier: Curing,De-shuttering,De-Staging | PR-24 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.32 | 3283 | Portal Pier | P231 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.34 | 3454 | Pile Cap | P232 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.43.1 | PILE1800 | Piles | P-4 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.192 | CW-Sec-3-DN-813 | Pier Cap Erection | P-185-DN | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.118 | CW-Sec-3-462 | Pier | P-112 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.116 | CW-Sec-3-1751 | Pier: Curing, De-Shuttering, De-Staging | P-110 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12000 | PR23-PR24-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12010 | PR23-PR24-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12020 | PR23-PR24-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12030 | PR23-PR24-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12040 | PR24-PR25-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12050 | PR24-PR25-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12060 | PR24-PR25-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12070 | PR24-PR25-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.41 | 3412 | Pier Cap Erection | P261 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.84 | CW-Sec-3-351 | Pier Cap Erection | P-84 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.85 | CW-Sec-3-PR-5-113 | Pedestal & Seismic arrestors | P-83 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.4 | CW-Sec-2B2-MIB-553-1 | Raft | CH. 8.236 MIB 2X2.5 length 43.446 Br No 553 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.192 | CW-Sec-3-PR-5-228 | Pedestal & Seismic arrestors | P-185-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.134 | CW-Sec-3-525 | Pile Cap | P-128 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.31 | 3280 | Portal beam cast in situ | P230 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.31.41 | CW-Sec-4-PR-5-325 | Pedestal & Seismic arrestors | P261 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.13 | CW-Sec-4-1820 | Portal Beam: Curing, De-Shuttering, De-Staging | P207 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.4.83 | CW-Sec-3-355 | Pier Cap Erection | P-85 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.84 | CW-Sec-3-PR-5-114 | Pedestal & Seismic arrestors | P-84 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.4 | CW-Sec-2B2-ERS | Outer side of Track-2B Ch. 5.700 to Ch. 10.700-P2 | Earth Retaining Structure | 230
Not Started | BLP-DWP-R5-5.5.6.9.11.15.5 | UGE11490 | U-Girder | P76-P77 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.190 | CW-Sec-3-2401 | Pier: Curing, De-Shuttering, De-Staging | P-185-UP | 7
Not Started | BLP-DWP-R5-5.5.4.2.4.9 | IGE10120 | I-Girder | PR16-PR17 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.4.92 | CW-Sec-3-359 | Pier Cap Erection | P-86 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.191 | CW-Sec-3-DN-817 | Pier Cap Erection | P-184-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.83 | CW-Sec-3-PR-5-115 | Pedestal & Seismic arrestors | P-85 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.136 | PILE3510 | Piles | P-130 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.121 | PILE3330 | Piles | P-115 | 9
Not Started | BLP-DWP-R5-5.5.7.10.4.43.6 | PILE1830 | Piles | P-5 | 6
Not Started | BLP-DWP-R5-5.5.7.2.4 | CW-Sec-4B-ROB-410A-8 | Approaches and misc Works | CH. 19.2 ROB Re-construction (2 sapns)(35+27) length Br No 410A | 50
Not Started | BLP-DWP-R5-5.5.6.9.11.2.2 | UGE11540 | U-Girder | P77-P78 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.1.1.13 | CW-Sec-2A-MIB-545-3 | Slab | CH. 5.398 MIB 2X2.65 length 22.17 Br No 545 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.14 | CW-Sec-2A-MIB-546-3 | Slab | CH. 5.566 MIB 2X2.65 length 27.51 Br No 546 | 15
Not Started | BLP-DWP-R5-5.5.5.1.4.2 | CW-Sec-2A-Blan-3 | Blanketing-2A Ch. 1.950 to Ch. 2.950 | Blanketing-2A Ch. (-) 0.050 to Ch. 5.700 | 40
Not Started | BLP-DWP-R5-5.5.5.2.3.2.1 | CW-Sec-2B2-RUB-143-1 | Raft | CH. 7.547 RUB (1no x 30m) Re-construction length 48.96 LC-143 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.2 | CW-Sec-2B2-RUB-141-1 | Raft | CH. 6.675 RUB (1no x 30m) Re-construction length 41.31 LC-141 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.3 | CW-Sec-2B2-RUB-144-1 | Raft | CH. 8.175 RUB (1no x 30m) Re-construction length 41.31 LC-144 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.4 | CW-Sec-2B2-RUB-KNG-1 | Raft | CH. 8.675 RUB 1no. X 6X5.5 length 40 Kanaka nagar | 25
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1146 | P243-P244 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1153 | P247-P248 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1175 | P125-P126 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.117 | CW-Sec-3-1761 | Pier: Curing, De-Shuttering, De-Staging | P-111 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.24 | CW-Sec-1B-PR-1-407 | Portal Beam: Curing,De-shuttering,De-Staging | PR-21 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.4.93 | CW-Sec-3-363 | Pier Cap Erection | P-87 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.92 | CW-Sec-3-PR-5-116 | Pedestal & Seismic arrestors | P-86 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.191 | CW-Sec-3-PR-5-229 | Pedestal & Seismic arrestors | P-184-UP | 15
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12380 | P-181-DN | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12520 | P-172-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12560 | P-174-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12580 | P-175-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12620 | P-176-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12640 | PR-26 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12670 | P-178-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.29 | CW-Sec-1B-PR-26-3 | Pier | PR-26 | 12
Not Started | BLP-DWP-R5-5.5.4.2.33.30 | CW-Sec-1B-PR-27-2 | Pile Cap | PR-27 | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.2.4 | UGE11560 | U-Girder | P78-P79 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.135 | CW-Sec-3-529 | Pile Cap | P-129 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.120 | CW-Sec-3-469 | Pile Cap | P-114 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.32 | PILE2040 | Piles | PR-29 | 18
Not Started | BLP-DWP-R5-5.5.7.10.4.31.31 | 3418 | Pile Cap | P272 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.39 | 3435 | Pier | P264 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.40 | CW-Sec-4-1830 | Pier: Curing, De-Shuttering, De-Staging | P263 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.94 | CW-Sec-3-367 | Pier Cap Erection | P-88 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.93 | CW-Sec-3-PR-5-117 | Pedestal & Seismic arrestors | P-87 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.119 | CW-Sec-3-466 | Pier | P-113 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.193 | CW-Sec-3-DN-809 | Pier Cap Erection | P-184-DN | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.3 | UGE11550 | U-Girder | P79-P80 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12080 | PR24-PR25-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12090 | PR24-PR25-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12100 | PR24-PR25-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12110 | PR24-PR25-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12120 | PR24-PR25-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12130 | PR25-PR26-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12140 | PR25-PR26-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12150 | PR25-PR26-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.13 | UGE10700 | U-Girder | P193-P194 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.91 | CW-Sec-3-371 | Pier Cap Erection | P-89 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.94 | CW-Sec-3-PR-5-118 | Pedestal & Seismic arrestors | P-88 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.137 | PILE3520 | Piles | P-131 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.28 | CW-Sec-1B-PR-1-477 | Portal Pier: Curing,De-shuttering,De-Staging | PR-25 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.15 | 3216 | Portal beam cast in situ | P229 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.23 | 3252 | Portal beam cast in situ | P221 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.22 | 3260 | Portal beam cast in situ | P222 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.21 | 3256 | Portal beam cast in situ | P223 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.20 | 3268 | Portal beam cast in situ | P224 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.19 | 3276 | Portal beam cast in situ | P225 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.18 | 3272 | Portal beam cast in situ | P226 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.17 | 3264 | Portal beam cast in situ | P227 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.16 | 3248 | Portal beam cast in situ | P228 | 36
Not Started | BLP-DWP-R5-5.5.7.10.1.29.12 | UGE10730 | U-Girder | P236-P237 | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.43.5 | PILE1850 | Piles | P-6 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.9.1.193 | CW-Sec-3-PR-5-227 | Pedestal & Seismic arrestors | P-184-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.8 | UGE11590 | U-Girder | P80-P81 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.1 | CW-Sec-2B2-MIB-547-2 | Wall | CH. 5.8 MIB 2X2.5 length 29.896 Br No 547 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.2 | CW-Sec-2B2-MIB-552-2 | Wall | CH. 7.4 MIB 2X2.64 length 43.72 Br No 552 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.3 | CW-Sec-2B2-MIB-558-2 | Wall | CH. 9.466 MIB 2X2.5 length 35.684 Br No 558 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.118 | CW-Sec-3-1771 | Pier: Curing, De-Shuttering, De-Staging | P-112 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.11 | UGE10750 | U-Girder | P237-P238 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.90 | CW-Sec-3-375 | Pier Cap Erection | P-90 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.91 | CW-Sec-3-PR-5-119 | Pedestal & Seismic arrestors | P-89 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.2 | 1199 | Steel girder assembly & erection | P185-P186 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.10 | UGE10740 | U-Girder | P238-P239 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.7 | UGE11610 | U-Girder | P81-P82 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.136 | CW-Sec-3-533 | Pile Cap | P-130 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.122 | PILE3340 | Piles | P-116 | 9
Not Started | BLP-DWP-R5-5.5.6.9.10.4.89 | CW-Sec-3-379 | Pier Cap Erection | P-91 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.90 | CW-Sec-3-PR-5-120 | Pedestal & Seismic arrestors | P-90 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.40 | 3428 | Pier Cap Erection | P263 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.32 | CW-Sec-4-1840 | Portal Pier: Curing, De-Shuttering, De-Staging | P231 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.2.6 | UGE11600 | U-Girder | P82-P83 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1139 | P239-P240 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1150 | P116-P117 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1154 | P118-P119 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1160 | P251-P252 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1161 | P252-P253 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1164 | P254-P255 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1173 | P124-P125 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.4 | CW-Sec-2B2-MIB-553-2 | Wall | CH. 8.236 MIB 2X2.5 length 43.446 Br No 553 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.88 | CW-Sec-3-383 | Pier Cap Erection | P-92 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.89 | CW-Sec-3-PR-5-121 | Pedestal & Seismic arrestors | P-91 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.121 | CW-Sec-3-473 | Pile Cap | P-115 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.138 | PILE3530 | Piles | P-132 | 6
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12460 | P-185-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12590 | P-8 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12630 | P-11 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12650 | P-177-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12690 | P-179-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12710 | P-181-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.31 | CW-Sec-1B-P-28-2 | Pile Cap | PR-28 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.40 | CW-Sec-4-PR-5-326 | Pedestal & Seismic arrestors | P263 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.29 | A1010 | Open Web Truss | P260-P261 | 5
Not Started | BLP-DWP-R5-5.5.7.10.4.43.4 | PILE1840 | Piles | P-7 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.2.5 | UGE11570 | U-Girder | P83-P84 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.120 | CW-Sec-3-470 | Pier | P-114 | 12
Not Started | BLP-DWP-R5-5.5.4.2.33.28 | CW-Sec-1B-PR-25-4 | Portal Beam Cast In Situ | PR-25 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.27 | CW-Sec-1B-PR-24-4 | Portal Beam Cast In Situ | PR-24 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.26 | CW-Sec-1B-PR-23-4 | Portal Beam Cast In Situ | PR-23 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.25 | CW-Sec-1B-PR-1-427 | Portal Beam: Curing,De-shuttering,De-Staging | PR-22 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.43.188 | 3506 | Pile Cap | P-1 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.87 | CW-Sec-3-387 | Pier Cap Erection | P-93 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.88 | CW-Sec-3-PR-5-122 | Pedestal & Seismic arrestors | P-92 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.30 | CW-Sec-1B-PR-27-3 | Pier | PR-27 | 12
Not Started | BLP-DWP-R5-5.5.4.2.33.29 | CW-Sec-1B-PR-1-497 | Pier: Curing,De-shuttering,De-Staging | PR-26 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.33 | 3290 | Pile Cap | P233 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.1.34 | 3455 | Portal Pier | P232 | 16
Not Started | BLP-DWP-R5-5.5.6.9.11.2.14 | UGE11650 | U-Girder | P84-P85 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12160 | PR25-PR26-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12170 | PR25-PR26-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12180 | PR25-PR26-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12190 | PR25-PR26-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12200 | PR25-PR26-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12210 | PR25-PR26-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12220 | PR26-PR27-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12230 | PR26-PR27-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.100 | CW-Sec-3-391 | Pier Cap Erection | P-94 | 2
Not Started | BLP-DWP-R5-5.5.5.1.1.13 | CW-Sec-2A-MIB-545-4 | Return wall | CH. 5.398 MIB 2X2.65 length 22.17 Br No 545 | 15
Not Started | BLP-DWP-R5-5.5.5.1.1.14 | CW-Sec-2A-MIB-546-4 | Return wall | CH. 5.566 MIB 2X2.65 length 27.51 Br No 546 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.87 | CW-Sec-3-PR-5-123 | Pedestal & Seismic arrestors | P-93 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.119 | CW-Sec-3-1781 | Pier: Curing, De-Shuttering, De-Staging | P-113 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.2.13 | UGE11640 | U-Girder | P85-P86 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.32 | 3284 | Portal beam cast in situ | P231 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.1.12 | CW-Sec-4-1850 | Portal Beam: Curing, De-Shuttering, De-Staging | P208 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.11 | CW-Sec-4-1860 | Portal Beam: Curing, De-Shuttering, De-Staging | P209 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.10 | CW-Sec-4-1870 | Portal Beam: Curing, De-Shuttering, De-Staging | P210 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.9 | CW-Sec-4-1880 | Portal Beam: Curing, De-Shuttering, De-Staging | P211 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.8 | CW-Sec-4-1890 | Portal Beam: Curing, De-Shuttering, De-Staging | P212 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.7 | CW-Sec-4-1900 | Portal Beam: Curing, De-Shuttering, De-Staging | P213 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.4.101 | CW-Sec-3-395 | Pier Cap Erection | P-95 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.100 | CW-Sec-3-PR-5-124 | Pedestal & Seismic arrestors | P-94 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.139 | PILE3540 | Piles | P-133 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.123 | PILE3350 | Piles | P-117 | 9
Not Started | BLP-DWP-R5-5.5.7.10.4.31.38 | 3431 | Pier | P265 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.39 | CW-Sec-4-1910 | Pier: Curing, De-Shuttering, De-Staging | P264 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.43.3 | PILE1820 | Piles | P-8 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.2.12 | UGE11670 | U-Girder | P86-P87 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.137 | CW-Sec-3-537 | Pile Cap | P-131 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.102 | CW-Sec-3-399 | Pier Cap Erection | P-96 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.101 | CW-Sec-3-PR-5-125 | Pedestal & Seismic arrestors | P-95 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.21 | CW-Sec-1B-PR-5-19 | Pedestal & Seismic arrestors | PR-18 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.22 | CW-Sec-1B-PR-5-20 | Pedestal & Seismic arrestors | PR-19 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.23 | CW-Sec-1B-PR-5-21 | Pedestal & Seismic arrestors | PR-20 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.11 | UGE11690 | U-Girder | P87-P88 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1147 | P244-P245 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1168 | P257-P258 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1169 | P258-P259 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1172 | P259-P260 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1183 | P266-P267 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.122 | CW-Sec-3-477 | Pile Cap | P-116 | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.1 | PILE2050 | Piles | PR-30 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.103 | CW-Sec-3-403 | Pier Cap Erection | P-97 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.102 | CW-Sec-3-PR-5-126 | Pedestal & Seismic arrestors | P-96 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.121 | CW-Sec-3-474 | Pier | P-115 | 12
Not Started | BLP-DWP-R5-5.5.5.2.3.1.1 | CW-Sec-2B2-MIB-547-3 | Slab | CH. 5.8 MIB 2X2.5 length 29.896 Br No 547 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.2 | CW-Sec-2B2-MIB-552-3 | Slab | CH. 7.4 MIB 2X2.64 length 43.72 Br No 552 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.3 | CW-Sec-2B2-MIB-558-3 | Slab | CH. 9.466 MIB 2X2.5 length 35.684 Br No 558 | 20
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12540 | P-173-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12660 | PR-27 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12700 | P-180-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12720 | P-182-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12730 | P-183-UP | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.2.10 | UGE11680 | U-Girder | P88-P89 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.43.188 | 3507 | Pier | P-1 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.43.189 | 3538 | Pile Cap | P-2 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.104 | CW-Sec-3-407 | Pier Cap Erection | P-98 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.103 | CW-Sec-3-PR-5-127 | Pedestal & Seismic arrestors | P-97 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.140 | PILE3550 | Piles | P-134 | 6
Not Started | BLP-DWP-R5-5.5.5.2.3.5.1 | CW-Sec-2B2-EW-1 | Cutting / Filling-2B Ch. 5.700 to Ch. 6.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P2 | 150
Not Started | BLP-DWP-R5-5.5.7.10.4.43.14 | PILE1860 | Piles | P-9 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.29 | CW-Sec-1B-PR-26-4 | Pier Cap erection | PR-26 | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.9 | UGE11660 | U-Girder | P89-P90 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.120 | CW-Sec-3-1791 | Pier: Curing, De-Shuttering, De-Staging | P-114 | 7
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12240 | PR26-PR27-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12250 | PR26-PR27-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12260 | PR26-PR27-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12270 | PR26-PR27-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12280 | PR26-PR27-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12290 | PR26-PR27-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12300 | PR26-PR27-9 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12310 | PR27-PR28-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.39 | 3436 | Pier Cap Erection | P264 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.105 | CW-Sec-3-411 | Pier Cap Erection | P-99 | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.2.1 | CW-Sec-2B2-RUB-143-2 | Wall | CH. 7.547 RUB (1no x 30m) Re-construction length 48.96 LC-143 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.2 | CW-Sec-2B2-RUB-141-2 | Wall | CH. 6.675 RUB (1no x 30m) Re-construction length 41.31 LC-141 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.3 | CW-Sec-2B2-RUB-144-2 | Wall | CH. 8.175 RUB (1no x 30m) Re-construction length 41.31 LC-144 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.4 | CW-Sec-2B2-RUB-KNG-2 | Wall | CH. 8.675 RUB 1no. X 6X5.5 length 40 Kanaka nagar | 25
Not Started | BLP-DWP-R5-5.5.6.9.10.4.104 | CW-Sec-3-PR-5-128 | Pedestal & Seismic arrestors | P-98 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.4 | CW-Sec-2B2-MIB-553-3 | Slab | CH. 8.236 MIB 2X2.5 length 43.446 Br No 553 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.30 | CW-Sec-1B-PR-1-507 | Pier: Curing,De-shuttering,De-Staging | PR-27 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.29 | CW-Sec-1B-PR-5-27 | Pedestal & Seismic arrestors | PR-26 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.1 | UGE11630 | U-Girder | P90-P91 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.124 | PILE3360 | Piles | P-118 | 9
Not Started | BLP-DWP-R5-5.5.4.2.33.2 | PILE2060 | Piles | PR-31 | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.39 | CW-Sec-4-PR-5-327 | Pedestal & Seismic arrestors | P264 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.106 | CW-Sec-3-415 | Pier Cap Erection | P-100 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.105 | CW-Sec-3-PR-5-129 | Pedestal & Seismic arrestors | P-99 | 15
Not Started | BLP-DWP-R5-5.5.5.1.4.1 | CW-Sec-2A-EW-4 | Cutting / Filling-2A Ch. 2.950 to Ch. 3.950 | Cutting / Filling-2A Ch. (-) 0.050 to Ch. 5.700 | 40
Not Started | BLP-DWP-R5-5.5.7.10.4.1.13 | CW-Sec-4-PR-5-240 | Pedestal & Seismic arrestors | P207 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.28 | UGE11740 | U-Girder | P91-P92 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.138 | CW-Sec-3-541 | Pile Cap | P-132 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.107 | CW-Sec-3-419 | Pier Cap Erection | P-101 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.106 | CW-Sec-3-PR-5-130 | Pedestal & Seismic arrestors | P-100 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.123 | CW-Sec-3-481 | Pile Cap | P-117 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.30 | CW-Sec-4-1920 | Portal Beam: Curing, De-Shuttering, De-Staging | P214 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.29 | CW-Sec-4-1930 | Portal Beam: Curing, De-Shuttering, De-Staging | P215 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.28 | CW-Sec-4-1940 | Portal Beam: Curing, De-Shuttering, De-Staging | P216 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.27 | CW-Sec-4-1950 | Portal Beam: Curing, De-Shuttering, De-Staging | P217 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.26 | CW-Sec-4-1960 | Portal Beam: Curing, De-Shuttering, De-Staging | P218 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.25 | CW-Sec-4-1970 | Portal Beam: Curing, De-Shuttering, De-Staging | P219 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.24 | CW-Sec-4-1980 | Portal Beam: Curing, De-Shuttering, De-Staging | P220 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.4.141 | PILE3560 | Piles | P-135 | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.1 | CW-Sec-1B-P-29-24 | Pile Cap | PR-30 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.34 | CW-Sec-4-1990 | Portal Pier: Curing, De-Shuttering, De-Staging | P232 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.43.13 | PILE1880 | Piles | P-10 | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.2.27 | UGE11720 | U-Girder | P92-P93 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.5 | CW-Sec-2B2-MIB-563-1 | Raft | CH. 10.244 MIB 2X2.5 length 31.914 Br No 563 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.6 | CW-Sec-2B2-MIB-548-1 | Raft | CH. 6.49 MIB 2X2.5 length 34.71 Br No 548 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1155 | P248-P249 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1158 | P120-P121 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1162 | P253-P254 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1176 | P262-P263 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1177 | P126-P127 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1180 | P264-P265 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1181 | P128-P129 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.122 | CW-Sec-3-478 | Pier | P-116 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.108 | CW-Sec-3-423 | Pier Cap Erection | P-102 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.107 | CW-Sec-3-PR-5-131 | Pedestal & Seismic arrestors | P-101 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.3 | CW-Sec-2B2-MJB-560-2 | Foundation | CH. 9.992 MJB 2X30.5 length Br No 560 | 80
Not Started | BLP-DWP-R5-5.5.3.4 | PCC12610 | P-10 | Pier Cap Casting | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.24 | CW-Sec-1B-PR-5-22 | Pedestal & Seismic arrestors | PR-21 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.31 | CW-Sec-1B-P-28-3 | Portal Pier | PR-28 | 16
Not Started | BLP-DWP-R5-5.5.4.2.33.32 | CW-Sec-1B-P-29-2 | Pile Cap | PR-29 | 20
Not Started | BLP-DWP-R5-5.5.6.9.11.2.26 | UGE11760 | U-Girder | P93-P94 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.172 | PILE4030 | Piles | P-171-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.182 | PILE4190 | Piles | P-171-UP | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.37 | 3443 | Pier | P266 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.2 | 3570 | Pile Cap | P-3 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.38 | CW-Sec-4-2010 | Pier: Curing, De-Shuttering, De-Staging | P265 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.31 | CW-Sec-4-2000 | Portal Beam: Curing, De-Shuttering, De-Staging | P230 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.4.109 | CW-Sec-3-427 | Pier Cap Erection | P-103 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.108 | CW-Sec-3-PR-5-132 | Pedestal & Seismic arrestors | P-102 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.121 | CW-Sec-3-1801 | Pier: Curing, De-Shuttering, De-Staging | P-115 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.33 | 3291 | Portal Pier | P233 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.38 | 3462 | Pile Cap | P234 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.190 | CW-Sec-3-UP-821 | Pier Cap Erection | P-185-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.25 | UGE11780 | U-Girder | P94-P95 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.4.26 | IGE10150 | I-Girder | PR17-PR18 | 4
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12320 | PR27-PR28-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12330 | PR27-PR28-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12340 | PR27-PR28-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12342 | PR30-PR31-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12343 | PR30-PR31-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12344 | PR30-PR31-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12345 | PR30-PR31-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12346 | PR31-PR32-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.43.189 | 3539 | Pier | P-2 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.43.188 | CW-Sec-4-2020 | Pier: Curing, De-Shuttering, De-Staging | P-1 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.9 | UGE10720 | U-Girder | P239-P240 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.110 | CW-Sec-3-431 | Pier Cap Erection | P-104 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.109 | CW-Sec-3-PR-5-133 | Pedestal & Seismic arrestors | P-103 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.142 | PILE3570 | Piles | P-136 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.125 | PILE3370 | Piles | P-119 | 9
Not Started | BLP-DWP-R5-5.5.4.2.33.2 | CW-Sec-1B-P-29-64 | Pile Cap | PR-31 | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.1 | UGE10690 | U-Girder | P241-P242 | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.43.12 | PILE1870 | Piles | P-11 | 0
Not Started | BLP-DWP-R5-5.5.6.9.10.9.2.190 | CW-Sec-3-PR-5-230 | Pedestal & Seismic arrestors | P-185-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.24 | UGE11770 | U-Girder | P95-P96 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.5.1 | CW-Sec-2B2-EW-2 | Cutting / Filling-2B Ch. 6.700 to Ch. 7.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P2 | 150
Not Started | BLP-DWP-R5-5.5.7.10.4.1.34 | 3456 | Portal beam cast in situ | P232 | 36
Not Started | BLP-DWP-R5-5.5.7.10.1.29.28 | UGE10780 | U-Girder | P242-P243 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.99 | CW-Sec-3-435 | Pier Cap Erection | P-105 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.110 | CW-Sec-3-PR-5-134 | Pedestal & Seismic arrestors | P-104 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.27 | UGE10770 | U-Girder | P243-P244 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.23 | UGE11750 | U-Girder | P96-P97 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.139 | CW-Sec-3-545 | Pile Cap | P-133 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.124 | CW-Sec-3-485 | Pile Cap | P-118 | 10
Not Started | BLP-DWP-R5-5.5.4.2.4.25 | IGE10140 | I-Girder | PR18-PR19 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.173 | PILE4040 | Piles | P-172-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.181 | PILE4200 | Piles | P-172-UP | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.98 | CW-Sec-3-439 | Pier Cap Erection | P-106 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.99 | CW-Sec-3-PR-5-135 | Pedestal & Seismic arrestors | P-105 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.123 | CW-Sec-3-482 | Pier | P-117 | 12
Not Started | BLP-DWP-R5-5.5.4.2.33.1 | CW-Sec-1B-P-29-34 | Pier | PR-30 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.38 | 3432 | Pier Cap Erection | P265 | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.22 | UGE11810 | U-Girder | P97-P98 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.1.4.2 | CW-Sec-2A-Blan-4 | Blanketing-2A Ch. 2.950 to Ch. 3.950 | Blanketing-2A Ch. (-) 0.050 to Ch. 5.700 | 40
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1163 | P121-P122 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1170 | P123-P124 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1191 | P220-P221 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.97 | CW-Sec-3-443 | Pier Cap Erection | P-107 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.98 | CW-Sec-3-PR-5-136 | Pedestal & Seismic arrestors | P-106 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.1 | CW-Sec-2B2-MIB-547-4 | Return wall | CH. 5.8 MIB 2X2.5 length 29.896 Br No 547 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.2 | CW-Sec-2B2-MIB-552-4 | Return wall | CH. 7.4 MIB 2X2.64 length 43.72 Br No 552 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.3 | CW-Sec-2B2-MIB-558-4 | Return wall | CH. 9.466 MIB 2X2.5 length 35.684 Br No 558 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.115 | PILE3580 | Piles | P-137 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.172 | CW-Sec-3-DN-703 | Pile Cap | P-171-DN | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.182 | CW-Sec-3-UP-755 | Pile Cap | P-171-UP | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.43.188 | 3508 | Pier Cap Erection | P-1 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.38 | CW-Sec-4-PR-5-328 | Pedestal & Seismic arrestors | P265 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.23 | CW-Sec-4-2030 | Portal Beam: Curing, De-Shuttering, De-Staging | P221 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.22 | CW-Sec-4-2040 | Portal Beam: Curing, De-Shuttering, De-Staging | P222 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.21 | CW-Sec-4-2050 | Portal Beam: Curing, De-Shuttering, De-Staging | P223 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.20 | CW-Sec-4-2060 | Portal Beam: Curing, De-Shuttering, De-Staging | P224 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.19 | CW-Sec-4-2070 | Portal Beam: Curing, De-Shuttering, De-Staging | P225 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.18 | CW-Sec-4-2080 | Portal Beam: Curing, De-Shuttering, De-Staging | P226 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.17 | CW-Sec-4-2090 | Portal Beam: Curing, De-Shuttering, De-Staging | P227 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.16 | CW-Sec-4-2100 | Portal Beam: Curing, De-Shuttering, De-Staging | P228 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.1.15 | CW-Sec-4-2110 | Portal Beam: Curing, De-Shuttering, De-Staging | P229 | 31
Not Started | BLP-DWP-R5-5.5.6.9.11.2.21 | UGE11800 | U-Girder | P98-P99 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.122 | CW-Sec-3-1811 | Pier: Curing, De-Shuttering, De-Staging | P-116 | 7
Not Started | BLP-DWP-R5-5.5.4.2.4.24 | IGE10160 | I-Girder | PR19-PR20 | 4
Not Started | BLP-DWP-R5-5.5.7.10.4.43.1 | 3554 | Pile Cap | P-4 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.96 | CW-Sec-3-447 | Pier Cap Erection | P-108 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.97 | CW-Sec-3-PR-5-137 | Pedestal & Seismic arrestors | P-107 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.25 | CW-Sec-1B-PR-5-23 | Pedestal & Seismic arrestors | PR-22 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.38 | 3463 | Pier | P234 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.1.37 | 3470 | Pile Cap | P235 | 20
Not Started | BLP-DWP-R5-5.5.4.2.33.30 | CW-Sec-1B-PR-27-4 | Pier Cap erection | PR-27 | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.20 | UGE12070 | U-Girder | P99-P100 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.126 | PILE3390 | Piles | P-120 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.175 | PILE4050 | Piles | P-173-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.180 | PILE4210 | Piles | P-173-UP | 6
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12350 | P194-P195-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12360 | P194-P195-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12370 | P194-P195-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12380 | P194-P195-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12390 | P194-P195-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12347 | PR31-PR32-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12348 | PR31-PR32-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12349 | PR31-PR32-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.26 | UGE10800 | U-Girder | P244-P245 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.95 | CW-Sec-3-451 | Pier Cap Erection | P-109 | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.5 | CW-Sec-2B2-MIB-563-2 | Wall | CH. 10.244 MIB 2X2.5 length 31.914 Br No 563 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.6 | CW-Sec-2B2-MIB-548-2 | Wall | CH. 6.49 MIB 2X2.5 length 34.71 Br No 548 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.96 | CW-Sec-3-PR-5-138 | Pedestal & Seismic arrestors | P-108 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.4 | CW-Sec-2B2-MIB-553-4 | Return wall | CH. 8.236 MIB 2X2.5 length 43.446 Br No 553 | 20
Not Started | BLP-DWP-R5-5.5.7.10.1.29.25 | UGE10820 | U-Girder | P245-P246 | 1
Not Started | BLP-DWP-R5-5.5.4.2.33.30 | CW-Sec-1B-PR-5-28 | Pedestal & Seismic arrestors | PR-27 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.19 | UGE12290 | U-Girder | P100-P101 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.4.23 | IGE10170 | I-Girder | PR20-PR21 | 4
Not Started | BLP-DWP-R5-5.5.7.10.4.43.2 | 3571 | Pier | P-3 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.43.189 | CW-Sec-4-2120 | Pier: Curing, De-Shuttering, De-Staging | P-2 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.24 | UGE10810 | U-Girder | P246-P247 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.116 | CW-Sec-3-455 | Pier Cap Erection | P-110 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.95 | CW-Sec-3-PR-5-139 | Pedestal & Seismic arrestors | P-109 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.125 | CW-Sec-3-489 | Pile Cap | P-119 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.114 | PILE3590 | Piles | P-138 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.173 | CW-Sec-3-DN-707 | Pile Cap | P-172-DN | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.2 | 1248 | Steel girder assembly & erection | P185-P186 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.31 | CW-Sec-1B-PR-1-517 | Portal Pier: Curing,De-shuttering,De-Staging | PR-28 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.36 | 3451 | Pier | P267 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.12 | CW-Sec-4-PR-5-241 | Pedestal & Seismic arrestors | P208 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.11 | CW-Sec-4-PR-5-242 | Pedestal & Seismic arrestors | P209 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.10 | CW-Sec-4-PR-5-243 | Pedestal & Seismic arrestors | P210 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.9 | CW-Sec-4-PR-5-244 | Pedestal & Seismic arrestors | P211 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.8 | CW-Sec-4-PR-5-245 | Pedestal & Seismic arrestors | P212 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.7 | CW-Sec-4-PR-5-246 | Pedestal & Seismic arrestors | P213 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.37 | CW-Sec-4-2130 | Pier: Curing, De-Shuttering, De-Staging | P266 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.23 | UGE10790 | U-Girder | P247-P248 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.18 | UGE12180 | U-Girder | P101-P102 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.140 | CW-Sec-3-549 | Pile Cap | P-134 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.124 | CW-Sec-3-486 | Pier | P-118 | 12
Not Started | BLP-DWP-R5-5.5.4.2.33.26 | CW-Sec-1B-PR-1-447 | Portal Beam: Curing,De-shuttering,De-Staging | PR-23 | 31
Not Started | BLP-DWP-R5-5.5.4.2.33.27 | CW-Sec-1B-PR-1-467 | Portal Beam: Curing,De-shuttering,De-Staging | PR-24 | 31
Not Started | BLP-DWP-R5-5.5.4.2.33.28 | CW-Sec-1B-PR-1-487 | Portal Beam: Curing,De-shuttering,De-Staging | PR-25 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.4.117 | CW-Sec-3-459 | Pier Cap Erection | P-111 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.116 | CW-Sec-3-PR-5-140 | Pedestal & Seismic arrestors | P-110 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.33 | CW-Sec-4-2140 | Portal Pier: Curing, De-Shuttering, De-Staging | P233 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.2.17 | UGE11790 | U-Girder | P102-P103 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.2.1 | CW-Sec-2B2-RUB-143-3 | Slab | CH. 7.547 RUB (1no x 30m) Re-construction length 48.96 LC-143 | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.2.2 | CW-Sec-2B2-RUB-141-3 | Slab | CH. 6.675 RUB (1no x 30m) Re-construction length 41.31 LC-141 | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.2.3 | CW-Sec-2B2-RUB-144-3 | Slab | CH. 8.175 RUB (1no x 30m) Re-construction length 41.31 LC-144 | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.2.4 | CW-Sec-2B2-RUB-KNG-3 | Slab | CH. 8.675 RUB 1no. X 6X5.5 length 40 Kanaka nagar | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.3 | CW-Sec-2B2-MJB-560-3 | Substructure | CH. 9.992 MJB 2X30.5 length Br No 560 | 80
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1166 | P255-P256 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1184 | P267-P268 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1185 | P268-P269 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1188 | P219-P220 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1189 | P270-P271 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1199 | P135-P136 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.115 | CW-Sec-3-561 | Pile Cap | P-137 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.127 | PILE3400 | Piles | P-121 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.174 | PILE4060 | Piles | P-174-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.203 | PILE4220 | Piles | P-174-UP | 6
Not Started | BLP-DWP-R5-5.5.6.9.11.6.2.4 | 1198 | Steel girder assembly & erection | P184-P185 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.118 | CW-Sec-3-463 | Pier Cap Erection | P-112 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.117 | CW-Sec-3-PR-5-141 | Pedestal & Seismic arrestors | P-111 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.123 | CW-Sec-3-1821 | Pier: Curing, De-Shuttering, De-Staging | P-117 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.172 | CW-Sec-3-DN-704 | Pier | P-171-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.182 | CW-Sec-3-UP-756 | Pier | P-171-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.181 | CW-Sec-3-UP-759 | Pile Cap | P-172-UP | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.2 | CW-Sec-1B-P-29-74 | Pier | PR-31 | 12
Not Started | BLP-DWP-R5-5.5.4.2.33.1 | CW-Sec-1B-PR-1-557 | Pier: Curing,De-shuttering,De-Staging | PR-30 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.32 | CW-Sec-1B-P-29-3 | Portal Pier | PR-29 | 16
Not Started | BLP-DWP-R5-5.5.6.9.11.2.16 | UGE11960 | U-Girder | P103-P104 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.43.6 | 3578 | Pile Cap | P-5 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.32 | CW-Sec-4-2150 | Portal Beam: Curing, De-Shuttering, De-Staging | P231 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.4.119 | CW-Sec-3-467 | Pier Cap Erection | P-113 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.118 | CW-Sec-3-PR-5-142 | Pedestal & Seismic arrestors | P-112 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.126 | CW-Sec-3-493 | Pile Cap | P-120 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.113 | PILE3600 | Piles | P-139 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.175 | CW-Sec-3-DN-711 | Pile Cap | P-173-DN | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.43.189 | 3540 | Pier Cap Erection | P-2 | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.15 | UGE11710 | U-Girder | P104-P105 by LG | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.31 | CW-Sec-1B-P-28-4 | Portal Beam Cast In Situ | PR-28 | 36
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12400 | P194-P195-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12410 | P194-P195-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12420 | P194-P195-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12430 | P195-P196-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12440 | P195-P196-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12450 | P195-P196-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12460 | P195-P196-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12470 | P195-P196-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.37 | 3444 | Pier Cap Erection | P266 | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.29.22 | UGE10850 | U-Girder | P248-P249 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.120 | CW-Sec-3-471 | Pier Cap Erection | P-114 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.119 | CW-Sec-3-PR-5-143 | Pedestal & Seismic arrestors | P-113 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.38 | CW-Sec-4-2160 | Pier: Curing, De-Shuttering, De-Staging | P234 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.21 | UGE10840 | U-Girder | P249-P250 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.37 | UGE12400 | U-Girder | P105-P106 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.5.1 | CW-Sec-2B2-EW-3 | Cutting / Filling-2B Ch. 7.700 to Ch. 8.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P2 | 120
Not Started | BLP-DWP-R5-5.5.6.9.10.4.128 | PILE3420 | Piles | P-122 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.179 | PILE4070 | Piles | P-175-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.202 | PILE4230 | Piles | P-175-UP | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.1.33 | 3292 | Portal beam cast in situ | P233 | 36
Not Started | BLP-DWP-R5-5.5.7.10.4.31.37 | CW-Sec-4-PR-5-329 | Pedestal & Seismic arrestors | P266 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.20 | UGE10870 | U-Girder | P250-P251 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.121 | CW-Sec-3-475 | Pier Cap Erection | P-115 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.120 | CW-Sec-3-PR-5-144 | Pedestal & Seismic arrestors | P-114 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.125 | CW-Sec-3-490 | Pier | P-119 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.173 | CW-Sec-3-DN-708 | Pier | P-172-DN | 12
Not Started | BLP-DWP-R5-5.5.7.10.1.29.19 | UGE10890 | U-Girder | P251-P252 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.36 | UGE11070 | U-Girder | P106-P107 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.141 | CW-Sec-3-553 | Pile Cap | P-135 | 10
Not Started | BLP-DWP-R5-5.5.4.2.4.22 | IGE10190 | I-Girder | PR21-PR22 | 4
Not Started | BLP-DWP-R5-5.5.4.2.33.1 | CW-Sec-1B-P-29-44 | Pier Cap erection | PR-30 | 2
Not Started | BLP-DWP-R5-5.5.7.2.6.2 | CW-Sec-4B-Blan-6 | Blanketing-4B Ch. 23.100 to Ch. 24.100 | Blanketing-4B Ch. 18.100 to Ch. 24.425 | 90
Not Started | BLP-DWP-R5-5.5.7.10.4.43.1 | 3555 | Pier | P-4 | 15
Not Started | BLP-DWP-R5-5.MS.7 | MS-AG5 | MS-5: Partial Access of section for a minimum 4 Km | Milestone- At Grade | 0
Not Started | BLP-DWP-R5-5.5.7.10.4.43.2 | CW-Sec-4-2170 | Pier: Curing, De-Shuttering, De-Staging | P-3 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.18 | UGE10880 | U-Girder | P252-P253 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.122 | CW-Sec-3-479 | Pier Cap Erection | P-116 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.121 | CW-Sec-3-PR-5-145 | Pedestal & Seismic arrestors | P-115 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.127 | CW-Sec-3-497 | Pile Cap | P-121 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.112 | PILE3620 | Piles | P-140 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.174 | CW-Sec-3-DN-715 | Pile Cap | P-174-DN | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.17 | UGE10830 | U-Girder | P253-P254 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.35 | UGE12620 | U-Girder | P107-P108 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.5 | CW-Sec-2B2-MIB-563-3 | Slab | CH. 10.244 MIB 2X2.5 length 31.914 Br No 563 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.6 | CW-Sec-2B2-MIB-548-3 | Slab | CH. 6.49 MIB 2X2.5 length 34.71 Br No 548 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1171 | P218-P219 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1174 | P261-P262 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1178 | P263-P264 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1196 | P133-P134 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.114 | CW-Sec-3-565 | Pile Cap | P-138 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.30 | CW-Sec-4-PR-5-247 | Pedestal & Seismic arrestors | P214 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.29 | CW-Sec-4-PR-5-248 | Pedestal & Seismic arrestors | P215 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.28 | CW-Sec-4-PR-5-249 | Pedestal & Seismic arrestors | P216 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.27 | CW-Sec-4-PR-5-250 | Pedestal & Seismic arrestors | P217 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.26 | CW-Sec-4-PR-5-251 | Pedestal & Seismic arrestors | P218 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.25 | CW-Sec-4-PR-5-252 | Pedestal & Seismic arrestors | P219 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.24 | CW-Sec-4-PR-5-253 | Pedestal & Seismic arrestors | P220 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.124 | CW-Sec-3-1831 | Pier: Curing, De-Shuttering, De-Staging | P-118 | 7
Not Started | BLP-DWP-R5-5.5.4.2.33.1 | CW-Sec-1B-PR-5-41 | Pedestal & Seismic arrestors | PR-30 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.16 | UGE10860 | U-Girder | P254-P255 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.123 | CW-Sec-3-483 | Pier Cap Erection | P-117 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.122 | CW-Sec-3-PR-5-146 | Pedestal & Seismic arrestors | P-116 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.7 | CW-Sec-2B2-MIB-549-1 | Raft | CH. 6.913 MIB 2X2.5 length 31.367 Br No 549 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.8 | CW-Sec-2B2-MIB-550-1 | Raft | CH. 7.025 MIB 2X2.5 length 52.604 Br No 550 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.9 | CW-Sec-2B2-MIB-550A1 | Raft | CH. 7.125 MIB 5X3.53 length 52.602 Br No 550A | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.180 | CW-Sec-3-UP-763 | Pile Cap | P-173-UP | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.2.34 | UGE11180 | U-Girder | P108-P109 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.129 | PILE3430 | Piles | P-123 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.178 | PILE4080 | Piles | P-176-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.201 | PILE4240 | Piles | P-176-UP | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.35 | 3447 | Pier | P268 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.5 | 3586 | Pile Cap | P-6 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.36 | CW-Sec-4-2180 | Pier: Curing, De-Shuttering, De-Staging | P267 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.123 | CW-Sec-3-PR-5-147 | Pedestal & Seismic arrestors | P-117 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.126 | CW-Sec-3-494 | Pier | P-120 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.175 | CW-Sec-3-DN-712 | Pier | P-173-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.181 | CW-Sec-3-UP-760 | Pier | P-172-UP | 12
Not Started | BLP-DWP-R5-5.5.4.2.33.2 | CW-Sec-1B-PR-1-567 | Pier: Curing,De-shuttering,De-Staging | PR-31 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.172 | CW-Sec-3-2411 | Pier: Curing, De-Shuttering, De-Staging | P-171-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.182 | CW-Sec-3-2541 | Pier: Curing, De-Shuttering, De-Staging | P-171-UP | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.37 | 3471 | Portal Pier | P235 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.1.31 | CW-Sec-4-PR-5-263 | Pedestal & Seismic arrestors | P230 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.33 | UGE11510 | U-Girder | P109-P110 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12480 | P195-P196-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12490 | P195-P196-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12500 | P195-P196-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12510 | P196-P197-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12520 | P196-P197-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12530 | P196-P197-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12540 | P196-P197-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12550 | P196-P197-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.128 | CW-Sec-3-501 | Pile Cap | P-122 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.111 | PILE3630 | Piles | P-141 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.179 | CW-Sec-3-DN-719 | Pile Cap | P-175-DN | 10
Not Started | BLP-DWP-R5-5.5.5.2.3.1.10 | CW-Sec-2B2-MIB-551-1 | Raft | CH. 7.192 MIB 2X2.91 length 50.138 Br No 551 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.2 | 3572 | Pier Cap Erection | P-3 | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.32 | UGE11400 | U-Girder | P110-P111 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.124 | CW-Sec-3-487 | Pier Cap Erection | P-118 | 2
Not Started | BLP-DWP-R5-5.5.5.1.4.1 | CW-Sec-2A-EW-5 | Cutting / Filling-2A Ch. 3.950 to Ch. 4.950 | Cutting / Filling-2A Ch. (-) 0.050 to Ch. 5.700 | 40
Not Started | BLP-DWP-R5-5.5.4.2.33.32 | CW-Sec-1B-PR-1-537 | Portal Pier: Curing,De-shuttering,De-Staging | PR-29 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.2.31 | UGE12510 | U-Girder | P111-P112 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.142 | CW-Sec-3-557 | Pile Cap | P-136 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.130 | PILE3440 | Piles | P-124 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.177 | PILE4090 | Piles | P-177-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.200 | PILE4250 | Piles | P-177-UP | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.4.127 | CW-Sec-3-498 | Pier | P-121 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.124 | CW-Sec-3-PR-5-148 | Pedestal & Seismic arrestors | P-118 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.125 | CW-Sec-3-1841 | Pier: Curing, De-Shuttering, De-Staging | P-119 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.174 | CW-Sec-3-DN-716 | Pier | P-174-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.173 | CW-Sec-3-2421 | Pier: Curing, De-Shuttering, De-Staging | P-172-DN | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.36 | 3452 | Pier Cap Erection | P267 | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.30 | 1108 | Steel girder assembly & erection | P112-P113 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1179 | P127-P128 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1192 | P271-P272 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1193 | P131-P132 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1197 | P134-P135 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1207 | P140-P141 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.113 | CW-Sec-3-569 | Pile Cap | P-139 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.172 | CW-Sec-3-DN-705 | Pier Cap Erection | P-171-DN | 2
Not Started | BLP-DWP-R5-5.5.4.2.33.2 | CW-Sec-1B-P-29-84 | Pier Cap erection | PR-31 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.129 | CW-Sec-3-505 | Pile Cap | P-123 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.148 | PILE3640 | Piles | P-142 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.178 | CW-Sec-3-DN-723 | Pile Cap | P-176-DN | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.203 | CW-Sec-3-UP-767 | Pile Cap | P-174-UP | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.36 | CW-Sec-4-PR-5-330 | Pedestal & Seismic arrestors | P267 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.72 | UGE11820 | U-Girder | P113-P114 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.6.1.4 | 1197 | Steel girder assembly & erection | P184-P185 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.172 | CW-Sec-3-PR-5-201 | Pedestal & Seismic arrestors | P-171-DN | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.2 | CW-Sec-1B-PR-5-51 | Pedestal & Seismic arrestors | PR-31 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.4 | 3582 | Pile Cap | P-7 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.23 | CW-Sec-4-PR-5-254 | Pedestal & Seismic arrestors | P221 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.22 | CW-Sec-4-PR-5-255 | Pedestal & Seismic arrestors | P222 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.21 | CW-Sec-4-PR-5-256 | Pedestal & Seismic arrestors | P223 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.20 | CW-Sec-4-PR-5-257 | Pedestal & Seismic arrestors | P224 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.19 | CW-Sec-4-PR-5-258 | Pedestal & Seismic arrestors | P225 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.18 | CW-Sec-4-PR-5-259 | Pedestal & Seismic arrestors | P226 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.17 | CW-Sec-4-PR-5-260 | Pedestal & Seismic arrestors | P227 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.16 | CW-Sec-4-PR-5-261 | Pedestal & Seismic arrestors | P228 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.15 | CW-Sec-4-PR-5-262 | Pedestal & Seismic arrestors | P229 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.34 | CW-Sec-4-2190 | Portal Beam: Curing, De-Shuttering, De-Staging | P232 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.43.6 | 3579 | Pier | P-5 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.1 | CW-Sec-4-2200 | Pier: Curing, De-Shuttering, De-Staging | P-4 | 7
Not Started | BLP-DWP-R5-5.5.6.9.11.2.71 | UGE11730 | U-Girder | P114-P115 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.131 | PILE3450 | Piles | P-125 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.176 | PILE4100 | Piles | P-178-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.199 | PILE4260 | Piles | P-178-UP | 6
Not Started | BLP-DWP-R5-5.5.4.2.33.32 | CW-Sec-1B-P-29-4 | Portal Beam Cast In Situ | PR-29 | 36
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12560 | P196-P197-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12570 | P196-P197-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12580 | P196-P197-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12590 | P197-P198-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12600 | P197-P198-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12610 | P197-P198-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12620 | P197-P198-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12630 | P197-P198-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.15 | UGE10760 | U-Girder | P255-P256 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.128 | CW-Sec-3-502 | Pier | P-122 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.126 | CW-Sec-3-1851 | Pier: Curing, De-Shuttering, De-Staging | P-120 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.179 | CW-Sec-3-DN-720 | Pier | P-175-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.180 | CW-Sec-3-UP-764 | Pier | P-173-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.175 | CW-Sec-3-2431 | Pier: Curing, De-Shuttering, De-Staging | P-173-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.181 | CW-Sec-3-2551 | Pier: Curing, De-Shuttering, De-Staging | P-172-UP | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.37 | UGE10900 | U-Girder | P256-P257 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.70 | UGE11840 | U-Girder | P115-P116 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.125 | CW-Sec-3-491 | Pier Cap Erection | P-119 | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.7 | CW-Sec-2B2-MIB-549-2 | Wall | CH. 6.913 MIB 2X2.5 length 31.367 Br No 549 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.8 | CW-Sec-2B2-MIB-550-2 | Wall | CH. 7.025 MIB 2X2.5 length 52.604 Br No 550 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.9 | CW-Sec-2B2-MIB-550A2 | Wall | CH. 7.125 MIB 5X3.53 length 52.602 Br No 550A | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.173 | CW-Sec-3-DN-709 | Pier Cap Erection | P-172-DN | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.29.36 | UGE10930 | U-Girder | P257-P258 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.130 | CW-Sec-3-509 | Pile Cap | P-124 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.147 | PILE3650 | Piles | P-143 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.177 | CW-Sec-3-DN-727 | Pile Cap | P-177-DN | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.34 | 3439 | Pier | P269 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.35 | CW-Sec-4-2210 | Pier: Curing, De-Shuttering, De-Staging | P268 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.35 | UGE10920 | U-Girder | P258-P259 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.69 | UGE11870 | U-Girder | P116-P117 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.125 | CW-Sec-3-PR-5-149 | Pedestal & Seismic arrestors | P-119 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.34 | UGE10950 | U-Girder | P259-P260 | 1
Not Started | BLP-DWP-R5-5.5.7.10.1.2.13 | IGE10270 | I-Girder | P194-P195 | 4
Not Started | BLP-DWP-R5-5.5.4.2.33.26 | CW-Sec-1B-PR-5-24 | Pedestal & Seismic arrestors | PR-23 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.27 | CW-Sec-1B-PR-5-25 | Pedestal & Seismic arrestors | PR-24 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.28 | CW-Sec-1B-PR-5-26 | Pedestal & Seismic arrestors | PR-25 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.37 | CW-Sec-4-2220 | Portal Pier: Curing, De-Shuttering, De-Staging | P235 | 7
Not Started | BLP-DWP-R5-5.5.5.1.4.2 | CW-Sec-2A-Blan-5 | Blanketing-2A Ch. 3.950 to Ch. 4.950 | Blanketing-2A Ch. (-) 0.050 to Ch. 5.700 | 45
Not Started | BLP-DWP-R5-5.5.5.2.3.2.1 | CW-Sec-2B2-RUB-143-4 | Approaches & misc. work | CH. 7.547 RUB (1no x 30m) Re-construction length 48.96 LC-143 | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.2.5 | CW-Sec-2B2-RUB-142-1 | Raft | CH. 6.944 RUB (1no x 30m) LC-142 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.6 | CW-Sec-2B2-RUB-140-1 | Raft | CH. 6.313 RUB (1no x 30m) Re-construction length 41.31 LC-140 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.7 | CW-Sec-2B2-RUB-144A1 | Raft | CH. 8.775 RUB (1no x 30m) Re-construction length 62.73 LC-144A | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.8 | CW-Sec-2B2-RUB-NAG-1 | Raft | CH. 7.075 RUB (1no x 30m) Re-construction length 40 Nagawara | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.1.5 | CW-Sec-2B2-MIB-563-4 | Return wall | CH. 10.244 MIB 2X2.5 length 31.914 Br No 563 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.6 | CW-Sec-2B2-MIB-548-4 | Return wall | CH. 6.49 MIB 2X2.5 length 34.71 Br No 548 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1182 | P265-P266 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1186 | P269-P270 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1204 | P138-P139 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.112 | CW-Sec-3-573 | Pile Cap | P-140 | 10
Not Started | BLP-DWP-R5-5.5.5.2.3.1.10 | CW-Sec-2B2-MIB-551-2 | Wall | CH. 7.192 MIB 2X2.91 length 50.138 Br No 551 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.187 | PILE4110 | Piles | P-179-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.198 | PILE4270 | Piles | P-179-UP | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.43.1 | 3556 | Pier Cap Erection | P-4 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.129 | CW-Sec-3-506 | Pier | P-123 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.127 | CW-Sec-3-1861 | Pier: Curing, De-Shuttering, De-Staging | P-121 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.178 | CW-Sec-3-DN-724 | Pier | P-176-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.202 | CW-Sec-3-UP-771 | Pile Cap | P-175-UP | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.174 | CW-Sec-3-2441 | Pier: Curing, De-Shuttering, De-Staging | P-174-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.126 | CW-Sec-3-495 | Pier Cap Erection | P-120 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.175 | CW-Sec-3-DN-713 | Pier Cap Erection | P-173-DN | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.43.3 | 3574 | Pile Cap | P-8 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.131 | CW-Sec-3-513 | Pile Cap | P-125 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.146 | PILE3660 | Piles | P-144 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.176 | CW-Sec-3-DN-731 | Pile Cap | P-178-DN | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.32 | CW-Sec-4-PR-5-264 | Pedestal & Seismic arrestors | P231 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.2.2 | CW-Sec-2B2-RUB-141-4 | Approaches & misc. work | CH. 6.675 RUB (1no x 30m) Re-construction length 41.31 LC-141 | 30
Not Started | BLP-DWP-R5-5.5.6.9.11.2.68 | UGE11860 | U-Girder | P117-P118 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.126 | CW-Sec-3-PR-5-150 | Pedestal & Seismic arrestors | P-120 | 15
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12640 | P197-P198-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12650 | P197-P198-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12660 | P197-P198-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12670 | P198-P199-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12680 | P198-P199-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12690 | P198-P199-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12700 | P198-P199-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12710 | P198-P199-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.35 | 3448 | Pier Cap Erection | P268 | 2
Not Started | BLP-DWP-R5-5.5.7.10.7 | CW-Sec-4-DS20 | Deck Slab | Deck slab | 93
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.186 | PILE4120 | Piles | P-180-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.197 | PILE4280 | Piles | P-180-UP | 6
Not Started | BLP-DWP-R5-5.5.7.10.4.31.35 | CW-Sec-4-PR-5-331 | Pedestal & Seismic arrestors | P268 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.132 | CW-Sec-3-518 | Pier | P-126 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.130 | CW-Sec-3-510 | Pier | P-124 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.128 | CW-Sec-3-1871 | Pier: Curing, De-Shuttering, De-Staging | P-122 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.177 | CW-Sec-3-DN-728 | Pier | P-177-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.203 | CW-Sec-3-UP-768 | Pier | P-174-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.173 | CW-Sec-3-PR-5-202 | Pedestal & Seismic arrestors | P-172-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.179 | CW-Sec-3-2451 | Pier: Curing, De-Shuttering, De-Staging | P-175-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.180 | CW-Sec-3-2561 | Pier: Curing, De-Shuttering, De-Staging | P-173-UP | 7
Not Started | BLP-DWP-R5-5.5.5.2.3.5.1 | CW-Sec-2B2-EW-4 | Cutting / Filling-2B Ch. 8.700 to Ch. 9.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P2 | 120
Not Started | BLP-DWP-R5-5.5.6.9.10.4.127 | CW-Sec-3-499 | Pier Cap Erection | P-121 | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.2.3 | CW-Sec-2B2-RUB-144-4 | Approaches & misc. work | CH. 8.175 RUB (1no x 30m) Re-construction length 41.31 LC-144 | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.174 | CW-Sec-3-DN-717 | Pier Cap Erection | P-174-DN | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.43.5 | 3587 | Pier | P-6 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.6 | CW-Sec-4-2230 | Pier: Curing, De-Shuttering, De-Staging | P-5 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.2.29 | IGE10280 | I-Girder | P195-P196 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.4.145 | PILE3670 | Piles | P-145 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.187 | CW-Sec-3-DN-735 | Pile Cap | P-179-DN | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1187 | P129-P130 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1200 | P222-P223 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1201 | P136-P137 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1205 | P139-P140 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1215 | P144-P145 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.111 | CW-Sec-3-577 | Pile Cap | P-141 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.127 | CW-Sec-3-PR-5-151 | Pedestal & Seismic arrestors | P-121 | 15
Not Started | BLP-DWP-R5-5.5.4.2.33.31 | CW-Sec-1B-PR-1-527 | Portal Beam: Curing,De-shuttering,De-Staging | PR-28 | 31
Not Started | BLP-DWP-R5-5.5.5.2.3.1.7 | CW-Sec-2B2-MIB-549-3 | Slab | CH. 6.913 MIB 2X2.5 length 31.367 Br No 549 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.8 | CW-Sec-2B2-MIB-550-3 | Slab | CH. 7.025 MIB 2X2.5 length 52.604 Br No 550 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.9 | CW-Sec-2B2-MIB-550A3 | Slab | CH. 7.125 MIB 5X3.53 length 52.602 Br No 550A | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.201 | CW-Sec-3-UP-775 | Pile Cap | P-176-UP | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.185 | PILE4130 | Piles | P-181-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.196 | PILE4290 | Piles | P-181-UP | 6
Not Started | BLP-DWP-R5-5.5.5.2.3.2.4 | CW-Sec-2B2-RUB-KNG-4 | Approaches & misc. work | CH. 8.675 RUB 1no. X 6X5.5 length 40 Kanaka nagar | 30
Not Started | BLP-DWP-R5-5.5.7.10.4.1.38 | 3464 | Pier Cap Erection | P234 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.31.33 | 3423 | Pier | P270 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.14 | 3594 | Pile Cap | P-9 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.34 | CW-Sec-4-2250 | Pier: Curing, De-Shuttering, De-Staging | P269 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.33 | CW-Sec-4-2240 | Portal Beam: Curing, De-Shuttering, De-Staging | P233 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.4.133 | CW-Sec-3-522 | Pier | P-127 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.131 | CW-Sec-3-514 | Pier | P-125 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.67 | UGE11830 | U-Girder | P118-P119 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.129 | CW-Sec-3-1881 | Pier: Curing, De-Shuttering, De-Staging | P-123 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.176 | CW-Sec-3-DN-732 | Pier | P-178-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.178 | CW-Sec-3-2461 | Pier: Curing, De-Shuttering, De-Staging | P-176-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.128 | CW-Sec-3-503 | Pier Cap Erection | P-122 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.179 | CW-Sec-3-DN-721 | Pier Cap Erection | P-175-DN | 2
Not Started | BLP-DWP-R5-5.5.4.2.4.21 | IGE10180 | I-Girder | PR22-PR23 | 4
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12720 | P198-P199-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12730 | P198-P199-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12740 | P198-P199-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12750 | P199-P200-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12760 | P199-P200-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12770 | P199-P200-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12780 | P199-P200-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12790 | P199-P200-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.1.37 | 3472 | Portal beam cast in situ | P235 | 36
Not Started | BLP-DWP-R5-5.5.7.10.1.29.33 | UGE10970 | U-Girder | P261-P262 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.5.144 | PILE3680 | Piles | P-146 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.186 | CW-Sec-3-DN-739 | Pile Cap | P-180-DN | 10
Not Started | BLP-DWP-R5-5.5.5.2.3.1.10 | CW-Sec-2B2-MIB-551-3 | Slab | CH. 7.192 MIB 2X2.91 length 50.138 Br No 551 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.43.6 | 3580 | Pier Cap Erection | P-5 | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.29.32 | UGE10960 | U-Girder | P262-P263 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.128 | CW-Sec-3-PR-5-152 | Pedestal & Seismic arrestors | P-122 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.31 | UGE10910 | U-Girder | P263-P264 | 1
Not Started | BLP-DWP-R5-5.5.7.10.1.29.30 | UGE10940 | U-Girder | P264-P265 | 1
Not Started | BLP-DWP-R5-5.5.4.2.4.20 | IGE10200 | I-Girder | PR23-PR24 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.184 | PILE4140 | Piles | P-182-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.195 | PILE4300 | Piles | P-182-UP | 6
Not Started | BLP-DWP-R5-5.5.7.10.1.2.38 | IGE10290 | I-Girder | P195-P197 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.4.136 | CW-Sec-3-534 | Pier | P-130 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.134 | CW-Sec-3-526 | Pier | P-128 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.66 | UGE11910 | U-Girder | P119-P120 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.130 | CW-Sec-3-1891 | Pier: Curing, De-Shuttering, De-Staging | P-124 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.132 | CW-Sec-3-1911 | Pier: Curing, De-Shuttering, De-Staging | P-126 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.187 | CW-Sec-3-DN-736 | Pier | P-179-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.202 | CW-Sec-3-UP-772 | Pier | P-175-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.177 | CW-Sec-3-2471 | Pier: Curing, De-Shuttering, De-Staging | P-177-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.203 | CW-Sec-3-2571 | Pier: Curing, De-Shuttering, De-Staging | P-174-UP | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.31.34 | 3440 | Pier Cap Erection | P269 | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.11 | CW-Sec-2B2-MIB-554-1 | Raft | CH. 8.375 MIB 2X1.8 length 52.49 Br No 554 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.12 | CW-Sec-2B2-MIB-555-1 | Raft | CH. 8.6 MIB 2X2.5 length 46.642 Br No 555 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1190 | P130-P131 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1194 | P272-Abutment | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1208 | P225-P226 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1212 | P142-P143 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.129 | CW-Sec-3-507 | Pier Cap Erection | P-123 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.148 | CW-Sec-3-581 | Pile Cap | P-142 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.178 | CW-Sec-3-DN-725 | Pier Cap Erection | P-176-DN | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.143 | PILE3690 | Piles | P-147 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.185 | CW-Sec-3-DN-743 | Pile Cap | P-181-DN | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.200 | CW-Sec-3-UP-779 | Pile Cap | P-177-UP | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.34 | CW-Sec-4-PR-5-332 | Pedestal & Seismic arrestors | P269 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.129 | CW-Sec-3-PR-5-153 | Pedestal & Seismic arrestors | P-123 | 15
Not Started | BLP-DWP-R5-5.5.4.2.4.19 | IGE10210 | I-Girder | PR24-PR25 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.175 | CW-Sec-3-PR-5-203 | Pedestal & Seismic arrestors | P-173-DN | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.13 | 3602 | Pile Cap | P-10 | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.43.4 | 3583 | Pier | P-7 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.1.34 | CW-Sec-4-PR-5-265 | Pedestal & Seismic arrestors | P232 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.5 | CW-Sec-4-2260 | Pier: Curing, De-Shuttering, De-Staging | P-6 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.5.144 | CW-Sec-3-597 | Pile Cap | P-146 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.183 | PILE4150 | Piles | P-183-DN | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.194 | PILE4310 | Piles | P-183-UP | 6
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12800 | P199-P200-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12810 | P199-P200-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12820 | P199-P200-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12830 | P200-P201-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12840 | P200-P201-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12850 | P200-P201-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12860 | P200-P201-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12870 | P200-P201-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.5.2.3.2.5 | CW-Sec-2B2-RUB-142-2 | Wall | CH. 6.944 RUB (1no x 30m) LC-142 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.6 | CW-Sec-2B2-RUB-140-2 | Wall | CH. 6.313 RUB (1no x 30m) Re-construction length 41.31 LC-140 | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.7 | CW-Sec-2B2-RUB-144A2 | Wall | CH. 8.775 RUB (1no x 30m) Re-construction length 62.73 LC-144A | 25
Not Started | BLP-DWP-R5-5.5.5.2.3.2.8 | CW-Sec-2B2-RUB-NAG-2 | Wall | CH. 7.075 RUB (1no x 30m) Re-construction length 40 Nagawara | 25
Not Started | BLP-DWP-R5-5.5.6.9.10.4.137 | CW-Sec-3-538 | Pier | P-131 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.135 | CW-Sec-3-530 | Pier | P-129 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.65 | UGE11900 | U-Girder | P120-P121 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.131 | CW-Sec-3-1901 | Pier: Curing, De-Shuttering, De-Staging | P-125 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.133 | CW-Sec-3-1921 | Pier: Curing, De-Shuttering, De-Staging | P-127 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.186 | CW-Sec-3-DN-740 | Pier | P-180-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.176 | CW-Sec-3-2481 | Pier: Curing, De-Shuttering, De-Staging | P-178-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.130 | CW-Sec-3-511 | Pier Cap Erection | P-124 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.177 | CW-Sec-3-DN-729 | Pier Cap Erection | P-177-DN | 2
Not Started | BLP-DWP-R5-5.5.4.2.3 | CW-EW-Sec-1B | Embankment- 1B Ch.(-)0.185 to Ch.(-)0.080 | Ramp portion Ch.(-)0.080 to Ch.(-)0.050 | 15
Not Started | BLP-DWP-R5-5.5.4.2.4.18 | IGE10230 | I-Girder | PR25-PR26 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.150 | PILE3700 | Piles | P-148 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.184 | CW-Sec-3-DN-747 | Pile Cap | P-182-DN | 10
Not Started | BLP-DWP-R5-5.5.5.1.4.1 | CW-Sec-2A-EW-6 | Cutting / Filling-2A Ch. 4.950 to Ch. 5.700 | Cutting / Filling-2A Ch. (-) 0.050 to Ch. 5.700 | 45
Not Started | BLP-DWP-R5-5.5.7.10.4.31.32 | 3407 | Pier | P271 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.33 | CW-Sec-4-2270 | Pier: Curing, De-Shuttering, De-Staging | P270 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.130 | CW-Sec-3-PR-5-154 | Pedestal & Seismic arrestors | P-124 | 15
Not Started | BLP-DWP-R5-5.5.4.2.4.17 | IGE10220 | I-Girder | PR26-PR27 | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.39 | IGE10300 | I-Girder | P197-P198 | 4
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1195 | P132-P133 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1209 | P226-P227 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1213 | P228-P229 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1216 | P145-P146 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1223 | P151-P152 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.147 | CW-Sec-3-585 | Pile Cap | P-143 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.5.143 | CW-Sec-3-601 | Pile Cap | P-147 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | PILE3920 | Piles | PR-168 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | CW-Sec-3-688 | Precast portal beam casting at location | PR-168 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | CW-Sec-3-694 | Precast portal beam casting at location | PR-169 | 36
Not Started | BLP-DWP-R5-5.5.4.2.33.32 | CW-Sec-1B-PR-1-547 | Portal Beam: Curing,De-shuttering,De-Staging | PR-29 | 31
Not Started | BLP-DWP-R5-5.5.7.10.4.43.5 | 3588 | Pier Cap Erection | P-6 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.140 | CW-Sec-3-550 | Pier | P-134 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.138 | CW-Sec-3-542 | Pier | P-132 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.64 | UGE11930 | U-Girder | P121-P122 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.7 | CW-Sec-2B2-MIB-549-4 | Return wall | CH. 6.913 MIB 2X2.5 length 31.367 Br No 549 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.8 | CW-Sec-2B2-MIB-550-4 | Return wall | CH. 7.025 MIB 2X2.5 length 52.604 Br No 550 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.9 | CW-Sec-2B2-MIB-550A4 | Return wall | CH. 7.125 MIB 5X3.53 length 52.602 Br No 550A | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.134 | CW-Sec-3-1931 | Pier: Curing, De-Shuttering, De-Staging | P-128 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.136 | CW-Sec-3-1951 | Pier: Curing, De-Shuttering, De-Staging | P-130 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.185 | CW-Sec-3-DN-744 | Pier | P-181-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.201 | CW-Sec-3-UP-776 | Pier | P-176-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.199 | CW-Sec-3-UP-783 | Pile Cap | P-178-UP | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.187 | CW-Sec-3-2491 | Pier: Curing, De-Shuttering, De-Staging | P-179-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.202 | CW-Sec-3-2581 | Pier: Curing, De-Shuttering, De-Staging | P-175-UP | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.131 | CW-Sec-3-515 | Pier Cap Erection | P-125 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.176 | CW-Sec-3-DN-733 | Pier Cap Erection | P-178-DN | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.43.12 | 3598 | Pile Cap | P-11 | 0
Not Started | BLP-DWP-R5-5.5.6.9.10.5.149 | PILE3710 | Piles | P-149 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.183 | CW-Sec-3-DN-751 | Pile Cap | P-183-DN | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.132 | CW-Sec-3-519 | Pier Cap Erection | P-126 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.144 | CW-Sec-3-598 | Pier | P-146 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.131 | CW-Sec-3-PR-5-155 | Pedestal & Seismic arrestors | P-125 | 15
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12880 | P200-P201-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12890 | P200-P201-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12900 | P200-P201-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12910 | P201-P202-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12920 | P201-P202-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12930 | P201-P202-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12940 | P201-P202-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12950 | P201-P202-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.33 | 3424 | Pier Cap Erection | P270 | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.29.72 | UGE10990 | U-Girder | P265-P266 | 1
Not Started | BLP-DWP-R5-5.5.5.2.3.1.11 | CW-Sec-2B2-MIB-554-2 | Wall | CH. 8.375 MIB 2X1.8 length 52.49 Br No 554 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.12 | CW-Sec-2B2-MIB-555-2 | Wall | CH. 8.6 MIB 2X2.5 length 46.642 Br No 555 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.10 | CW-Sec-2B2-MIB-551-4 | Return wall | CH. 7.192 MIB 2X2.91 length 50.138 Br No 551 | 20
Not Started | BLP-DWP-R5-5.5.7.10.1.29.71 | UGE10980 | U-Girder | P266-P267 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.133 | CW-Sec-3-523 | Pier Cap Erection | P-127 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.150 | CW-Sec-3-605 | Pile Cap | P-148 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.132 | CW-Sec-3-PR-5-156 | Pedestal & Seismic arrestors | P-126 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.33 | CW-Sec-4-PR-5-333 | Pedestal & Seismic arrestors | P270 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.70 | UGE11010 | U-Girder | P267-P268 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.141 | CW-Sec-3-554 | Pier | P-135 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.139 | CW-Sec-3-546 | Pier | P-133 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.63 | UGE11950 | U-Girder | P122-P123 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.135 | CW-Sec-3-1941 | Pier: Curing, De-Shuttering, De-Staging | P-129 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.137 | CW-Sec-3-1961 | Pier: Curing, De-Shuttering, De-Staging | P-131 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.184 | CW-Sec-3-DN-748 | Pier | P-182-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.174 | CW-Sec-3-PR-5-204 | Pedestal & Seismic arrestors | P-174-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.186 | CW-Sec-3-2501 | Pier: Curing, De-Shuttering, De-Staging | P-180-DN | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.29.69 | UGE11030 | U-Girder | P268-P269 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.134 | CW-Sec-3-527 | Pier Cap Erection | P-128 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.133 | CW-Sec-3-PR-5-157 | Pedestal & Seismic arrestors | P-127 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.187 | CW-Sec-3-DN-737 | Pier Cap Erection | P-179-DN | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.43.3 | 3575 | Pier | P-8 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.4 | CW-Sec-4-2280 | Pier: Curing, De-Shuttering, De-Staging | P-7 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.2.40 | IGE10310 | I-Girder | P198-P199 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.5.154 | PILE3730 | Piles | P-150 | 6
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1198 | P221-P222 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1202 | P223-P224 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1217 | P146-P147 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1220 | PR167-PR168 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1221 | P149-P150 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.146 | CW-Sec-3-589 | Pile Cap | P-144 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.134 | CW-Sec-3-PR-5-158 | Pedestal & Seismic arrestors | P-128 | 15
Not Started | BLP-DWP-R5-5.5.4.2.3 | CW-Blan-Sec-1B | Blanketing- 1B Ch.(-)0.185 to Ch.(-)0.080 | Ramp portion Ch.(-)0.080 to Ch.(-)0.050 | 5
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.198 | CW-Sec-3-UP-787 | Pile Cap | P-179-UP | 10
Not Started | BLP-DWP-R5-5.5.4.1.2 | CW-EW-Sec-1A | Cutting / Filling-1A Ch. (-) 0.964 to Ch. (-) 0. 675 | Formation | 30
Not Started | BLP-DWP-R5-5.5.4.2.33.31 | CW-Sec-1B-PR-5-29 | Pedestal & Seismic arrestors | PR-28 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.149 | CW-Sec-3-609 | Pile Cap | P-149 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | PILE3940 | Piles | PR-169 | 12
Not Started | BLP-DWP-R5-5.5.7.10.4.31.31 | 3419 | Pier | P272 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.31.32 | CW-Sec-4-2290 | Pier: Curing, De-Shuttering, De-Staging | P271 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.142 | CW-Sec-3-558 | Pier | P-136 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.114 | CW-Sec-3-566 | Pier | P-138 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.62 | UGE11940 | U-Girder | P123-P124 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.138 | CW-Sec-3-1971 | Pier: Curing, De-Shuttering, De-Staging | P-132 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.140 | CW-Sec-3-1991 | Pier: Curing, De-Shuttering, De-Staging | P-134 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.183 | CW-Sec-3-DN-752 | Pier | P-183-DN | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.200 | CW-Sec-3-UP-780 | Pier | P-177-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.185 | CW-Sec-3-2511 | Pier: Curing, De-Shuttering, De-Staging | P-181-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.201 | CW-Sec-3-2591 | Pier: Curing, De-Shuttering, De-Staging | P-176-UP | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.1.33 | CW-Sec-4-PR-5-266 | Pedestal & Seismic arrestors | P233 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.135 | CW-Sec-3-531 | Pier Cap Erection | P-129 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.186 | CW-Sec-3-DN-741 | Pier Cap Erection | P-180-DN | 2
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12960 | P201-P202-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12970 | P201-P202-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12980 | P201-P202-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC12990 | P202-P203-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13000 | P202-P203-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13010 | P202-P203-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13020 | P202-P203-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13030 | P202-P203-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.5.153 | PILE3740 | Piles | P-151 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | CW-Sec-3-685 | Pile Cap | PR-168 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.43.4 | 3584 | Pier Cap Erection | P-7 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.136 | CW-Sec-3-535 | Pier Cap Erection | P-130 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.143 | CW-Sec-3-602 | Pier | P-147 | 12
Not Started | BLP-DWP-R5-5.5.5.2.3.5.1 | CW-Sec-2B2-EW-5 | Cutting / Filling-2B Ch. 9.700 to Ch. 10.700 | Cutting / Filling-2B Ch. 5.700 to Ch. 10.700-P2 | 120
Not Started | BLP-DWP-R5-5.5.6.9.10.4.135 | CW-Sec-3-PR-5-159 | Pedestal & Seismic arrestors | P-129 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.144 | CW-Sec-3-2111 | Pier: Curing, De-Shuttering, De-Staging | P-146 | 7
Not Started | BLP-DWP-R5-5.5.5.1.4.2 | CW-Sec-2A-Blan-6 | Blanketing-2A Ch. 4.950 to Ch. 5.700 | Blanketing-2A Ch. (-) 0.050 to Ch. 5.700 | 35
Not Started | BLP-DWP-R5-5.5.6.9.10.4.137 | CW-Sec-3-539 | Pier Cap Erection | P-131 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.154 | CW-Sec-3-613 | Pile Cap | P-150 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.136 | CW-Sec-3-PR-5-160 | Pedestal & Seismic arrestors | P-130 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.41 | IGE10320 | I-Girder | P199-P200 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.4.115 | CW-Sec-3-562 | Pier | P-137 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.113 | CW-Sec-3-570 | Pier | P-139 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.61 | UGE11920 | U-Girder | P124-P125 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.139 | CW-Sec-3-1981 | Pier: Curing, De-Shuttering, De-Staging | P-133 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.141 | CW-Sec-3-2001 | Pier: Curing, De-Shuttering, De-Staging | P-135 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.184 | CW-Sec-3-2521 | Pier: Curing, De-Shuttering, De-Staging | P-182-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | CW-Sec-3-686 | Portal Pier | PR-168 | 16
Not Started | BLP-DWP-R5-5.5.7.10.4.31.32 | 3408 | Pier Cap Erection | P271 | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.2.5 | CW-Sec-2B2-RUB-142-3 | Slab | CH. 6.944 RUB (1no x 30m) LC-142 | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.2.6 | CW-Sec-2B2-RUB-140-3 | Slab | CH. 6.313 RUB (1no x 30m) Re-construction length 41.31 LC-140 | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.2.7 | CW-Sec-2B2-RUB-144A3 | Slab | CH. 8.775 RUB (1no x 30m) Re-construction length 62.73 LC-144A | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.2.8 | CW-Sec-2B2-RUB-NAG-3 | Slab | CH. 7.075 RUB (1no x 30m) Re-construction length 40 Nagawara | 30
Not Started | BLP-DWP-R5-5.5.5.2.3.3 | CW-Sec-2B2-MJB-560-4 | Super Structure Erection | CH. 9.992 MJB 2X30.5 length Br No 560 | 50
Not Started | BLP-DWP-R5-5.5.5.2.3.1.11 | CW-Sec-2B2-MIB-554-3 | Slab | CH. 8.375 MIB 2X1.8 length 52.49 Br No 554 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.12 | CW-Sec-2B2-MIB-555-3 | Slab | CH. 8.6 MIB 2X2.5 length 46.642 Br No 555 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1203 | P137-P138 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1206 | P224-P225 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1210 | P227-P228 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1224 | P152-P153 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1231 | P155-P156 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.138 | CW-Sec-3-543 | Pier Cap Erection | P-132 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.145 | CW-Sec-3-593 | Pile Cap | P-145 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.137 | CW-Sec-3-PR-5-161 | Pedestal & Seismic arrestors | P-131 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.185 | CW-Sec-3-DN-745 | Pier Cap Erection | P-181-DN | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.37 | CW-Sec-4-2300 | Portal Beam: Curing, De-Shuttering, De-Staging | P235 | 31
Not Started | BLP-DWP-R5-5.5.6.9.11.2.60 | UGE11880 | U-Girder | P125-P126 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.13 | CW-Sec-2B2-MIB-556-1 | Raft | CH. 8.75 MIB 2X2.5 length 49.474 Br No 556 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.14 | CW-Sec-2B2-MIB-557-1 | Raft | CH. 9.2 MIB 2X2.5 length 30.593 Br No 557 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.15 | CW-Sec-2B2-MIB-559-1 | Raft | CH. 9.9 MIB 2X1.80 length 38.518 Br No 559 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.152 | PILE3750 | Piles | P-152 | 6
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.197 | CW-Sec-3-UP-791 | Pile Cap | P-180-UP | 10
Not Started | BLP-DWP-R5-5.5.7.10.1.29.68 | UGE11020 | U-Girder | P269-P270 | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.31.32 | CW-Sec-4-PR-5-334 | Pedestal & Seismic arrestors | P271 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.138 | CW-Sec-3-PR-5-162 | Pedestal & Seismic arrestors | P-132 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.179 | CW-Sec-3-PR-5-205 | Pedestal & Seismic arrestors | P-175-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.59 | UGE11990 | U-Girder | P126-P127 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.43.14 | 3595 | Pier | P-9 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.3 | CW-Sec-4-2310 | Pier: Curing, De-Shuttering, De-Staging | P-8 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.5.153 | CW-Sec-3-617 | Pile Cap | P-151 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | PILE3950 | Piles | PR-170 | 12
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13040 | P202-P203-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13050 | P202-P203-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13060 | P202-P203-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13070 | P203-P204-1 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13080 | P203-P204-2 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13090 | P203-P204-3 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13100 | P203-P204-4 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13110 | P203-P204-5 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.112 | CW-Sec-3-574 | Pier | P-140 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.148 | CW-Sec-3-582 | Pier | P-142 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.58 | UGE11980 | U-Girder | P127-P128 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.142 | CW-Sec-3-2011 | Pier: Curing, De-Shuttering, De-Staging | P-136 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.114 | CW-Sec-3-2031 | Pier: Curing, De-Shuttering, De-Staging | P-138 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.199 | CW-Sec-3-UP-784 | Pier | P-178-UP | 12
Not Started | BLP-DWP-R5-5.5.5.2.3.1.16 | CW-Sec-2B2-MIB-561-1 | Raft | CH. 10.059 MIB 2X1.8 length 38.893 Br No 561 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.183 | CW-Sec-3-2531 | Pier: Curing, De-Shuttering, De-Staging | P-183-DN | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.200 | CW-Sec-3-2601 | Pier: Curing, De-Shuttering, De-Staging | P-177-UP | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.139 | CW-Sec-3-547 | Pier Cap Erection | P-133 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.184 | CW-Sec-3-DN-749 | Pier Cap Erection | P-182-DN | 2
Not Started | BLP-DWP-R5-5.5.4.2.4.28 | IGE10240 | I-Girder | PR27-PR28 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | CW-Sec-3-691 | Pile Cap | PR-169 | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.31.31 | CW-Sec-4-2320 | Pier: Curing, De-Shuttering, De-Staging | P272 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.140 | CW-Sec-3-551 | Pier Cap Erection | P-134 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.150 | CW-Sec-3-606 | Pier | P-148 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.139 | CW-Sec-3-PR-5-163 | Pedestal & Seismic arrestors | P-133 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.143 | CW-Sec-3-2121 | Pier: Curing, De-Shuttering, De-Staging | P-147 | 7
Not Started | BLP-DWP-R5-5.5.4.2.4.27 | IGE10250 | I-Girder | PR30-PR31 | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.1.38 | CW-Sec-4-PR-5-267 | Pedestal & Seismic arrestors | P234 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.42 | IGE10330 | I-Girder | P200-P201 | 4
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1214 | P143-P144 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1218 | P147-P148 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1225 | P153-P154 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1228 | P230-P231 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1229 | P141-P142 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.141 | CW-Sec-3-555 | Pier Cap Erection | P-135 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.152 | CW-Sec-3-621 | Pile Cap | P-152 | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.140 | CW-Sec-3-PR-5-164 | Pedestal & Seismic arrestors | P-134 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.3 | 3576 | Pier Cap Erection | P-8 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.111 | CW-Sec-3-578 | Pier | P-141 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.147 | CW-Sec-3-586 | Pier | P-143 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.57 | UGE12020 | U-Girder | P128-P129 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.115 | CW-Sec-3-2021 | Pier: Curing, De-Shuttering, De-Staging | P-137 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.113 | CW-Sec-3-2041 | Pier: Curing, De-Shuttering, De-Staging | P-139 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.196 | CW-Sec-3-UP-795 | Pile Cap | P-181-UP | 10
Not Started | BLP-DWP-R5-5.5.4.2.33.32 | CW-Sec-1B-PR-5-30 | Pedestal & Seismic arrestors | PR-29 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | CW-Sec-3-692 | Portal Pier | PR-169 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.4.142 | CW-Sec-3-559 | Pier Cap Erection | P-136 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.141 | CW-Sec-3-PR-5-165 | Pedestal & Seismic arrestors | P-135 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.183 | CW-Sec-3-DN-753 | Pier Cap Erection | P-183-DN | 2
Not Started | BLP-DWP-R5-5.5.4.1.2 | CW-Blan-Sec-1A | Blanketing-1A Ch. (-) 0.964 to Ch. (-) 0. 675 | Formation | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.56 | UGE12040 | U-Girder | P129-P130 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.153 | CW-Sec-3-618 | Pier | P-151 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.142 | CW-Sec-3-PR-5-166 | Pedestal & Seismic arrestors | P-136 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.182 | CW-Sec-3-UP-757 | Pier Cap Erection | P-171-UP | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.5.2 | CW-Sec-2B2-Blan-1 | Blanketing-2B Ch. 5.700 to Ch. 6.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P2 | 30
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13120 | P203-P204-6 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13130 | P203-P204-7 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.3 | IGC13140 | P203-P204-8 | I-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.7.10.4.31.31 | 3420 | Pier Cap Erection | P272 | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.55 | UGE12030 | U-Girder | P130-P131 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | CW-Sec-3-2331 | Portal Pier: Curing, De-Shuttering, De-Staging | PR-168 | 7
Not Started | BLP-DWP-R5-5.5.5.2.3.1.13 | CW-Sec-2B2-MIB-556-2 | Wall | CH. 8.75 MIB 2X2.5 length 49.474 Br No 556 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.14 | CW-Sec-2B2-MIB-557-2 | Wall | CH. 9.2 MIB 2X2.5 length 30.593 Br No 557 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.15 | CW-Sec-2B2-MIB-559-2 | Wall | CH. 9.9 MIB 2X1.80 length 38.518 Br No 559 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.181 | CW-Sec-3-UP-761 | Pier Cap Erection | P-172-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.182 | CW-Sec-3-PR-5-214 | Pedestal & Seismic arrestors | P-171-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | CW-Sec-3-700 | Precast portal beam casting at location | PR-170 | 36
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | CW-Sec-3-3861 | Portal Beam: Curing, De-Shuttering, De-Staging | PR-168 | 31
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | CW-Sec-3-3881 | Portal Beam: Curing, De-Shuttering, De-Staging | PR-169 | 31
Not Started | BLP-DWP-R5-5.5.7.10.1.29.67 | UGE11000 | U-Girder | P270-P271 | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.31.31 | CW-Sec-4-PR-5-335 | Pedestal & Seismic arrestors | P272 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.146 | CW-Sec-3-590 | Pier | P-144 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.54 | UGE12000 | U-Girder | P131-P132 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.112 | CW-Sec-3-2051 | Pier: Curing, De-Shuttering, De-Staging | P-140 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.148 | CW-Sec-3-2071 | Pier: Curing, De-Shuttering, De-Staging | P-142 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.198 | CW-Sec-3-UP-788 | Pier | P-179-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.178 | CW-Sec-3-PR-5-206 | Pedestal & Seismic arrestors | P-176-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.199 | CW-Sec-3-2611 | Pier: Curing, De-Shuttering, De-Staging | P-178-UP | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.115 | CW-Sec-3-563 | Pier Cap Erection | P-137 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.180 | CW-Sec-3-UP-765 | Pier Cap Erection | P-173-UP | 2
Not Started | BLP-DWP-R5-5.5.7.2.6.2 | CW-Sec-4B-Blan-7 | Blanketing-4B Ch. 24.100 to Ch. 24.425 | Blanketing-4B Ch. 18.100 to Ch. 24.425 | 90
Not Started | BLP-DWP-R5-5.5.7.10.4.43.13 | 3603 | Pier | P-10 | 15
Not Started | BLP-DWP-R5-5.5.7.10.4.43.14 | CW-Sec-4-2330 | Pier: Curing, De-Shuttering, De-Staging | P-9 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.2.43 | IGE10340 | I-Girder | P201-P202 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | CW-Sec-3-697 | Pile Cap | PR-170 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.11 | CW-Sec-2B2-MIB-554-4 | Return wall | CH. 8.375 MIB 2X1.8 length 52.49 Br No 554 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.12 | CW-Sec-2B2-MIB-555-4 | Return wall | CH. 8.6 MIB 2X2.5 length 46.642 Br No 555 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1211 | P154-P155 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1232 | P156-P157 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1236 | P159-P160 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1239 | P161-P162 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.114 | CW-Sec-3-567 | Pier Cap Erection | P-138 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.149 | CW-Sec-3-610 | Pier | P-149 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.5.152 | CW-Sec-3-622 | Pier | P-152 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.115 | CW-Sec-3-PR-5-167 | Pedestal & Seismic arrestors | P-137 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.150 | CW-Sec-3-2131 | Pier: Curing, De-Shuttering, De-Staging | P-148 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.203 | CW-Sec-3-UP-769 | Pier Cap Erection | P-174-UP | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.16 | CW-Sec-2B2-MIB-561-2 | Wall | CH. 10.059 MIB 2X1.8 length 38.893 Br No 561 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.180 | CW-Sec-3-PR-5-216 | Pedestal & Seismic arrestors | P-173-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.195 | CW-Sec-3-UP-799 | Pile Cap | P-182-UP | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.4.113 | CW-Sec-3-571 | Pier Cap Erection | P-139 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.114 | CW-Sec-3-PR-5-168 | Pedestal & Seismic arrestors | P-138 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.202 | CW-Sec-3-UP-773 | Pier Cap Erection | P-175-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.203 | CW-Sec-3-PR-5-217 | Pedestal & Seismic arrestors | P-174-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | CW-Sec-3-687 | Portal cap & pedestal | PR-168 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.145 | CW-Sec-3-594 | Pier | P-145 | 12
Not Started | BLP-DWP-R5-5.5.6.9.11.2.53 | UGE12080 | U-Girder | P132-P133 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.111 | CW-Sec-3-2061 | Pier: Curing, De-Shuttering, De-Staging | P-141 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.4.147 | CW-Sec-3-2081 | Pier: Curing, De-Shuttering, De-Staging | P-143 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | CW-Sec-3-698 | Portal Pier | PR-170 | 16
Not Started | BLP-DWP-R5-5.5.6.9.10.4.112 | CW-Sec-3-575 | Pier Cap Erection | P-140 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.113 | CW-Sec-3-PR-5-169 | Pedestal & Seismic arrestors | P-139 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.201 | CW-Sec-3-UP-777 | Pier Cap Erection | P-176-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.202 | CW-Sec-3-PR-5-218 | Pedestal & Seismic arrestors | P-175-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.52 | UGE12060 | U-Girder | P133-P134 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.4.43.14 | 3596 | Pier Cap Erection | P-9 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.112 | CW-Sec-3-PR-5-170 | Pedestal & Seismic arrestors | P-140 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.153 | CW-Sec-3-2161 | Pier: Curing, De-Shuttering, De-Staging | P-151 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.200 | CW-Sec-3-UP-781 | Pier Cap Erection | P-177-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.201 | CW-Sec-3-PR-5-219 | Pedestal & Seismic arrestors | P-176-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.51 | UGE12100 | U-Girder | P134-P135 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | CW-Sec-3-3871 | Portal Pier: Curing, De-Shuttering, De-Staging | PR-169 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.199 | CW-Sec-3-UP-785 | Pier Cap Erection | P-178-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.200 | CW-Sec-3-PR-5-220 | Pedestal & Seismic arrestors | P-177-UP | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.44 | IGE10350 | I-Girder | P202-P203 | 4
Not Started | BLP-DWP-R5-5.5.6.9.11.2.50 | UGE12120 | U-Girder | P135-P136 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.146 | CW-Sec-3-2091 | Pier: Curing, De-Shuttering, De-Staging | P-144 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.197 | CW-Sec-3-UP-792 | Pier | P-180-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.198 | CW-Sec-3-2621 | Pier: Curing, De-Shuttering, De-Staging | P-179-UP | 7
Not Started | BLP-DWP-R5-5.5.5.2.3.2.5 | CW-Sec-2B2-RUB-142-4 | Approaches & misc. work | CH. 6.944 RUB (1no x 30m) LC-142 | 30
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1222 | P150-P151 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1226 | PR168-PR169 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1233 | P157-P158 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1237 | P148-P149 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.4.111 | CW-Sec-3-579 | Pier Cap Erection | P-141 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.199 | CW-Sec-3-PR-5-221 | Pedestal & Seismic arrestors | P-178-UP | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.13 | CW-Sec-2B2-MIB-556-3 | Slab | CH. 8.75 MIB 2X2.5 length 49.474 Br No 556 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.14 | CW-Sec-2B2-MIB-557-3 | Slab | CH. 9.2 MIB 2X2.5 length 30.593 Br No 557 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.15 | CW-Sec-2B2-MIB-559-3 | Slab | CH. 9.9 MIB 2X1.80 length 38.518 Br No 559 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.194 | CW-Sec-3-UP-803 | Pile Cap | P-183-UP | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.181 | CW-Sec-3-PR-5-215 | Pedestal & Seismic arrestors | P-172-UP | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.66 | UGE11050 | U-Girder | P271-P272 | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.1.37 | CW-Sec-4-PR-5-268 | Pedestal & Seismic arrestors | P235 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.148 | CW-Sec-3-583 | Pier Cap Erection | P-142 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.154 | CW-Sec-3-614 | Pier | P-150 | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.4.111 | CW-Sec-3-PR-5-171 | Pedestal & Seismic arrestors | P-141 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.149 | CW-Sec-3-2141 | Pier: Curing, De-Shuttering, De-Staging | P-149 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.5.152 | CW-Sec-3-2171 | Pier: Curing, De-Shuttering, De-Staging | P-152 | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.177 | CW-Sec-3-PR-5-207 | Pedestal & Seismic arrestors | P-177-DN | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.29.65 | UGE11040 | U-Girder | P272-Abutment | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.43.12 | 3599 | Pier | P-11 | 0
Not Started | BLP-DWP-R5-5.5.7.10.1.2.4 | UGE10280 | U-Girder | P186-P187 | 1
Not Started | BLP-DWP-R5-5.5.7.10.4.43.13 | CW-Sec-4-2340 | Pier: Curing, De-Shuttering, De-Staging | P-10 | 7
Not Started | BLP-DWP-R5-5.5.7.10.4.43.12 | CW-Sec-4-2350 | Pier: Curing, De-Shuttering, De-Staging | P-11 | 7
Not Started | BLP-DWP-R5-5.5.5.2.3.2.6 | CW-Sec-2B2-RUB-140-4 | Approaches & misc. work | CH. 6.313 RUB (1no x 30m) Re-construction length 41.31 LC-140 | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.4.147 | CW-Sec-3-587 | Pier Cap Erection | P-143 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.148 | CW-Sec-3-PR-5-172 | Pedestal & Seismic arrestors | P-142 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | CW-Sec-3-693 | Portal cap & pedestal | PR-169 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.3 | UGE10270 | U-Girder | P187-P188 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.49 | UGE12110 | U-Girder | P136-P137 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.145 | CW-Sec-3-2101 | Pier: Curing, De-Shuttering, De-Staging | P-145 | 7
Not Started | BLP-DWP-R5-5.5.5.2.3.1.16 | CW-Sec-2B2-MIB-561-3 | Slab | CH. 10.059 MIB 2X1.8 length 38.893 Br No 561 | 20
Not Started | BLP-DWP-R5-5.5.7.10.1.2.8 | UGE10300 | U-Girder | P188-P189 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.4.146 | CW-Sec-3-591 | Pier Cap Erection | P-144 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.147 | CW-Sec-3-PR-5-173 | Pedestal & Seismic arrestors | P-143 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.198 | CW-Sec-3-UP-789 | Pier Cap Erection | P-179-UP | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.7 | UGE10320 | U-Girder | P189-P190 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.48 | UGE12050 | U-Girder | P137-P138 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.6 | UGE10310 | U-Girder | P190-P191 | 1
Not Started | BLP-DWP-R5-5.MS.6 | MS-EV5 | MS-5: Partial Access of Viaduct(min 3Km) to Track & S&T Team | Milestone - Elevated | 0
Not Started | BLP-DWP-R5-5.5.6.9.10.4.146 | CW-Sec-3-PR-5-174 | Pedestal & Seismic arrestors | P-144 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.2.7 | CW-Sec-2B2-RUB-144A4 | Approaches & misc. work | CH. 8.775 RUB (1no x 30m) Re-construction length 62.73 LC-144A | 30
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.198 | CW-Sec-3-PR-5-222 | Pedestal & Seismic arrestors | P-179-UP | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.5 | UGE10290 | U-Girder | P191-P192 | 1
Not Started | BLP-DWP-R5-5.5.7.10.1.2.45 | IGE10360 | I-Girder | P203-P204 | 4
Not Started | BLP-DWP-R5-5.5.6.9.11.2.47 | UGE12090 | U-Girder | P138-P139 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | CW-Sec-3-2351 | Portal Pier: Curing, De-Shuttering, De-Staging | PR-170 | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.2.14 | UGE10340 | U-Girder | P192-P193 | 1
Not Started | BLP-DWP-R5-5.5.5.2.3.1.17 | CW-Sec-2B2-MIB-562-1 | Raft | CH. 10.15 MIB 2X2.5 length 35.356 Br No 562 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.18 | CW-Sec-2B2-MIB-564-1 | Raft | CH. 10.564 MIB 2X2.5 length 27.018 Br No 564 | 15
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1219 | P160-P161 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1240 | P232-P233 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1244 | P163-P164 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1247 | P165-P166 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.7.10.4.43.13 | 3604 | Pier Cap Erection | P-10 | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.12 | UGE10360 | U-Girder | P204-P205 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.2.46 | UGE11970 | U-Girder | P139-P140 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.196 | CW-Sec-3-UP-796 | Pier | P-181-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.197 | CW-Sec-3-2631 | Pier: Curing, De-Shuttering, De-Staging | P-180-UP | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.2.11 | UGE10380 | Steel Composite Girder | P207-P208 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.4.145 | CW-Sec-3-595 | Pier Cap Erection | P-145 | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.2.8 | CW-Sec-2B2-RUB-NAG-4 | Approaches & misc. work | CH. 7.075 RUB (1no x 30m) Re-construction length 40 Nagawara | 30
Not Started | BLP-DWP-R5-5.5.7.10.4.43.12 | 3600 | Pier Cap Erection | P-11 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.144 | CW-Sec-3-599 | Pier Cap Erection | P-146 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.4.145 | CW-Sec-3-PR-5-175 | Pedestal & Seismic arrestors | P-145 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.154 | CW-Sec-3-2151 | Pier: Curing, De-Shuttering, De-Staging | P-150 | 7
Not Started | BLP-DWP-R5-5.5.5.2.3.5.2 | CW-Sec-2B2-Blan-2 | Blanketing-2B Ch. 6.700 to Ch. 7.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P2 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.5.143 | CW-Sec-3-603 | Pier Cap Erection | P-147 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.144 | CW-Sec-3-PR-5-176 | Pedestal & Seismic arrestors | P-146 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | CW-Sec-3-699 | Portal cap & pedestal | PR-170 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.45 | UGE12140 | U-Girder | P140-P141 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.176 | CW-Sec-3-PR-5-208 | Pedestal & Seismic arrestors | P-178-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | CW-Sec-3-689 | Portal beam erection | PR-168 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.5.150 | CW-Sec-3-607 | Pier Cap Erection | P-148 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.143 | CW-Sec-3-PR-5-177 | Pedestal & Seismic arrestors | P-147 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.197 | CW-Sec-3-UP-793 | Pier Cap Erection | P-180-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.2.44 | UGE12170 | U-Girder | P141-P142 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1230 | PR169-PR170 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1234 | P158-P159 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1241 | P162-P163 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1245 | P235-P236 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1248 | P171-P172 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.5.149 | CW-Sec-3-611 | Pier Cap Erection | P-149 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.150 | CW-Sec-3-PR-5-178 | Pedestal & Seismic arrestors | P-148 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.197 | CW-Sec-3-PR-5-223 | Pedestal & Seismic arrestors | P-180-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.2.43 | UGE12160 | U-Girder | P142-P143 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.13 | CW-Sec-2B2-MIB-556-4 | Return wall | CH. 8.75 MIB 2X2.5 length 49.474 Br No 556 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.14 | CW-Sec-2B2-MIB-557-4 | Return wall | CH. 9.2 MIB 2X2.5 length 30.593 Br No 557 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.15 | CW-Sec-2B2-MIB-559-4 | Return wall | CH. 9.9 MIB 2X1.80 length 38.518 Br No 559 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | CW-Sec-3-695 | Portal beam erection | PR-169 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.7.169 | CW-Sec-3-PR-5-198 | Pedestal & Seismic arrestors | PR-168 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.154 | CW-Sec-3-615 | Pier Cap Erection | P-150 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.149 | CW-Sec-3-PR-5-179 | Pedestal & Seismic arrestors | P-149 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | CW-Sec-3-3891 | Portal Beam: Curing, De-Shuttering, De-Staging | PR-170 | 31
Not Started | BLP-DWP-R5-5.5.6.9.11.2.42 | UGE12200 | U-Girder | P143-P144 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.195 | CW-Sec-3-UP-800 | Pier | P-182-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.196 | CW-Sec-3-2641 | Pier: Curing, De-Shuttering, De-Staging | P-181-UP | 7
Not Started | BLP-DWP-R5-5.5.6.9.10.5.153 | CW-Sec-3-619 | Pier Cap Erection | P-151 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.154 | CW-Sec-3-PR-5-180 | Pedestal & Seismic arrestors | P-150 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.17 | CW-Sec-2B2-MIB-562-2 | Wall | CH. 10.15 MIB 2X2.5 length 35.356 Br No 562 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.18 | CW-Sec-2B2-MIB-564-2 | Wall | CH. 10.564 MIB 2X2.5 length 27.018 Br No 564 | 15
Not Started | BLP-DWP-R5-5.5.5.2.3.1.16 | CW-Sec-2B2-MIB-561-4 | Return wall | CH. 10.059 MIB 2X1.8 length 38.893 Br No 561 | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.7.170 | CW-Sec-3-PR-5-199 | Pedestal & Seismic arrestors | PR-169 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.5.152 | CW-Sec-3-623 | Pier Cap Erection | P-152 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.153 | CW-Sec-3-PR-5-181 | Pedestal & Seismic arrestors | P-151 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.10 | UGE10370 | U-Girder | P208-P209 | 1
Not Started | BLP-DWP-R5-5.5.5.2.3.5.2 | CW-Sec-2B2-Blan-3 | Blanketing-2B Ch. 7.700 to Ch. 8.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P2 | 30
Not Started | BLP-DWP-R5-5.5.7.10.1.2.9 | UGE10350 | U-Girder | P209-P210 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.6.151 | CW-Sec-3-627 | Pier Cap Erection | P-153 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.5.152 | CW-Sec-3-PR-5-182 | Pedestal & Seismic arrestors | P-152 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.1 | UGE10330 | Open Web truss | P210-P211 | 5
Not Started | BLP-DWP-R5-5.5.6.9.11.2.41 | UGE12220 | U-Girder | P144-P145 by LG | 2
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1227 | P229-P230 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1252 | P174-P175 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1253 | P175-P176 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1255 | P177-P178 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.6.155 | CW-Sec-3-631 | Pier Cap Erection | P-154 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.151 | CW-Sec-3-PR-5-183 | Pedestal & Seismic arrestors | P-153 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.196 | CW-Sec-3-UP-797 | Pier Cap Erection | P-181-UP | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.3.2 | UGE12230 | U-Girder | P145-P146 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.157 | CW-Sec-3-635 | Pier Cap Erection | P-155 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.155 | CW-Sec-3-PR-5-184 | Pedestal & Seismic arrestors | P-154 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.187 | CW-Sec-3-PR-5-209 | Pedestal & Seismic arrestors | P-179-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.196 | CW-Sec-3-PR-5-224 | Pedestal & Seismic arrestors | P-181-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.3.4 | UGE12260 | U-Girder | P146-P147 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.28 | UGE10410 | U-Girder | P212-P213 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.6.156 | CW-Sec-3-639 | Pier Cap Erection | P-156 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.157 | CW-Sec-3-PR-5-185 | Pedestal & Seismic arrestors | P-155 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.27 | UGE10400 | U-Girder | P213-P214 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.3.3 | UGE12240 | U-Girder | P147-P148 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.194 | CW-Sec-3-UP-804 | Pier | P-183-UP | 12
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.195 | CW-Sec-3-2651 | Pier: Curing, De-Shuttering, De-Staging | P-182-UP | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.2.26 | UGE10430 | U-Girder | P214-P215 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.6.161 | CW-Sec-3-643 | Pier Cap Erection | P-157 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.156 | CW-Sec-3-PR-5-186 | Pedestal & Seismic arrestors | P-156 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.25 | UGE10450 | U-Girder | P215-P216 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.3.8 | UGE12280 | U-Girder | P148-P149 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.24 | UGE10440 | U-Girder | P216-P217 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.6.160 | CW-Sec-3-647 | Pier Cap Erection | P-158 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.161 | CW-Sec-3-PR-5-187 | Pedestal & Seismic arrestors | P-157 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.23 | UGE10420 | U-Girder | P217-P218 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.3.7 | UGE12310 | U-Girder | P149-P150 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.22 | UGE10480 | U-Girder | P218-P219 | 1
Not Started | BLP-DWP-R5-5.5.5.2.3.1.17 | CW-Sec-2B2-MIB-562-3 | Slab | CH. 10.15 MIB 2X2.5 length 35.356 Br No 562 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.18 | CW-Sec-2B2-MIB-564-3 | Slab | CH. 10.564 MIB 2X2.5 length 27.018 Br No 564 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1235 | P170-P171 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1238 | P231-P232 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1242 | P233-P234 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1249 | P166-P167 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1256 | P178-P179 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.6.9.10.6.159 | CW-Sec-3-651 | Pier Cap Erection | P-159 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.160 | CW-Sec-3-PR-5-188 | Pedestal & Seismic arrestors | P-158 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.21 | UGE10470 | U-Girder | P219-P220 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.3.6 | UGE12300 | U-Girder | P150-P151 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.20 | UGE10500 | U-Girder | P220-P221 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.6.158 | CW-Sec-3-655 | Pier Cap Erection | P-160 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.159 | CW-Sec-3-PR-5-189 | Pedestal & Seismic arrestors | P-159 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.195 | CW-Sec-3-UP-801 | Pier Cap Erection | P-182-UP | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.19 | UGE10520 | U-Girder | P221-P222 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.3.5 | UGE12270 | U-Girder | P151-P152 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.18 | UGE10510 | U-Girder | P222-P223 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.6.167 | CW-Sec-3-659 | Pier Cap Erection | P-161 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.158 | CW-Sec-3-PR-5-190 | Pedestal & Seismic arrestors | P-160 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.195 | CW-Sec-3-PR-5-225 | Pedestal & Seismic arrestors | P-182-UP | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.17 | UGE10460 | U-Girder | P223-P224 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.4.2 | UGE11620 | U-Girder | P152-P153 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.16 | UGE10490 | U-Girder | P224-P225 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.6.168 | CW-Sec-3-663 | Pier Cap Erection | P-162 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.167 | CW-Sec-3-PR-5-191 | Pedestal & Seismic arrestors | P-161 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.15 | UGE10390 | U-Girder | P225-P226 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.4.4 | UGE12190 | U-Girder | P153-P154 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.186 | CW-Sec-3-PR-5-210 | Pedestal & Seismic arrestors | P-180-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.194 | CW-Sec-3-2661 | Pier: Curing, De-Shuttering, De-Staging | P-183-UP | 7
Not Started | BLP-DWP-R5-5.5.7.10.1.2.37 | UGE10530 | U-Girder | P226-P227 | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.6.166 | CW-Sec-3-667 | Pier Cap Erection | P-163 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.168 | CW-Sec-3-PR-5-192 | Pedestal & Seismic arrestors | P-162 | 15
Not Started | BLP-DWP-R5-5.5.7.10.1.2.36 | UGE10560 | U-Girder | P227-P228 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.4.3 | UGE12150 | U-Girder | P154-P155 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.35 | UGE10550 | U-Girder | P228-P229 | 1
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1246 | P164-P165 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1250 | P172-P173 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1260 | P182-P183 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1261 | P234-P235 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1263 | P173-P174 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.10.6.165 | CW-Sec-3-671 | Pier Cap Erection | P-164 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.166 | CW-Sec-3-PR-5-193 | Pedestal & Seismic arrestors | P-163 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.4.8 | UGE12320 | U-Girder | P155-P156 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.164 | CW-Sec-3-675 | Pier Cap Erection | P-165 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.165 | CW-Sec-3-PR-5-194 | Pedestal & Seismic arrestors | P-164 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.4.7 | UGE12340 | U-Girder | P156-P157 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | CW-Sec-3-701 | Portal beam erection | PR-170 | 4
Not Started | BLP-DWP-R5-5.5.6.9.10.6.163 | CW-Sec-3-679 | Pier Cap Erection | P-166 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.164 | CW-Sec-3-PR-5-195 | Pedestal & Seismic arrestors | P-165 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.194 | CW-Sec-3-UP-805 | Pier Cap Erection | P-183-UP | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.34 | UGE10580 | U-Girder | P229-P230 | 1
Not Started | BLP-DWP-R5-5.5.7.10.1.2.33 | UGE10600 | U-Girder | P230-P231 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.4.6 | UGE12330 | U-Girder | P157-P158 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.162 | CW-Sec-3-683 | Pier Cap Erection | P-167 | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.6.163 | CW-Sec-3-PR-5-196 | Pedestal & Seismic arrestors | P-166 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.8.2.194 | CW-Sec-3-PR-5-226 | Pedestal & Seismic arrestors | P-183-UP | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.4.5 | UGE12210 | U-Girder | P158-P159 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.5.2 | CW-Sec-2B2-Blan-4 | Blanketing-2B Ch. 8.700 to Ch. 9.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P2 | 30
Not Started | BLP-DWP-R5-5.MS.7 | MS-AG6 | MS-6: Partial Access of section for (min. another 10 Km) Total=14Km | Milestone- At Grade | 0
Not Started | BLP-DWP-R5-5.5.6.9.10.7.171 | CW-Sec-3-PR-5-200 | Pedestal & Seismic arrestors | PR-170 | 15
Not Started | BLP-DWP-R5-5.5.6.9.10.6.162 | CW-Sec-3-PR-5-197 | Pedestal & Seismic arrestors | P-167 | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.4.14 | UGE12350 | U-Girder | P159-P160 by LG | 2
Not Started | BLP-DWP-R5-5.5.5.2.3.1.17 | CW-Sec-2B2-MIB-562-4 | Return wall | CH. 10.15 MIB 2X2.5 length 35.356 Br No 562 | 20
Not Started | BLP-DWP-R5-5.5.5.2.3.1.18 | CW-Sec-2B2-MIB-564-4 | Return wall | CH. 10.564 MIB 2X2.5 length 27.018 Br No 564 | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1243 | P171-P172 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1251 | P173-P174 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1257 | P179-P180 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1264 | P174-P175 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1268 | P178-P179 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1269 | P179-P180 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1271 | P181-P182 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.4.13 | UGE12380 | U-Girder | P160-P161 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.185 | CW-Sec-3-PR-5-211 | Pedestal & Seismic arrestors | P-181-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.4.12 | UGE12360 | U-Girder | P161-P162 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.32 | UGE10590 | U-Girder | P231-P232 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.4.11 | UGE12410 | U-Girder | P162-P163 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.31 | UGE10540 | U-Girder | P232-P233 | 1
Not Started | BLP-DWP-R5-5.5.7.10.1.2.30 | UGE10570 | U-Girder | P233-P234 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.4.10 | UGE12430 | U-Girder | P163-P164 by LG | 2
Not Started | BLP-DWP-R5-5.MS.6 | MS-EV6 | MS-6: Partial Access of Viaduct(bal 3Km) to Track & S&T Team | Milestone - Elevated | 0
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1254 | P176-P177 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1258 | P180-P181 | U-Girder Casting | 20
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1259 | P181-P182 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1262 | P172-P173 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1265 | P175-P176 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1272 | P182-P183 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.8 | CW-Fin | Finishing Works | Finishing | 60
Not Started | BLP-DWP-R5-5.5.6.9.11.5.2 | UGE12470 | U-Girder | PR167-PR168 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.5.4 | UGE12490 | U-Girder | PR168-PR169 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.5.3 | UGE12480 | U-Girder | PR169-PR170 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.184 | CW-Sec-3-PR-5-212 | Pedestal & Seismic arrestors | P-182-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.4 | UGE10020 | U-Girder | P170-P171 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.4.9 | UGE12420 | U-Girder | P164-P165 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.2 | UGE10000 | U-Girder | P171-P172 by LG | 1
Not Started | BLP-DWP-R5-5.5.7.10.1.2.72 | UGE10620 | U-Girder | P234-P235 | 1
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1266 | P176-P177 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1267 | P177-P178 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1270 | P180-P181 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1273 | P183-P184 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.3.2 | UGC1274 | P183-P184 | U-Girder Casting | 10
Not Started | BLP-DWP-R5-5.5.6.9.11.4.1 | UGE12390 | U-Girder | P165-P166 by LG | 2
Not Started | BLP-DWP-R5-5.5.7.10.1.2.71 | UGE10610 | U-Girder | P235-P236 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.4.15 | UGE12440 | U-Girder | P166-P167 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.3 | UGE10010 | U-Girder | P172-P173 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.10.8.1.183 | CW-Sec-3-PR-5-213 | Pedestal & Seismic arrestors | P-183-DN | 15
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.8 | UGE10040 | U-Girder | P173-P174 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.7 | UGE10060 | U-Girder | P174-P175 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.6 | UGE10050 | U-Girder | P175-P176 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.5 | UGE10030 | U-Girder | P176-P177 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.14 | UGE10070 | U-Girder | P177-P178 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.13 | UGE10090 | U-Girder | P178-P179 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.12 | UGE10080 | U-Girder | P179-P180 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.11 | UGE10110 | U-Girder | P180-P181 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.10 | UGE10130 | U-Girder | P181-P182 by LG | 1
Not Started | BLP-DWP-R5-5.5.5.2.3.5.2 | CW-Sec-2B2-Blan-5 | Blanketing-2B Ch. 5.700 to Ch. 6.700 | Blanketing-2B Ch. 5.700 to Ch. 10.700-P2 | 30
Not Started | BLP-DWP-R5-5.5.6.9.11.16.16.9 | UGE10120 | U-Girder | P182-P183 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.2 | UGE10100 | U-Girder | P171-P172 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.6.1.2 | UGE10250 | U-Girder | P183-P184 | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.3 | UGE10140 | U-Girder | P172-P173 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.6.2.2 | UGE10260 | U-Girder | P183-P184 | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.8 | UGE10160 | U-Girder | P173-P174 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.7 | UGE10180 | U-Girder | P174-P175 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.6 | UGE10170 | U-Girder | P175-P176 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.5 | UGE10150 | U-Girder | P176-P177 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.14 | UGE10190 | U-Girder | P177-P178 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.13 | UGE10210 | U-Girder | P178-P179 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.12 | UGE10200 | U-Girder | P179-P180 by LG | 2
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.11 | UGE10220 | U-Girder | P180-P181 by LG | 1
Not Started | BLP-DWP-R5-5.5.8 | CW-Test & HO | Testing and Handing over | Finishing | 30
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.10 | UGE10240 | U-Girder | P181-P182 by LG | 1
Not Started | BLP-DWP-R5-5.5.6.9.11.16.1.9 | UGE10230 | U-Girder | P182-P183 by LG | 1
Not Started | BLP-DWP-R5-5.MS.6 | MS-EV7 | MS-7: Completion of Entire Work as per the Contract | Milestone - Elevated | 0
Not Started | BLP-DWP-R5-5.MS.7 | MS-AG7 | MS-7: Completion of Entire Work | Milestone- At Grade | 0

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Hour ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd/MM/yyyy CurrencyFormat=US Dollar