## Activity List
Sr.No. | Description | Remaks
1 | Bulk Excavation
2 | Concrete Finishing
3 | Concrete Placement
4 | Floor Finishes
5 | Kerbs & Paving
6 | Painting
7 | Reinforcement Ratios
8 | Roof Insulation
9 | Screeding
10 | Trench Excavation
11 | Waterproofing
12 | Basement Excavation'
13 | Brickwork
14 | Ceiling Finishes'
15 | Concrete Mixing'
16 | Grit Blasting'
17 | Formwork
18 | Plastering
19 | Paintwork
20 | Rule of Thumb
21 | Wall Finishes
22 | Tower Cranes

## Bulk Excavation
Construction Wet Trades - Blockwork
Ref | Task / Description | Slow | Ave | Fast | Units
630 | Thermalite Blockwork, under 100mm thick | 1.8 | 2.5 | 3.2 | m2/hr
631 | Thermalite Blockwork, under 100-150mm thick | 1.4 | 1.9 | 2.5 | m2/hr
632 | Thermalite Blockwork, over 150mm thick | 1.2 | 1.6 | 2.1 | m2/hr
633 | Lightweight Concrete Blockwork, under 100mm thick | 1.5 | 2.2 | 2.9 | m2/hr
634 | Lightweight Concrete Blockwork, under 100-150mm thick | 1.4 | 1.9 | 2.1 | m2/hr
635 | Lightweight Concrete Blockwork, over 150mm thick | 1.2 | 1.6 | 2.0 | m2/hr
636 | Heavyweight Concrete Blockwork, under 100mm thick | 1.4 | 2.1 | 2.9 | m2/hr
637 | Heavyweight Concrete Blockwork, under 100-150mm thick | 1.2 | 1.6 | 2.1 | m2/hr
638 | Heavyweight Concrete Blockwork, over 150mm thick | 1.1 | 1.4 | 1.8 | m2/hr
639 | Face Finish, Raked Out | - | 71.4 | - | m2/hr
640 | Face Finish, Bag Rubbed | - | 29.4 | - | m2/hr
641 | Face Finish, Flush Pointing | - | 17.6 | - | m2/hr
Foundations and Excavation - Bulk Excavation
Ref | Task / Description | Slow | Ave | Fast | Units
270 | Excavation Bulking Factor, Sand/Soil | - | 15.0 | 20.0 | %
271 | Excavation Bulking Factor, Gravel | - | 33.0 | - | %
272 | Excavation Bulking Factor, Clay/Chalk | - | 40.0 | - | %
273 | Excavation Bulking Factor, Boulder Clay | - | 45.0 | - | %
274 | Excavation Bulking Factor, Rock | - | 60.0 | - | %
275 | Spoil Weight, Rock | - | 2.5 | - | Tonnes/m3
276 | Spoil Weight, Concrete | - | 2.4 | - | Tonnes/m3
277 | Spoil Weight, Landfill/CDG | - | 1.9 | - | Tonnes/m3
278 | Spoil Weight, Sand | - | 1.8 | - | Tonnes/m3
279 | Rail Mounted Grab, 2.0m3 bucket 2.4min lift cycle | 30.0 | 48.0 | 59.0 | m3/hr
280 | Crane Mounted Clamshell Grab, 2.0m3 bucket 2.9min lift cycle | 25.0 | 33.0 | 41.0 | m3/hr
281 | Crane Mounted Clamshell Grab, 2.5m3 bucket 2.9min lift cycle | 34.0 | 42.0 | 52.0 | m3/hr
282 | Hydraulic Excavator, 0.3m3 bucket, Sand/Soil | 6.9 | 8.7 | 10.2 | m3/hr
283 | Hydraulic Excavator, 0.4m3 bucket, Sand/Soil | 23.4 | 28.6 | 33.4 | m3/hr
284 | Hydraulic Excavator, 0.5m3 bucket, Sand/Soil | 45.5 | 50.0 | 58.0 | m3/hr
285 | Hydraulic Excavator, 0.3m3 bucket, Gravel Beds | 5.6 | 7.1 | 8.2 | m3/hr
286 | Hydraulic Excavator, 0.4m3 bucket, Gravel Beds | 20.5 | 25.0 | 29.0 | m3/hr
287 | Hydraulic Excavator, 0.5m3 bucket, Gravel Beds | 36.8 | 40.0 | 46.0 | m3/hr
288 | Hydraulic Excavator, 0.3m3 bucket, Clay/Chalk | 5.6 | 7.1 | 8.3 | m3/hr
289 | Hydraulic Excavator, 0.4m3 bucket, Clay/Chalk | 20.5 | 25.0 | 28.7 | m3/hr
290 | Hydraulic Excavator, 0.5m3 bucket, Clay/Chalk | 37.0 | 40.0 | 46.0 | m3/hr
291 | Hydraulic Excavator, 0.3m3 bucket, Hard Ground | 4.5 | 6.1 | 7.2 | m3/hr
292 | Hydraulic Excavator, 0.4m3 bucket, Hard Ground | 17.9 | 22.2 | 25.0 | m3/hr
293 | Hydraulic Excavator, 0.5m3 bucket, Hard Ground | 25.7 | 28.6 | 32.9 | m3/hr

## Concrete Finishing
Concrete Works - Concrete Finishing
Ref | Task / Description | Slow | Ave | Fast | Units
485 | Surface Finishing, Steel Float By Hand | 9.2 | 13.9 | 25.0 | m2/hr
486 | Surface Finishing, Wood Float By Hand | 11.7 | 17.2 | 29.4 | m2/hr
487 | Surface Finishing, Power Float | 13.9 | 20.8 | 37.0 | m2/hr
488 | Surface Finishing, Light Brush on Trowel | 55.8 | 90.1 | 170.0 | m2/hr
489 | Surface Finishing, Brush on Trowel Margin | 28.8 | 48.5 | 85.0 | m2/hr
490 | Surface Finishing, Sprayed By Pump, expose aggregate | 65.0 | 95.0 | 145.0 | m2/hr
491 | Surface Finishing, Wire Brush, expose aggregate | 15.0 | 25.0 | 30.0 | m2/hr
492 | Making Good Walls, prepare, shutter, pour | - | 5.5 | 8.6 | m2/hr
493 | Making Good Columns, prepare, shutter, pour | - | 2.8 | 6.9 | m2/hr
494 | Making Good Sides of Beams, prepare, shutter, pour | - | 2.8 | 7.0 | m2/hr
495 | Making Good Slab Soffits, prepare, shutter, pour | - | 4.2 | 5.5 | m2/hr
496 | Making Good Bolt Holes, prepare, shutter, pour | 14.8 | 16.8 | 25.8 | no/hr
497 | Making Good Rubdown Precast Concrete, prepare, shutter, pour | - | 18.0 | - | m2/hr
498 | Making Good Scabble 3 head brush hammer, prepare, shutter, pour | 30.7 | 59.5 | 73.8 | hrs/m2

## Concrete Placement
Concrete Works - Concrete Placement
Ref | Task / Description | Slow | Ave | Fast | Units
460 | Placing concrete, lorry based pump | 30.0 | 40.0 | 50.0 | m3/hr
461 | Hollorib Decking, concrete topping | 85.0 | 100.0 | 120.0 | m2/hr
462 | Hollorib Decking, concrete topping, incl PowerFloat | 40.0 | 50.0 | 70.0 | m2/hr
463 | Placing Concrete, By Wheelbarrow over 1-10m | 2.1 | 2.3 | 2.5 | m3/hr
464 | Placing Concrete, By Wheelbarrow over 10-20m | 1.5 | 1.8 | 2.1 | m3/hr
465 | Placing Concrete, By Wheelbarrow over 20-50m | 0.8 | 1.1 | 1.5 | m3/hr
466 | Placing Direct From Readymix Lorry, Mass Fill | 2.8 | 3.1 | 3.3 | m3/hr
467 | Placing Direct From Readymix Lorry, 50mm Blinding | - | 1.3 | 1.6 | m3/hr
468 | Placing Direct From Readymix Lorry, Ground Beams | 1.5 | - | 1.7 | m3/hr
469 | Placing Direct From Readymix Lorry, Pile Caps | 1.0 | 1.5 | 2.3 | m3/hr
470 | Placing Direct From Readymix Lorry, Duct Walls | - | 0.8 | 1.1 | m3/hr
471 | Placing Direct From Readymix Lorry, Stub Columns | - | 0.4 | 0.6 | m3/hr
472 | Placing Direct From Readymix Lorry, Ground Slab | 2.1 | 2.3 | 2.6 | m3/hr
473 | Placing Direct From Readymix Lorry,Drains Bed and Cover | - | 0.9 | 1.0 | m3/hr
474 | Placing From Tower Crane, Pile Caps | 1.2 | 1.4 | 1.6 | m3/hr
475 | Placing From Tower Crane, Mass Fill | 4.0 | 4.5 | 5.5 | m3/hr
476 | Placing From Tower Crane, Slabs under 150mm thick | 0.9 | 1.3 | 1.7 | m3/hr
477 | Placing From Tower Crane, Slabs over 150mm thick | 1.2 | 1.5 | 1.8 | m3/hr
478 | Placing From Tower Crane, Trough/Coffered Slabs | 0.9 | 1.1 | 1.2 | m3/hr
479 | Placing From Tower Crane, Stairs and Landings | 0.6 | 0.7 | 0.9 | m3/hr
480 | Placing From Tower Crane, Blinding | 0.8 | 1.0 | 1.1 | m3/hr
481 | Placing From Tower Crane, Beams under 150mm thick | 0.5 | 0.6 | 0.8 | m3/hr
482 | Placing From Tower Crane, Beams over 150mm thick | 0.6 | 0.8 | 1.0 | m3/hr
483 | Placing From Tower Crane, Walls | 0.6 | 1.1 | 1.5 | m3/hr
484 | Placing From Tower Crane, Columns | 0.4 | 0.5 | 0.6 | m3/hr

## Floor Finishes
Architectural Builders Work and Finishes - Floor Finishes
Ref | Task / Description | Slow | Ave | Fast | Units
691 | Granolithic Flooring | - | 3.1 | - | m2/hr
692 | Terrazzo Flooring, in-situ | - | 3.6 | - | m2/hr
693 | Terrazzo Flooring, pre-cast | - | 4.6 | 5.1 | m2/hr
694 | Mosaic Tiling, 0.045x0.045m | - | 1.5 | 2.2 | m2/hr
695 | Clay, quarry Tiles, small areas, much cutting | - | 0.8 | 1.1 | m2/hr
696 | Clay, quarry Tiles, large areas, little cutting | - | 2.2 | 2.8 | m2/hr
697 | Raised Floor System | - | 2.6 | - | m2/hr
698 | Linolium/Thermo-Plastic Flooring | - | 3.1 | 5.0 | m2/hr
699 | Thermo-Plastic Floor Tiles | - | 3.3 | 5.6 | m2/hr
700 | Wood Block Flooring, lay blocks | - | 1.5 | 2.1 | m2/hr
701 | Wood Block Flooring, sand and polish | - | 3.1 | - | m2/hr
702 | Carpeting, Underlay & Gripper | - | 5.6 | 6.1 | m2/hr
703 | Carpeting, Adhesive Fixing | - | 3.5 | 4.2 | m2/hr
704 | Carpeting, Fully Fitted | - | 2.0 | 2.8 | m2/hr
705 | Hardboard Sheeting Coverings, small areas | - | 3.7 | 4.1 | m2/hr
706 | Hardboard Sheeting Coverings, large areas | - | 6.6 | 7.2 | m2/hr
707 | Floor Sheeting Coverings, Lay Lino | - | 9.5 | 10.5 | m2/hr

## Kerbs & Paving
Roads & External Works - Kerbs & Paving
Ref | Task / Description | Slow | Ave | Fast | Units
984 | Concrete Slabs, laid on bedding, to slight falls | 2.7 | - | 4.2 | m2/hr
985 | Concrete Slabs, laid on bedding, to steep falls | 2.3 | - | 2.7 | m2/hr
986 | Concrete Slabs, laid in mortar, to slight falls | 1.5 | - | 2.3 | m2/hr
987 | Concrete Slabs, laid in mortar, to steep falls | 1.1 | - | 1.5 | m2/hr
988 | Concrete Slabs, laid on sand, to slight falls | 1.7 | - | 2.8 | m2/hr
989 | Concrete Slabs, laid on sand, to steep falls | 1.6 | - | 1.9 | m2/hr
990 | Cobble Stones, laid in mortar, no patterns | - | 0.3 | - | m2/hr
991 | Cobble Stones, laid in mortar, with patterns | - | 0.2 | - | m2/hr
992 | Artificial Stone, laid on sand, with patterns | - | 2.5 | - | m2/hr
993 | Brick Paviors, in mortar, straight joints | 0.9 | 1.3 | 1.9 | m2/hr
994 | Brick Paviors, in mortar, herringbone pattern | - | 1.0 | 1.2 | m2/hr
995 | Gravel Paths, including preparation of sub-base | - | 10.5 | - | m2/hr
996 | Concrete Paths, 100mm thick, including preparation of sub-base | - | 2.5 | - | m2/hr
997 | Concrete Kerbs or Channels, laid straight | - | 6.2 | - | m/hr
998 | Concrete Kerbs or Channels, laid to 5m radius | - | 4.5 | - | m/hr
999 | Concrete Kerbs or Channels, laid to 10m radius | - | 5.0 | - | m/hr
1000 | Concrete Kerbs or Channels, laid to 20m radius | - | 5.5 | - | m/hr
1001 | Stone/Granite Kerbs or Channels, laid straight | - | 3.5 | - | m/hr
1002 | Concrete Edging, laid straight | - | 7.7 | - | m/hr
1003 | Concrete Edging, laid to 5m radius | - | 5.8 | - | m/hr
1004 | Concrete Edging, laid to 10m radius | - | 6.2 | - | m/hr
1005 | Concrete Edging, laid to 20m radius | - | 7.1 | - | m/hr
1006 | Cutting and Fitting Ends, Concrete Kerbs | - | 6.6 | - | no/hr
1007 | Cutting and Fitting Ends, Channels | - | 5.8 | - | no/hr
1008 | Cutting and Fitting Ends, Concrete Edging | - | 8.3 | - | no/hr

## Painting
Architectural Builders Work and Finishes - Painting
Ref | Task / Description | Slow | Ave | Fast | Units
841 | Prepare Walls | - | 14.2 | - | m2/hr
842 | Prepare Doors | - | 12.5 | - | m2/hr
843 | Prepare Door Frames | - | 25.0 | - | m/hr
844 | Burn Off / Heat Strip Paintwork | - | 1.1 | - | m2/hr
845 | Internal Timber, 1 coat primer before fixing, generally | - | 6.7 | - | m2/hr
846 | Internal Timber, 1 coat primer before fixing, timber lengths | - | 20.0 | - | m/hr
847 | Internal Timber, knot, 1 primer, stop, 1 undercoat, 1 gloss | - | 1.7 | 2.1 | m2/hr
848 | Internal Timber, touchup primer, 1 undercoat, 1 coat gloss | - | 3.1 | 3.8 | m2/hr
849 | Internal Timber, polyurethane varnish, 2 coats | - | 3.3 | - | m2/hr
850 | Internal Timber, polyurethane varnish, 3 coats | - | 2.2 | - | m2/hr
851 | Internal Timber, linseed oil to hardwood, 2 coats | - | 3.6 | - | m2/hr
852 | External Timber, windows and frames | - | 2.4 | - | m2/hr
853 | External Timber, knot, 1 primer, 2 undercoats, 1 coat gloss, | - | 1.5 | - | m2/hr
854 | External Timber, touchup primer, 2 undercoats, 1 coat gloss, | - | 2.0 | - | m2/hr
855 | External Timber, 2 coats wood preservative | - | 4.0 | - | m2/hr
856 | External Timber, 3 coats polyurethane varnish | - | 2.0 | - | m2/hr
857 | Internal Walls, 2 coats emulsion to plaster | - | 8.0 | - | m2/hr
858 | Internal Walls, 2 coats emulsion to brick/blockwork | - | 6.0 | - | m2/hr
859 | Internal Walls, 1 mist, 2 coats emulsion to plaster | - | 6.0 | - | m2/hr
860 | Internal Walls, 1 mist, 2 coats emulsion to brick/blockwork | - | 4.5 | - | m2/hr
861 | Internal Walls, 1 primer, 1 undercoat, 1 gloss to plaster | - | 2.3 | - | m2/hr
862 | Internal Walls, undercoat to door frame | - | 20.0 | - | m/hr
863 | Internal Walls, gloss to door frame | - | 16.5 | - | m/hr
864 | Internal Walls, undercoat to door | - | 7.1 | - | m2/hr
865 | Internal Walls, gloss to door | - | 6.2 | - | m2/hr
866 | External Walls, 2 coats sandtex to render/concrete | - | 2.5 | - | m2/hr
867 | External Walls, 2 coats sandtex to brick/blockwork | - | 2.0 | - | m2/hr
868 | External Walls, 1 sealer, 2 emulsion to render/concrete | - | 2.0 | - | m2/hr
869 | External Walls, 1 sealer, 2 emulsion to brick/blockwork | - | 1.7 | - | m2/hr
870 | Floors, epoxy paint | - | 2.9 | - | m2/hr
871 | Ceilings, emulsion paint, 2 coats | - | 6.1 | - | m2/hr
872 | Ceilings, emulsion paint, 3 coats | - | 5.0 | - | m2/hr
873 | Ceilings, textured paint | - | 4.2 | - | m2/hr
874 | Ceilings, artex finish | - | 4.1 | - | m2/hr
875 | Internal Steelwork, 1 primer, 1 undercoat, 1 gloss | 1.3 | 2.4 | - | m2/hr
876 | External Steelwork, 1 primer, 2 undercoats, 1 gloss | 0.9 | 1.7 | - | m2/hr
877 | Guttering Steelwork, 1 coat primer, 2 undercoats, 1 gloss | - | 2.5 | - | m/hr

## Reinforcement Ratios
Concrete Works - Reinforcement Ratios
Ref | Task / Description | Slow | Ave | Fast | Units
442 | Pile Cap, Concrete m3 x Ratio = Rebar Tonnes | - | 14.8 | - | % ratio
443 | Base Slab, Concrete m3 x Ratio = Rebar Tonnes | - | 13.2 | 14.1 | % ratio
444 | Suspended Slab, Concrete m3 x Ratio = Rebar Tonnes | - | 20.6 | 25.6 | % ratio
445 | Platform Slab, Concrete m3 x Ratio = Rebar Tonnes | - | 15.6 | - | % ratio
446 | Columns, Concrete m3 x Ratio = Rebar Tonnes | 15.8 | 18.7 | 28.7 | % ratio
447 | Walls, Concrete m3 x Ratio = Rebar Tonnes | 14.7 | 15.0 | - | % ratio

## Roof Insulation
Roof Structures and Coverings - Roof Insulation
Ref | Task / Description | Slow | Ave | Fast | Units
541 | Polystyrene Boards | - | 8.5 | - | m2/hr
542 | Glass Fibre, low pitch | - | 12.0 | - | m2/hr
543 | Glass Fibre, steep pitch | - | 19.0 | - | m2/hr

## Screeding
Construction Wet Trades - Screeding
Ref | Task / Description | Slow | Ave | Fast | Units
642 | Sand/Cement Floor Screed, 15-20mm thick | - | 4.8 | 5.7 | m2/hr
643 | Sand/Cement Floor Screed, 20-30mm thick | - | 4.6 | 5.5 | m2/hr
644 | Sand/Cement Floor Screed, 30-40mm thick | 3.2 | 4.2 | 5.3 | m2/hr
645 | Sand/Cement Floor Screed, 40-50mm thick | 2.0 | 3.8 | 5.2 | m2/hr
646 | Sand/Cement Floor Screed, 50-65mm thick | - | 3.3 | 3.9 | m2/hr
647 | Sand/Cement Floor Screed, 65-100mm thick | - | 3.0 | 3.6 | m2/hr
648 | Fix/Setout Screed Battens | - | 10.0 | - | m/hr

## Trench Excavation
Foundations and Excavation - Trench Excavation
Ref | Task / Description | Slow | Ave | Fast | Units
306 | Hydraulic Excavator, 0.3m3 bucket, Sand/Soil | 5.6 | 7.1 | 8.2 | m3/hr
307 | Hydraulic Excavator, 0.3m3 bucket, Gravel Beds | 4.8 | 6.1 | 7.3 | m3/hr
308 | Hydraulic Excavator, 0.3m3 bucket, Clay/Chalk | 4.8 | 6.1 | 7.1 | m3/hr
309 | Hydraulic Excavator, 0.3m3 bucket, Hard Ground | 9.7 | 5.4 | 6.4 | m3/hr
310 | Hydraulic Excavator, 0.4m3 bucket, Sand/Soil | 20.5 | 25.0 | 29.2 | m3/hr
311 | Hydraulic Excavator, 0.4m3 bucket, Gravel Beds | 18.2 | 22.2 | 26.0 | m3/hr
312 | Hydraulic Excavator, 0.4m3 bucket, Clay/Chalk | 18.2 | 22.2 | 26.0 | m3/hr
313 | Hydraulic Excavator, 0.4m3 bucket, Hard Ground | 17.0 | 20.0 | 23.4 | m3/hr
314 | Hydraulic Excavator, 0.5m3 bucket, Sand/Soil | 26.0 | 28.6 | 33.1 | m3/hr
315 | Hydraulic Excavator, 0.5m3 bucket, Gravel Beds | 26.3 | 28.6 | 33.2 | m3/hr
316 | Hydraulic Excavator, 0.5m3 bucket, Clay/Chalk | 26.3 | 28.6 | 33.2 | m3/hr
317 | Hydraulic Excavator, 0.5m3 bucket, Hard Ground | 22.7 | 25.0 | 28.8 | m3/hr
318 | Excavate and Board Trench, 0.5-1.5m deep, < 2.0m wide | 3.3 | 4.5 | 6.8 | m2/hr
319 | Excavate and Board Trench, 1.5-3.0m deep, < 2.0m wide | 3.0 | 4.2 | 6.5 | m2/hr
320 | Excavate and Board Trench, 3.0-4.5m deep, < 2.0m wide | 2.7 | 4.0 | 6.0 | m2/hr
321 | Excavate and Board Trench, 0.5-1.5m deep, > 2.0m wide | 6.6 | 7.1 | 8.8 | m2/hr
322 | Excavate and Board Trench, 1.5-3.0m deep, > 2.0m wide | 6.2 | 6.7 | 9.2 | m2/hr
323 | Excavate and Board Trench, 3.0-4.5m deep, > 2.0m wide | 5.8 | 6.2 | 10.5 | m2/hr

## Waterproofing
Water Engineering - Waterproofing
Ref | Task / Description | Slow | Ave | Fast | Units
1181 | Asphalt coatings, horizontal surfaces | 3.5 | 4.2 | 5.8 | m2/hr
1182 | Asphalt coatings, vertical surfaces | 1.2 | 1.7 | 2.2 | m2/hr
1183 | Bituminous Brushed application, 2 coats | 4.8 | 5.0 | 6.3 | m2/hr
1184 | Bituminous Brushed application, 3 coats | 3.3 | 3.5 | 4.4 | m2/hr
1185 | Bituminous Sheets, horizontal surfaces | 3.8 | 4.0 | 4.8 | m2/hr
1186 | Bituminous Sheets, vertical surfaces | 3.3 | 3.5 | 4.2 | m2/hr
1187 | Polythene Sheets, horizontal surfaces | - | 20.0 | - | m2/hr
1188 | Bentonite Sheets, horizontal surfaces | 18.7 | 25.0 | 31.3 | m2/hr
1189 | Bentonite Sheets, vertical surfaces | 11.2 | 15.0 | 17.3 | m2/hr
1190 | Epoxy Based application, 1 coat | - | 75.0 | - | m2/hr
1191 | Epoxy Based application, 2 coat | - | 38.0 | - | m2/hr

## Basement Excavation
Foundations and Excavation - Basement Excavation
Ref | Task / Description | Slow | Ave | Fast | Units
294 | Hydraulic Excavator, 0.3m3 bucket, Sand/Soil - Basement Works | 6.4 | 8.0 | 9.4 | m3/hr
295 | Hydraulic Excavator, 0.3m3 bucket, Gravel Beds - Basement Works | 5.5 | 6.9 | 8.1 | m3/hr
296 | Hydraulic Excavator, 0.3m3 bucket, Clay/Chalk - Basement Works | 5.2 | 6.5 | 7.9 | m3/hr
297 | Hydraulic Excavator, 0.3m3 bucket, Hard Ground - Basement Works | 4.7 | 5.9 | 8.2 | m3/hr
298 | Hydraulic Excavator, 0.4m3 bucket, Sand/Soil - Basement Works | 12.6 | 15.4 | 18.9 | m3/hr
299 | Hydraulic Excavator, 0.4m3 bucket, Gravel Beds - Basement Works | 11.7 | 14.3 | 16.7 | m3/hr
300 | Hydraulic Excavator, 0.4m3 bucket, Clay/Chalk - Basement Works | 10.9 | 13.3 | 15.6 | m3/hr
301 | Hydraulic Excavator, 0.4m3 bucket, Hard Ground - Basement Works | 9.7 | 11.8 | 14.0 | m3/hr
302 | Hydraulic Excavator, 0.5m3 bucket, Sand/Soil - Basement Works | 18.2 | 20.0 | 23.0 | m3/hr
303 | Hydraulic Excavator, 0.5m3 bucket, Gravel Beds - Basement Works | 16.5 | 18.1 | 20.0 | m3/hr
304 | Hydraulic Excavator, 0.5m3 bucket, Clay/Chalk - Basement Works | 15.4 | 16.7 | 19.3 | m3/hr
305 | Hydraulic Excavator, 0.5m3 bucket, Hard Ground - Basement Works | 13.3 | 15.4 | 17.7 | m3/hr

## Brickwork
Construction Wet Trades - Brickwork
Ref | Task / Description | Slow | Ave | Fast | Units
593 | English Bond, 0.5 Brick thick | 0.7 | 0.8 | 1.1 | m2/hr
594 | English Bond, 1.0 Brick thick | 0.6 | 0.8 | 0.9 | m2/hr
595 | English Bond, 1.5 Brick thick | 0.4 | 0.5 | 0.6 | m2/hr
596 | English Bond, 2.0 Brick thick | 0.3 | 0.4 | 0.5 | m2/hr
597 | Flemish Bond, 0.5 Brick thick | 0.8 | 0.9 | 1.2 | m2/hr
598 | Flemish Bond, 1.0 Brick thick | 0.6 | 0.7 | 0.9 | m2/hr
599 | Flemish Bond, 1.5 Brick thick | 0.3 | 0.8 | 1.0 | m2/hr
600 | Flemish Bond, 2.0 Brick thick | 0.3 | 0.4 | 0.5 | m2/hr
601 | Flemish Garden Wall Bond, 0.5 Brick thick | 0.8 | 1.2 | 1.4 | m2/hr
602 | English Garden Wall Bond, 0.5 Brick thick | 0.8 | 1.0 | 1.3 | m2/hr
603 | Stretcher Bond, 0.5 Brick thick | 1.0 | 1.3 | 1.6 | m2/hr
604 | Building in Metal Door Frame | 0.5 | 0.5 | 0.3 | hrs/no
605 | Building in Metal Window | 0.6 | 0.5 | 0.4 | hrs/no
606 | Building in Wood Door Frame | 0.4 | 0.3 | 0.2 | hrs/no
607 | Building in Wood Window | 0.6 | 0.5 | 0.4 | hrs/no
608 | Building Brick on Edge Coping | - | 3.7 | - | hrs/m
609 | Building Brick on Edge Canted Cills | - | 1.8 | - | hrs/m
610 | Pointing to Frames | 12.4 | 15.4 | 17.8 | hrs/m
611 | Bitumen DPC, horizontal under 100mm wide | - | 2.9 | - | m2/hr
612 | Bitumen DPC, horizontal 100-255mm wide | - | 9.1 | - | m2/hr
613 | Bitumen DPC, horizontal over 255mm wide | - | 14.3 | - | m2/hr
614 | Bitumen DPC, vertical under 100mm wide | - | 5.8 | - | m2/hr
615 | Bitumen DPC, vertical100-225mm wide | - | 7.8 | - | m2/hr
616 | Bitumen DPC, vertical over 225mm wide | - | 10.0 | - | m2/hr
617 | Reinforcement ExMet, horizontal under 100mm wide | - | 5.8 | - | m2/hr
618 | Reinforcement ExMet, horizontal over 100mm wide | - | 9.1 | - | m2/hr
619 | Reinforcement ExMet, vertical under 100mm wide | - | 3.8 | - | m2/hr
620 | Reinforcement ExMet, vertical over 100mm wide | - | 5.8 | - | m2/hr
621 | Face Finish as work Proceeds, Raking Out | 26.3 | 27.8 | 29.4 | m2/hr
622 | Face Finish as work Proceeds, Flush and Rubbed | 4.2 | 4.3 | 4.5 | m2/hr
623 | Face Finish as work Proceeds, Struck Pointing | 2.8 | 3.0 | 3.1 | m2/hr
624 | Face Finish as work Proceeds, Bag Rubbed | - | 1.1 | - | m2/hr
625 | Face Finish as work Proceeds, Bucket Handle | 5.4 | 5.6 | 5.8 | m2/hr
626 | Face Finish as work Proceeds, Recessed 5-10mm | 4.2 | 4.7 | 4.9 | m2/hr
627 | Face Finish after completion, Flush and Rubbed | 1.9 | 2.0 | 2.1 | m2/hr
628 | Face Finish after completion, Struck Pointing | - | 1.3 | 1.2 | m2/hr
629 | Face Finish after completion, Bucket Handle | 2.5 | 2.7 | 2.9 | m2/hr

## Ceiling Finishes
Architectural Builders Work and Finishes - Ceiling Finishes
Ref | Task / Description | Slow | Ave | Fast | Units
722 | Suspended Ceilings, office situations | - | 2.6 | 3.5 | m2/hr
723 | Suspended Ceilings, First Fix | - | 0.7 | - | m2/hr
724 | Suspended Ceilings, Second Fix | - | 1.2 | - | m2/hr
0.7
1.2
0.5

## Concrete Mixing
Concrete Works - Concrete Mixing
Ref | Task / Description | Slow | Ave | Fast | Units
448 | Concrete Weight, 1m3 | - | 2.4 | - | Tonnes
449 | Readymix Lorry, Length | - | 8.3 | - | m
450 | Readymix Lorry, Width | - | 2.5 | - | m
451 | Readymix Lorry, Height | - | 3.7 | - | m
452 | Readymix Lorry, Length | - | 24.4 | - | Tonnes
453 | Readymix Lorry, Turning Circle | - | 16.4 | - | m
454 | Readymix Lorry, Allowable Access Ramp Gradient | - | 17.0 | 20.0 | degrees
455 | Mixing Concrete, By Hand | - | 0.3 | - | m3/hr
456 | Mixing Concrete, Single Drum Paddle Mixer | 158.0 | 180.0 | 210.0 | m3/hr
457 | Mixing Concrete, Double Drum Paddle Mixer | 315.0 | 370.0 | 420.0 | m3/hr
458 | Mixing Concrete, Single Drum Plant Pan Mixer | - | 120.0 | - | m3/hr
459 | Mixing Concrete, Dry Mix Plant | - | 90.0 | - | m3/hr

## Grit Blasting
Bridge Works - Finishes
Ref | Task / Description | Slow | Ave | Fast | Units
968 | Simple Universal Beam Steel Bridge, bridge lighting, handrails etc | - | 17.0 | - | m/day
Structural Frames - Finishes
Ref | Task / Description | Slow | Ave | Fast | Units
1236 | Grit Blasting to structural steel frames, standard to SA2.5 | 60.0 | 80.0 | 100.0 | m2/12hours

## Formwork
Bridge Works - Formwork
Ref | Task / Description | Slow | Ave | Fast | Units
963 | Shaft Slip Forming | - | 300.0 | 500.0 | mm/hr
Concrete Works - Formwork
Ref | Task / Description | Slow | Ave | Fast | Units
350 | Pilecaps, < 0.7m2 | 0.9 | 1.6 | 2.0 | m2/hr
351 | Pilecaps, 0.7-2.5m2 | 1.6 | 2.0 | 2.3 | m2/hr
352 | Pilecaps, 2.5-3.0m2 | 2.0 | 2.3 | 2.5 | m2/hr
353 | Pilecaps, > 3.0m2 | 2.3 | 2.5 | 3.1 | m2/hr
354 | Ground Beams, < 0.7m2 | 1.1 | 1.7 | 1.8 | m2/hr
355 | Ground Beams, 0.7-1.5m2 | 1.7 | 1.8 | 2.5 | m2/hr
356 | Ground Beams, 1.5-3.0m2 | 1.8 | 2.5 | 2.6 | m2/hr
357 | Ground Beams, 3.0-5.0m2 | 2.5 | 2.6 | 3.5 | m2/hr
358 | Elevated Plain Slab Soffit | 0.6 | 0.8 | 1.2 | m2/hr
359 | Beams, on erected falsework, width 100-200mm | 0.9 | 1.0 | 1.1 | m2/hr
360 | Beams, on erected falsework, width 200-300mm | 1.0 | 1.1 | 1.3 | m2/hr
361 | Beams, on erected falsework, width 300-500mm | 1.2 | 1.3 | 1.5 | m2/hr
362 | Beams, on erected falsework, width 500-750mm | 1.5 | 1.6 | 1.8 | m2/hr
363 | Beams, on erected falsework, width over 750mm | 1.4 | 1.5 | 1.7 | m2/hr
364 | Walls, Construct Kickers | 5.3 | 7.1 | 10.0 | m2/hr
365 | Walls, Fully Framed Formwork/Struts, 1.0-2.0m2 | 0.9 | 1.8 | 1.9 | m2/hr
366 | Walls, Fully Framed Formwork/Struts, 2.0-5.0m2 | 1.0 | 2.2 | 2.5 | m2/hr
367 | Walls, Fully Framed Formwork/Struts, over 5.0m2 | 1.2 | 2.5 | 2.9 | m2/hr
368 | Walls, StoriForm Shutters, 1.0-3.0m2 | 1.0 | 1.4 | 2.0 | m2/hr
369 | Walls, StoriForm Shutters, 3.0-5.0m2 | 1.9 | 2.3 | 3.3 | m2/hr
370 | Walls, StoriForm Shutters, 5.0-10.0m2 | 2.3 | 2.8 | 3.5 | m2/hr
371 | Walls, StoriForm Shutters, 10.0-15.0m2 | 3.2 | 4.5 | 4.0 | m2/hr
372 | Walls, StoriForm Shutters, over 15.0m2 | 3.8 | 4.8 | 5.4 | m2/hr
373 | Ground Slabs | 1.0 | 1.5 | 1.8 | m2/hr
374 | Columns, Construct Kickers, direct to slab | 3.2 | 4.1 | 5.4 | no/hr
375 | Columns, Construct Kickers, suspended from soffit slab | 1.2 | 2.8 | 3.2 | no/hr
376 | Columns, Square Sides, Timber Clamp/Prop, csa < 0.1m2 | 1.3 | 1.6 | 1.8 | m2/hr
377 | Columns, Square Sides, Timber Clamp/Prop, csa 0.1-0.4m2 | 1.8 | 2.1 | 2.4 | m2/hr
378 | Columns, Square Sides, Timber Clamp/Prop, csa over 0.4m2 | 2.0 | 2.3 | 2.5 | m2/hr
379 | Columns, Square Sides, Steel Forms, 1.5 x 1.5 x 9.0m high | 7.9 | 9.5 | 10.3 | m2/hr
380 | Columns, Square Sides, Steel Forms, 2.0 x 2.0 x 9.0m high | 6.9 | 7.5 | 8.3 | m2/hr
381 | Columns, Square Sides, Steel Forms, 2.0 x 4.0 x 9.0m high | 8.5 | 10.2 | 12.0 | m2/hr
382 | Columns, Round Sides, Sacrificial Plastic Mould, 3.0-4.0m dia | 3.5 | 4.5 | 6.0 | m2/hr
383 | Columns, Round Sides, Steel Mould, 3.0-4.0m dia | 5.2 | 6.5 | 7.5 | m2/hr
384 | Columns, Sloping Column Heads, extra over rate | - | 2.5 | 3.5 | hrs/no
385 | Staircases, Stair Soffit, Sloping | 0.7 | 0.8 | 1.0 | m2/hr
386 | Staircases, Stair Soffit, Flat Landing | 0.8 | 0.9 | 1.2 | m2/hr
387 | Staircases, Wall Strings | 0.4 | 0.6 | - | m2/hr
388 | Staircases, Open Strings | 0.7 | 0.8 | - | m2/hr
389 | Staircases, Riser Boards fixed to strings | - | 2.5 | 2.8 | m2/hr
390 | Staircases, Risers fixed to Strings | - | 2.3 | 2.6 | m2/hr
391 | Waffle Flooring, 2.4m grid | 1.1 | 1.4 | 1.8 | m2/hr
392 | Shaft Slip Forming | - | 300.0 | 500.0 | mm/hr
393 | Table Form, Aluminum System, 400m2 bays | 2.1 | 3.2 | 3.8 | m2/hr
394 | Table Form, H-Frame Steel Falsework, 400m2 bays | 1.9 | 3.0 | 3.5 | m2/hr
395 | Tunnel Forms, Wall and Slab poured as one | - | 15.6 | 17.5 | m2/hr
396 | Hollorib Decking, lay deck | - | 43.5 | 47.5 | m2/hr
397 | Hollorib Decking, shear connecting studs | - | 29.3 | 31.2 | m2/hr
398 | Stop Ends, no perforations | 2.8 | 3.5 | 4.2 | m2/hr
399 | Stop Ends, minor perforations | 1.2 | 1.5 | 1.9 | m2/hr
400 | Stop Ends, dense perforations | 0.9 | 1.1 | 1.4 | m2/hr
401 | Box Outs, 0.01-0.05m2 | 7.6 | 8.2 | 9.1 | no/hr
402 | Box Outs, over 0.05m2 | 3.1 | 3.9 | 4.5 | no/hr
403 | Dummy Frames, under 3.0m2 | 4.5 | 6.2 | 7.1 | no/hr
404 | Dummy Frames, over 3.0m2 | 3.1 | 3.7 | 4.5 | no/hr

## Plastering
Construction Wet Trades - Plastering
Ref | Task / Description | Slow | Ave | Fast | Units
654 | Browning (undercoat), Internal Walls under 2.5m high | 2.2 | 2.8 | 3.1 | m2/hr
655 | Browning (undercoat), Internal Walls over 2.5m high | 2.1 | 2.6 | 2.8 | m2/hr
656 | Browning (undercoat), Reveals and Columns less than 100mm wide | 9.9 | 10.0 | 10.1 | m2/hr
657 | Browning (undercoat), Reveals and Columns 100-200mm wide | 5.2 | 5.4 | 6.4 | m2/hr
658 | Browning (undercoat), Reveals and Columns 200-300mm wide | 3.3 | 3.6 | 3.9 | m2/hr
659 | Covings | - | 5.0 | - | m/hr
660 | Skimming (topcoat), Internal Walls under 2.5m high | 6.1 | 6.7 | 7.3 | m2/hr
661 | Skimming (topcoat), Internal Walls over 2.5m high | 5.5 | 6.1 | 6.7 | m2/hr
662 | Skimming (topcoat), Reveals and Columns less than 100mm wide | 12.6 | 13.8 | 15.4 | m2/hr
663 | Skimming (topcoat), Reveals and Columns 100-200mm wide | 7.7 | 8.3 | 9.8 | m2/hr
664 | Skimming (topcoat), Reveals and Columns 200-300mm wide | 4.5 | 5.0 | 5.5 | m2/hr
665 | Plaster Board to Ceilings | 3.2 | 4.5 | 5.5 | m2/hr
666 | Plastering Ceilings, 1 Bonding, 1 Skimming | 1.1 | 1.7 | 2.4 | m2/hr
667 | Plastering Ceilings, Topcoat Skimming | 2.7 | 3.2 | 5.4 | m2/hr

## Paintwork
Bridge Works - Paintwork
Ref | Task / Description | Slow | Ave | Fast | Units
966 | Simple Universal Beam Steel Bridge, paintwork to all steel | - | 6.9 | - | m/day

## Reinforcement
Concrete Works - Reinforcement
Ref | Task / Description | Slow | Ave | Fast | Units
405 | Slabs/Foundations, steelfixing, 6mm | 40.3 | 38.4 | 36.5 | hrs/tonne
406 | Slabs/Foundations, steelfixing, 8mm | 28.2 | 26.9 | 25.8 | hrs/tonne
407 | Slabs/Foundations, steelfixing, 10mm | 22.5 | 20.6 | 20.1 | hrs/tonne
408 | Slabs/Foundations, steelfixing, 12mm | 16.9 | 16.3 | 15.4 | hrs/tonne
409 | Slabs/Foundations, steelfixing, 16mm | 12.0 | 11.5 | 10.9 | hrs/tonne
410 | Slabs/Foundations, steelfixing, 20mm | 9.2 | 8.6 | 8.2 | hrs/tonne
411 | Slabs/Foundations, steelfixing, 25mm | 6.9 | 6.7 | 6.5 | hrs/tonne
412 | Slabs/Foundations, steelfixing, 32mm | 5.7 | 5.5 | 5.2 | hrs/tonne
413 | Slabs/Foundations, steelfixing, 40mm | 5.3 | 5.1 | 4.9 | hrs/tonne
414 | Slabs/Foundations, steelfixing, 50mm | 5.2 | 4.9 | 4.6 | hrs/tonne
415 | Beams/Columns, steelfixing, 6mm | 55.4 | 52.8 | 50.6 | hrs/tonne
416 | Beams/Columns, steelfixing, 8mm | 38.8 | 37.0 | 35.1 | hrs/tonne
417 | Beams/Columns, steelfixing, 10mm | 29.5 | 28.4 | 26.9 | hrs/tonne
418 | Beams/Columns, steelfixing, 12mm | 23.4 | 22.4 | 21.9 | hrs/tonne
419 | Beams/Columns, steelfixing, 16mm | 16.6 | 15.8 | 15.1 | hrs/tonne
420 | Beams/Columns, steelfixing, 20mm | 12.4 | 11.9 | 11.3 | hrs/tonne
421 | Beams/Columns, steelfixing, 25mm | 9.9 | 9.2 | 8.7 | hrs/tonne
422 | Beams/Columns, steelfixing, 32mm | 6.8 | 6.6 | 6.2 | hrs/tonne
423 | Beams/Columns, steelfixing, 40mm | 6.1 | 5.9 | 5.6 | hrs/tonne
424 | Beams/Columns, steelfixing, 50mm | 6.1 | 5.9 | 5.6 | hrs/tonne
425 | Walls, steelfixing, 6mm | 41.2 | 40.8 | 39.1 | hrs/tonne
426 | Walls, steelfixing, 8mm | 29.2 | 28.6 | 27.4 | hrs/tonne
427 | Walls, steelfixing, 10mm | 22.7 | 22.0 | 21.2 | hrs/tonne
428 | Walls, steelfixing, 12mm | 17.6 | 17.3 | 16.9 | hrs/tonne
429 | Walls, steelfixing, 16mm | 12.4 | 12.2 | 11.8 | hrs/tonne
430 | Walls, steelfixing, 20mm | 9.4 | 9.2 | 8.7 | hrs/tonne
431 | Walls, steelfixing, 25mm | 7.4 | 7.2 | 7.0 | hrs/tonne
432 | Walls, steelfixing, 32mm | 7.0 | 6.8 | 6.4 | hrs/tonne
433 | Walls, steelfixing, 40mm | 6.4 | 6.1 | 5.9 | hrs/tonne
434 | Walls, steelfixing, 50mm | 5.3 | 5.1 | 4.8 | hrs/tonne
435 | Staircases, steelfixing, 6mm | 48.9 | 48.0 | 45.5 | hrs/tonne
436 | Staircases, steelfixing, 8mm | 34.4 | 33.6 | 31.9 | hrs/tonne
437 | Staircases, steelfixing, 10mm | 26.6 | 25.8 | 24.3 | hrs/tonne
438 | Staircases, steelfixing, 12mm | 20.9 | 20.4 | 19.5 | hrs/tonne
439 | Staircases, steelfixing, 16mm | 14.6 | 14.4 | 13.8 | hrs/tonne
440 | Staircases, steelfixing, 20mm | 11.3 | 10.8 | 10.5 | hrs/tonne
441 | Staircases, steelfixing, 25mm | 8.6 | 8.4 | 8.2 | hrs/tonne

## Rule of Thumb
Quick Reference - Rule of Thumb
Ref | Task / Description | Slow | Ave | Fast | Units
1 | Site Investigation Pre Drilling | 5.0 | 4.0 | 3.0 | days/no
2 | Ground Excavation, Hydraulic Backhoe | - | 50.0 | - | m3/day
3 | Bored Piling, 25-70m deep | 10.0 | 8.0 | 6.0 | days/no
4 | Formwork Fixing | - | 12.0 | - | m2/day
5 | Reinforcement Fixing | - | 0.7 | - | Tonnes/day
6 | Concrete Placement | - | 16.0 | - | m3/day
7 | Scaffold Erection, Steel Falsework | - | 140.0 | - | m3/day
8 | Blockwork Laying | - | 7.0 | - | m2/day
9 | Plastering and Rendering | - | 12.0 | - | m2/day
10 | Blockwork Laying | 7.0 | 12.0 | 17.5 | m2/day
11 | Stonework Cladding | - | 5.1 | - | m2/day
12 | Window Glazing | - | 1.5 | - | m2/hr
13 | Granolithic Flooring | - | 4.5 | - | m2/hr
14 | Floor Screeding | - | 4.5 | - | m2/hr
15 | Floor Screeding | - | 60.0 | - | m2/day
16 | Ceramic Wall Tiling | - | 1.5 | - | m2/hr

## Wall Finishes
Architectural Builders Work and Finishes - Wall Finishes
Ref | Task / Description | Slow | Ave | Fast | Units
708 | Mosaic Tiling, 0.045x0.045m | - | 1.1 | 1.5 | no/hr
709 | Clay, quarry Tiles, Window Cills, setout and level | - | 55.5 | - | m/hr
710 | Clay, quarry Tiles, Window Cills, fix, grout and clean | - | 1.5 | - | m2/hr
711 | Ceramic Tiles 150x150mm, Ledges/Upstands | 20.4 | 27.1 | 32.0 | no/hr
712 | Ceramic Tiles 150x150mm, Areas under 1.5m2 per room | 0.9 | 1.0 | 1.2 | m2/hr
713 | Ceramic Tiles 150x150mm, Areas of 1.5-2.5m2 per room | 1.4 | 1.6 | 1.9 | m2/hr
714 | Ceramic Tiles 150x150mm, Areas over 2.5m2 per room | 1.5 | 1.7 | 2.1 | m2/hr
715 | Ceramic Tiles 150x150mm, Extra Over for Cutting | - | 41.6 | - | no/hr
716 | Ceramic Tiles 108x108mm, Ledges/Upstands | - | 62.5 | - | no/hr
717 | Ceramic Tiles 108x108mm, Areas under 1.5m2 per room | 1.0 | 1.3 | 1.5 | m2/hr
718 | Ceramic Tiles 108x108mm, Areas of 1.5-2.5m2 per room | 1.6 | 1.8 | 2.1 | m2/hr
719 | Ceramic Tiles 108x108mm, Areas over 2.5m2 per room | 1.7 | 1.9 | 2.2 | m2/hr
720 | Ceramic Tiles 108x108mm, Extra Over for Cutting | - | 125.0 | - | no/hr
721 | Ceramic Tiles, Grouting Works | 2.2 | 2.5 | 2.6 | m2/hr

## Tower Cranes
Scaffolds and Crainage - Tower Cranes
Ref | Task / Description | Slow | Ave | Fast | Units
345 | Erect and Setup 50m gib | - | 11.0 | 7.5 | days
346 | Dismantle 50m gib | - | 10.0 | - | days
347 | Lifting, Reinforcement Bins and Cages, 1st 15m lift | - | 3.2 | - | mins/lift
348 | Lifting, Reinforcement Bins and Cages, above 1st 15m lift | - | 0.5 | - | mins/15m
349 | Lifting, Crane Tracking Time | - | 3.3 | - | seconds/m