## Sheet2
Progress Summary till 5 Oct. 2010
Project: Evyap Egypt
Date: 5 Oct. 2010
Ser. | Item | Progress % | Notes
A- | Workshop
1 | PC floors | 95
2 | Masonry work 6 m height & cap beams | 55 | 3m height additional work
3 | Internal plaster | 40 | 3m height additional work
4 | External plaster | 30 | 3m height additional work
5 | Painting | 4 | 3m height additional work
6 | Grout for column neck | 100 | Variation
7 | Polyethylene Pipes | 50 | Variation
8 | PVC pipes 6 bar | 40 | Variation
9 | PVC windows | 2 | Variation
B- | Internal Frame
| Extra internal frame | 95 | New One (Modification)
C- | Boiler
1 | RC Foundations | 100 | due to modifications
2 | PC Foundations | 100 | due to modifications
2 | RC Floor | 70 | due to modifications
3 | Grout for column neck | 100 | Started 28.8.2010
4 | PVC pipes 200 mm | 100
5 | Masonry work above ground level | 0 | Depend on Grout start
D- | Fence (6 parts)
1 | Plaster (part 1,2,4,5,6) | 95 | due to modifications(extra height)
2 | Excavation (part 3) | 50 | there was problem in levels to start work
3 | PC & RC foundations (part 3) | 50
4 | Graviato | 55
E- | Cooling Tower |  | Additional works
1 | PC foundations | 100 | due to NEW modifications 1.8.2010
2 | RC foundations | 100 | due to NEW modifications 1.8.2010
3 | RC walls | 100
F- | Old Fence Modifications |  | Additional works
1 | Demolish of old RC beam | 100
2 | Masonry work | 95
3 | RC column & beam | 90
4 | Plaster | 80
G | Scale pit |  | Variation
1 | Cutting asphalt | 100
2 | Excavation | 100
3 | Pink lime stone | 100
4 | PC Footing | 100
5 | RC Footing | 100
6 | RC walls | 40
H | Sewer channel for rain water in workshop |  | Variation
1 | PC floors demolish | 100
2 | Excavation | 100
3 | PC floors | 101