## LIST
Detailed Schedule Checklist
| Project Name | : | Airfield Facilities Upgrades (AFU) - Phase 1
| Contract Number | : | R-14-084-BF |  |  |  | STATUS | IF NO | PROJECT NAME | PROJECT CODE | CONTRACT NUMBER | CONTRACTOR
| Project Code | : | RUH-CP-1402
| Contractor | : | Almabani General Contractor
| Submittal Number | : |  |  |  |  | YES | MAJOR | Airfield Facilities Upgrades (AFU) - Phase 1 | RUH-CP-1402 | R-14-084-BF | Almabani General Contractor
| Submitted Date | : |  |  |  |  | NO | MINOR | Development & Expansion of Existing Terminals (T3) | RUH-CP-1501A | R-00-074-DB-0 | Riyadh Airport Contractor
| Revision | : |  |  |  |  | NA |  | TR4 | RUH-CP-1501C | R-13-067-SD-0 | Riyadh Airport Contractor
| Date of Review | : | [6 empty] | SCAHC ER | RUH-CP-1501B | TO BE AWARDED | Riyadh Airport Contractor
[9 empty] | LC3 | RUH-CP-1502 | R-00-085-DB-0 | Saudi Services of Electro-Mechanic
S.No | Description |  |  | Status | Fill only Colored | Remarks
A | General
1 | Is the Detailed schedule submitted within 60 days from commencement date? |  |  | NO | MINOR
2 | Does the Title page or Footer / Header block show the followings:
a | Project Name, Contract Number and Project Code |  |  | YES
b | Contractor Name/Logo |  |  | YES
c | Client & Consultant Name/Logo |  |  | NO | MINOR | KKIA Logo Missing
d | Data Date (Start Date of Contract) |  |  | YES
e | Schedule Submittal Date (In Revision Box) |  |  | NO | MINOR | No Revision tables in footer
3 | Does the Contractor used latest version of Oracle Primavera as per specifications |  |  | YES
4 | Does Contractor follow the default settings in Primavera as per specifications as below:
a | Retained Logic |  |  | YES
b | Early Start |  |  | YES
c | Non Critical |  |  | YES
d | Finish Float |  |  | YES
e | Longest Path |  |  | NO | MINOR
5 | Does Detailed Schedule complies with complete Contract time frame/Duration of the project |  |  | YES
6 | Does Detailed schedule is defined in detail reflecting entire scope of work |  |  | YES
8 | Does Detailed schedule shows the Project Phases/Zones/Levels as agreed |  |  | YES
9 | Does Primavera layout files (PLF) provided |  |  | YES
10 | Any other Information |  |  | NA
B | Work Breakdown Structure (WBS)
1 | Does WBS structure is inline with schedule guidelines provided by Engineer or as per Price Breakdown structure Uniformat Level |  |  | NO | MINOR
2 | Does WBS Codes are inline with schedule guidelines provided by Engineer |  |  | YES
3 | Does Budgeted Cost at each WBS/Work package is inline with Price breakdown structure |  |  | NO | MINOR | Primavera Bug error
4 | Does Start/Finish dates for each WBS are inline with contractual requirements/mutually agreed by all |  |  | NA
5 | Does Project Budgeted Cost = Contract Price/Value |  |  | NO | MINOR | Primavera Bug error
6 | Any other Information |  |  | NA
C | Activities
1 | Does Activity duration is in workdays |  |  | YES
2 | Does All activities are Task Dependant type only except summary level activities which may be Level of Effort or WBS Summary type at each major work packages |  |  | YES
3 | Does Duration type = Fixed Duration and Units, applied for all activities unless specified by Engineer |  |  | YES
4 | Does Percent complete type = Physical %, applied for all activities |  |  | YES
5 | Does Activity ID numbering system is as per Engineer schedule guidelines or acceptable to Engineer |  |  | NO | MINOR
6 | Does different Calendars defined considering Client working days, Holidays, Ramadan period, Adverse weather etc |  |  | NO | MINOR
7 | Does Activity Codes are as per Engineer schedule guidelines or acceptable to Engineer as following
a | Detailed and General Requirements comprising Milestones |  |  | YES
b | Mobilization comprising Temp. facilities, Permits, Method statements etc |  |  | YES
c | Design/Engineering/BIM comprising Specifications, shop drawings, 3D Modeling etc |  |  | YES
d | Procurment comprising Long lead items, Purchase Order etc |  |  | NO | MINOR | Not assined for POs
e | Discipline comprising Civil, Electrical, Mechanical, Process Areas etc |  |  | NO | MINOR
f | Project Phases/ Phasing Plan etc |  |  | YES
g | Sub-Contractors/ Interfaces etc |  |  | NO | MINOR | Not assigned
8 | Does Activity relationships are as per following:
a | Does all activities have atleast one predecessor and one successor except Project commencement date and Project Completion date |  |  | NO | MINOR | Few summary activities appplied
b | Does Finish to start logics appplied no less than 80% of all relationships |  |  | NO | MINOR
c | Does No more than 20% of all logic relationships other than Finish-to-Start applied |  |  | NO | MAJOR | May be problem whille tracking, updating
d | No negativeLead/Lag relationships are used |  |  | YES
9 | Does Detailed Schedule comprises following milestones as per contract
a | Contractual Milestones |  |  | YES
b | Critical Milestones |  |  | NO | MINOR | Not mentioned
c | Intermediate Milestones at each work packages/discipline etc |  |  | NO | MINOR | Not mentioned
d | Commencement Milestones per phases/area etc |  |  | YES
e | Completion Milestones pper phases/area etc |  |  | YES
10 | Does Activities with Constraints followed as per below:
a | Date constaints is limited to "Start on or Before" and "Finish on or Before" for only Milestone activities |  |  | YES
b | Date constraints of "Start on or After", "Finish on or After", "Mandatory Start',"Mandatory Finish" are not assigned to any activity |  |  | YES
c | Float and Duration constraints are not assigned to any activity |  |  | YES
11 | Activities shall provide Permits, Inspection/Surveys, Other agency utility relocations, Temporary facilities, Mobilizations
a | Permit activities |  |  | YES
b | Inspection/Survey activities |  |  | YES
c | Temporary Facilities activities |  |  | YES
d | Mobilization activities |  |  | YES
e | Other agency Utility relocations activities |  |  | NA
f | Interface activities |  |  | NO | MINOR | Required for monitoring
g | Method Statement/Work Plans |  |  | YES
h | Any other specific activities |  |  | NA
12 | Does Design/Engineering submittal activities complies following Structure:
a | Intermediate Design activities |  |  | YES
b | Pre-Final Design activities |  |  | YES
c | Final Design activities |  |  | YES
13 | Does Design/Engineering submittal activities complies following pattern for Sl.12 strucutre:
a | Preparation and Submission |  |  | YES
b | Review by Engineer (Duration as per contract) |  |  | YES
c | Incorporation of comments & Re-Submission |  |  | YES
d | Approval/Comment by Engineer (Duration as per contract) |  |  | YES
14 | Does BIM submittals complies following Structure and follow sl.13 pattern:
a | LOD 1 |  |  | YES
b | LOD 2 |  |  | YES
c | LOD 3 |  |  | YES
d | LOD 4 |  |  | YES
e | LOD 5 |  |  | YES
15 | Does Shop Drawing activities complies following pattern:
a | Preparation and Submission |  |  | YES
b | Review by Engineer (Duration as per contract) |  |  | YES
c | Incorporation of comments & Re-Submission |  |  | YES
d | Approval/Comment by Engineer (Duration as per contract) |  |  | YES
16 | Does Material Approval of sample submittal activities complies following pattern:
a | Preparation and Submission |  |  | YES
b | Review by Engineer (Duration as per contract) |  |  | YES
c | Incorporation of comments & Re-Submission |  |  | YES
d | Approval/Comment by Engineer (Duration as per contract) |  |  | YES
17 | Does Procurement activities complies following pattern:
a | Tender and PO issuance |  |  | YES
b | Shop drawing Activities |  |  | YES
c | Material Approval of sample submittal activities |  |  | YES
d | Material Fabrication |  |  | NO | MAJOR
e | FAT |  |  | NO | MAJOR
f | Delivery of Items |  |  | YES
18 | Does Detailed schedule comprises the construction of temporary facilities
19 | Does Construction Activities are inline with uniformat level i.e. Price Breakdown Structure (PBS)
20 | Does the logic sequence applied as mentioned in Narrative Report for all construction Activities
21 | Does the logic sequence applied as mentioned in Narrative Report for all Testing Activities
22 | Does the logic sequence applied as mentioned in Narrative Report for all Commissioning Activities
23 | Does ORAT activities are sequentially logical and in agreed timelines
24 | Does Activity duration not exceed 30 days except for non-construction activities incl. mobilization, procurement and concrete curing activities |  |  | NO | MINOR | To be provided by Contractor
25 | Schedule does not use Negative Lead/Lag relationships |  |  | NO | MAJOR
26 | Does Sequential Logics are realistic in nature ie. Mobilization-> Design-> Procurment-> Construction-> Testing & Commissioning |  |  | YES
27 | Does Logics applied fulfills Phasing Plans/Agreed dates for completion |  |  | NO | MAJOR
28 | Does all Contractual major submittals (Ex. HSE Plan, QA/QC etc) listed in schedule |  |  | NO | MAJOR
29 | Does schedule has As-built drawing activities |  |  | NO | MAJOR
30 | Any other Information |  |  | NA
D | Critical Path Method (CPM)
1 | Is Critical path defined clearly |  |  | NO | MINOR
2 | Does Critical activities defined as “Longest Path” |  |  | NO | MINOR
4 | Does Detailed schedule have reasonable Critical path and total float as finish float |  |  | YES
5 | Does Critical path have negative floats |  |  | NO | MAJOR | "Must finish by" is left blank
6 | Any other Information |  |  | NA
E | Resources
1 | Does Detailed schedule is resource loaded (Man, Material & Machinary) |  |  | YES
2 | Does the Resources loaded are broken down by craft or trade man |  |  | YES
3 | Does Material type resource is used as Cost loaded for activities having cost |  |  | YES
4 | Does Resources Budgeted units/time and Budget units values for activities are same as per Resources calculation document provided by contractor |  |  | NO | MINOR
5 | Any other Information |  |  | NA

## DASHBOARD
Detailed Schedule Checklist
[6 empty] | STATUS |  |  | If NO
Description | YES | NO | NA | MAJOR | MINOR | % YES | % NO | % NA | % MAJOR | % MINOR | Weightage
General | 12 | 4 | 1 | 0 | 4 | 70.59% | 23.53% | 5.882% | 0% | 100% | 10
Work Breakdown Structure (WBS) | 1 | 3 | 2 | 0 | 3 | 16.67% | 50% | 33.33% | 0% | 100% | 20
Activities | 45 | 18 | 3 | 7 | 11 | 68.18% | 27.27% | 4.545% | 38.89% | 61.11% | 30
Critical Path Method (CPM) | 1 | 3 | 1 | 1 | 2 | 20% | 60% | 20% | 33.33% | 66.67% | 10
Resources | 3 | 1 | 1 | 0 | 1 | 60% | 20% | 20% | 0% | 100% | 30
SUMMARY | 62 | 29 | 8 | 8 | 21 | 50.85% | 32.53% | 16.62% | 14.44% | 85.56% | 100
REMARKS/COMMENTS:
1. Schedule is Approved with Exceptions
2. Critical Path shall be defined a Longest Path
3. Procurement Activities Fabrication & FAT information to be provided
4
5
6
7
8
9
10

## lEGEND
LEGEND
| YES | : | Agreed/Mentioned as per requirements
| NO | : | Not Mentioned/ Not as per requirements
| NA | : | Not Applicable
| MAJOR | : | Not mentioned but strictly follow/fulfill as per requirements
| MINOR | : | Not Mentioned as per requirements but may be acceptable