## Main Dashboard (1)
PCS-Close Out Monthly Report
Project Name: |  |  | Budget:
Employer: |  |  | Commencement date:
Design consultant |  |  | Contract completion date:
Supervision consultant |  |  | Modified / forecasted completion date :
Contractor: |  |  | Total contractual project duration:
Project Manager
Date:
Overall Close Out Report
Complied Criteria on Close Out Monthly Report
Actual Construction Status as of August-16
No | Criteria | Weight | Actual achievement | Remarks
1 | O&M manuals | 5% | 3% | progressing properly
2 | Testing & Commissioning | 5% | 2% | End of project f inal report to be attached within the close out report
3 | Training | 5% | 5% | PM to confirm no training sessions required on the contract
4 | Authorities approval | 15% | 0%
5 | Asset register | 5% | 3% | progressing properly
6 | As built drawings | 10% | 1% | progressing ,Log approved
7 | Master Key & Access Cards | 5% | 1% | progressing ,Log approved
8 | Spare parts/special tools | 5% | 1% | progressing ,Log approved
9 | Updated Snags List | 5% | 0% | On the due time will be progress
10 | QA/QC Report | 10% | 7% | Musanada approved QA/QC Template to be used
11 | HSE report | 10% | 7% | Musanada approved HSE Template to be used
12 | Warranties | 5% | 0.5% | progressing ,Log approved
13 | lesson learned | 5% | 5% | All captured
14 | Taking Over Certificate | 5% | 0% | ON the due date will to update PCS-Close out unit
15 | Close Out Report | 5% | 2.7% | Prepration going on

## Detailed Dashboard(2)
PCS-Close Out Monthly Report Actual Construction Status as of
s.no
[5 empty] | S.no | Assigned Weight | Actuals To Date | Balance To Complete
1- O&M Manuals |  | Assigned Weight |  | 5% | 1 | 5% | 3% | 2%
| Weight | Quantity | Achievements | Status | 2 | 10% | 2% | 8%
1.1 -Total numbers of O &M manuals required as per building systems component , |  |  |  |  | 3 | 5% | 0.5% | 4.5%
defined and agreed between contractor and consultant , fixed in a log sheet for tracking | 20% | 5 | 100% | 1% | 4 | 5% | 0% | 5%
1.2- Total O & M numbers approved by Consultant & confirmed by PM | 40% | 5 | 100% | 2% | 5 | 5% | 1% | 4%
1.3- Total O & M numbers Reviewed & accepted by FM/client representative/end user | 30% | 0 | 0 | 0% | 6 | 5% | 1% | 4%
1.4- Total complete quantity consisting all twenty sections delivered to the site | 10% | 0 | 0 | 0% | 7 | 5% | 1% | 4%
O&M Manuals Actual % To Date |  |  |  | 3% | 8 | 5% | 0.5% | 4.5%
2- Testing & Commissioning (T&C) |  | Assigned Weight |  | 10% | 9 | 5% | 0% | 5%
| Weight | Quantity | Achievements | Status | 10 | 10% | 5% | 5%
2.1 -Total number of systems T&C test must be carried out as per building system components wise , the same to be prepared as per the attached sheet bearing consultant, contractor and third-party stamps , the same to be updated every week | 20% | 4216 | 100% | 2% | 11 | 10% | 5% | 5%
2.2.Total number of passed test stage commissioning (ATP3) as stand alone | 70% | 0 | 0% | 0% | 12 | 5% | 0.5% | 4.5%
2.3- Total number of passed test stage integration with BMS (ATP4) | 0% | 0 | 0% | 0% | 13 | 5% | 3% | 2%
2.4- Final T&C report issued and approved from all parties (contractor, consultant, Third party PM and UPC) | 10% | 0 | 0% | 0% | 14 | 5% | 0% | 5%
T&C Actual % To Date |  |  |  | 2% | 15 | 5% | 2.7% | 1.3%
3- Training |  | Assigned Weight |  | 5% | Grand Total | 100% | 38.3% | 61.7%
| Weight | Quantity | Achievements | Status
3.1 -Total number of systems required training defined by contract to be prepared in the attached flow sheet with schedule plan dates | 10% | 10 | 100% | 0.5%
3.2 -Consultant and PM confirmed on achievement training by contractor/supplier to FM and client representatives | 40% | 0 | 0% | 0%
3.3 -Approval on achieved training by FM and client | 50% | 0 | 0% | 0%
Training Actual % To Date |  |  |  | 0.5%
4- Authorities Approvals |  | Assigned Weight |  | 15%
| Weight | Quantity | Achievements | Status
4.1 Abu Dhabi Al Ain Municipality (Building complstion certificate) | 10% | 1 | 0% | 0%
4.2 Abu Dhabi Sewerage Service Company (ADSSC) | 10% | 1 | 0% | 0%
4.3 AbuDhabi/ Al Ain Distribution Company Power ( ADDC & AADC - Power) | 10% | 1 | 0% | 0%
4.4 AbuDhabi/ Al Ain Distribution Company Water (AADC - Water) | 10% | 1 | 0% | 0%
4.5 Telecom authority / Etisalat | 10% | 1 | 0% | 0%
4.6 AbuDhab/Al Ain City Municipality(Storm Water Network) | 5% | 1 | 0% | 0% |  |  | Not to fill/Modify any thing on first two Sheet- 1 & 2
4.7 AbuDhabi /Al Ain City Municipality(Irrigation Network) | 5% | 1 | 0% | 0%
4.8 AbuDhabi / Al Ain City Municipality(PRFD) | 5% | 1 | 0% | 0%
4.9 AbuDhabi /Al Ain City Municipality(Street Light Network) | 5% | 1 | 0% | 0%
4.10 AbuDhabi /Al Ain City Municipality(Road Works) | 5% | 1 | 0% | 0%
4.11 Civil defence for fire hydrant net work | 10% | 1 | 0% | 0%
4.12UPC - Estidama /villa /community | 10% | 1 | 0% | 0%
4.13 Department of Transport(Traffic Signal) | 5% | 1 | 0% | 0%
Authorities Approvals Actual % To Date |  |  |  | 0%
5- Assets Register |  | Assigned Weight |  | 5%
| Weight | Quantity | Achievements | Status |  |  | Other attached excel sheets will be filled witth the information.sheet 1 & 2 for referance and information only.
5.1 -Total No's of assets systems must be registered base on building component break down list prepared by contractor as per attached Musanda format or/ client format | 20% | 29646 | 100% | 1%
5.2- Total No's prepared Building component breakdown list, as per Musanada or client format reviewed and approved by consultant and PM | 40% | 29646 | 100% | 2%
5.3 -Total No's reviewed accepted by FM or client (Asset manager) | 40% | 0 | 0% | 0%
Asset Register Actual % To Date |  |  |  | 3%
6- As Built Drawings |  | Assigned Weight |  | 5%
| Weight | Quantity | Achievements | Status
6.1 -Total quantity of as built drawings (agreed by PM/consultant / contractor) as per building systems components wise , to be followed on tracker sheet | 20% | 564 | 100% | 1%
6.2 Total quantity of as built drawings approved by consultant and confirmed by PM | 40% | 0 |  | 0%
6.3- Total quantity of as built drawings reviewed & and accepted by FM or client representative | 30% | 0 | 0% | 0%
6.4- Total quantity of as built soft and hard copy delivered and distributed | 10% | 0 | 0% | 0%
As Built Drawings Actual % To Date |  |  |  | 1%
7- Master Keys & Access Cards |  | Assigned Weight |  | 5%
| Weight | Quantity | Achievements | Status
7.1-Total number of keys must be submitted by Contractor | 20% | 3566 | 100% | 1%
Keys Per room (doors). |  | 0
Master Keys Per Zone - Sub Master Key (SMK)
Main Master Keys - Grand Master Key (GMK)
7.2- Approved by consultant & Reviewed by PM and confirmed by FM | 20% | 0 | 0% | 0%
7.3 - PM submitted to client security representatives | 20% | 0 | 0% | 0%
7.4 -Total number of access cards must be submitted by Contractor
7.5 - Approved by consultant & Reviewed by PM and confirmed by FM | 20% | 0 | 0% | 0%
7.6 -PM submitted to client security representatives | 20% | 0 | 0% | 0%
Master Keys & Access Cards Actual % To Date |  |  |  | 1%
8- Spare Parts / Special Tools |  | Assigned Weight |  | 5%
| Weight | Quantity | Achievements | Status |  |  |  |  | 0%
8.1 -Total number of spare parts/special tools to be submitted by main contractor as per the contractual obligation | 10% | 11 | 100% | 0.5% |  |  |  |  | 100%
8.2 Approved by consultant | 20% | 0 | 0% | 0%
8.3- Acceptance and confirmed by PM | 20% | 0 | 0% | 0%
8.4- FM or client accepted to receive and deliver | 20% | 0 | 0% | 0%
8.5 -PM confirmed Spare Parts / Special tools delivered to site | 30% | 0 | 0% | 0%
Spare Parts / Special Tools Actual % To date |  |  |  | 0.5%
9- Updated Snag List |  | Assigned Weight |  | 5%
| Weight | Quantity | Achievements | Status
9.1 -Total lists of snags for all discipline's to be prepared by contractor and agreed with consultant and PM | 10% | 0 | 0% | 0%
9.2 Consultant approval for the list of snags and confirmed by PM | 20% | 0 | 0% | 0%
9.3- Final lists of snags reviewed by FM/client/client representative | 30% | 0 | 0% | 0%
9.4- BCM and FM Divisions agreed on way forward plan and responsibilities to deliver snags | 40% | 0 | 0% | 0%
Updated Snag List Actual % To Date |  |  |  | 0%
10- Quality Assurance Report |  | Assigned Weight |  | 10%
| Weight | Report | Achievements | Status
10.1-QA/QC Monthly reports updates prepared and approved by consultant ,PM | 100% | 1 | 50% | 5% |  |  |  | 5
Quality Assurance Report Actual % To Date |  |  |  | 5%
11- HSE Report |  | Assigned Weight |  | 10%
| Weight | Report | Achievements | Status
11.1-HSE Monthly reports updates prepared and approved by consultant ,PM | 100% | 1 | 70% | 7%
HSE Report Actual % To Date |  |  |  | 7%
12- Warranties |  | Assigned Weight |  | 5%
| Weight | Quantity | Achievements | Status
12.1-Total number of warranties must be submitted by main contractor as per building component system wise fixed in a logsheet for tracking | 10% | 22 | 100% | 0.5%
12.2- Total number of warranties (draft) approved by consultant &confirmed by PM | 50% | 22 | 0% | 0%
12.3 -Total number of warranties(draft) reviewed and accepted by FM | 20% | 22 | 0% | 0%
12.4 -PM & FM confirmation on the receipt of total number of original warranties | 20% | 22 | 0% | 0%
Warranties Actual % To Date |  |  |  | 0.5%
13- Lesson Learned |  | Assigned Weight |  | 5%
| Weight | Report | Achievements | Status
13.1- Lesson learned shared, gathered and captured by PM on Musanda attached format | 50% | 1 | 100% | 2.5%
13.2- PM Submit the collected lesson learned to the design section | 50% | 1 | 0% | 2.5%
Lesson Learned Actual % To Date |  |  |  | 5%
14- Taking Over Certificate |  | Assigned Weight |  | 5%
| Weight | Report | Achievements | Status
14.1 - Consultant issuance of TOC | 20% | 1 | 0% | 0%
14.2 - initials of committee members for handover acceptance | 80% | 1 | 0% | 0%
Taking Over Certificate Actual % To Date |  |  |  | 0%
15- Close Out Report |  | Assigned Weight |  | 5%
| Weight | Report | Achievements | Status
15.1- Close out report prepared by contractor as per Musanada template and submit to engineer | 20% | 1 | 90% | 0.9%
15.2 Close out report reviewed and approved by consultant | 30% | 1 | 90% | 0.9%
15.3 -Close out report reviewed and approved PM | 20% | 1 | 90% | 0.9%
15.4-Close out report reviewed and accepted by FM/client/client representative | 30% | 1 | 0% | 0%
Project close out Report Actual % To date |  |  |  | 2.7%

## Flow sheet (16) close out repor
Flow sheet No(16) for close out report
Project Closeout Report |  |  |  | No | Appendixes | Weight | Status
No | Contents | Weight | Status | 1 | Commercial report | 3%
1 | Brief Description of Projects | 2% |  | 2 | Remaining works/defects | 2%
2 | Key Milestone Dates for Projects | 3% |  | 3 | List of as-built drawings & soft copy | 5%
3 | Project Cost Details | 4% |  | 4 | List of O&M manuals & soft copy | 5%
4 | Client | 1% |  | 5 | Testing & commissioning records | 5%
5 | Employer | 1% |  | 6 | List of spare parts/materials | 5% |  | :
6 | Project Management Consultant | 1% |  | 7 | Original warrantees & guaranties | 3%
7 | Consultant | 1% |  | 8 | Original statutory permits & NOCs | 5%
8 | Contractor | 1% |  | 9 | List of keys & access cards | 2%
9 | Design Review/Lessons Learned & Recommendations | 20% |  | 10 | List of training | 3%
10 | Other Matters | 1% |  | 11 | Assets register | 5%
11 | Photographs | 5% |  | 12 | Health & safety file | 2%
Total |  | 40% |  | 13 | As-built specifications | 5%
|  |  |  | 14 | Sustainability targets | 5%
|  |  |  | 15 | Risk registry | 2%
|  |  |  | 16 | Quality control records | 3%
|  |  |  | Total |  | 60%
Musanada Template for preparing project close out report…to be used