## Dashboard
|  | PROGRESS AS ON |  |  |  |  | 2015-11-28
CLIENT:
CONSULTANT:
CONTRACTOR: BOJAMHOOR TRADING & CONTRACTING CO. W.L.L.
CONTRACT AMOUNT
PROJECT START DATE
PROJECT COMPLETION DATE
FORECASTED COMPLETION DATE | [12 empty] | 2016-10-14
DELAY IN CALENDAR DAYS |  | 0 | [10 empty] | 2016-11-27
45
[13 empty] | PLANNED PROGRESS (Baseline) | 31.29%
[13 empty] | PLANNED PROGRESS (Mitigation) | 20.61%
[13 empty] | ACTUAL PROGRESS (Mitigation) | 20.65%
[13 empty] | VARIANCE (Baseline) | -10.65%
[13 empty] | VARIANCE (Mitigation) | 0.04001%
[13 empty] | TOTAL AMOUNT | 139900000
B1-3rd FLOOR BEAMS & SLAB, 1F BLOCKWORK & GF-1F MEP WORKS, AREA-1, BUILDING-1 |  | B1-SHUTTERING ROOF FLOOR SLAB, 1F BLOCKWORK & GF-1F MEP WORKS AT AREA-2, BUILDING-1 | [6 empty] | B1-CASTED 3RD FLOOR COLUMNS, GF-1F MEP WORKS AT AREA-3, BUILDING-1 | B2-SHUTTERING FOR ROOF BEAM & SLAB, GF-RF BLOCKWORK & MEP WORK AT AREA-2, BUILDING-2 |  |  | INVOICED AMOUNT | 29471076.12
[13 empty] | REMAINING INVOICE | 110428923.88
[13 empty] | PROJECT DURATION | 731 | 2014-10-15 | 2016-10-14
[13 empty] | COMPLETED DURATION | 410 | 2014-10-15 | 2015-11-28
[13 empty] | REMAINING DURATION | 321
[14 empty] | PRELIMINARIES | B1-EARTHWORKS | B1-CONCRETE WORKS | B1-BLOCK WORKS | B1-THERMAL & WATERPROOFING | B1-MEP WORK | B1-FINISHES | B1-EXTERNAL WORK | B2-EARTHWORKS | B2-CONCRETE WORKS | B2-BLOCK WORKS | B2-THERMAL & WATERPROOFING | B2-FINISHES | B2-MEP WORK
[13 empty] | PLANNED | 64.44% | 100% | 88.53% | 98.38% | 11.06% | 9.18% | 3.103% | 7.982% | 100% | 62.11% | 23.07% | 25.99% | MEP Work | 0.5717%
[13 empty] | ACTUAL | 64.44% | 100% | 87.67% | 97.24% | 11.19% | 0.17% | 3.121% | 10.5% | 100% | 53.65% | 39.25% | 25.99% | 0.5717% | 1.328%
[14 empty] | 516235.5 | 516235 | 516235 | 516235 | Earthworks | 100% | 100%
[14 empty] | 12212416.81 | 10811782.25 | 9991237.78 | 10706755.7 | Concrete Works | 88.53% | 87.67%
[14 empty] | 2533503.5 | 280325.4 | 283431 | 283431 | Thermal & Moisture | 11.06% | 11.19%
[14 empty] | 1247312 | 1227080.3 | 1185573.7 | 1212880 | Solid Block | 98.38% | 97.24%
[14 empty] | 33494163.4 | 3074746.95 | 3280453.95 | 3574423.57 | MEP Work | 9.18% | 10.67%
[14 empty] | 14451176.3 | 448437 | 331096.49 | 451054.45 | Finishes | 3.103% | 3.121%
[14 empty] | 3213396.34 | 256479.8 | 303484.9 | 337360.3 | External Work | 7.982% | 10.5%
[14 empty] | 343304.5 | 343306 | 343306 | 343306 | Earthworks | 100% | 100%
[14 empty] | 7195046.1 | 4469059.822 | 3500596.2319 | 3860399.8335 | Concrete Works | 62.11% | 53.65%
[14 empty] | 1220475.3 | 317197 | 317197 | 317197 | Thermal & Moisture | 25.99% | 25.99%
[14 empty] | 678533.9 | 156554 | 252439.35 | 266350.25 | Solid Block | 23.07% | 39.25%
[14 empty] | 6367487.5 | 6296 | 4722 | 5036.8 | Finishes | 0.09888% | 0.0791%
[14 empty] | 12205282.98 | 69780.633 | 114967.5855 | 162101.495 | MEP Work | 0.5717% | 1.328%
0.64
0.6075
PLANNED (Baseline) | 1262 | 1218 | 1192 | 1183 | 1230 |  | 1215 | [5 empty] | 5207561.37
PLANNED (Mitigation) | 796 | 906 | 888 | 846 | 725 | 158 | 744
ACTUAL | 505 | 489 | 489 | 487 | 496 | 78 | 516
MONTH | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-28
[14 empty] | Planned | Submitted | Approved | Revised | Pending | Remaining | Total | Planned | Actual
|  | SHOP DRAWING | TOTAL NO | SUBMITTED | APPROVED | REVISE | PENDING | YET TO SUBMIT |  |  |  |  | Structural | 57 | 41 | 28 | 10 | 3 | 19 | 60 | 0.95 | 0.68333
|  |  | 329 | 321 | 257 | 36 | 28 | 8 |  |  |  |  | Architectural | 22 | 17 | 11 | 4 | 2 | 41 | 58 | 0.37931 | 0.2931
|  | CIVIL | 137 | 135 | 133 | 1 | 1 | 2 |  |  |  |  | Electrical | 25 | 15 | 4 | 7 | 4 | 74 | 89 | 0.2809 | 0.16854
|  | MECHANICAL | 104 | 100 | 71 | 24 | 5 | 4 |  |  |  |  | Plumbing | 19 | 11 | 5 | 6 | 0 | 24 | 35 | 0.54286 | 0.31429
|  | ELECTRICAL | 88 | 86 | 53 | 11 | 22 | 2 |  |  |  |  | Fire Fighting, Irrigation, Pool & Lift | 10 | 8 | 3 | 5 | 0 | 30 | 38 | 0.26316 | 0.21053
[13 empty] | Coordination | 1 | 2 | 0 | 2 | 0 | 9 | 11 | 0.090909 | 0.18182
[13 empty] | HVAC | 3 | 6 | 2 | 2 | 2 | 24 | 30 | 0.1 | 0.2
[13 empty] | Total | 137 | 100 | 53 | 36 | 11 | 221 | 321 | 0.42679 | 0.31153
|  | MATERIAL SUBMITTALS | SUBMITTED | APPROVED | REVISE | PENDING
|  | CIVIL | 76 | 74 | 2 | 0
|  | MECHANICAL | 92 | 92 | 0 | 0
|  | ELECTRICAL | 30 | 25 | 2 | 3
|  | INSPECTION REQUEST | SUBMITTED | APPROVED | NOT APPROVED | PENDING
|  | CIVIL | 1816 | 1388 | 391 | 37
|  | MECHANICAL | 161 | 142 | 12 | 7
|  | ELECTRICAL | 290 | 261 | 10 | 19
[11 empty] | 2011-09-24 | 2011-10-01 | 2011-10-08 | 40831 | 2011-10-22 | 2011-10-29 | 2011-11-05 | 2011-11-12 | 2011-11-19 | 2011-11-26 | 2011-12-03 | 2011-12-10 | 2011-12-17 | 2011-12-24 | 2011-12-31 | 2012-01-07 | 2012-01-14 | 2012-01-21 | 2012-01-28 | 2012-02-04 | 2012-02-11 | 2012-02-18 | 2012-02-25 | 2012-03-03 | 2012-03-10 | 2012-03-17 | 2012-03-24 | 2012-03-31 | 2012-04-07 | 2012-04-14 | 2012-04-21 | 2012-04-28 | 2012-05-05 | 2012-05-12 | 2012-05-19 | 2012-05-26 | 2012-06-02 | 2012-06-09 | 2012-06-16 | 2012-06-23 | 2012-06-30 | 2012-07-07 | 2012-07-14 | 2012-07-21 | 2012-07-28 | 2012-08-04 | 2012-08-11 | 2012-08-18 | 2012-08-25 | 2012-09-01 | 2012-09-08
[11 empty] | 131912 | 643706 | 1009481 | 1287969 | 1575605 | 1760830 | 1798664 | 1915218 | 2107058 | 2382238 | 2748007 | 3166664 | 3577564 | 3831357 | 4081048 | 4462728 | 5031673 | 5580053 | 6006644 | 6492527 | 7136994 | 7896556 | 8769271 | 9999343 | 11900695 | 13632742 | 14607153 | 15427008 | 16215317 | 16982353 | 17687641 | 18413613 | 19011308 | 19878546 | 20783856 | 21439221 | 21704978 | 21827606 | 22012669 | 22119833 | 22177198 | 22196382 | 22269461 | 22302596 | 22302596 | 22302596 | 22302596 | 22302596 | 22302596 | 22302596 | 22302596
ACTIVITY HIGHLIGHTS
1. EARTHWORK AT BUILDING-1
2. CONCRETE WORK AT BUILDING-1
3. WATERPROOFING AT BUILDING-1
4. BLOCKWORK AT BUILDING-1
5. MEP WORKS - BUILDING-1
6. FINISHES - BUILDING-1
7. EXTERNAL WORKS BUILDING-1
8. EARTHWORK AT BUILDING-2
9. CONCRETE WORK AT BUILDING-2
10. WATERPROOFING AT BUILDING-2
11. BLOCKWORK AT BUILDING-2
12. FINISHES - BUILDING-2
13. MEP WORKS BUILDING-2

## Cashflow
| 2014-10-12 | 2014-10-19 | 2014-10-26 | 2014-11-02 | 2014-11-09 | 2014-11-16 | 2014-11-23 | 2014-11-30 | 2014-12-07 | 2014-12-14 | 2014-12-21 | 2014-12-28 | 2015-01-04 | 2015-01-11 | 2015-01-18 | 2015-01-25 | 2015-02-01 | 2015-02-08 | 2015-02-15 | 2015-02-22 | 2015-03-01 | 2015-03-08 | 2015-03-15 | 2015-03-22 | 2015-03-29 | 2015-04-05 | 2015-04-12 | 2015-04-19 | 2015-04-26 | 2015-05-03 | 2015-05-10 | 2015-05-17 | 2015-05-24 | 2015-05-31 | 2015-06-07 | 2015-06-14 | 2015-06-21 | 2015-06-28 | 2015-07-05 | 2015-07-12 | 2015-07-19 | 2015-07-26 | 2015-08-02 | 2015-08-09 | 2015-08-16 | 2015-08-23 | 2015-08-30 | 2015-09-06 | 2015-09-13 | 2015-09-20 | 2015-09-27 | 2015-10-04 | 2015-10-11 | 2015-10-18 | 2015-10-25 | 2015-11-01 | 2015-11-08 | 2015-11-15 | 2015-11-22 | 2015-11-29 | 2015-12-06 | 2015-12-13 | 2015-12-20 | 2015-12-27 | 2016-01-03 | 2016-01-10 | 2016-01-17 | 2016-01-24 | 2016-01-31 | 2016-02-07 | 2016-02-14 | 2016-02-21 | 2016-02-28 | 2016-03-06 | 2016-03-13 | 2016-03-20 | 2016-03-27 | 2016-04-03 | 2016-04-10 | 2016-04-17 | 2016-04-24 | 2016-05-01 | 2016-05-08 | 2016-05-15 | 2016-05-22 | 2016-05-29 | 2016-06-05 | 2016-06-12 | 2016-06-19 | 2016-06-26 | 2016-07-03 | 2016-07-10 | 2016-07-17 | 2016-07-24 | 2016-07-31 | 2016-08-07 | 2016-08-14 | 2016-08-21 | 2016-08-28 | 2016-09-04 | 2016-09-11 | 2016-09-18 | 2016-09-25 | 2016-10-02 | 42652
Planned Mo. Cashflow | 45808.22 | 98625.92 | 144779.77 | 144779.77 | 1001922.63 | 1307856.69 | 440709.53 | 101389.98 | 101946.02 | 99242.47 | 107688.73 | 143518.65 | 165527.85 | 272470.38 | 407521.31 | 251602.5 | 274046.92 | 334133.96 | 363545.08 | 315390.49 | 302018.12 | 440206.05 | 462020.1 | 414514.7 | 269223.69 | 327511.15 | 354295.45 | 357575.07 | 417149.17 | 554927.95 | 727376 | 629920.31 | 820053.8 | 833984.73 | 852495.01 | 1125559.25 | 1157755.44 | 861627.08 | 1249373.58 | 1131367.69 | 580253.46 | 1184716.02 | 1913391.82 | 1362915.78 | 743358.23 | 739531.65 | 1034912.68 | 1003866.91 | 1048838.93 | 598639.68 | 834451.98 | 1253828.43 | 1277479.6 | 1659029.78 | 1987538.01 | 1977440.72 | 1699856.76 | 2133345.85 | 2060648.86 | 2279435.07 | 2166255.09 | 2296941.79 | 2563918.63 | 2716902.59 | 2744923.1 | 3601467.78 | 4276834.71 | 4400286.92 | 4019435.04 | 4769645.22 | 5257864.4 | 4789077.67 | 4391887.39 | 3341632.17 | 3316754.77 | 3175335.83 | 2880789.21 | 2381584.46 | 2381991.52 | 2953708.19 | 2909635.06 | 2818150.18 | 2666399.61 | 2870306.12 | 2392595.99 | 2286482.24 | 2348510.91 | 1627950.64 | 1169758.8 | 1190736.31 | 803055.97 | 587806.71 | 461214.24 | 436845.34 | 522553.67 | 487204.24 | 397270.72 | 231784.84 | 196057.39 | 103418.45 | 96682.03 | 119791.87 | 119591.53 | 102792.96 | 62760.27
Planned Mo. Cum. Cashflow | 45808.22 | 144434.14 | 289213.91 | 433993.68 | 1435916.31 | 2743773 | 3184482.53 | 3285872.51 | 3387818.53 | 3487061 | 3594749.73 | 3738268.38 | 3903796.23 | 4176266.61 | 4583787.92 | 4835390.42 | 5109437.34 | 5443571.3 | 5807116.38 | 6122506.87 | 6424524.99 | 6864731.04 | 7326751.14 | 7741265.84 | 8010489.53 | 8338000.68 | 8692296.13 | 9049871.2 | 9467020.37 | 10021948.32 | 10749324.32 | 11379244.63 | 12199298.43 | 13033283.16 | 13885778.17 | 15011337.42 | 16169092.86 | 17030719.94 | 18280093.52 | 19411461.21 | 19991714.67 | 21176430.69 | 23089822.51 | 24452738.29 | 25196096.52 | 25935628.17 | 26970540.85 | 27974407.76 | 29023246.69 | 29621886.37 | 30456338.35 | 31710166.78 | 32987646.38 | 34646676.16 | 36634214.17 | 38611654.89 | 40311511.65 | 42444857.5 | 44505506.36 | 46784941.43 | 48951196.52 | 51248138.31 | 53812056.94 | 56528959.53 | 59273882.63 | 62875350.41 | 67152185.12 | 71552472.04 | 75571907.08 | 80341552.3 | 85599416.7 | 90388494.37 | 94780381.76 | 98122013.93 | 101438768.7 | 104614104.53 | 107494893.74 | 109876478.2 | 112258469.72 | 115212177.91 | 118121812.97 | 120939963.15 | 123606362.76 | 126476668.88 | 128869264.87 | 131155747.11 | 133504258.02 | 135132208.66 | 136301967.46 | 137492703.77 | 138295759.74 | 138883566.45 | 139344780.69 | 139781626.03 | 140304179.7 | 140791383.94 | 141188654.66 | 141420439.5 | 141616496.89 | 141719915.34 | 141816597.37 | 141936389.24 | 142055980.77 | 142158773.73 | 142221534
Mitigation Mo. Cashflow | 45808.22 | 98625.92 | 144779.77 | 144779.77 | 1001922.63 | 1307856.69 | 440709.53 | 101389.98 | 101946.02 | 99242.47 | 107688.73 | 143518.65 | 165527.85 | 272470.38 | 407521.31 | 251602.5 | 274046.92 | 296237.96 | 355499.08 | 307344.49 | 276062.07 | 316609.35 | 159536.78 | 158277.81 | 106492.28 | 249209.66 | 164513.89 | 182737.79 | 304947.43 | 358920.41 | 283773.59 | 389589.68 | 309899.98 | 563205.33 | 416111.76 | 460683.7 | 547797.48 | 316488.5 | 320862.16 | 224390.05 | 229881.53 | 421547.15 | 517935.91 | 524304.23 | 497614.74 | 546478.62 | 607243.46 | 689472.15 | 445202.55 | 551576.66 | 564277.1 | 762616.9 | 1165244.23 | 1600819.98 | 1565129.03 | 1430043.46 | 1620274.54 | 1847791.74 | 1542471.1 | 1548548.09 | 1977559.5 | 2200552.31 | 2317423.01 | 2454830.61 | 2959593.44 | 4866809.74 | 4505032.17 | 3952426.94 | 5448956.03 | 5385659.63 | 5009673.59 | 4605550.15 | 4239264.27 | 5541464.2 | 6008507.79 | 4840463.59 | 4140554.69 | 4103139.54 | 4245019.35 | 4561888.88 | 4232052.82 | 3456283 | 2295461.49 | 1759259.75 | 2881573.43 | 3167398.98 | 2370329.99 | 2014820.07 | 1659590.48 | 1004151.43 | 372766.07 | 361801.54 | 486247.83 | 423931.08 | 276012.94 | 256274.35 | 204251.43 | 155544.4 | 113565.7 | 102582.52 | 97260.52 | 90213.98 | 81264.38 | 80164.38 | 57260.27
Mitigation Mo. Cum. Cashflow | 45808.22 | 144434.14 | 289213.91 | 433993.68 | 1435916.3 | 2743772.99 | 3184482.52 | 3285872.5 | 3387818.52 | 3487060.99 | 3594749.72 | 3738268.37 | 3903796.22 | 4176266.61 | 4583787.91 | 4835390.41 | 5109437.33 | 5405675.29 | 5761174.37 | 6068518.86 | 6344580.92 | 6661190.27 | 6820727.06 | 6979004.87 | 7085497.15 | 7334706.81 | 7499220.7 | 7681958.49 | 7986905.92 | 8345826.33 | 8629599.92 | 9019189.6 | 9329089.58 | 9892294.91 | 10308406.67 | 10769090.37 | 11316887.85 | 11633376.34 | 11954238.5 | 12178628.56 | 12408510.09 | 12830057.23 | 13347993.14 | 13872297.38 | 14369912.12 | 14916390.74 | 15523634.2 | 16213106.35 | 16658308.9 | 17209885.56 | 17774162.66 | 18536779.56 | 19702023.79 | 21302843.77 | 22867972.8 | 24298016.26 | 25918290.8 | 27766082.54 | 29308553.64 | 30857101.72 | 32834661.22 | 35035213.54 | 37352636.55 | 39807467.16 | 42767060.6 | 47633870.34 | 52138902.52 | 56091329.45 | 61540285.48 | 66925945.11 | 71935618.71 | 76541168.86 | 80780433.12 | 86321897.32 | 92330405.11 | 97170868.7 | 101311423.39 | 105414562.93 | 109659582.28 | 114221471.16 | 118453523.98 | 121909806.99 | 124205268.48 | 125964528.23 | 128846101.66 | 132013500.64 | 134383830.63 | 136398650.7 | 138058241.17 | 139062392.61 | 139435158.67 | 139796960.22 | 140283208.05 | 140707139.13 | 140983152.07 | 141239426.42 | 141443677.85 | 141599222.25 | 141712787.95 | 141815370.46 | 141912630.98 | 142002844.96 | 142084109.35 | 142164273.73 | 142221534
Actual Mo. Cashflow | 2014-10-12: 72303.4592; 2014-10-19: 125121.1592; 2014-10-26: 171275.0092; 2014-11-02: 171275.0092; 2014-11-09: 1028417.8692; 2014-11-16: 1334351.9292; 2014-11-23: 449516.7692; 2014-11-30: 106659.6192; 2014-12-07: 106659.6192; 2014-12-14: 106659.6192; 2014-12-21: 106659.6192; 2014-12-28: 106659.6192; 2015-01-04: 106659.6192; 2015-01-11: 133790.08; 2015-01-18: 129301.15; 2015-01-25: 133628.26; 2015-02-01: 364073.52; 2015-02-08: 276753.52; 2015-02-15: 680854.42; 2015-02-22: 278976.94; 2015-03-01: 253421.88; 2015-03-08: 290316.94; 2015-03-15: 209629.7977; 2015-03-22: 183223.2781; 2015-03-29: 227554.4544; 2015-04-05: 255998.7612; 2015-04-12: 213332.301; 2015-04-19: 213332.301; 2015-04-26: 284443.068; 2015-05-03: 227554.4544; 2015-05-10: 227554.4544; 2015-05-17: 341331.6816; 2015-05-24: 426664.602; 2015-05-31: 341331.6816; 2015-06-07: 497775.369; 2015-06-14: 511997.5224; 2015-06-21: 426664.602; 2015-06-28: 554663.9826; 2015-07-05: 468636.806; 2015-07-12: 406893.0896; 2015-07-19: 262242.3764; 2015-07-26: 540441.8292; 2015-08-02: 440886.7554; 2015-08-09: 469331.0622; 2015-08-16: 583108.2894; 2015-08-23: 511997.5224; 2015-08-30: 639996.903; 2015-09-06: 711107.67; 2015-09-13: 810662.7438; 2015-09-20: 739551.9768; 2015-09-27: 847594.4246; 2015-10-04: 850911.7499; 2015-10-11: 878970.7011; 2015-10-18: 1035888.2888; 2015-10-25: 1324503.0733; 2015-11-01: 1455440.4526; 2015-11-08: 1512843.0131; 2015-11-15: 1508913.8473; 2015-11-22: 1689140.1831
Actual Mo. Cum. Cashflow | 2014-10-12: 72303.4592; 2014-10-19: 197424.6185; 2014-10-26: 368699.6277; 2014-11-02: 539974.6369; 2014-11-09: 1568392.5062; 2014-11-16: 2902744.4354; 2014-11-23: 3352261.2046; 2014-11-30: 3458920.8238; 2014-12-07: 3565580.4431; 2014-12-14: 3672240.0623; 2014-12-21: 3778899.6815; 2014-12-28: 3885559.3008; 2015-01-04: 3992218.92; 2015-01-11: 4126009; 2015-01-18: 4255310.15; 2015-01-25: 4388938.41; 2015-02-01: 4753011.93; 2015-02-08: 5029765.45; 2015-02-15: 5710619.87; 2015-02-22: 5989596.81; 2015-03-01: 6243018.69; 2015-03-08: 6533335.63; 2015-03-15: 6742965.4277; 2015-03-22: 6926188.7058; 2015-03-29: 7153743.1602; 2015-04-05: 7409741.9214; 2015-04-12: 7623074.2224; 2015-04-19: 7836406.5234; 2015-04-26: 8120849.5914; 2015-05-03: 8348404.0458; 2015-05-10: 8575958.5002; 2015-05-17: 8917290.1818; 2015-05-24: 9343954.7838; 2015-05-31: 9685286.4654; 2015-06-07: 10183061.8344; 2015-06-14: 10695059.3568; 2015-06-21: 11121723.9588; 2015-06-28: 11676387.9414; 2015-07-05: 12145024.7474; 2015-07-12: 12551917.837; 2015-07-19: 12814160.2134; 2015-07-26: 13354602.0426; 2015-08-02: 13795488.798; 2015-08-09: 14264819.8602; 2015-08-16: 14847928.1496; 2015-08-23: 15359925.672; 2015-08-30: 15999922.575; 2015-09-06: 16711030.245; 2015-09-13: 17521692.9888; 2015-09-20: 18261244.9656; 2015-09-27: 19108839.3902; 2015-10-04: 19959751.1401; 2015-10-11: 20838721.8413; 2015-10-18: 21874610.1301; 2015-10-25: 23199113.2034; 2015-11-01: 24654553.656; 2015-11-08: 26167396.6691; 2015-11-15: 27676310.5164; 2015-11-22: 29365450.6995
Planned Mo. Progress % | 0.03221% | 0.06935% | 0.1018% | 0.1018% | 0.7045% | 0.9196% | 0.3099% | 0.07129% | 0.07168% | 0.06978% | 0.07572% | 0.1009% | 0.1164% | 0.1916% | 0.2865% | 0.1769% | 0.1927% | 0.2349% | 0.2556% | 0.2218% | 0.2124% | 0.3095% | 0.3249% | 0.2915% | 0.1893% | 0.2303% | 0.2491% | 0.2514% | 0.2933% | 0.3902% | 0.5114% | 0.4429% | 0.5766% | 0.5864% | 0.5994% | 0.7914% | 0.8141% | 0.6058% | 0.8785% | 0.7955% | 0.408% | 0.833% | 1.345% | 0.9583% | 0.5227% | 0.52% | 0.7277% | 0.7058% | 0.7375% | 0.4209% | 0.5867% | 0.8816% | 0.8982% | 1.167% | 1.397% | 1.39% | 1.195% | 1.5% | 1.449% | 1.603% | 1.523% | 1.615% | 1.803% | 1.91% | 1.93% | 2.532% | 3.007% | 3.094% | 2.826% | 3.354% | 3.697% | 3.367% | 3.088% | 2.35% | 2.332% | 2.233% | 2.026% | 1.675% | 1.675% | 2.077% | 2.046% | 1.982% | 1.875% | 2.018% | 1.682% | 1.608% | 1.651% | 1.145% | 0.8225% | 0.8372% | 0.5647% | 0.4133% | 0.3243% | 0.3072% | 0.3674% | 0.3426% | 0.2793% | 0.163% | 0.1379% | 0.07272% | 0.06798% | 0.08423% | 0.08409% | 0.07228% | 0.04413%
Planned Mo. Cum. Progress % | 0.03221% | 0.1016% | 0.2034% | 0.3052% | 1.01% | 1.929% | 2.239% | 2.31% | 2.382% | 2.452% | 2.528% | 2.628% | 2.745% | 2.936% | 3.223% | 3.4% | 3.593% | 3.828% | 4.083% | 4.305% | 4.517% | 4.827% | 5.152% | 5.443% | 5.632% | 5.863% | 6.112% | 6.363% | 6.657% | 7.047% | 7.558% | 8.001% | 8.578% | 9.164% | 9.763% | 10.55% | 11.37% | 11.97% | 12.85% | 13.65% | 14.06% | 14.89% | 16.24% | 17.19% | 17.72% | 18.24% | 18.96% | 19.67% | 20.41% | 20.83% | 21.41% | 22.3% | 23.19% | 24.36% | 25.76% | 27.15% | 28.34% | 29.84% | 31.29% | 32.9% | 34.42% | 36.03% | 37.84% | 39.75% | 41.68% | 44.21% | 47.22% | 50.31% | 53.14% | 56.49% | 60.19% | 63.55% | 66.64% | 68.99% | 71.32% | 73.56% | 75.58% | 77.26% | 78.93% | 81.01% | 83.05% | 85.04% | 86.91% | 88.93% | 90.61% | 92.22% | 93.87% | 95.02% | 95.84% | 96.68% | 97.24% | 97.65% | 97.98% | 98.28% | 98.65% | 98.99% | 99.27% | 99.44% | 99.57% | 99.65% | 99.72% | 99.8% | 99.88% | 99.96% | 100%
Mitigation Mo. Progress % | 0.03221% | 0.06935% | 0.1018% | 0.1018% | 0.7045% | 0.9196% | 0.3099% | 0.07129% | 0.07168% | 0.06978% | 0.07572% | 0.1009% | 0.1164% | 0.1916% | 0.2865% | 0.1769% | 0.1927% | 0.2083% | 0.25% | 0.2161% | 0.1941% | 0.2226% | 0.1122% | 0.1113% | 0.07488% | 0.1752% | 0.1157% | 0.1285% | 0.2144% | 0.2524% | 0.1995% | 0.2739% | 0.2179% | 0.396% | 0.2926% | 0.3239% | 0.3852% | 0.2225% | 0.2256% | 0.1578% | 0.1616% | 0.2964% | 0.3642% | 0.3687% | 0.3499% | 0.3842% | 0.427% | 0.4848% | 0.313% | 0.3878% | 0.3968% | 0.5362% | 0.8193% | 1.126% | 1.1% | 1.006% | 1.139% | 1.299% | 1.085% | 1.089% | 1.39% | 1.547% | 1.629% | 1.726% | 2.081% | 3.422% | 3.168% | 2.779% | 3.831% | 3.787% | 3.522% | 3.238% | 2.981% | 3.896% | 4.225% | 3.403% | 2.911% | 2.885% | 2.985% | 3.208% | 2.976% | 2.43% | 1.614% | 1.237% | 2.026% | 2.227% | 1.667% | 1.417% | 1.167% | 0.706% | 0.2621% | 0.2544% | 0.3419% | 0.2981% | 0.1941% | 0.1802% | 0.1436% | 0.1094% | 0.07985% | 0.07213% | 0.06839% | 0.06343% | 0.05714% | 0.05637% | 0.04026%
Mitigation Mo. Cum. Progress % | 0.03221% | 0.1016% | 0.2034% | 0.3052% | 1.01% | 1.929% | 2.239% | 2.31% | 2.382% | 2.452% | 2.528% | 2.628% | 2.745% | 2.936% | 3.223% | 3.4% | 3.593% | 3.801% | 4.051% | 4.267% | 4.461% | 4.684% | 4.796% | 4.907% | 4.982% | 5.157% | 5.273% | 5.401% | 5.616% | 5.868% | 6.068% | 6.342% | 6.56% | 6.956% | 7.248% | 7.572% | 7.957% | 8.18% | 8.405% | 8.563% | 8.725% | 9.021% | 9.385% | 9.754% | 10.1% | 10.49% | 10.92% | 11.4% | 11.71% | 12.1% | 12.5% | 13.03% | 13.85% | 14.98% | 16.08% | 17.08% | 18.22% | 19.52% | 20.61% | 21.7% | 23.09% | 24.63% | 26.26% | 27.99% | 30.07% | 33.49% | 36.66% | 39.44% | 43.27% | 47.06% | 50.58% | 53.82% | 56.8% | 60.7% | 64.92% | 68.32% | 71.23% | 74.12% | 77.1% | 80.31% | 83.29% | 85.72% | 87.33% | 88.57% | 90.6% | 92.82% | 94.49% | 95.91% | 97.07% | 97.78% | 98.04% | 98.3% | 98.64% | 98.94% | 99.13% | 99.31% | 99.45% | 99.56% | 99.64% | 99.71% | 99.78% | 99.85% | 99.9% | 99.96% | 100%
Actual Mo. Progress % | 2014-10-12: 0.05084%; 2014-10-19: 0.08798%; 2014-10-26: 0.1204%; 2014-11-02: 0.1204%; 2014-11-09: 0.7231%; 2014-11-16: 0.9382%; 2014-11-23: 0.3161%; 2014-11-30: 0.075%; 2014-12-07: 0.075%; 2014-12-14: 0.075%; 2014-12-21: 0.075%; 2014-12-28: 0.075%; 2015-01-04: 0.075%; 2015-01-11: 0.09407%; 2015-01-18: 0.09092%; 2015-01-25: 0.09396%; 2015-02-01: 0.256%; 2015-02-08: 0.1946%; 2015-02-15: 0.4787%; 2015-02-22: 0.1962%; 2015-03-01: 0.1782%; 2015-03-08: 0.2041%; 2015-03-15: 0.1474%; 2015-03-22: 0.1288%; 2015-03-29: 0.16%; 2015-04-05: 0.18%; 2015-04-12: 0.16%; 2015-04-19: 0.14%; 2015-04-26: 0.2%; 2015-05-03: 0.15%; 2015-05-10: 0.17%; 2015-05-17: 0.23%; 2015-05-24: 0.31%; 2015-05-31: 0.24%; 2015-06-07: 0.35%; 2015-06-14: 0.36%; 2015-06-21: 0.3%; 2015-06-28: 0.39%; 2015-07-05: 0.3295%; 2015-07-12: 0.2861%; 2015-07-19: 0.1844%; 2015-07-26: 0.38%; 2015-08-02: 0.31%; 2015-08-09: 0.33%; 2015-08-16: 0.41%; 2015-08-23: 0.36%; 2015-08-30: 0.45%; 2015-09-06: 0.5%; 2015-09-13: 0.57%; 2015-09-20: 0.52%; 2015-09-27: 0.596%; 2015-10-04: 0.5983%; 2015-10-11: 0.618%; 2015-10-18: 0.7284%; 2015-10-25: 0.9313%; 2015-11-01: 1.023%; 2015-11-08: 1.064%; 2015-11-15: 1.061%; 2015-11-22: 1.188%
Actual Mo. Cum. Progress % | 2014-10-12: 0.05084%; 2014-10-19: 0.1388%; 2014-10-26: 0.2592%; 2014-11-02: 0.3797%; 2014-11-09: 1.103%; 2014-11-16: 2.041%; 2014-11-23: 2.357%; 2014-11-30: 2.432%; 2014-12-07: 2.507%; 2014-12-14: 2.582%; 2014-12-21: 2.657%; 2014-12-28: 2.732%; 2015-01-04: 2.807%; 2015-01-11: 2.901%; 2015-01-18: 2.992%; 2015-01-25: 3.086%; 2015-02-01: 3.342%; 2015-02-08: 3.537%; 2015-02-15: 4.015%; 2015-02-22: 4.211%; 2015-03-01: 4.39%; 2015-03-08: 4.594%; 2015-03-15: 4.741%; 2015-03-22: 4.87%; 2015-03-29: 5.03%; 2015-04-05: 5.21%; 2015-04-12: 5.37%; 2015-04-19: 5.51%; 2015-04-26: 5.71%; 2015-05-03: 5.86%; 2015-05-10: 6.03%; 2015-05-17: 6.26%; 2015-05-24: 6.57%; 2015-05-31: 6.81%; 2015-06-07: 7.16%; 2015-06-14: 7.52%; 2015-06-21: 7.82%; 2015-06-28: 8.21%; 2015-07-05: 8.54%; 2015-07-12: 8.826%; 2015-07-19: 9.01%; 2015-07-26: 9.39%; 2015-08-02: 9.7%; 2015-08-09: 10.03%; 2015-08-16: 10.44%; 2015-08-23: 10.8%; 2015-08-30: 11.25%; 2015-09-06: 11.75%; 2015-09-13: 12.32%; 2015-09-20: 12.84%; 2015-09-27: 13.44%; 2015-10-04: 14.03%; 2015-10-11: 14.65%; 2015-10-18: 15.38%; 2015-10-25: 16.31%; 2015-11-01: 17.34%; 2015-11-08: 18.4%; 2015-11-15: 19.46%; 2015-11-22: 20.65%
[56 empty] | 0.2507% | 0.1752% | -0.06312% | 0.04001%
[56 empty] | -9.814% | -9.945% | -10.38% | -10.65%

## Baseline
Activity Name | time axis 2014-10-15 to 2016-10-13
MANPOWER | [9 empty] | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | [5 empty] | 11 | 11 | 11 | 11 |  | 11 | 11 | 11 | 11 | 11 | 11 |  | 11 | 11 | 11 | 11 | 11 | 17 |  | 17 | 17 | 17 | 17 | 17 |  |  | 17 | 17 | 17 | 17 | 17 | 17 |  | 34 | 34 | 34 | 36 | 36 | 61 |  | 85 | 80 | 80 | 88 | 60 | 60 |  | 79 | 123 | 120 | 115 | 102 | 102 |  | 98 | 107 | 107 | 111 | 117 | 97 |  | 91 | 71 | 71 | 76 | 95 | 89 |  | 81 | 91 | 88 | 84 | 79 | 98 |  | 76 | 86 | 132 | 111 | 118 | 99 |  | 77 | 85 | 110 | 113 | 114 | 155 |  | 112 | 129 | 146 | 156 | 115 | 150 |  | 177 | 156 | 168 | 195 | 163 | 159 |  | 150 | 143 | 141 | 106 | 100 | 108 |  | 120 | 134 | 101 | 126 | 121 | 133 |  | 146 | 155 | 157 | 149 | 117 | 188 |  | 135 | 114 | 119 | 124 | 87 | 87 |  | 86 | 88 | 104 | 79 | 107 | 138 |  | 137 | 93 | 75 | 75 | 51 | 54 |  | 86 | 81 | 69 | 68 | 73 | 75 |  | 69 | 68 | 98 | 81 | 71 | 91 |  | 108 | 180 | 205 | 178 | 176 | 166 |  | 181 | 181 | 172 | 129 | 214 | 274 |  | 334 | 307 | 265 | 234 | 234 | 234 |  | 160 | 110 | 159 | 138 | 219 | 180 |  | 205 | 226 | 220 | 262 | 264 | 275 |  | 227 | 254 | 252 | 410 | 392 | 450 |  | 413 | 406 | 438 | 368 | 312 | 245 |  | 217 | 243 | 198 | 207 | 270 | 234 |  | 314 | 339 | 325 | 299 | 360 | 432 |  | 546 | 599 | 583 | 558 | 558 | 558 |  | 491 | 318 | 285 | 340 | 435 | 433 | [5 empty] | 435 | 466 |  | 436 | 536 | 536 | 505 | 443 | 613 |  | 691 | 812 | 789 | 791 | 649 | 619 |  | 617 | 428 | 355 | 377 | 297 | 391 |  | 352 | 344 | 388 | 350 | 401 | 360 |  | 311 | 286 | 367 | 448 | 461 | 463 |  | 463 | 449 | 434 | 515 | 463 | 440 |  | 410 | 408 | 403 | 446 | 472 | 562 |  | 563 | 547 | 522 | 518 | 507 | 531 |  | 545 | 543 | 539 | 547 | [5 empty] | 529 | 529 | 573 | 548 |  | 604 | 582 | 607 | 641 | 668 | 725 |  | 768 | 815 | 782 | 798 | 848 | 816 |  | 836 | 800 | 820 | 838 | 822 | 872 |  | 893 | 941 | 993 | 1027 | 1068 | 1085 |  | 1078 | 1073 | 1078 | 1103 | 1141 | 1159 |  | 1136 | 1056 | 1028 | 1106 | 1120 | 1182 |  | 1153 | 1102 | 1086 | 1107 | 1108 | 1150 |  | 1234 | 1262 | 1218 | 1192 | 1183 | 1230 |  | 1215 | 1335 | 1340 | 1427 | 1456 | 1426 |  | 1433 | 1419 | 1401 | 1447 | 1402 | 1320 |  | 1355 | 1368 | 1320 | 1332 | 1300 | 1327 |  | 1350 | 1346 | 1404 | 1396 | 1346 | 1373 |  | 1404 | 1352 | 1402 | 1427 | 1473 | 1495 |  | 1591 | 1541 | 1570 | 1463 | 1470 | 1500 |  | 1611 | 1631 | 1692 | 1683 | 1682 | 1662 |  | 1662 | 1784 | 1776 | 1820 | 1833 | 1830 |  | 1812 | 1910 | 1886 | 1861 | 1944 | 1969 |  | 1918 | 1934 | 2022 | 1949 | 1906 | 2020 |  | 1864 | 1914 | 1893 | 1936 | 1856 | 1897 |  | 1820 | 1828 | 1847 | 1871 | 1931 | 1857 |  | 1819 | 1899 | 1895 | 1914 | 1929 | 1922 |  | 1900 | 1835 | 1747 | 1722 | 1725 | 1644 |  | 1623 | 1579 | 1472 | 1457 | 1440 | 1421 |  | 1399 | 1331 | 1343 | 1405 | 1523 | 1492 |  | 1513 | 1477 | 1502 | 1496 | 1448 | 1414 |  | 1415 | 1277 | 1216 | 1205 | 1276 | 1239 |  | 1194 | 1098 | 1099 | 1115 | 1122 | 1144 |  | 1147 | 1118 | 1153 | 1166 | 1185 | 1121 |  | 1147 | 1124 | 1160 | 1085 | 1071 | 1036 |  | 1036 | 991 | 987 | 973 | 962 | 904 |  | 946 | 928 | 959 | 1032 | 1068 | 1007 |  | 988 | 965 | 954 | 960 | 956 | 932 |  | 897 | 906 | 893 | 843 | 784 | 709 |  | 642 | 520 | 517 | 508 | 540 | 538 |  | 531 | 506 | 492 | 513 | 504 | 482 |  | 512 | 472 | 471 | 548 | 552 | 546 |  | 536 | 467 | 437 | 403 | 385 | 390 |  | 396 | 452 | 451 | 405 | 419 | 437 |  | 393 | 418 | 420 | 438 | 444 | 467 |  | 493 | 501 | 495 | 467 | 365 | [5 empty] | 351 | 335 | 323 |  | 285 | 255 | 213 | 203 | 186 | 181 |  | 165 | 153 | 153 | 153 | 153 | 152 |  | 152 | 154 | 154 | 154 | 154 | 154 |  | 154 | 154 | 154 | 154 | 154 | 124 |  | 124 | 124 | 111 | 111 | 101 | 101 |  | 96 | 42 | 42 | 42 | 42 | 42 |  | 42 | 42 | 53 | 53 | 53 | 59 |  | 67 | 67 | 67 | 67 | 37 | [5 empty] | 37 | 40 | 40 |  | 27 | 21 | 19 | 9 | 9 | 9 |  | 9 | 9 | 6 | 6 | 6 | 6 |  | 6 | 6 | 6 | 6 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4
Carpenter-Conc | 2014-10-24: 10; 2014-10-25: 10; 2014-10-26: 10; 2014-10-27: 10; 2014-10-28: 10; 2014-10-29: 10; 2014-10-30: 10; 2014-10-31: 10; 2014-11-01: 10; 2014-11-02: 10; 2014-11-03: 10; 2014-11-04: 10; 2014-11-05: 10; 2014-11-06: 10; 2014-11-07: 10; 2014-11-08: 10; 2014-11-09: 10; 2014-11-10: 10; 2014-11-11: 10; 2014-11-12: 10; 2014-11-13: 10; 2014-11-14: 10; 2014-11-15: 10; 2014-11-16: 10; 2014-11-17: 10; 2014-11-18: 10; 2015-01-11: 10; 2015-01-12: 10; 2015-01-13: 10; 2015-01-14: 10; 2015-01-15: 10; 2015-01-17: 10; 2015-01-18: 10; 2015-01-19: 10; 2015-01-20: 10; 2015-01-21: 13; 2015-01-22: 3; 2015-01-24: 3; 2015-01-25: 3; 2015-01-26: 3; 2015-01-27: 3; 2015-01-28: 13; 2015-01-29: 10; 2015-01-31: 10; 2015-02-01: 10; 2015-02-02: 10; 2015-02-03: 10; 2015-02-04: 10; 2015-02-05: 10; 2015-02-07: 10; 2015-02-08: 14; 2015-02-09: 14; 2015-02-10: 14; 2015-02-11: 18; 2015-02-12: 18; 2015-02-14: 18; 2015-02-15: 14; 2015-02-16: 14; 2015-02-17: 14; 2015-02-18: 10; 2015-02-19: 10; 2015-02-21: 4; 2015-02-22: 4; 2015-02-23: 4; 2015-02-24: 9; 2015-02-25: 5; 2015-02-26: 5; 2015-02-28: 15; 2015-03-01: 15; 2015-03-02: 15; 2015-03-03: 20; 2015-03-04: 20; 2015-03-05: 20; 2015-03-07: 20; 2015-03-08: 24; 2015-03-09: 19; 2015-03-10: 19; 2015-03-11: 9; 2015-03-12: 9; 2015-03-14: 21; 2015-03-15: 22; 2015-03-16: 17; 2015-03-17: 17; 2015-03-18: 17; 2015-03-19: 27; 2015-03-21: 27; 2015-03-22: 37; 2015-03-23: 40; 2015-03-24: 40; 2015-03-25: 28; 2015-03-26: 23; 2015-03-28: 23; 2015-03-29: 23; 2015-03-30: 25; 2015-03-31: 5; 2015-04-01: 5; 2015-04-02: 5; 2015-04-04: 7; 2015-04-05: 7; 2015-04-06: 7; 2015-04-07: 12; 2015-04-08: 10; 2015-04-09: 15; 2015-04-11: 10; 2015-04-12: 10; 2015-04-13: 10; 2015-04-14: 5; 2015-04-15: 5; 2015-04-16: 5; 2015-04-18: 5; 2015-04-19: 5; 2015-04-20: 5; 2015-04-21: 5; 2015-04-22: 5; 2015-04-23: 3; 2015-04-25: 3; 2015-04-26: 3; 2015-04-27: 3; 2015-04-28: 3; 2015-04-29: 1; 2015-04-30: 1; 2015-05-02: 8; 2015-05-03: 42; 2015-05-04: 50; 2015-05-05: 49; 2015-05-06: 49; 2015-05-07: 49; 2015-05-09: 49; 2015-05-10: 49; 2015-05-11: 49; 2015-05-12: 28; 2015-05-13: 78; 2015-05-14: 78; 2015-05-16: 70; 2015-05-17: 72; 2015-05-18: 60; 2015-05-19: 62; 2015-05-20: 62; 2015-05-21: 60; 2015-05-23: 23; 2015-05-24: 21; 2015-05-25: 21; 2015-05-26: 23; 2015-05-27: 50; 2015-05-28: 28; 2015-05-30: 61; 2015-05-31: 61; 2015-06-01: 62; 2015-06-02: 63; 2015-06-03: 63; 2015-06-04: 62; 2015-06-06: 46; 2015-06-07: 101; 2015-06-08: 68; 2015-06-09: 126; 2015-06-10: 125; 2015-06-11: 115; 2015-06-13: 115; 2015-06-14: 114; 2015-06-15: 114; 2015-06-16: 79; 2015-06-17: 79; 2015-06-18: 21; 2015-06-20: 20; 2015-06-21: 42; 2015-06-22: 23; 2015-06-23: 50; 2015-06-24: 50; 2015-06-25: 53; 2015-06-27: 80; 2015-06-28: 80; 2015-06-29: 80; 2015-06-30: 67; 2015-07-01: 121; 2015-07-02: 153; 2015-07-04: 153; 2015-07-05: 153; 2015-07-06: 145; 2015-07-07: 145; 2015-07-08: 146; 2015-07-09: 146; 2015-07-11: 110; 2015-07-12: 55; 2015-07-13: 46; 2015-07-14: 85; 2015-07-15: 125; 2015-07-16: 105; 2015-07-22: 104; 2015-07-23: 104; 2015-07-25: 104; 2015-07-26: 104; 2015-07-27: 104; 2015-07-28: 100; 2015-07-29: 68; 2015-07-30: 180; 2015-08-01: 182; 2015-08-02: 182; 2015-08-03: 185; 2015-08-04: 161; 2015-08-05: 126; 2015-08-06: 126; 2015-08-08: 132; 2015-08-09: 43; 2015-08-10: 47; 2015-08-11: 47; 2015-08-12: 45; 2015-08-13: 65; 2015-08-15: 50; 2015-08-16: 49; 2015-08-17: 51; 2015-08-18: 51; 2015-08-19: 46; 2015-08-20: 33; 2015-08-22: 33; 2015-08-23: 10; 2015-08-24: 66; 2015-08-25: 67; 2015-08-26: 67; 2015-08-27: 67; 2015-08-29: 65; 2015-08-30: 72; 2015-08-31: 71; 2015-09-01: 77; 2015-09-02: 18; 2015-09-03: 17; 2015-09-05: 11; 2015-09-06: 13; 2015-09-07: 7; 2015-09-08: 6; 2015-09-09: 7; 2015-09-10: 7; 2015-09-12: 5; 2015-09-13: 5; 2015-09-14: 5; 2015-09-15: 3; 2015-09-16: 11; 2015-09-17: 11; 2015-09-19: 13; 2015-09-20: 20; 2015-09-21: 19; 2015-09-22: 19; 2015-09-28: 19; 2015-09-29: 19; 2015-09-30: 19; 2015-10-01: 5; 2015-10-03: 10; 2015-10-04: 13; 2015-10-05: 19; 2015-10-06: 17; 2015-10-07: 31; 2015-10-08: 30; 2015-10-10: 39; 2015-10-11: 43; 2015-10-12: 46; 2015-10-13: 48; 2015-10-14: 50; 2015-10-15: 32; 2015-10-17: 32; 2015-10-18: 24; 2015-10-19: 18; 2015-10-20: 22; 2015-10-21: 23; 2015-10-22: 19; 2015-10-24: 17; 2015-10-25: 30; 2015-10-26: 41; 2015-10-27: 42; 2015-10-28: 45; 2015-10-29: 45; 2015-10-31: 45; 2015-11-01: 54; 2015-11-02: 55; 2015-11-03: 55; 2015-11-04: 54; 2015-11-05: 54; 2015-11-07: 44; 2015-11-08: 15; 2015-11-09: 9; 2015-11-10: 19; 2015-11-11: 32; 2015-11-12: 34; 2015-11-14: 35; 2015-11-15: 30; 2015-11-16: 30; 2015-11-17: 24; 2015-11-18: 24; 2015-11-19: 24; 2015-11-21: 34; 2015-11-22: 31; 2015-11-23: 23; 2015-11-24: 21; 2015-11-25: 20; 2015-11-26: 20; 2015-11-28: 16; 2015-11-29: 20; 2015-11-30: 30; 2015-12-01: 30; 2015-12-02: 30; 2015-12-03: 28; 2015-12-05: 32; 2015-12-06: 32; 2015-12-07: 32; 2015-12-08: 22; 2015-12-09: 23; 2015-12-10: 28; 2015-12-12: 29; 2015-12-13: 30; 2015-12-14: 29; 2015-12-15: 26; 2015-12-16: 14; 2015-12-17: 4; 2015-12-19: 15; 2015-12-20: 18; 2015-12-21: 29; 2015-12-22: 32; 2015-12-23: 30; 2015-12-24: 30; 2015-12-26: 42; 2015-12-27: 41; 2015-12-28: 61; 2015-12-29: 61; 2015-12-30: 60; 2015-12-31: 53; 2016-01-02: 57; 2016-01-03: 57; 2016-01-04: 57; 2016-01-05: 47; 2016-01-06: 47; 2016-01-07: 33; 2016-01-09: 33; 2016-01-10: 34; 2016-01-11: 37; 2016-01-12: 34; 2016-01-13: 34; 2016-01-14: 14; 2016-01-16: 14; 2016-01-17: 14; 2016-01-18: 14; 2016-01-19: 13; 2016-01-20: 11; 2016-01-21: 14; 2016-01-23: 14; 2016-01-24: 14; 2016-01-25: 14; 2016-01-26: 14; 2016-01-27: 14; 2016-01-28: 14; 2016-01-30: 3; 2016-02-18: 1; 2016-02-20: 4; 2016-02-21: 4; 2016-02-22: 4; 2016-02-23: 4; 2016-02-24: 4; 2016-02-25: 4; 2016-02-27: 4; 2016-02-28: 4; 2016-02-29: 4; 2016-03-01: 3; 2016-03-08: 1; 2016-03-09: 4; 2016-03-10: 5; 2016-03-12: 8; 2016-03-13: 8; 2016-03-14: 8; 2016-03-15: 8; 2016-03-16: 8; 2016-03-17: 8; 2016-03-19: 8; 2016-03-20: 8; 2016-03-21: 8; 2016-03-22: 7; 2016-03-23: 4; 2016-03-24: 4; 2016-03-26: 4; 2016-03-27: 6; 2016-03-28: 10; 2016-03-29: 10; 2016-03-30: 10; 2016-03-31: 9; 2016-04-02: 7; 2016-04-03: 8; 2016-04-04: 7; 2016-04-05: 6; 2016-04-06: 6; 2016-04-07: 5; 2016-04-09: 4; 2016-04-10: 3; 2016-04-11: 0; 2016-04-12: 1; 2016-04-13: 4; 2016-04-14: 4; 2016-04-16: 4; 2016-04-17: 4; 2016-04-18: 4; 2016-04-19: 4; 2016-04-20: 4; 2016-04-21: 4; 2016-04-23: 4; 2016-04-24: 3
Steel Fixer - Conc | 2014-10-24: 2; 2014-10-25: 2; 2014-10-26: 2; 2014-10-27: 2; 2014-10-28: 2; 2014-10-29: 2; 2014-10-30: 2; 2014-10-31: 2; 2014-11-01: 2; 2014-11-02: 2; 2014-11-03: 2; 2014-11-04: 2; 2014-11-05: 2; 2014-11-06: 2; 2014-11-07: 2; 2014-11-08: 2; 2014-11-09: 2; 2014-11-10: 2; 2014-11-11: 2; 2014-11-12: 2; 2014-11-13: 2; 2014-11-14: 2; 2014-11-15: 2; 2014-11-16: 2; 2014-11-17: 2; 2014-11-18: 2; 2015-01-11: 12; 2015-01-12: 12; 2015-01-13: 12; 2015-01-14: 12; 2015-01-15: 12; 2015-01-17: 12; 2015-01-18: 12; 2015-01-19: 12; 2015-01-20: 12; 2015-01-21: 12; 2015-01-22: 12; 2015-01-24: 12; 2015-01-25: 4; 2015-01-26: 4; 2015-01-27: 8; 2015-01-28: 8; 2015-01-29: 8; 2015-01-31: 8; 2015-02-01: 8; 2015-02-02: 8; 2015-02-03: 4; 2015-02-04: 4; 2015-02-05: 4; 2015-02-07: 4; 2015-02-09: 14; 2015-02-10: 14; 2015-02-11: 14; 2015-02-12: 14; 2015-02-14: 14; 2015-02-15: 14; 2015-02-16: 12; 2015-02-17: 12; 2015-02-18: 12; 2015-02-19: 12; 2015-02-21: 12; 2015-02-22: 12; 2015-02-25: 5; 2015-02-26: 9; 2015-02-28: 9; 2015-03-01: 9; 2015-03-02: 9; 2015-03-03: 9; 2015-03-04: 14; 2015-03-05: 16; 2015-03-07: 16; 2015-03-08: 16; 2015-03-09: 16; 2015-03-10: 12; 2015-03-11: 7; 2015-03-12: 15; 2015-03-14: 15; 2015-03-15: 17; 2015-03-16: 17; 2015-03-17: 15; 2015-03-18: 12; 2015-03-19: 20; 2015-03-21: 20; 2015-03-22: 18; 2015-03-23: 18; 2015-03-24: 12; 2015-03-25: 12; 2015-03-26: 10; 2015-03-28: 6; 2015-03-29: 2; 2015-03-30: 2; 2015-03-31: 2; 2015-04-01: 2; 2015-04-02: 2; 2015-04-04: 2; 2015-04-05: 2; 2015-04-06: 2; 2015-04-09: 2; 2015-04-11: 2; 2015-04-12: 2; 2015-04-13: 2; 2015-04-14: 2; 2015-04-15: 2; 2015-04-16: 2; 2015-04-18: 10; 2015-04-19: 10; 2015-04-20: 10; 2015-04-21: 8; 2015-04-22: 8; 2015-04-23: 10; 2015-04-25: 10; 2015-04-26: 10; 2015-04-27: 10; 2015-04-28: 10; 2015-04-29: 2; 2015-04-30: 6; 2015-05-02: 20; 2015-05-03: 20; 2015-05-04: 21; 2015-05-05: 21; 2015-05-06: 20; 2015-05-07: 20; 2015-05-09: 20; 2015-05-10: 20; 2015-05-11: 11; 2015-05-12: 8; 2015-05-13: 8; 2015-05-14: 41; 2015-05-16: 41; 2015-05-17: 36; 2015-05-18: 36; 2015-05-19: 36; 2015-05-20: 36; 2015-05-21: 36; 2015-05-23: 36; 2015-05-24: 18; 2015-05-25: 18; 2015-05-26: 21; 2015-05-27: 22; 2015-05-28: 37; 2015-05-30: 26; 2015-05-31: 26; 2015-06-01: 26; 2015-06-02: 26; 2015-06-03: 27; 2015-06-04: 20; 2015-06-06: 19; 2015-06-07: 5; 2015-06-08: 33; 2015-06-09: 45; 2015-06-10: 41; 2015-06-11: 68; 2015-06-13: 68; 2015-06-14: 68; 2015-06-15: 68; 2015-06-16: 68; 2015-06-17: 50; 2015-06-18: 50; 2015-06-20: 61; 2015-06-21: 33; 2015-06-22: 44; 2015-06-23: 22; 2015-06-24: 23; 2015-06-25: 31; 2015-06-27: 31; 2015-06-28: 31; 2015-06-29: 24; 2015-06-30: 24; 2015-07-01: 13; 2015-07-02: 43; 2015-07-04: 71; 2015-07-05: 67; 2015-07-06: 67; 2015-07-07: 67; 2015-07-08: 67; 2015-07-09: 67; 2015-07-11: 68; 2015-07-12: 45; 2015-07-13: 17; 2015-07-14: 46; 2015-07-15: 54; 2015-07-16: 63; 2015-07-22: 65; 2015-07-23: 64; 2015-07-25: 64; 2015-07-26: 64; 2015-07-27: 64; 2015-07-28: 44; 2015-07-29: 43; 2015-07-30: 43; 2015-08-01: 74; 2015-08-02: 102; 2015-08-03: 102; 2015-08-04: 102; 2015-08-05: 90; 2015-08-06: 84; 2015-08-08: 77; 2015-08-09: 68; 2015-08-10: 52; 2015-08-11: 24; 2015-08-12: 31; 2015-08-13: 32; 2015-08-15: 29; 2015-08-16: 20; 2015-08-17: 18; 2015-08-18: 17; 2015-08-19: 17; 2015-08-20: 17; 2015-08-22: 5; 2015-08-23: 6; 2015-08-24: 5; 2015-08-25: 33; 2015-08-26: 33; 2015-08-27: 32; 2015-08-29: 32; 2015-08-30: 32; 2015-08-31: 34; 2015-09-01: 34; 2015-09-02: 33; 2015-09-03: 3; 2015-09-05: 4; 2015-09-06: 6; 2015-09-07: 6; 2015-09-08: 7; 2015-09-09: 10; 2015-09-10: 9; 2015-09-12: 7; 2015-09-13: 7; 2015-09-14: 4; 2015-09-15: 4; 2015-09-16: 3; 2015-09-17: 5; 2015-09-19: 7; 2015-09-20: 8; 2015-09-21: 7; 2015-09-22: 7; 2015-09-28: 7; 2015-09-29: 7; 2015-09-30: 8; 2015-10-01: 8; 2015-10-03: 6; 2015-10-04: 9; 2015-10-05: 9; 2015-10-06: 7; 2015-10-07: 5; 2015-10-08: 14; 2015-10-10: 14; 2015-10-11: 27; 2015-10-12: 31; 2015-10-13: 34; 2015-10-14: 32; 2015-10-15: 30; 2015-10-17: 16; 2015-10-18: 16; 2015-10-19: 10; 2015-10-20: 6; 2015-10-21: 6; 2015-10-22: 3; 2015-10-24: 3; 2015-11-01: 4; 2015-11-02: 4; 2015-11-03: 4; 2015-11-04: 4; 2015-11-05: 4; 2015-11-07: 4; 2015-11-08: 4; 2015-11-09: 4; 2015-11-10: 3; 2015-11-11: 7; 2015-11-12: 9; 2015-11-14: 10; 2015-11-15: 10; 2015-11-16: 10; 2015-11-17: 10; 2015-11-18: 10; 2015-11-19: 10; 2015-11-21: 10; 2015-11-22: 7; 2015-11-23: 3; 2015-11-24: 1; 2015-12-05: 2; 2015-12-06: 2; 2015-12-07: 2; 2015-12-08: 2; 2015-12-09: 2; 2015-12-10: 2; 2015-12-12: 2; 2015-12-13: 2; 2015-12-14: 2; 2015-12-15: 2; 2016-03-27: 1; 2016-03-28: 1; 2016-03-29: 1; 2016-03-30: 1; 2016-03-31: 1; 2016-04-02: 1; 2016-04-03: 1; 2016-04-04: 1; 2016-04-05: 1; 2016-04-06: 1; 2016-04-07: 1; 2016-04-09: 1; 2016-04-10: 0
Mason - Conc | 2014-10-24: 2; 2014-10-25: 2; 2014-10-26: 2; 2014-10-27: 2; 2014-10-28: 2; 2014-10-29: 2; 2014-10-30: 2; 2014-10-31: 2; 2014-11-01: 2; 2014-11-02: 2; 2014-11-03: 2; 2014-11-04: 2; 2014-11-05: 2; 2014-11-06: 2; 2014-11-07: 2; 2014-11-08: 2; 2014-11-09: 2; 2014-11-10: 2; 2014-11-11: 2; 2014-11-12: 2; 2014-11-13: 2; 2014-11-14: 2; 2014-11-15: 2; 2014-11-16: 2; 2014-11-17: 2; 2014-11-18: 2; 2015-01-01: 14; 2015-01-03: 14; 2015-01-04: 14; 2015-01-05: 14; 2015-01-06: 14; 2015-01-18: 1; 2015-01-19: 1; 2015-01-20: 1; 2015-01-21: 1; 2015-01-22: 1; 2015-01-24: 1; 2015-01-25: 1; 2015-01-26: 1; 2015-02-03: 2; 2015-02-04: 2; 2015-02-05: 2; 2015-02-07: 2; 2015-02-08: 2; 2015-02-09: 8; 2015-02-16: 10; 2015-02-17: 11; 2015-02-18: 11; 2015-02-19: 19; 2015-02-21: 11; 2015-02-22: 17; 2015-02-23: 27; 2015-02-24: 27; 2015-02-25: 17; 2015-02-26: 15; 2015-02-28: 15; 2015-03-01: 10; 2015-03-02: 10; 2015-03-03: 15; 2015-03-04: 15; 2015-03-05: 15; 2015-03-07: 5; 2015-03-08: 5; 2015-03-09: 5; 2015-03-11: 10; 2015-03-12: 8; 2015-03-14: 10; 2015-03-15: 10; 2015-03-17: 10; 2015-03-18: 10; 2015-03-19: 2; 2015-03-21: 2; 2015-03-22: 2; 2015-03-23: 2; 2015-03-24: 2; 2015-03-25: 2; 2015-03-26: 17; 2015-03-28: 2; 2015-03-29: 2; 2015-03-30: 2; 2015-03-31: 17; 2015-04-01: 10; 2015-04-02: 10; 2015-04-09: 10; 2015-04-11: 20; 2015-04-18: 10; 2015-04-19: 10; 2015-04-20: 2; 2015-04-21: 2; 2015-04-22: 2; 2015-04-23: 6; 2015-04-25: 6; 2015-04-26: 10; 2015-04-27: 8; 2015-04-28: 4; 2015-04-29: 4; 2015-04-30: 10; 2015-05-03: 2; 2015-05-04: 10; 2015-05-06: 2; 2015-05-09: 10; 2015-05-10: 10; 2015-05-11: 20; 2015-05-12: 20; 2015-05-13: 10; 2015-05-16: 20; 2015-05-17: 10; 2015-05-18: 10; 2015-05-25: 10; 2015-05-27: 10; 2015-05-30: 2; 2015-05-31: 10; 2015-06-01: 8; 2015-06-02: 26; 2015-06-03: 26; 2015-06-04: 36; 2015-06-06: 29; 2015-06-07: 10; 2015-06-08: 10; 2015-06-09: 10; 2015-06-10: 10; 2015-06-11: 11; 2015-06-18: 10; 2015-06-21: 10; 2015-06-23: 10; 2015-06-24: 20; 2015-06-27: 10; 2015-06-28: 20; 2015-06-29: 20; 2015-06-30: 20; 2015-07-01: 10; 2015-07-02: 4; 2015-07-04: 19; 2015-07-05: 33; 2015-07-06: 33; 2015-07-07: 23; 2015-07-08: 23; 2015-07-09: 23; 2015-07-11: 23; 2015-07-12: 26; 2015-07-13: 40; 2015-07-14: 3; 2015-07-15: 3; 2015-07-16: 3; 2015-07-22: 3; 2015-07-23: 14; 2015-07-25: 3; 2015-07-26: 23; 2015-07-27: 23; 2015-07-28: 20; 2015-07-29: 21; 2015-08-01: 2; 2015-08-02: 12; 2015-08-03: 15; 2015-08-04: 15; 2015-08-05: 11; 2015-08-06: 9; 2015-08-08: 9; 2015-08-09: 11; 2015-08-10: 5; 2015-08-11: 25; 2015-08-12: 3; 2015-08-13: 3; 2015-08-16: 8; 2015-08-17: 22; 2015-08-18: 16; 2015-08-19: 30; 2015-08-20: 22; 2015-08-22: 28; 2015-08-23: 17; 2015-08-24: 6; 2015-08-25: 6; 2015-08-26: 4; 2015-08-27: 5; 2015-08-29: 6; 2015-08-30: 4; 2015-08-31: 6; 2015-09-01: 7; 2015-09-02: 2; 2015-09-03: 13; 2015-09-05: 3; 2015-09-06: 2; 2015-09-07: 2; 2015-09-08: 2; 2015-09-09: 4; 2015-09-10: 5; 2015-09-12: 12; 2015-09-13: 12; 2015-09-14: 14; 2015-09-15: 14; 2015-09-16: 4; 2015-09-17: 4; 2015-09-19: 6; 2015-09-20: 6; 2015-09-21: 4; 2015-09-22: 4; 2015-09-28: 6; 2015-09-29: 6; 2015-09-30: 6; 2015-10-01: 4; 2015-10-03: 14; 2015-10-04: 6; 2015-10-05: 6; 2015-10-06: 4; 2015-10-07: 5; 2015-10-08: 4; 2015-10-10: 4; 2015-10-11: 5; 2015-10-12: 5; 2015-10-13: 8; 2015-10-14: 10; 2015-10-15: 10; 2015-10-17: 20; 2015-10-18: 10; 2015-10-19: 16; 2015-10-20: 14; 2015-10-21: 10; 2015-10-22: 7; 2015-10-24: 7; 2015-10-25: 4; 2015-10-26: 4; 2015-10-27: 2; 2015-10-28: 2; 2015-10-29: 2; 2015-10-31: 2; 2015-11-01: 4; 2015-11-02: 4; 2015-11-03: 6; 2015-11-04: 6; 2015-11-05: 6; 2015-11-07: 6; 2015-11-08: 6; 2015-11-09: 6; 2015-11-10: 5; 2015-11-11: 13; 2015-11-12: 15; 2015-11-14: 18; 2015-11-15: 18; 2015-11-16: 18; 2015-11-17: 18; 2015-11-18: 18; 2015-11-19: 18; 2015-11-21: 16; 2015-11-22: 13; 2015-11-23: 9; 2015-11-24: 7; 2015-11-25: 6; 2015-11-26: 6; 2015-11-28: 6; 2015-11-29: 6; 2015-11-30: 6; 2015-12-01: 4; 2015-12-02: 4; 2015-12-03: 4; 2015-12-05: 8; 2015-12-06: 8; 2015-12-07: 8; 2015-12-08: 8; 2015-12-09: 8; 2015-12-10: 4; 2015-12-12: 8; 2015-12-13: 8; 2015-12-14: 12; 2015-12-15: 12; 2015-12-16: 8; 2015-12-17: 8; 2015-12-19: 12; 2015-12-20: 12; 2015-12-21: 16; 2015-12-22: 16; 2015-12-23: 16; 2015-12-24: 21; 2015-12-26: 24; 2015-12-27: 24; 2015-12-28: 24; 2015-12-29: 20; 2015-12-30: 20; 2015-12-31: 22; 2016-01-02: 24; 2016-01-03: 24; 2016-01-04: 24; 2016-01-05: 24; 2016-01-06: 24; 2016-01-07: 24; 2016-01-09: 24; 2016-01-10: 24; 2016-01-11: 19; 2016-01-12: 16; 2016-01-13: 16; 2016-01-14: 16; 2016-01-16: 12; 2016-01-17: 22; 2016-01-18: 16; 2016-01-19: 14; 2016-01-20: 14; 2016-01-21: 19; 2016-01-23: 15; 2016-01-24: 18; 2016-01-25: 18; 2016-01-26: 18; 2016-01-27: 17; 2016-01-28: 18; 2016-01-30: 18; 2016-01-31: 5; 2016-02-01: 5; 2016-02-02: 3; 2016-02-03: 2; 2016-02-04: 2; 2016-03-02: 4; 2016-03-03: 4; 2016-03-23: 2; 2016-03-24: 2; 2016-03-27: 1; 2016-03-28: 2; 2016-03-29: 2; 2016-03-30: 2; 2016-03-31: 2; 2016-04-02: 2; 2016-04-03: 2; 2016-04-04: 2; 2016-04-05: 2; 2016-04-06: 2; 2016-04-07: 2; 2016-04-09: 2; 2016-04-10: 1
Labour - BTCC | [9 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [43 empty] | 14 |  | 14 | 14 | 14 | 18 | 4 | 4 |  | 8 | 30 | 30 | 30 | 26 | 26 |  | 22 | 26 | 26 | 30 | 33 | 23 |  | 20 | 8 | 8 | 11 | 21 | 18 |  | 18 | 23 | 23 | 21 | 21 | 30 |  | 30 | 40 | 60 | 52 | 56 | 47 |  | 37 | 33 | 41 | 42 | 42 | 60 |  | 41 | 47 | 51 | 56 | 41 | 58 |  | 72 | 61 | 67 | 77 | 68 | 66 |  | 64 | 60 | 59 | 49 | 43 | 49 |  | 59 | 58 | 44 | 52 | 50 | 60 |  | 66 | 71 | 70 | 64 | 48 | 56 |  | 37 | 31 | 33 | 28 | 19 | 19 |  | 21 | 22 | 30 | 33 | 32 | 49 |  | 44 | 24 | 15 | 10 | 9 | 12 |  | 30 | 30 | 25 | 28 | 33 | 35 |  | 33 | 28 | 29 | 24 | 18 | 28 |  | 39 | 73 | 84 | 73 | 71 | 69 |  | 79 | 79 | 80 | 56 | 100 | 132 |  | 144 | 135 | 114 | 102 | 102 | 98 |  | 61 | 41 | 51 | 44 | 82 | 65 |  | 89 | 97 | 96 | 115 | 116 | 122 |  | 102 | 124 | 123 | 193 | 184 | 202 |  | 187 | 183 | 199 | 164 | 146 | 98 |  | 98 | 112 | 94 | 99 | 126 | 117 |  | 155 | 165 | 158 | 145 | 178 | 213 |  | 256 | 266 | 258 | 248 | 249 | 249 |  | 215 | 137 | 114 | 158 | 206 | 195 | [5 empty] | 196 | 206 |  | 196 | 231 | 231 | 217 | 185 | 276 |  | 309 | 347 | 334 | 325 | 264 | 256 |  | 255 | 159 | 141 | 133 | 113 | 160 |  | 142 | 140 | 154 | 147 | 156 | 135 |  | 113 | 106 | 150 | 180 | 178 | 182 |  | 181 | 176 | 162 | 196 | 163 | 156 |  | 140 | 147 | 150 | 164 | 177 | 219 |  | 234 | 231 | 214 | 212 | 209 | 211 |  | 195 | 188 | 186 | 190 | [5 empty] | 178 | 178 | 185 | 190 |  | 206 | 174 | 187 | 194 | 227 | 249 |  | 264 | 277 | 263 | 261 | 282 | 267 |  | 268 | 255 | 244 | 235 | 230 | 223 |  | 215 | 237 | 243 | 251 | 253 | 249 |  | 254 | 243 | 240 | 237 | 236 | 246 |  | 214 | 188 | 204 | 249 | 247 | 255 |  | 251 | 246 | 244 | 255 | 252 | 267 |  | 275 | 291 | 258 | 273 | 245 | 243 |  | 235 | 250 | 265 | 290 | 289 | 291 |  | 281 | 269 | 263 | 260 | 248 | 229 |  | 209 | 195 | 171 | 150 | 163 | 175 |  | 183 | 204 | 219 | 221 | 216 | 237 |  | 248 | 248 | 272 | 273 | 284 | 287 |  | 274 | 252 | 256 | 211 | 223 | 213 |  | 235 | 235 | 227 | 218 | 216 | 196 |  | 194 | 226 | 207 | 201 | 189 | 178 |  | 165 | 151 | 140 | 120 | 120 | 121 |  | 107 | 90 | 106 | 101 | 103 | 135 |  | 134 | 143 | 135 | 135 | 129 | 138 |  | 139 | 134 | 134 | 133 | 134 | 131 |  | 134 | 148 | 147 | 147 | 129 | 128 |  | 137 | 135 | 143 | 138 | 136 | 136 |  | 133 | 135 | 121 | 122 | 125 | 126 |  | 131 | 135 | 132 | 117 | 121 | 108 |  | 105 | 106 | 102 | 103 | 113 | 109 |  | 106 | 107 | 94 | 95 | 100 | 99 |  | 97 | 96 | 94 | 89 | 90 | 89 |  | 86 | 75 | 74 | 76 | 87 | 87 |  | 95 | 95 | 95 | 95 | 99 | 99 |  | 99 | 96 | 92 | 90 | 90 | 92 |  | 98 | 83 | 93 | 110 | 116 | 115 |  | 114 | 113 | 112 | 112 | 120 | 120 |  | 117 | 117 | 121 | 113 | 100 | 73 |  | 82 | 78 | 77 | 77 | 77 | 77 |  | 77 | 69 | 67 | 67 | 65 | 57 |  | 57 | 32 | 32 | 32 | 32 | 32 |  | 32 | 32 | 32 | 32 | 32 | 32 |  | 32 | 32 | 32 | 32 | 32 | 32 |  | 32 | 32 | 32 | 40 | 46 | 54 |  | 60 | 60 | 60 | 60 | 60 | [5 empty] | 60 | 60 | 65 |  | 65 | 65 | 65 | 65 | 57 | 51 |  | 43 | 37 | 37 | 37 | 37 | 39 |  | 39 | 39 | 39 | 39 | 39 | 39 |  | 39 | 39 | 39 | 39 | 39 | 39 |  | 39 | 39 | 32 | 32 | 32 | 32 |  | 32 | 15 | 15 | 15 | 15 | 15 |  | 15 | 15 | 15 | 15 | 15 | 15 |  | 15 | 15 | 15 | 15
Mason - Block | 2015-02-01: 5; 2015-02-02: 5; 2015-02-03: 5; 2015-02-04: 5; 2015-02-05: 5; 2015-02-07: 5; 2015-02-08: 5; 2015-02-09: 5; 2015-02-10: 5; 2015-02-11: 5; 2015-02-12: 5; 2015-02-14: 5; 2015-02-15: 5; 2015-02-16: 5; 2015-02-17: 5; 2015-02-18: 5; 2015-02-19: 5; 2015-02-26: 5; 2015-02-28: 5; 2015-03-01: 5; 2015-03-02: 5; 2015-03-03: 5; 2015-03-04: 5; 2015-03-05: 5; 2015-03-07: 5; 2015-03-08: 5; 2015-03-09: 5; 2015-03-14: 4; 2015-03-15: 4; 2015-03-16: 4; 2015-03-17: 4; 2015-03-18: 4; 2015-03-19: 4; 2015-03-21: 8; 2015-03-22: 8; 2015-03-23: 8; 2015-03-24: 8; 2015-03-25: 4; 2015-03-26: 4; 2015-03-28: 4; 2015-03-29: 4; 2015-03-30: 4; 2015-03-31: 4; 2015-06-15: 16; 2015-06-16: 16; 2015-06-17: 16; 2015-06-18: 16; 2015-06-20: 16; 2015-06-21: 16; 2015-06-22: 16; 2015-06-23: 16; 2015-06-24: 32; 2015-06-25: 32; 2015-06-27: 32; 2015-06-28: 32; 2015-06-29: 32; 2015-06-30: 32; 2015-07-01: 32; 2015-07-02: 16; 2015-07-04: 16; 2015-07-05: 16; 2015-07-06: 16; 2015-07-07: 16; 2015-07-08: 16; 2015-07-09: 16; 2015-07-11: 16; 2015-07-12: 16; 2015-07-13: 16; 2015-07-14: 26; 2015-07-15: 26; 2015-07-16: 26; 2015-07-22: 26; 2015-07-23: 26; 2015-07-25: 26; 2015-07-26: 41; 2015-07-27: 41; 2015-07-28: 51; 2015-07-29: 51; 2015-07-30: 51; 2015-08-01: 51; 2015-08-02: 51; 2015-08-03: 35; 2015-08-04: 50; 2015-08-05: 40; 2015-08-06: 40; 2015-08-08: 40; 2015-08-09: 40; 2015-08-10: 40; 2015-08-11: 40; 2015-08-12: 35; 2015-08-13: 50; 2015-08-15: 50; 2015-08-16: 50; 2015-08-17: 50; 2015-08-18: 50; 2015-08-19: 50; 2015-08-20: 50; 2015-08-22: 35; 2015-08-23: 51; 2015-08-24: 51; 2015-08-25: 51; 2015-08-26: 51; 2015-08-27: 51; 2015-08-29: 51; 2015-08-30: 41; 2015-08-31: 26; 2015-09-01: 32; 2015-09-02: 60; 2015-09-03: 72; 2015-09-05: 72; 2015-09-06: 72; 2015-09-07: 72; 2015-09-08: 72; 2015-09-09: 80; 2015-09-10: 102; 2015-09-12: 112; 2015-09-13: 112; 2015-09-14: 112; 2015-09-15: 112; 2015-09-16: 112; 2015-09-17: 112; 2015-09-19: 96; 2015-09-20: 85; 2015-09-21: 84; 2015-09-22: 84; 2015-09-28: 84; 2015-09-29: 84; 2015-09-30: 84; 2015-10-01: 84; 2015-10-03: 62; 2015-10-04: 40; 2015-10-05: 46; 2015-10-06: 56; 2015-10-07: 73; 2015-10-08: 84; 2015-10-10: 84; 2015-10-11: 84; 2015-10-12: 84; 2015-10-13: 68; 2015-10-14: 96; 2015-10-15: 112; 2015-10-17: 112; 2015-10-18: 112; 2015-10-19: 112; 2015-10-20: 112; 2015-10-21: 112; 2015-10-22: 106; 2015-10-24: 96; 2015-10-25: 98; 2015-10-26: 86; 2015-10-27: 86; 2015-10-28: 86; 2015-10-29: 86; 2015-10-31: 86; 2015-11-01: 46; 2015-11-02: 30; 2015-11-03: 30; 2015-11-04: 30; 2015-11-05: 60; 2015-11-07: 60; 2015-11-08: 72; 2015-11-09: 70; 2015-11-10: 80; 2015-11-11: 60; 2015-11-12: 60; 2015-11-14: 60; 2015-11-15: 60; 2015-11-16: 60; 2015-11-17: 70; 2015-11-18: 70; 2015-11-19: 70; 2015-11-21: 70; 2015-11-22: 90; 2015-11-23: 80; 2015-11-24: 92; 2015-11-25: 88; 2015-11-26: 80; 2015-11-28: 70; 2015-11-29: 70; 2015-11-30: 70; 2015-12-01: 70; 2015-12-02: 70; 2015-12-03: 70; 2015-12-05: 60; 2015-12-06: 60; 2015-12-07: 60; 2015-12-08: 60; 2015-12-09: 40; 2015-12-10: 20; 2015-12-12: 8; 2015-12-16: 10; 2015-12-17: 10; 2015-12-19: 10; 2015-12-20: 10; 2015-12-21: 10; 2015-12-22: 10; 2015-12-23: 10; 2015-12-24: 10; 2015-12-26: 10; 2015-12-27: 10; 2015-12-28: 10; 2015-12-29: 10; 2015-12-30: 10; 2015-12-31: 10
Mason - Plaster | 2015-06-14: 1; 2015-06-15: 1; 2015-06-16: 1; 2015-06-17: 1; 2015-06-18: 1; 2015-06-20: 1; 2015-06-21: 1; 2015-06-22: 1; 2015-06-23: 1; 2015-06-24: 1; 2015-06-25: 1; 2015-06-27: 1; 2015-06-28: 1; 2015-06-29: 1; 2015-06-30: 1; 2015-07-01: 1; 2015-07-11: 1; 2015-07-12: 1; 2015-07-13: 1; 2015-07-14: 1; 2015-07-15: 1; 2015-07-16: 1; 2015-07-22: 1; 2015-07-23: 1; 2015-07-25: 2; 2015-07-26: 2; 2015-07-27: 2; 2015-07-28: 2; 2015-07-29: 2; 2015-07-30: 2; 2015-08-01: 2; 2015-08-02: 2; 2015-08-03: 2; 2015-08-04: 2; 2015-08-05: 2; 2015-08-06: 2; 2015-08-08: 2; 2015-08-09: 2; 2015-08-10: 2; 2015-08-11: 2; 2015-08-12: 2; 2015-08-13: 13; 2015-08-15: 13; 2015-08-16: 13; 2015-08-17: 13; 2015-08-18: 13; 2015-08-19: 13; 2015-08-20: 13; 2015-08-22: 14; 2015-08-23: 25; 2015-08-24: 25; 2015-08-25: 25; 2015-08-26: 25; 2015-08-27: 29; 2015-08-29: 29; 2015-08-30: 29; 2015-08-31: 29; 2015-09-01: 31; 2015-09-02: 32; 2015-09-03: 32; 2015-09-05: 32; 2015-09-06: 36; 2015-09-07: 45; 2015-09-08: 59; 2015-09-09: 60; 2015-09-10: 60; 2015-09-12: 60; 2015-09-13: 58; 2015-09-14: 41; 2015-09-15: 41; 2015-09-16: 41; 2015-09-17: 41; 2015-09-19: 42; 2015-09-20: 39; 2015-09-21: 43; 2015-09-22: 47; 2015-09-28: 32; 2015-09-29: 32; 2015-09-30: 32; 2015-10-01: 32; 2015-10-03: 41; 2015-10-04: 41; 2015-10-05: 41; 2015-10-06: 41; 2015-10-07: 41; 2015-10-08: 41; 2015-10-10: 41; 2015-10-11: 41; 2015-10-12: 41; 2015-10-13: 50; 2015-10-14: 37; 2015-10-15: 22; 2015-10-17: 26; 2015-10-18: 26; 2015-10-19: 26; 2015-10-20: 26; 2015-10-21: 26; 2015-10-22: 31; 2015-10-24: 33; 2015-10-25: 33; 2015-10-26: 33; 2015-10-27: 37; 2015-10-28: 37; 2015-10-29: 37; 2015-10-31: 37; 2015-11-01: 37; 2015-11-02: 49; 2015-11-03: 44; 2015-11-04: 46; 2015-11-05: 50; 2015-11-07: 51; 2015-11-08: 52; 2015-11-09: 75; 2015-11-10: 88; 2015-11-11: 88; 2015-11-12: 88; 2015-11-14: 73; 2015-11-15: 73; 2015-11-16: 72; 2015-11-17: 80; 2015-11-18: 80; 2015-11-19: 89; 2015-11-21: 89; 2015-11-22: 89; 2015-11-23: 76; 2015-11-24: 80; 2015-11-25: 80; 2015-11-26: 86; 2015-11-28: 84; 2015-11-29: 84; 2015-11-30: 84; 2015-12-01: 88; 2015-12-02: 88; 2015-12-03: 92; 2015-12-05: 92; 2015-12-06: 101; 2015-12-07: 89; 2015-12-08: 81; 2015-12-09: 81; 2015-12-10: 81; 2015-12-12: 68; 2015-12-13: 68; 2015-12-14: 39; 2015-12-15: 35; 2015-12-16: 43; 2015-12-17: 63; 2015-12-19: 50; 2015-12-20: 66; 2015-12-21: 61; 2015-12-22: 61; 2015-12-23: 61; 2015-12-24: 61; 2015-12-26: 60; 2015-12-27: 60; 2015-12-28: 60; 2015-12-29: 60; 2015-12-30: 60; 2015-12-31: 60; 2016-01-02: 60; 2016-01-03: 60; 2016-01-04: 60; 2016-01-05: 46; 2016-01-06: 46; 2016-01-07: 46; 2016-01-09: 46; 2016-01-10: 46; 2016-01-11: 46; 2016-01-12: 46; 2016-01-13: 46; 2016-01-14: 46; 2016-01-16: 46; 2016-01-17: 62; 2016-01-18: 62; 2016-01-19: 62; 2016-01-20: 62; 2016-01-21: 40; 2016-01-23: 40; 2016-01-24: 28; 2016-01-25: 20; 2016-01-26: 20; 2016-01-27: 20; 2016-01-28: 19; 2016-01-30: 19; 2016-01-31: 19; 2016-02-01: 19; 2016-02-02: 19; 2016-02-03: 19; 2016-02-04: 17; 2016-02-06: 17; 2016-02-07: 17; 2016-02-08: 17; 2016-02-09: 17; 2016-02-10: 17; 2016-02-11: 17; 2016-02-13: 17; 2016-02-14: 17; 2016-02-15: 17; 2016-02-16: 17; 2016-02-17: 17; 2016-02-18: 17; 2016-02-20: 17; 2016-02-21: 17; 2016-02-22: 17; 2016-02-23: 17; 2016-02-24: 17; 2016-02-25: 17; 2016-02-27: 17; 2016-02-28: 17; 2016-02-29: 17; 2016-03-01: 17; 2016-03-02: 17; 2016-03-03: 17; 2016-03-05: 17; 2016-03-06: 17; 2016-03-07: 17; 2016-03-08: 17; 2016-03-09: 17; 2016-03-10: 17; 2016-03-12: 17; 2016-03-13: 17; 2016-03-14: 17; 2016-03-15: 17; 2016-03-16: 17; 2016-03-17: 17; 2016-03-19: 17; 2016-03-20: 17; 2016-03-21: 17; 2016-03-22: 17; 2016-03-23: 17; 2016-03-24: 17; 2016-03-26: 17; 2016-03-27: 17; 2016-03-28: 17; 2016-03-29: 17; 2016-03-30: 17; 2016-03-31: 17; 2016-04-02: 17; 2016-04-03: 17; 2016-04-04: 17; 2016-04-05: 17; 2016-04-06: 17; 2016-04-07: 17; 2016-04-09: 17; 2016-04-10: 17; 2016-04-11: 17; 2016-04-12: 17; 2016-04-13: 17; 2016-04-14: 17; 2016-04-16: 17; 2016-04-17: 17; 2016-04-18: 17; 2016-04-19: 17; 2016-04-20: 17; 2016-04-21: 17; 2016-04-23: 17; 2016-04-24: 17; 2016-04-25: 17; 2016-04-26: 17; 2016-04-27: 17; 2016-04-28: 17; 2016-04-30: 17; 2016-05-03: 17; 2016-05-04: 17; 2016-05-05: 17; 2016-05-07: 17; 2016-05-08: 17; 2016-05-09: 17; 2016-05-10: 17; 2016-05-11: 17; 2016-05-12: 17; 2016-05-14: 17; 2016-05-15: 17; 2016-05-16: 17; 2016-05-17: 17; 2016-05-18: 17; 2016-05-19: 17; 2016-05-21: 17; 2016-05-22: 17; 2016-05-23: 17; 2016-05-24: 17; 2016-05-25: 17; 2016-05-26: 17; 2016-05-28: 17; 2016-05-29: 17; 2016-05-30: 17; 2016-05-31: 17; 2016-06-01: 17; 2016-06-02: 17; 2016-06-04: 17; 2016-06-05: 17; 2016-06-06: 17; 2016-06-07: 17; 2016-06-08: 17; 2016-06-09: 17; 2016-06-11: 17; 2016-06-12: 17; 2016-06-13: 17; 2016-06-14: 17; 2016-06-15: 17; 2016-06-16: 17; 2016-06-18: 17; 2016-06-19: 17; 2016-06-20: 17; 2016-06-21: 17; 2016-06-22: 17; 2016-06-23: 17; 2016-06-25: 17; 2016-06-26: 17; 2016-06-27: 17; 2016-06-28: 17; 2016-06-29: 17; 2016-06-30: 17; 2016-07-02: 17; 2016-07-03: 17; 2016-07-04: 17; 2016-07-05: 17; 2016-07-06: 17; 2016-07-12: 17; 2016-07-13: 17; 2016-07-14: 17; 2016-07-16: 17; 2016-07-17: 17; 2016-07-18: 17; 2016-07-19: 17; 2016-07-20: 17; 2016-07-21: 17; 2016-07-23: 17; 2016-07-24: 17; 2016-07-25: 17; 2016-07-26: 17; 2016-07-27: 17; 2016-07-28: 17; 2016-07-30: 17; 2016-07-31: 17; 2016-08-01: 17; 2016-08-02: 17; 2016-08-03: 17; 2016-08-04: 17; 2016-08-06: 17; 2016-08-07: 17; 2016-08-08: 17; 2016-08-09: 17; 2016-08-10: 17; 2016-08-11: 17; 2016-08-13: 17; 2016-08-14: 17; 2016-08-15: 17; 2016-08-16: 17; 2016-08-17: 17; 2016-08-18: 17; 2016-08-20: 17
Painter - BTCC | 2015-01-06: 4; 2015-01-07: 4; 2015-01-08: 4; 2015-01-10: 4; 2015-01-11: 4; 2015-01-12: 4; 2015-01-13: 4; 2015-01-18: 3; 2015-01-19: 3; 2015-01-20: 3; 2015-01-21: 3; 2015-01-22: 3; 2015-02-05: 9; 2015-02-07: 9; 2015-02-08: 9; 2015-02-09: 9; 2015-02-10: 9; 2015-02-11: 9; 2015-02-18: 4; 2015-02-19: 14; 2015-02-21: 14; 2015-02-22: 14; 2015-02-23: 20; 2015-02-24: 20; 2015-02-25: 14; 2015-02-26: 24; 2015-02-28: 28; 2015-03-01: 22; 2015-03-02: 28; 2015-03-03: 28; 2015-03-04: 14; 2015-03-05: 10; 2015-03-07: 18; 2015-03-08: 10; 2015-03-09: 14; 2015-03-10: 18; 2015-03-11: 14; 2015-03-12: 14; 2015-03-14: 6; 2015-03-15: 2; 2015-03-16: 3; 2015-03-17: 3; 2015-03-18: 3; 2015-03-19: 3; 2015-03-21: 5; 2015-03-22: 2; 2015-03-23: 2; 2015-03-24: 2; 2015-03-25: 2; 2015-03-26: 2; 2015-03-28: 2; 2015-04-01: 2; 2015-04-02: 2; 2015-04-04: 12; 2015-04-05: 13; 2015-04-06: 21; 2015-04-07: 21; 2015-04-08: 21; 2015-04-09: 21; 2015-04-11: 11; 2015-04-12: 11; 2015-04-13: 2; 2015-04-14: 2; 2015-04-15: 2; 2015-04-16: 2; 2015-04-18: 2; 2015-04-19: 2; 2015-04-20: 6; 2015-04-21: 7; 2015-04-22: 7; 2015-04-23: 7; 2015-04-25: 3; 2015-04-26: 3; 2015-04-27: 6; 2015-04-28: 3; 2015-04-29: 9; 2015-04-30: 9; 2015-05-02: 9; 2015-05-03: 9; 2015-05-04: 3; 2015-05-05: 3; 2015-05-13: 4; 2015-05-14: 13; 2015-05-16: 13; 2015-05-17: 17; 2015-05-18: 8; 2015-05-19: 4; 2015-05-20: 4; 2015-06-04: 4; 2015-06-06: 8; 2015-06-07: 8; 2015-06-08: 12; 2015-06-09: 12; 2015-06-10: 8; 2015-06-11: 8; 2015-06-13: 4; 2015-09-01: 20; 2015-09-02: 20; 2015-09-03: 20; 2015-09-05: 20; 2015-09-06: 20; 2015-09-07: 20; 2015-09-08: 20; 2015-09-09: 20; 2015-09-10: 40; 2015-09-12: 40; 2015-09-13: 40; 2015-09-14: 40; 2015-09-15: 40; 2015-09-16: 40; 2015-09-17: 40; 2015-09-19: 35; 2015-09-20: 35; 2015-09-21: 35; 2015-09-22: 35; 2015-09-28: 35; 2015-09-29: 35; 2015-09-30: 35; 2015-10-01: 55; 2015-10-03: 75; 2015-10-04: 70; 2015-10-05: 70; 2015-10-06: 70; 2015-10-07: 70; 2015-10-08: 70; 2015-10-10: 70; 2015-10-11: 70; 2015-10-12: 55; 2015-10-13: 55; 2015-10-14: 55; 2015-10-15: 55; 2015-10-17: 55; 2015-10-18: 55; 2015-10-19: 50; 2015-10-20: 45; 2015-10-21: 50; 2015-10-22: 50; 2015-10-24: 50; 2015-10-25: 50; 2015-10-26: 50; 2015-10-27: 50; 2015-10-28: 50; 2015-10-29: 50; 2015-10-31: 50; 2015-11-01: 70; 2015-11-02: 70; 2015-11-03: 70; 2015-11-04: 70; 2015-11-05: 55; 2015-11-07: 40; 2015-11-08: 35; 2015-11-09: 36; 2015-11-10: 59; 2015-11-11: 59; 2015-11-12: 59; 2015-11-14: 59; 2015-11-15: 59; 2015-11-16: 58; 2015-11-17: 55; 2015-11-18: 51; 2015-11-19: 54; 2015-11-21: 54; 2015-11-22: 54; 2015-11-23: 54; 2015-11-24: 54; 2015-11-25: 38; 2015-11-26: 35; 2015-11-28: 25; 2015-11-29: 45; 2015-11-30: 45; 2015-12-01: 75; 2015-12-02: 75; 2015-12-03: 75; 2015-12-05: 78; 2015-12-06: 66; 2015-12-07: 72; 2015-12-08: 95; 2015-12-09: 95; 2015-12-10: 95; 2015-12-12: 93; 2015-12-13: 89; 2015-12-14: 97; 2015-12-15: 89; 2015-12-16: 79; 2015-12-17: 79; 2015-12-19: 69; 2015-12-20: 69; 2015-12-21: 69; 2015-12-22: 69; 2015-12-23: 69; 2015-12-24: 81; 2015-12-26: 71; 2015-12-27: 71; 2015-12-28: 71; 2015-12-29: 71; 2015-12-30: 73; 2015-12-31: 72; 2016-01-02: 72; 2016-01-03: 62; 2016-01-04: 71; 2016-01-05: 51; 2016-01-06: 55; 2016-01-07: 57; 2016-01-09: 57; 2016-01-10: 57; 2016-01-11: 49; 2016-01-12: 36; 2016-01-13: 39; 2016-01-14: 39; 2016-01-16: 39; 2016-01-17: 39; 2016-01-18: 31; 2016-01-19: 29; 2016-01-20: 25; 2016-01-21: 24; 2016-01-23: 24; 2016-01-24: 22; 2016-01-25: 19; 2016-01-26: 19; 2016-01-27: 19; 2016-01-28: 9; 2016-01-30: 9; 2016-01-31: 10; 2016-02-01: 28; 2016-02-02: 29; 2016-02-03: 47; 2016-02-04: 62; 2016-02-06: 62; 2016-02-07: 76; 2016-02-08: 69; 2016-02-09: 68; 2016-02-10: 63; 2016-02-11: 61; 2016-02-13: 61; 2016-02-14: 61; 2016-02-15: 61; 2016-02-16: 61; 2016-02-17: 64; 2016-02-18: 49; 2016-02-20: 49; 2016-02-21: 64; 2016-02-22: 79; 2016-02-23: 79; 2016-02-24: 64; 2016-02-25: 64; 2016-02-27: 79; 2016-02-28: 79; 2016-02-29: 94; 2016-03-01: 93; 2016-03-02: 90; 2016-03-03: 90; 2016-03-05: 90; 2016-03-06: 92; 2016-03-07: 92; 2016-03-08: 92; 2016-03-09: 92; 2016-03-10: 93; 2016-03-12: 96; 2016-03-13: 100; 2016-03-14: 100; 2016-03-15: 85; 2016-03-16: 83; 2016-03-17: 67; 2016-03-19: 64; 2016-03-20: 64; 2016-03-21: 64; 2016-03-22: 66; 2016-03-23: 72; 2016-03-24: 70; 2016-03-26: 70; 2016-03-27: 70; 2016-03-28: 55; 2016-03-29: 55; 2016-03-30: 55; 2016-03-31: 55; 2016-04-02: 55; 2016-04-03: 56; 2016-04-04: 56; 2016-04-05: 56; 2016-04-06: 56; 2016-04-07: 56; 2016-04-09: 54; 2016-04-10: 46; 2016-04-11: 46; 2016-04-12: 48; 2016-04-13: 56; 2016-04-14: 57; 2016-04-16: 65; 2016-04-17: 65; 2016-04-18: 65; 2016-04-19: 65; 2016-04-20: 67; 2016-04-21: 67; 2016-04-23: 67; 2016-04-24: 68; 2016-04-25: 69; 2016-04-26: 70; 2016-04-27: 71; 2016-04-28: 73; 2016-04-30: 79; 2016-05-01: 73; 2016-05-02: 77; 2016-05-03: 69; 2016-05-04: 69; 2016-05-05: 68; 2016-05-07: 67; 2016-05-08: 66; 2016-05-09: 65; 2016-05-10: 65; 2016-05-11: 66; 2016-05-12: 66; 2016-05-14: 66; 2016-05-15: 68; 2016-05-16: 74; 2016-05-17: 66; 2016-05-18: 49; 2016-05-19: 26; 2016-05-21: 41; 2016-05-22: 41; 2016-05-23: 40; 2016-05-24: 40; 2016-05-25: 40; 2016-05-26: 40; 2016-05-28: 40; 2016-05-29: 40; 2016-05-30: 40; 2016-05-31: 40; 2016-06-01: 38; 2016-06-02: 30; 2016-06-04: 30; 2016-06-05: 15; 2016-06-06: 15; 2016-06-07: 15; 2016-06-08: 15; 2016-06-09: 15; 2016-06-11: 15; 2016-06-12: 15; 2016-06-13: 15; 2016-06-14: 15; 2016-06-15: 15; 2016-06-16: 15; 2016-06-18: 15; 2016-06-19: 15; 2016-06-20: 15; 2016-06-21: 15; 2016-06-22: 15; 2016-06-23: 15; 2016-06-25: 15; 2016-06-26: 15; 2016-06-27: 15; 2016-06-28: 23; 2016-06-29: 29; 2016-06-30: 37; 2016-07-02: 43; 2016-07-03: 43; 2016-07-04: 43; 2016-07-05: 43; 2016-07-06: 43; 2016-07-12: 43; 2016-07-13: 43; 2016-07-14: 43; 2016-07-16: 43; 2016-07-17: 43; 2016-07-18: 43; 2016-07-19: 43; 2016-07-20: 35; 2016-07-21: 29; 2016-07-23: 21; 2016-07-24: 15; 2016-07-25: 15; 2016-07-26: 15; 2016-07-27: 15; 2016-07-28: 15; 2016-07-30: 15; 2016-07-31: 15; 2016-08-01: 15; 2016-08-02: 15; 2016-08-03: 15; 2016-08-04: 15; 2016-08-06: 15; 2016-08-07: 15; 2016-08-08: 15; 2016-08-09: 15; 2016-08-10: 15; 2016-08-11: 15; 2016-08-13: 15; 2016-08-14: 15; 2016-08-15: 15; 2016-08-16: 15; 2016-08-17: 15; 2016-08-18: 15; 2016-08-20: 15; 2016-08-21: 15; 2016-08-22: 15; 2016-08-23: 15; 2016-08-24: 15; 2016-08-25: 15; 2016-08-27: 15; 2016-08-28: 15; 2016-08-29: 15; 2016-08-30: 15; 2016-08-31: 15; 2016-09-01: 15; 2016-09-03: 15; 2016-09-04: 15; 2016-09-05: 15; 2016-09-06: 15
Mason - Tile Sitter | 2015-09-28: 2; 2015-09-29: 2; 2015-09-30: 8; 2015-10-01: 8; 2015-10-03: 8; 2015-10-04: 8; 2015-10-05: 8; 2015-10-06: 10; 2015-10-07: 10; 2015-10-08: 12; 2015-10-10: 18; 2015-10-11: 16; 2015-10-12: 10; 2015-10-13: 10; 2015-10-14: 10; 2015-10-15: 12; 2015-10-17: 13; 2015-10-18: 18; 2015-10-19: 18; 2015-10-20: 16; 2015-10-21: 10; 2015-10-22: 10; 2015-10-24: 12; 2015-10-25: 22; 2015-10-26: 29; 2015-10-27: 34; 2015-10-28: 33; 2015-10-29: 29; 2015-10-31: 34; 2015-11-01: 36; 2015-11-02: 36; 2015-11-03: 36; 2015-11-04: 34; 2015-11-05: 24; 2015-11-07: 17; 2015-11-08: 12; 2015-11-09: 12; 2015-11-10: 11; 2015-11-11: 15; 2015-11-12: 22; 2015-11-14: 30; 2015-11-15: 30; 2015-11-16: 30; 2015-11-17: 32; 2015-11-18: 33; 2015-11-19: 36; 2015-11-21: 36; 2015-11-22: 34; 2015-11-23: 29; 2015-11-24: 30; 2015-11-25: 22; 2015-11-26: 26; 2015-11-28: 34; 2015-11-29: 35; 2015-11-30: 41; 2015-12-01: 44; 2015-12-02: 42; 2015-12-03: 41; 2015-12-05: 36; 2015-12-06: 26; 2015-12-07: 26; 2015-12-08: 28; 2015-12-09: 35; 2015-12-10: 35; 2015-12-12: 38; 2015-12-13: 34; 2015-12-14: 28; 2015-12-15: 22; 2015-12-16: 30; 2015-12-17: 32; 2015-12-19: 38; 2015-12-20: 39; 2015-12-21: 44; 2015-12-22: 43; 2015-12-23: 39; 2015-12-24: 44; 2015-12-26: 44; 2015-12-27: 45; 2015-12-28: 49; 2015-12-29: 53; 2015-12-30: 65; 2015-12-31: 73; 2016-01-02: 64; 2016-01-03: 51; 2016-01-04: 48; 2016-01-05: 46; 2016-01-06: 54; 2016-01-07: 56; 2016-01-09: 65; 2016-01-10: 64; 2016-01-11: 65; 2016-01-12: 72; 2016-01-13: 67; 2016-01-14: 67; 2016-01-16: 69; 2016-01-17: 75; 2016-01-18: 70; 2016-01-19: 69; 2016-01-20: 63; 2016-01-21: 61; 2016-01-23: 52; 2016-01-24: 49; 2016-01-25: 49; 2016-01-26: 49; 2016-01-27: 51; 2016-01-28: 61; 2016-01-30: 58; 2016-01-31: 56; 2016-02-01: 54; 2016-02-02: 50; 2016-02-03: 35; 2016-02-04: 54; 2016-02-06: 55; 2016-02-07: 50; 2016-02-08: 49; 2016-02-09: 50; 2016-02-10: 49; 2016-02-11: 63; 2016-02-13: 65; 2016-02-14: 60; 2016-02-15: 60; 2016-02-16: 59; 2016-02-17: 57; 2016-02-18: 68; 2016-02-20: 68; 2016-02-21: 66; 2016-02-22: 51; 2016-02-23: 50; 2016-02-24: 48; 2016-02-25: 47; 2016-02-27: 41; 2016-02-28: 39; 2016-02-29: 28; 2016-03-01: 25; 2016-03-02: 25; 2016-03-03: 25; 2016-03-05: 46; 2016-03-06: 46; 2016-03-07: 32; 2016-03-08: 32; 2016-03-09: 32; 2016-03-10: 31; 2016-03-12: 30; 2016-03-13: 30; 2016-03-14: 27; 2016-03-15: 27; 2016-03-16: 32; 2016-03-17: 36; 2016-03-19: 36; 2016-03-20: 37; 2016-03-21: 33; 2016-03-22: 13; 2016-03-23: 18; 2016-03-24: 16; 2016-03-26: 25; 2016-03-27: 24; 2016-03-28: 22; 2016-03-29: 22; 2016-03-30: 26; 2016-03-31: 26; 2016-04-02: 26; 2016-04-03: 23; 2016-04-04: 22; 2016-04-05: 18; 2016-04-06: 19; 2016-04-07: 19; 2016-04-09: 20; 2016-04-10: 19; 2016-04-11: 20; 2016-04-12: 10; 2016-04-13: 10; 2016-04-14: 9; 2016-04-16: 9; 2016-04-17: 9; 2016-04-18: 9; 2016-04-19: 9; 2016-04-20: 11; 2016-04-21: 11; 2016-04-23: 11; 2016-04-24: 8; 2016-04-25: 6; 2016-04-26: 3; 2016-04-27: 2; 2016-04-28: 2; 2016-04-30: 2; 2016-05-01: 10; 2016-05-02: 16; 2016-05-03: 24; 2016-05-04: 30; 2016-05-05: 30; 2016-05-07: 30; 2016-05-08: 30; 2016-05-09: 30; 2016-05-10: 30; 2016-05-11: 29; 2016-05-12: 27; 2016-05-14: 24; 2016-05-15: 22; 2016-05-16: 20; 2016-05-17: 20; 2016-05-18: 14; 2016-05-19: 10; 2016-05-21: 4; 2016-07-14: 5; 2016-07-16: 5; 2016-07-17: 5; 2016-07-18: 5; 2016-07-19: 5; 2016-07-20: 5; 2016-07-21: 5; 2016-07-23: 5; 2016-07-24: 5; 2016-07-25: 5; 2016-07-26: 5; 2016-07-27: 5; 2016-07-28: 7; 2016-07-30: 7; 2016-07-31: 7; 2016-08-01: 7; 2016-08-02: 7; 2016-08-03: 7; 2016-08-04: 7; 2016-08-06: 7; 2016-08-07: 7; 2016-08-08: 7; 2016-08-09: 7; 2016-08-10: 7; 2016-08-11: 7; 2016-08-13: 7; 2016-08-14: 7
Heavy Equipment Operator | 2014-11-24: 7; 2014-11-25: 7; 2014-11-26: 7; 2014-11-27: 7; 2014-11-29: 7; 2014-11-30: 7; 2014-12-01: 7; 2014-12-02: 7; 2014-12-03: 7; 2014-12-04: 7; 2014-12-06: 7; 2014-12-07: 7; 2014-12-08: 7; 2014-12-09: 7; 2014-12-10: 7; 2014-12-11: 12; 2014-12-13: 12; 2014-12-14: 12; 2014-12-15: 12; 2014-12-16: 12; 2014-12-17: 12; 2014-12-20: 12; 2014-12-21: 12; 2014-12-22: 12; 2014-12-23: 12; 2014-12-24: 12; 2014-12-25: 12; 2014-12-27: 20; 2014-12-28: 20; 2014-12-29: 20; 2014-12-30: 14; 2014-12-31: 14; 2015-01-01: 19; 2015-01-03: 23; 2015-01-04: 18; 2015-01-05: 18; 2015-01-06: 18; 2015-01-07: 18; 2015-01-08: 18; 2015-01-10: 15; 2015-01-11: 15; 2015-01-12: 20; 2015-01-13: 19; 2015-01-14: 14; 2015-01-15: 14; 2015-01-17: 14; 2015-01-18: 14; 2015-01-19: 14; 2015-01-20: 14; 2015-01-21: 14; 2015-01-22: 14; 2015-01-24: 14; 2015-01-25: 14; 2015-01-26: 14; 2015-01-27: 14; 2015-01-28: 14; 2015-01-29: 14; 2015-01-31: 6; 2015-02-01: 6; 2015-02-02: 11; 2015-02-03: 11; 2015-02-04: 6; 2015-02-05: 6; 2015-02-07: 2; 2015-02-08: 2; 2015-02-09: 7; 2015-02-10: 2; 2015-02-11: 2; 2015-02-12: 2; 2015-02-15: 6; 2015-02-16: 17; 2015-02-17: 18; 2015-02-18: 18; 2015-02-19: 23; 2015-02-21: 18; 2015-02-22: 24; 2015-02-23: 35; 2015-02-24: 35; 2015-02-25: 24; 2015-02-26: 23; 2015-02-28: 23; 2015-03-01: 17; 2015-03-02: 17; 2015-03-03: 23; 2015-03-04: 17; 2015-03-05: 17; 2015-03-07: 12; 2015-03-08: 12; 2015-03-09: 12; 2015-03-11: 9; 2015-03-12: 5; 2015-03-14: 5; 2015-03-15: 11; 2015-03-16: 6; 2015-03-17: 15; 2015-03-18: 15; 2015-03-19: 8; 2015-03-21: 8; 2015-03-22: 8; 2015-03-23: 8; 2015-03-24: 8; 2015-03-25: 8; 2015-03-26: 38; 2015-03-28: 23; 2015-03-29: 17; 2015-03-30: 17; 2015-03-31: 32; 2015-04-01: 21; 2015-04-02: 21; 2015-04-04: 16; 2015-04-05: 16; 2015-04-06: 16; 2015-04-08: 17; 2015-04-09: 22; 2015-04-11: 31; 2015-04-12: 17; 2015-04-13: 17; 2015-04-14: 17; 2015-04-18: 5; 2015-04-19: 5; 2015-04-20: 1; 2015-04-21: 1; 2015-04-22: 1; 2015-04-23: 6; 2015-04-25: 6; 2015-04-26: 11; 2015-04-27: 26; 2015-04-28: 21; 2015-04-29: 21; 2015-04-30: 21; 2015-05-02: 16; 2015-05-03: 18; 2015-05-04: 21; 2015-05-05: 16; 2015-05-06: 18; 2015-05-07: 16; 2015-05-09: 7; 2015-05-10: 7; 2015-05-11: 12; 2015-05-12: 12; 2015-05-13: 9; 2015-05-16: 16; 2015-05-17: 7; 2015-05-18: 7; 2015-05-25: 9; 2015-05-27: 5; 2015-05-30: 2; 2015-05-31: 9; 2015-06-01: 10; 2015-06-02: 25; 2015-06-03: 25; 2015-06-04: 32; 2015-06-06: 24; 2015-06-07: 7; 2015-06-08: 7; 2015-06-09: 5; 2015-06-10: 5; 2015-06-11: 7; 2015-06-18: 9; 2015-06-21: 9; 2015-06-23: 9; 2015-06-24: 18; 2015-06-27: 5; 2015-06-28: 10; 2015-06-29: 10; 2015-06-30: 10; 2015-07-01: 5; 2015-07-02: 2; 2015-07-04: 10; 2015-07-05: 23; 2015-07-06: 23; 2015-07-07: 18; 2015-07-08: 18; 2015-07-09: 18; 2015-07-11: 18; 2015-07-12: 18; 2015-07-13: 31; 2015-07-23: 11; 2015-07-26: 10; 2015-07-27: 10; 2015-07-28: 10; 2015-07-29: 12; 2015-08-02: 5; 2015-08-03: 5; 2015-08-04: 5; 2015-08-05: 7; 2015-08-06: 4; 2015-08-08: 4; 2015-08-09: 7; 2015-08-11: 18; 2015-08-16: 9; 2015-08-17: 24; 2015-08-18: 18; 2015-08-19: 27; 2015-08-20: 18; 2015-08-22: 22; 2015-08-23: 10; 2015-08-24: 3; 2015-08-25: 5; 2015-08-26: 3; 2015-08-27: 5; 2015-08-29: 6; 2015-08-30: 3; 2015-08-31: 3; 2015-09-01: 3; 2015-09-03: 10; 2015-09-05: 1; 2015-09-10: 2; 2015-09-12: 5; 2015-09-13: 5; 2015-09-14: 5; 2015-09-15: 5; 2015-10-03: 9; 2015-10-07: 2; 2015-10-17: 9; 2015-10-19: 5; 2015-10-20: 4
Subcon - Excavation | 2014-11-24: 4; 2014-11-25: 4; 2014-11-26: 4; 2014-11-27: 4; 2014-11-29: 4; 2014-11-30: 4; 2014-12-01: 4; 2014-12-02: 4; 2014-12-03: 4; 2014-12-04: 4; 2014-12-06: 4; 2014-12-07: 4; 2014-12-08: 4; 2014-12-09: 4; 2014-12-10: 4; 2014-12-11: 5; 2014-12-13: 5; 2014-12-14: 5; 2014-12-15: 5; 2014-12-16: 5; 2014-12-17: 5; 2014-12-20: 5; 2014-12-21: 5; 2014-12-22: 5; 2014-12-23: 5; 2014-12-24: 5; 2014-12-25: 5; 2014-12-27: 14; 2014-12-28: 14; 2014-12-29: 14; 2014-12-30: 14; 2014-12-31: 14; 2015-01-01: 14; 2015-01-03: 34; 2015-01-04: 34; 2015-01-05: 34; 2015-01-06: 34; 2015-01-07: 34; 2015-01-08: 34; 2015-01-10: 44; 2015-01-11: 44; 2015-01-12: 44; 2015-01-13: 40; 2015-01-14: 40; 2015-01-15: 40; 2015-01-17: 40; 2015-01-18: 40; 2015-01-19: 40; 2015-01-20: 40; 2015-01-21: 40; 2015-01-22: 40; 2015-01-24: 40; 2015-01-25: 40; 2015-01-26: 40; 2015-01-27: 40; 2015-01-28: 40; 2015-01-29: 40; 2015-01-31: 30; 2015-02-01: 30; 2015-02-02: 30; 2015-02-03: 30; 2015-02-04: 30; 2015-02-05: 30; 2015-02-07: 10; 2015-02-08: 10; 2015-02-09: 10; 2015-02-10: 10; 2015-02-11: 10; 2015-02-12: 10
Subcon - Backfilling | 2015-02-15: 10; 2015-02-16: 10; 2015-02-17: 10; 2015-02-18: 10; 2015-02-19: 10; 2015-02-21: 10; 2015-02-22: 10; 2015-02-23: 10; 2015-02-24: 10; 2015-02-25: 10; 2015-02-26: 10; 2015-02-28: 10; 2015-03-01: 10; 2015-03-02: 10; 2015-03-03: 10; 2015-03-04: 10; 2015-03-05: 10; 2015-03-07: 10; 2015-03-08: 10; 2015-03-09: 10; 2015-03-15: 10; 2015-03-16: 10; 2015-03-17: 10; 2015-03-18: 10; 2015-03-19: 10; 2015-03-21: 10; 2015-03-22: 10; 2015-03-23: 10; 2015-03-24: 10; 2015-03-25: 10; 2015-03-26: 22; 2015-03-28: 22; 2015-03-29: 12; 2015-03-30: 12; 2015-03-31: 12; 2015-04-01: 12; 2015-04-02: 12; 2015-04-04: 12; 2015-04-05: 12; 2015-04-06: 12; 2015-04-08: 13; 2015-04-09: 13; 2015-04-11: 13; 2015-04-12: 23; 2015-04-13: 23; 2015-04-14: 33; 2015-04-15: 20; 2015-04-16: 20; 2015-04-18: 20; 2015-04-19: 20; 2015-04-20: 20; 2015-04-21: 10; 2015-04-22: 10; 2015-04-27: 12; 2015-04-28: 12; 2015-04-29: 12; 2015-04-30: 12; 2015-05-02: 12; 2015-05-03: 12; 2015-05-04: 12; 2015-05-05: 12; 2015-05-06: 12; 2015-05-07: 12; 2015-05-21: 10; 2015-05-23: 10; 2015-05-24: 20; 2015-05-25: 20; 2015-05-26: 20; 2015-05-27: 20; 2015-05-28: 20; 2015-05-30: 20; 2015-05-31: 10; 2015-06-01: 10
Subcon - Aluminium & Glass | 2015-11-23: 4; 2015-11-24: 20; 2015-11-25: 20; 2015-11-26: 20; 2015-11-28: 20; 2015-11-29: 24; 2015-11-30: 40; 2015-12-01: 40; 2015-12-02: 40; 2015-12-03: 40; 2015-12-05: 40; 2015-12-06: 40; 2015-12-07: 40; 2015-12-08: 40; 2015-12-09: 40; 2015-12-10: 40; 2015-12-12: 44; 2015-12-13: 61; 2015-12-14: 70; 2015-12-15: 86; 2015-12-16: 86; 2015-12-17: 86; 2015-12-19: 86; 2015-12-20: 86; 2015-12-21: 87; 2015-12-22: 92; 2015-12-23: 92; 2015-12-24: 87; 2015-12-26: 66; 2015-12-27: 66; 2015-12-28: 66; 2015-12-29: 66; 2015-12-30: 62; 2015-12-31: 50; 2016-01-02: 65; 2016-01-03: 61; 2016-01-04: 66; 2016-01-05: 66; 2016-01-06: 66; 2016-01-07: 66; 2016-01-09: 66; 2016-01-10: 66; 2016-01-11: 66; 2016-01-12: 64; 2016-01-13: 48; 2016-01-14: 43; 2016-01-16: 22; 2016-01-17: 22; 2016-01-18: 22; 2016-01-19: 22; 2016-01-20: 22; 2016-01-21: 22; 2016-01-23: 22; 2016-01-24: 22; 2016-01-25: 22; 2016-01-26: 26; 2016-01-27: 42; 2016-01-28: 46; 2016-01-30: 60; 2016-01-31: 60; 2016-02-01: 56; 2016-02-02: 40; 2016-02-03: 40; 2016-02-04: 40; 2016-02-06: 40; 2016-02-07: 40; 2016-02-08: 40; 2016-02-09: 40; 2016-02-10: 40; 2016-02-11: 36; 2016-02-13: 20; 2016-02-14: 24; 2016-02-15: 43; 2016-02-16: 60; 2016-02-17: 76; 2016-02-18: 79; 2016-02-20: 92; 2016-02-21: 92; 2016-02-22: 92; 2016-02-23: 92; 2016-02-24: 96; 2016-02-25: 112; 2016-02-27: 108; 2016-02-28: 92; 2016-02-29: 92; 2016-03-01: 92; 2016-03-02: 96; 2016-03-03: 109; 2016-03-05: 99; 2016-03-06: 112; 2016-03-07: 109; 2016-03-08: 96; 2016-03-09: 96; 2016-03-10: 96; 2016-03-12: 96; 2016-03-13: 96; 2016-03-14: 98; 2016-03-15: 102; 2016-03-16: 99; 2016-03-17: 88; 2016-03-19: 102; 2016-03-20: 102; 2016-03-21: 101; 2016-03-22: 97; 2016-03-23: 84; 2016-03-24: 84; 2016-03-26: 100; 2016-03-27: 96; 2016-03-28: 80; 2016-03-29: 76; 2016-03-30: 60; 2016-03-31: 60; 2016-04-02: 60; 2016-04-03: 56; 2016-04-04: 52; 2016-04-05: 62; 2016-04-06: 46; 2016-04-07: 46; 2016-04-09: 42; 2016-04-10: 42; 2016-04-11: 58; 2016-04-12: 62; 2016-04-13: 62; 2016-04-14: 60; 2016-04-16: 60; 2016-04-17: 60; 2016-04-18: 60; 2016-04-19: 56; 2016-04-20: 40; 2016-04-21: 40; 2016-04-23: 40; 2016-04-24: 44; 2016-04-25: 60; 2016-04-26: 62; 2016-04-27: 62; 2016-04-28: 62; 2016-04-30: 60; 2016-05-01: 60; 2016-05-02: 60; 2016-05-03: 60; 2016-05-04: 60; 2016-05-05: 56; 2016-05-07: 40; 2016-05-08: 40; 2016-05-09: 28; 2016-05-10: 20; 2016-05-11: 20; 2016-05-12: 20; 2016-05-14: 20; 2016-05-15: 20; 2016-05-16: 4
Subcon - Wooden Door | 2015-10-17: 3; 2015-10-18: 16; 2015-10-19: 16; 2015-10-20: 16; 2015-10-21: 16; 2015-10-22: 16; 2015-10-24: 16; 2015-10-25: 16; 2015-10-26: 19; 2015-10-27: 32; 2015-10-28: 30; 2015-10-29: 24; 2015-10-31: 24; 2015-11-01: 24; 2015-11-02: 24; 2015-11-03: 24; 2015-11-04: 24; 2015-11-05: 24; 2015-11-07: 22; 2015-11-08: 16; 2015-11-09: 14; 2015-11-10: 11; 2015-11-11: 27; 2015-11-12: 40; 2015-11-14: 40; 2015-11-15: 40; 2015-11-16: 40; 2015-11-17: 40; 2015-11-18: 38; 2015-11-19: 32; 2015-11-21: 36; 2015-11-22: 52; 2015-11-23: 50; 2015-11-24: 44; 2015-11-25: 48; 2015-11-26: 64; 2015-11-28: 64; 2015-11-29: 64; 2015-11-30: 67; 2015-12-01: 80; 2015-12-02: 80; 2015-12-03: 77; 2015-12-05: 58; 2015-12-06: 36; 2015-12-07: 36; 2015-12-08: 36; 2015-12-09: 32; 2015-12-10: 19; 2015-12-12: 36; 2015-12-13: 56; 2015-12-14: 72; 2015-12-15: 72; 2015-12-16: 72; 2015-12-17: 72; 2015-12-19: 72; 2015-12-20: 74; 2015-12-21: 80; 2015-12-22: 80; 2015-12-23: 77; 2015-12-24: 60; 2015-12-26: 40; 2015-12-27: 24; 2015-12-28: 24; 2015-12-29: 24; 2015-12-30: 24; 2015-12-31: 24; 2016-01-02: 28; 2016-01-03: 41; 2016-01-04: 28; 2016-01-05: 28; 2016-01-06: 28; 2016-01-07: 30; 2016-01-09: 36; 2016-01-10: 38; 2016-01-11: 44; 2016-01-12: 48; 2016-01-13: 60; 2016-01-14: 44; 2016-01-16: 46; 2016-01-17: 52; 2016-01-18: 52; 2016-01-19: 52; 2016-01-20: 52; 2016-01-21: 52; 2016-01-23: 60; 2016-01-24: 64; 2016-01-25: 42; 2016-01-26: 42; 2016-01-27: 42; 2016-01-28: 42; 2016-01-30: 50; 2016-01-31: 52; 2016-02-01: 52; 2016-02-02: 52; 2016-02-03: 52; 2016-02-04: 52; 2016-02-06: 52; 2016-02-07: 54; 2016-02-08: 62; 2016-02-09: 68; 2016-02-10: 68; 2016-02-11: 66; 2016-02-13: 60; 2016-02-14: 58; 2016-02-15: 52; 2016-02-16: 52; 2016-02-17: 52; 2016-02-18: 52; 2016-02-20: 50; 2016-02-21: 44; 2016-02-22: 44; 2016-02-23: 44; 2016-02-24: 42; 2016-02-25: 38; 2016-02-27: 36; 2016-02-28: 28; 2016-02-29: 34; 2016-03-01: 34; 2016-03-02: 34; 2016-03-03: 34; 2016-03-05: 26; 2016-03-06: 24; 2016-03-07: 24; 2016-03-08: 28; 2016-03-09: 50; 2016-03-10: 54; 2016-03-12: 54; 2016-03-13: 54; 2016-03-14: 51; 2016-03-15: 49; 2016-03-16: 76; 2016-03-17: 78; 2016-03-19: 82; 2016-03-20: 82; 2016-03-21: 82; 2016-03-22: 90; 2016-03-23: 94; 2016-03-24: 100; 2016-03-26: 100; 2016-03-27: 78; 2016-03-28: 74; 2016-03-29: 74; 2016-03-30: 74; 2016-03-31: 78; 2016-04-02: 83; 2016-04-03: 54; 2016-04-04: 46; 2016-04-05: 42; 2016-04-06: 42; 2016-04-07: 42; 2016-04-09: 34; 2016-04-10: 30; 2016-04-11: 24; 2016-04-12: 20; 2016-04-13: 20; 2016-04-14: 20; 2016-04-16: 20; 2016-04-17: 20; 2016-04-18: 16; 2016-04-24: 6; 2016-04-25: 10; 2016-04-26: 16; 2016-04-27: 20; 2016-04-28: 20; 2016-04-30: 21; 2016-05-01: 22; 2016-05-02: 23; 2016-05-03: 24; 2016-05-04: 24; 2016-05-05: 24; 2016-05-07: 24; 2016-05-08: 24; 2016-05-09: 24; 2016-05-10: 24; 2016-05-11: 18; 2016-05-12: 14; 2016-05-14: 8; 2016-05-15: 4; 2016-05-16: 4; 2016-05-17: 3; 2016-05-18: 2; 2016-05-19: 1
Subcon - Veneer MDF | 2015-10-07: 1; 2015-10-08: 4; 2015-10-10: 4; 2015-10-11: 4; 2015-10-12: 4; 2015-10-13: 3; 2015-10-17: 1; 2015-10-18: 4; 2015-10-19: 4; 2015-10-20: 4; 2015-10-21: 4; 2015-10-22: 3; 2015-10-28: 0; 2015-10-29: 2; 2015-10-31: 2; 2015-11-01: 2; 2015-11-02: 3; 2015-11-03: 6; 2015-11-04: 6; 2015-11-05: 6; 2015-11-07: 6; 2015-11-08: 3; 2015-11-17: 0; 2015-11-18: 2; 2015-11-19: 2; 2015-11-21: 2; 2015-11-22: 2; 2015-11-23: 2; 2015-11-24: 2; 2015-11-25: 2; 2015-11-26: 2; 2015-11-28: 0; 2015-11-29: 2; 2015-11-30: 2; 2015-12-01: 2; 2015-12-02: 2; 2015-12-03: 2; 2015-12-05: 2; 2015-12-06: 2; 2015-12-07: 2; 2015-12-08: 2; 2015-12-09: 2; 2015-12-10: 2; 2015-12-12: 2; 2015-12-13: 2; 2015-12-14: 2; 2015-12-15: 2; 2015-12-16: 2; 2015-12-26: 0; 2015-12-27: 2; 2015-12-28: 2; 2015-12-29: 4; 2015-12-30: 4; 2015-12-31: 4; 2016-01-02: 4; 2016-01-03: 5; 2016-01-04: 8; 2016-01-05: 6; 2016-01-06: 6; 2016-01-07: 4; 2016-01-09: 4; 2016-01-10: 5; 2016-01-11: 8; 2016-01-12: 7; 2016-01-13: 4; 2016-01-14: 4; 2016-01-16: 4; 2016-01-17: 4; 2016-01-18: 4; 2016-01-19: 3; 2016-01-26: 5; 2016-01-27: 8; 2016-01-28: 8; 2016-01-30: 8; 2016-01-31: 8; 2016-02-01: 12; 2016-02-02: 12; 2016-02-03: 8; 2016-02-04: 7; 2016-02-06: 12; 2016-02-07: 12; 2016-02-08: 12; 2016-02-09: 8; 2016-02-10: 8; 2016-02-11: 8; 2016-02-16: 4; 2016-02-17: 4; 2016-02-18: 4; 2016-02-20: 4; 2016-02-21: 4; 2016-02-22: 4; 2016-02-23: 4; 2016-02-25: 8; 2016-02-27: 8; 2016-02-28: 8; 2016-02-29: 8; 2016-03-01: 8; 2016-03-02: 8; 2016-03-07: 8; 2016-03-08: 8; 2016-03-09: 8; 2016-03-10: 8; 2016-03-12: 8; 2016-03-13: 8; 2016-03-21: 2; 2016-03-22: 8; 2016-03-23: 8; 2016-03-24: 8; 2016-03-26: 8; 2016-03-27: 8; 2016-03-28: 8; 2016-03-29: 8; 2016-03-30: 6; 2016-04-09: 2; 2016-04-10: 8; 2016-04-11: 10; 2016-04-12: 16; 2016-04-13: 16; 2016-04-14: 16; 2016-04-16: 16; 2016-04-17: 16; 2016-04-18: 14; 2016-04-19: 8; 2016-04-20: 6; 2016-05-09: 2; 2016-05-10: 3; 2016-05-11: 3; 2016-05-12: 3; 2016-05-14: 3; 2016-05-15: 3; 2016-05-16: 5; 2016-05-17: 6; 2016-05-18: 6; 2016-05-19: 6; 2016-05-21: 6; 2016-05-22: 6; 2016-05-23: 6; 2016-05-24: 6; 2016-05-25: 6; 2016-05-26: 4; 2016-05-28: 3; 2016-05-29: 3; 2016-05-30: 3; 2016-05-31: 3; 2016-06-01: 3; 2016-06-02: 1
Subcon - Toilet Cubicle | 2015-11-21: 2; 2015-11-22: 12; 2015-11-23: 12; 2015-11-24: 12; 2015-11-25: 12; 2015-11-26: 12; 2015-11-28: 12; 2015-11-29: 12; 2015-11-30: 12; 2015-12-01: 12; 2015-12-02: 12; 2015-12-03: 12; 2015-12-05: 12; 2015-12-06: 12; 2015-12-07: 12; 2015-12-08: 12; 2015-12-09: 10; 2015-12-15: 2; 2015-12-16: 12; 2015-12-17: 22; 2015-12-19: 22; 2015-12-20: 22; 2015-12-21: 22; 2015-12-22: 22; 2015-12-23: 22; 2015-12-24: 20; 2015-12-26: 10; 2016-01-04: 2; 2016-01-05: 10; 2016-01-06: 10; 2016-01-07: 10; 2016-01-09: 10; 2016-01-10: 10; 2016-01-11: 10; 2016-01-12: 10; 2016-01-13: 8; 2016-01-14: 2; 2016-01-16: 10; 2016-01-17: 10; 2016-01-18: 10; 2016-01-19: 10; 2016-01-20: 10; 2016-01-21: 10; 2016-01-23: 10; 2016-01-24: 8
Subcon - Kitchen Cabinet | 2015-11-09: 2; 2015-11-10: 10; 2015-11-11: 10; 2015-11-12: 10; 2015-11-14: 10; 2015-11-15: 10; 2015-11-16: 10; 2015-11-17: 10; 2015-11-18: 12; 2015-11-19: 20; 2015-11-21: 18; 2015-11-22: 10; 2015-11-23: 10; 2015-11-24: 10; 2015-11-25: 10; 2015-11-26: 10; 2015-11-28: 10; 2015-11-29: 10; 2015-11-30: 8; 2015-12-03: 4; 2015-12-05: 22; 2015-12-06: 30; 2015-12-07: 30; 2015-12-08: 30; 2015-12-09: 30; 2015-12-10: 30; 2015-12-12: 30; 2015-12-13: 30; 2015-12-14: 30; 2015-12-15: 26; 2015-12-16: 8; 2015-12-23: 4; 2015-12-24: 20; 2015-12-26: 20; 2015-12-27: 20; 2015-12-28: 20; 2015-12-29: 20; 2015-12-30: 20; 2015-12-31: 20; 2016-01-02: 20; 2016-01-03: 24; 2016-01-04: 36; 2016-01-05: 20; 2016-01-06: 20; 2016-01-07: 20; 2016-01-09: 20; 2016-01-10: 20; 2016-01-11: 20; 2016-01-12: 20; 2016-01-13: 20; 2016-01-14: 16; 2016-01-24: 2; 2016-01-25: 8; 2016-01-26: 9; 2016-01-27: 12; 2016-01-28: 12; 2016-01-30: 12; 2016-01-31: 12; 2016-02-01: 12; 2016-02-02: 12; 2016-02-03: 12; 2016-02-04: 12; 2016-02-06: 12; 2016-02-07: 10; 2016-02-11: 2; 2016-02-13: 8; 2016-02-14: 10; 2016-02-15: 20; 2016-02-16: 27; 2016-02-17: 34; 2016-02-18: 34; 2016-02-20: 36; 2016-02-21: 42; 2016-02-22: 42; 2016-02-23: 50; 2016-02-24: 58; 2016-02-25: 60; 2016-02-27: 56; 2016-02-28: 60; 2016-02-29: 50; 2016-03-01: 50; 2016-03-02: 58; 2016-03-03: 61; 2016-03-05: 58; 2016-03-06: 54; 2016-03-07: 54; 2016-03-08: 52; 2016-03-09: 36; 2016-03-10: 32; 2016-03-12: 24; 2016-03-13: 22; 2016-03-14: 24; 2016-03-15: 28; 2016-03-16: 10; 2016-03-17: 8; 2016-03-19: 8; 2016-03-20: 9; 2016-03-21: 12; 2016-03-22: 12; 2016-03-23: 12; 2016-03-24: 12; 2016-03-26: 12; 2016-03-27: 12; 2016-03-28: 12; 2016-03-29: 12; 2016-03-30: 12; 2016-03-31: 10; 2016-04-02: 1; 2016-04-03: 2; 2016-04-04: 3; 2016-04-05: 4; 2016-04-06: 4; 2016-04-07: 4; 2016-04-09: 4; 2016-04-10: 4; 2016-04-11: 4; 2016-04-12: 6; 2016-04-13: 8; 2016-04-14: 10; 2016-04-16: 12; 2016-04-17: 12; 2016-04-18: 12; 2016-04-19: 11; 2016-04-20: 10; 2016-04-21: 9; 2016-04-23: 8; 2016-04-24: 6; 2016-04-25: 4; 2016-04-26: 2
Subcon - Steel Door | 2015-11-16: 2; 2015-11-17: 8; 2015-11-18: 8; 2015-11-19: 8; 2015-11-21: 8; 2015-11-22: 8; 2015-11-23: 8; 2015-11-24: 8; 2015-11-25: 10; 2015-11-26: 16; 2015-11-28: 16; 2015-11-29: 16; 2015-11-30: 14; 2015-12-01: 8; 2015-12-02: 8; 2015-12-03: 8; 2015-12-05: 8; 2015-12-06: 8; 2015-12-07: 8; 2015-12-08: 8; 2015-12-09: 6; 2015-12-10: 3; 2015-12-12: 18; 2015-12-13: 24; 2015-12-14: 24; 2015-12-15: 24; 2015-12-16: 24; 2015-12-17: 24; 2015-12-19: 24; 2015-12-20: 24; 2015-12-21: 24; 2015-12-22: 21; 2015-12-23: 8; 2015-12-24: 8; 2015-12-26: 6; 2015-12-30: 3; 2015-12-31: 18; 2016-01-02: 26; 2016-01-03: 26; 2016-01-04: 26; 2016-01-05: 26; 2016-01-06: 26; 2016-01-07: 26; 2016-01-09: 26; 2016-01-10: 27; 2016-01-11: 29; 2016-01-12: 16; 2016-01-13: 16; 2016-01-14: 16; 2016-01-16: 16; 2016-01-17: 16; 2016-01-18: 16; 2016-01-19: 17; 2016-01-20: 20; 2016-01-21: 17; 2016-01-23: 6; 2016-01-24: 14; 2016-01-25: 14; 2016-01-26: 14; 2016-01-27: 14; 2016-01-28: 14; 2016-01-30: 14; 2016-01-31: 14; 2016-02-01: 12; 2016-02-02: 6; 2016-02-03: 14; 2016-02-04: 14; 2016-02-06: 13; 2016-02-07: 11; 2016-02-08: 14; 2016-02-09: 15; 2016-02-10: 18; 2016-02-11: 16; 2016-02-13: 8; 2016-02-14: 8; 2016-02-15: 8; 2016-02-16: 8; 2016-02-17: 8; 2016-02-18: 8; 2016-02-20: 8; 2016-02-21: 8; 2016-02-22: 8; 2016-02-23: 8; 2016-02-24: 9; 2016-02-25: 6; 2016-02-27: 5; 2016-02-28: 2; 2016-02-29: 2; 2016-03-01: 2; 2016-03-02: 4; 2016-03-03: 4; 2016-03-05: 4; 2016-03-06: 4; 2016-03-07: 2; 2016-03-08: 2; 2016-03-09: 2; 2016-03-10: 2; 2016-03-12: 2; 2016-03-13: 2; 2016-03-17: 6; 2016-03-19: 12; 2016-03-20: 12; 2016-03-21: 12; 2016-03-22: 12; 2016-03-23: 12; 2016-03-24: 24; 2016-03-26: 26; 2016-03-27: 26; 2016-03-28: 26; 2016-03-29: 26; 2016-03-30: 24; 2016-03-31: 24; 2016-04-02: 24; 2016-04-03: 24; 2016-04-04: 18; 2016-04-05: 10; 2016-04-06: 10; 2016-04-07: 10; 2016-04-09: 10; 2016-04-10: 10; 2016-04-11: 2; 2016-04-14: 2; 2016-04-16: 2; 2016-04-17: 2; 2016-04-18: 2; 2016-04-19: 2; 2016-04-20: 2; 2016-04-21: 2; 2016-04-23: 2; 2016-04-24: 2; 2016-04-25: 2; 2016-05-01: 6; 2016-05-02: 10; 2016-05-03: 16; 2016-05-04: 20; 2016-05-05: 20; 2016-05-07: 20; 2016-05-08: 20; 2016-05-09: 20; 2016-05-10: 20; 2016-05-11: 20; 2016-05-12: 14; 2016-05-14: 10; 2016-05-15: 4
Subcon - Steel Railing | 2015-11-09: 2; 2015-11-10: 8; 2015-11-11: 8; 2015-11-12: 8; 2015-11-14: 8; 2015-11-15: 8; 2015-11-16: 8; 2015-11-17: 8; 2015-11-18: 10; 2015-11-19: 16; 2015-11-21: 14; 2015-11-22: 8; 2015-11-23: 8; 2015-11-24: 8; 2015-11-25: 8; 2015-11-26: 8; 2015-11-28: 8; 2015-11-29: 8; 2015-11-30: 6; 2015-12-03: 2; 2015-12-05: 14; 2015-12-06: 20; 2015-12-07: 20; 2015-12-08: 20; 2015-12-09: 20; 2015-12-10: 20; 2015-12-12: 20; 2015-12-13: 20; 2015-12-14: 20; 2015-12-15: 18; 2015-12-16: 6; 2015-12-23: 2; 2015-12-24: 12; 2015-12-26: 12; 2015-12-27: 12; 2015-12-28: 12; 2015-12-29: 12; 2015-12-30: 12; 2015-12-31: 12; 2016-01-02: 12; 2016-01-03: 14; 2016-01-04: 22; 2016-01-05: 12; 2016-01-06: 12; 2016-01-07: 12; 2016-01-09: 12; 2016-01-10: 12; 2016-01-11: 12; 2016-01-12: 14; 2016-01-13: 20; 2016-01-14: 18; 2016-01-16: 8; 2016-01-17: 8; 2016-01-18: 8; 2016-01-19: 8; 2016-01-20: 8; 2016-01-21: 8; 2016-01-23: 8; 2016-01-24: 6; 2016-01-31: 2; 2016-02-01: 8; 2016-02-02: 10; 2016-02-03: 16; 2016-02-04: 16; 2016-02-06: 16; 2016-02-07: 16; 2016-02-08: 16; 2016-02-09: 16; 2016-02-10: 16; 2016-02-11: 14; 2016-02-13: 8; 2016-02-14: 6; 2016-02-16: 2; 2016-02-17: 8; 2016-02-18: 8; 2016-02-20: 8; 2016-02-21: 8; 2016-02-22: 8; 2016-02-23: 10; 2016-02-24: 16; 2016-02-25: 16; 2016-02-27: 16; 2016-02-28: 14; 2016-02-29: 8; 2016-03-01: 8; 2016-03-02: 8; 2016-03-03: 8; 2016-03-05: 8; 2016-03-06: 6; 2016-03-10: 2; 2016-03-12: 8; 2016-03-13: 8; 2016-03-14: 16; 2016-03-15: 18; 2016-03-16: 18; 2016-03-17: 18; 2016-03-19: 18; 2016-03-20: 18; 2016-03-21: 28; 2016-03-22: 26; 2016-03-23: 20; 2016-03-24: 20; 2016-03-26: 20; 2016-03-27: 20; 2016-03-28: 20; 2016-03-29: 20; 2016-03-30: 20; 2016-03-31: 20; 2016-04-02: 20; 2016-04-03: 20; 2016-04-04: 20; 2016-04-05: 20; 2016-04-06: 20; 2016-04-07: 20; 2016-04-09: 24; 2016-04-10: 24; 2016-04-11: 20; 2016-04-12: 20; 2016-04-13: 20; 2016-04-14: 20; 2016-04-16: 20; 2016-04-17: 20; 2016-04-18: 13; 2016-04-19: 11; 2016-04-20: 11; 2016-04-21: 11; 2016-04-23: 11; 2016-04-24: 11; 2016-04-25: 2; 2016-04-26: 2; 2016-04-27: 2; 2016-04-28: 2; 2016-04-30: 4; 2016-05-01: 4; 2016-05-02: 2; 2016-05-03: 2; 2016-05-04: 2; 2016-05-05: 2; 2016-05-07: 2; 2016-05-08: 2; 2016-05-09: 2; 2016-05-10: 2; 2016-05-11: 1; 2016-05-12: 1; 2016-05-14: 1; 2016-05-15: 1; 2016-05-16: 1; 2016-05-17: 1; 2016-07-21: 6; 2016-07-23: 6; 2016-07-24: 6; 2016-07-25: 6; 2016-07-26: 6; 2016-07-27: 6; 2016-07-28: 6; 2016-07-30: 6; 2016-07-31: 6; 2016-08-01: 6; 2016-09-01: 6; 2016-09-03: 6; 2016-09-04: 6; 2016-09-05: 6; 2016-09-06: 6; 2016-09-07: 6; 2016-09-13: 6; 2016-09-14: 6; 2016-09-15: 6; 2016-09-17: 6
Subcon - Structural Steel & Metal Decking | 2015-09-02: 20; 2015-09-03: 20; 2015-09-05: 32; 2015-09-06: 40; 2015-09-07: 40; 2015-09-08: 40; 2015-09-09: 40; 2015-09-10: 40; 2015-09-12: 40; 2015-09-13: 40; 2015-09-14: 40; 2015-09-15: 40; 2015-09-16: 40; 2015-09-17: 40; 2015-09-19: 40; 2015-09-20: 40; 2015-09-21: 40; 2015-09-22: 40; 2015-09-28: 40; 2015-09-29: 40; 2015-09-30: 40; 2015-10-01: 40; 2015-10-03: 40; 2015-10-04: 40; 2015-10-05: 40; 2015-10-06: 40; 2015-10-07: 20; 2015-10-08: 20; 2015-10-10: 8
Subcon - Vanity Counter | 2016-03-17: 6; 2016-03-19: 10; 2016-03-20: 10; 2016-03-21: 10; 2016-03-22: 10; 2016-03-23: 10; 2016-03-24: 18; 2016-03-26: 20; 2016-03-27: 20; 2016-03-28: 20; 2016-03-29: 20; 2016-03-30: 20; 2016-03-31: 20; 2016-04-02: 20; 2016-04-03: 20; 2016-04-04: 14; 2016-04-05: 10; 2016-04-06: 16; 2016-04-07: 20; 2016-04-09: 26; 2016-04-10: 30; 2016-04-11: 22; 2016-04-12: 20; 2016-04-13: 26; 2016-04-14: 36; 2016-04-16: 40; 2016-04-17: 40; 2016-04-18: 40; 2016-04-19: 40; 2016-04-20: 40; 2016-04-21: 40; 2016-04-23: 40; 2016-04-24: 34; 2016-04-25: 30; 2016-04-26: 24; 2016-04-27: 20; 2016-04-28: 20; 2016-04-30: 20; 2016-05-01: 14; 2016-05-02: 4
Subcon - False Ceiling | 2015-12-21: 10; 2015-12-22: 10; 2015-12-23: 10; 2015-12-24: 10; 2015-12-26: 10; 2015-12-27: 10; 2015-12-28: 10; 2015-12-29: 10; 2015-12-30: 10; 2015-12-31: 20; 2016-01-02: 20; 2016-01-03: 20; 2016-01-04: 20; 2016-01-05: 20; 2016-01-06: 28; 2016-01-07: 26; 2016-01-09: 46; 2016-01-10: 46; 2016-01-11: 46; 2016-01-12: 50; 2016-01-13: 50; 2016-01-14: 66; 2016-01-16: 76; 2016-01-17: 76; 2016-01-18: 62; 2016-01-19: 54; 2016-01-20: 70; 2016-01-21: 70; 2016-01-23: 70; 2016-01-24: 74; 2016-01-25: 74; 2016-01-26: 50; 2016-01-27: 58; 2016-01-28: 78; 2016-01-30: 98; 2016-01-31: 98; 2016-02-01: 78; 2016-02-02: 72; 2016-02-03: 88; 2016-02-04: 88; 2016-02-06: 80; 2016-02-07: 80; 2016-02-08: 92; 2016-02-09: 104; 2016-02-10: 88; 2016-02-11: 88; 2016-02-13: 80; 2016-02-14: 100; 2016-02-15: 76; 2016-02-16: 72; 2016-02-17: 72; 2016-02-18: 88; 2016-02-20: 104; 2016-02-21: 88; 2016-02-22: 88; 2016-02-23: 88; 2016-02-24: 108; 2016-02-25: 80; 2016-02-27: 80; 2016-02-28: 80; 2016-02-29: 96; 2016-03-01: 78; 2016-03-02: 72; 2016-03-03: 64; 2016-03-05: 64; 2016-03-06: 64; 2016-03-07: 56; 2016-03-08: 56; 2016-03-09: 60; 2016-03-10: 76; 2016-03-12: 60; 2016-03-13: 40; 2016-03-14: 52; 2016-03-15: 72; 2016-03-16: 94; 2016-03-17: 104; 2016-03-19: 102; 2016-03-20: 94; 2016-03-21: 105; 2016-03-22: 130; 2016-03-23: 148; 2016-03-24: 140; 2016-03-26: 140; 2016-03-27: 140; 2016-03-28: 142; 2016-03-29: 164; 2016-03-30: 171; 2016-03-31: 168; 2016-04-02: 164; 2016-04-03: 144; 2016-04-04: 146; 2016-04-05: 156; 2016-04-06: 156; 2016-04-07: 182; 2016-04-09: 176; 2016-04-10: 158; 2016-04-11: 147; 2016-04-12: 134; 2016-04-13: 130; 2016-04-14: 116; 2016-04-16: 98; 2016-04-17: 86; 2016-04-18: 79; 2016-04-19: 50; 2016-04-20: 50; 2016-04-21: 51; 2016-04-23: 53; 2016-04-24: 57; 2016-04-25: 49; 2016-04-26: 33; 2016-04-27: 33; 2016-04-28: 37; 2016-04-30: 37; 2016-05-01: 35; 2016-05-02: 35; 2016-05-03: 35; 2016-05-04: 35; 2016-05-05: 33; 2016-05-07: 32; 2016-05-08: 30; 2016-05-09: 32; 2016-05-10: 35; 2016-05-11: 31; 2016-05-12: 15; 2016-05-14: 16; 2016-05-15: 18; 2016-05-16: 20; 2016-05-17: 20; 2016-05-18: 21; 2016-05-19: 21; 2016-05-21: 18; 2016-05-22: 15; 2016-05-23: 16; 2016-05-24: 16; 2016-05-25: 18; 2016-05-26: 17; 2016-05-28: 15; 2016-05-29: 15; 2016-05-30: 17; 2016-05-31: 17; 2016-06-01: 17; 2016-06-02: 16; 2016-06-04: 16; 2016-06-05: 16; 2016-06-06: 15; 2016-06-07: 12; 2016-06-08: 12; 2016-06-09: 12; 2016-06-11: 12; 2016-06-12: 11; 2016-06-13: 8; 2016-06-14: 7; 2016-06-15: 6; 2016-06-16: 6; 2016-06-18: 5; 2016-06-19: 4; 2016-06-20: 3; 2016-06-21: 3; 2016-06-22: 4; 2016-06-23: 3; 2016-06-25: 3; 2016-06-26: 2; 2016-06-27: 2; 2016-06-28: 2; 2016-06-29: 1; 2016-06-30: 1; 2016-07-02: 0
Subcon - Landscape | 2016-04-04: 40; 2016-04-05: 40; 2016-04-06: 40; 2016-04-07: 40; 2016-04-09: 40; 2016-04-10: 40; 2016-04-11: 80; 2016-04-12: 93; 2016-04-13: 93; 2016-04-14: 93; 2016-04-16: 93; 2016-04-17: 93; 2016-04-18: 93; 2016-04-19: 93; 2016-04-20: 93; 2016-04-21: 53; 2016-04-23: 53; 2016-04-24: 53; 2016-04-25: 53; 2016-04-26: 53; 2016-04-27: 53; 2016-04-28: 13; 2016-04-30: 40; 2016-05-01: 40; 2016-05-02: 40; 2016-05-03: 40; 2016-05-04: 40; 2016-05-05: 40; 2016-05-07: 40; 2016-05-08: 40; 2016-05-09: 40; 2016-05-10: 40; 2016-05-11: 40; 2016-05-12: 40; 2016-05-14: 40; 2016-05-15: 40; 2016-05-16: 40; 2016-05-17: 40; 2016-05-18: 40; 2016-05-19: 40; 2016-05-21: 40; 2016-05-22: 40; 2016-05-23: 40; 2016-05-24: 40; 2016-05-25: 40; 2016-05-26: 40; 2016-05-28: 40; 2016-05-29: 40; 2016-05-30: 40; 2016-05-31: 40; 2016-06-01: 40; 2016-06-02: 40; 2016-06-04: 70; 2016-06-05: 70; 2016-06-06: 70; 2016-06-07: 70; 2016-06-08: 70; 2016-06-09: 70; 2016-06-11: 70; 2016-06-12: 70; 2016-06-13: 70; 2016-06-14: 70; 2016-06-15: 70; 2016-06-16: 70; 2016-06-18: 70; 2016-06-19: 70; 2016-06-20: 70; 2016-06-21: 50; 2016-06-22: 50; 2016-06-23: 50; 2016-06-25: 50; 2016-06-26: 50; 2016-06-27: 40; 2016-06-28: 40; 2016-06-29: 40; 2016-06-30: 40; 2016-07-02: 40; 2016-07-03: 40; 2016-07-04: 40; 2016-07-05: 40; 2016-07-06: 40; 2016-07-12: 40; 2016-07-13: 24; 2016-07-14: 24; 2016-07-16: 24; 2016-07-17: 24; 2016-07-18: 24; 2016-07-19: 34; 2016-07-20: 34; 2016-07-21: 34; 2016-07-23: 34; 2016-07-24: 34; 2016-07-25: 34; 2016-07-26: 34; 2016-07-27: 34; 2016-07-28: 34; 2016-07-30: 34; 2016-07-31: 50; 2016-08-01: 50; 2016-08-02: 50; 2016-08-03: 50; 2016-08-04: 50; 2016-08-06: 50; 2016-08-07: 50; 2016-08-08: 50; 2016-08-09: 50; 2016-08-10: 50; 2016-08-11: 20; 2016-08-13: 20; 2016-08-14: 20; 2016-08-15: 20; 2016-08-16: 20; 2016-08-17: 10; 2016-08-18: 10; 2016-08-20: 10; 2016-08-21: 10; 2016-08-22: 10; 2016-08-23: 10; 2016-08-24: 10; 2016-08-25: 10; 2016-08-27: 10; 2016-08-28: 10; 2016-08-29: 13; 2016-08-30: 13; 2016-08-31: 13; 2016-09-01: 13; 2016-09-03: 21; 2016-09-04: 21; 2016-09-05: 21; 2016-09-06: 21; 2016-09-07: 21; 2016-09-13: 21; 2016-09-14: 21; 2016-09-15: 21; 2016-09-17: 8; 2016-09-18: 8; 2016-09-19: 6; 2016-09-20: 6; 2016-09-21: 6; 2016-09-22: 6; 2016-09-24: 6; 2016-09-25: 6; 2016-09-26: 6; 2016-09-27: 6; 2016-09-28: 6; 2016-09-29: 6; 2016-10-01: 6; 2016-10-02: 6; 2016-10-03: 6; 2016-10-04: 6
Subcon - Mirror | 2016-04-14: 2; 2016-04-16: 4; 2016-04-17: 4; 2016-04-18: 4; 2016-04-19: 4; 2016-04-20: 4; 2016-04-21: 7; 2016-04-23: 8; 2016-04-24: 11; 2016-04-25: 13; 2016-04-26: 11; 2016-04-27: 9; 2016-04-28: 9; 2016-04-30: 9; 2016-05-01: 9; 2016-05-02: 9; 2016-05-03: 6; 2016-05-04: 5; 2016-05-05: 2; 2016-05-17: 3; 2016-05-18: 5; 2016-05-19: 5; 2016-05-21: 5; 2016-05-22: 5; 2016-05-23: 5; 2016-05-24: 5; 2016-05-25: 5; 2016-05-26: 5; 2016-05-28: 5; 2016-05-29: 2
Subcon - Electrical | 2015-05-16: 20; 2015-05-17: 20; 2015-05-18: 20; 2015-05-19: 20; 2015-05-20: 20; 2015-05-21: 20; 2015-05-23: 20; 2015-05-25: 20; 2015-05-26: 20; 2015-05-27: 20; 2015-05-28: 20; 2015-06-09: 20; 2015-06-10: 20; 2015-06-11: 40; 2015-06-13: 40; 2015-06-14: 40; 2015-06-15: 40; 2015-06-16: 40; 2015-06-17: 20; 2015-06-18: 40; 2015-06-20: 20; 2015-06-21: 20; 2015-06-22: 20; 2015-07-04: 20; 2015-07-05: 40; 2015-07-06: 40; 2015-07-07: 40; 2015-07-08: 40; 2015-07-09: 40; 2015-07-11: 40; 2015-07-12: 20; 2015-07-13: 20; 2015-07-14: 20; 2015-07-15: 20; 2015-07-16: 40; 2015-07-22: 40; 2015-07-23: 40; 2015-07-25: 40; 2015-07-26: 50; 2015-07-27: 50; 2015-07-28: 50; 2015-07-29: 50; 2015-07-30: 50; 2015-08-01: 50; 2015-08-02: 90; 2015-08-03: 90; 2015-08-04: 100; 2015-08-05: 80; 2015-08-06: 68; 2015-08-08: 68; 2015-08-09: 68; 2015-08-10: 28; 2015-08-11: 48; 2015-08-12: 38; 2015-08-13: 38; 2015-08-15: 38; 2015-08-16: 26; 2015-08-17: 26; 2015-08-18: 18; 2015-08-19: 28; 2015-08-20: 38; 2015-08-22: 28; 2015-08-23: 28; 2015-08-24: 28; 2015-08-25: 28; 2015-08-26: 48; 2015-08-27: 40; 2015-08-29: 40; 2015-08-30: 40; 2015-08-31: 50; 2015-09-01: 58; 2015-09-02: 58; 2015-09-03: 38; 2015-09-05: 38; 2015-09-06: 28; 2015-09-07: 18; 2015-09-08: 28; 2015-09-09: 28; 2015-09-10: 28; 2015-09-12: 18; 2015-09-13: 10; 2015-09-14: 10; 2015-09-15: 10; 2015-09-16: 10; 2015-09-17: 30; 2015-09-19: 60; 2015-09-20: 70; 2015-09-21: 70; 2015-09-22: 74; 2015-09-28: 80; 2015-09-29: 80; 2015-09-30: 80; 2015-10-01: 54; 2015-10-03: 60; 2015-10-04: 89; 2015-10-05: 89; 2015-10-06: 89; 2015-10-07: 91; 2015-10-08: 104; 2015-10-10: 109; 2015-10-11: 125; 2015-10-12: 115; 2015-10-13: 119; 2015-10-14: 125; 2015-10-15: 118; 2015-10-17: 114; 2015-10-18: 88; 2015-10-19: 104; 2015-10-20: 129; 2015-10-21: 116; 2015-10-22: 142; 2015-10-24: 152; 2015-10-25: 160; 2015-10-26: 176; 2015-10-27: 174; 2015-10-28: 176; 2015-10-29: 186; 2015-10-31: 166; 2015-11-01: 152; 2015-11-02: 148; 2015-11-03: 176; 2015-11-04: 176; 2015-11-05: 164; 2015-11-07: 154; 2015-11-08: 160; 2015-11-09: 144; 2015-11-10: 148; 2015-11-11: 142; 2015-11-12: 148; 2015-11-14: 140; 2015-11-15: 124; 2015-11-16: 120; 2015-11-17: 112; 2015-11-18: 132; 2015-11-19: 144; 2015-11-21: 158; 2015-11-22: 152; 2015-11-23: 161; 2015-11-24: 156; 2015-11-25: 156; 2015-11-26: 150; 2015-11-28: 174; 2015-11-29: 224; 2015-11-30: 211; 2015-12-01: 211; 2015-12-02: 211; 2015-12-03: 209; 2015-12-05: 210; 2015-12-06: 221; 2015-12-07: 211; 2015-12-08: 211; 2015-12-09: 203; 2015-12-10: 195; 2015-12-12: 187; 2015-12-13: 181; 2015-12-14: 200; 2015-12-15: 213; 2015-12-16: 185; 2015-12-17: 179; 2015-12-19: 221; 2015-12-20: 231; 2015-12-21: 237; 2015-12-22: 223; 2015-12-23: 215; 2015-12-24: 235; 2015-12-26: 268; 2015-12-27: 249; 2015-12-28: 252; 2015-12-29: 268; 2015-12-30: 259; 2015-12-31: 270; 2016-01-02: 261; 2016-01-03: 273; 2016-01-04: 297; 2016-01-05: 290; 2016-01-06: 287; 2016-01-07: 306; 2016-01-09: 309; 2016-01-10: 308; 2016-01-11: 368; 2016-01-12: 342; 2016-01-13: 381; 2016-01-14: 389; 2016-01-16: 409; 2016-01-17: 449; 2016-01-18: 451; 2016-01-19: 442; 2016-01-20: 429; 2016-01-21: 438; 2016-01-23: 444; 2016-01-24: 493; 2016-01-25: 470; 2016-01-26: 471; 2016-01-27: 500; 2016-01-28: 465; 2016-01-30: 459; 2016-01-31: 480; 2016-02-01: 496; 2016-02-02: 518; 2016-02-03: 490; 2016-02-04: 494; 2016-02-06: 495; 2016-02-07: 509; 2016-02-08: 498; 2016-02-09: 488; 2016-02-10: 433; 2016-02-11: 418; 2016-02-13: 467; 2016-02-14: 410; 2016-02-15: 400; 2016-02-16: 410; 2016-02-17: 408; 2016-02-18: 354; 2016-02-20: 338; 2016-02-21: 377; 2016-02-22: 397; 2016-02-23: 443; 2016-02-24: 448; 2016-02-25: 452; 2016-02-27: 453; 2016-02-28: 438; 2016-02-29: 435; 2016-03-01: 406; 2016-03-02: 403; 2016-03-03: 364; 2016-03-05: 318; 2016-03-06: 256; 2016-03-07: 242; 2016-03-08: 223; 2016-03-09: 213; 2016-03-10: 202; 2016-03-12: 192; 2016-03-13: 178; 2016-03-14: 182; 2016-03-15: 233; 2016-03-16: 347; 2016-03-17: 359; 2016-03-19: 361; 2016-03-20: 364; 2016-03-21: 353; 2016-03-22: 335; 2016-03-23: 341; 2016-03-24: 331; 2016-03-26: 319; 2016-03-27: 256; 2016-03-28: 228; 2016-03-29: 204; 2016-03-30: 266; 2016-03-31: 267; 2016-04-02: 272; 2016-04-03: 204; 2016-04-04: 186; 2016-04-05: 196; 2016-04-06: 220; 2016-04-07: 224; 2016-04-09: 238; 2016-04-10: 236; 2016-04-11: 258; 2016-04-12: 258; 2016-04-13: 258; 2016-04-14: 258; 2016-04-16: 260; 2016-04-17: 268; 2016-04-18: 298; 2016-04-19: 270; 2016-04-20: 296; 2016-04-21: 322; 2016-04-23: 320; 2016-04-24: 300; 2016-04-25: 312; 2016-04-26: 306; 2016-04-27: 300; 2016-04-28: 286; 2016-04-30: 288; 2016-05-01: 292; 2016-05-02: 308; 2016-05-03: 334; 2016-05-04: 346; 2016-05-05: 310; 2016-05-07: 314; 2016-05-08: 290; 2016-05-09: 286; 2016-05-10: 286; 2016-05-11: 298; 2016-05-12: 282; 2016-05-14: 282; 2016-05-15: 306; 2016-05-16: 304; 2016-05-17: 302; 2016-05-18: 298; 2016-05-19: 282; 2016-05-21: 241; 2016-05-22: 138; 2016-05-23: 136; 2016-05-24: 134; 2016-05-25: 152; 2016-05-26: 144; 2016-05-28: 140; 2016-05-29: 124; 2016-05-30: 124; 2016-05-31: 140; 2016-06-01: 120; 2016-06-02: 114; 2016-06-04: 114; 2016-06-05: 114; 2016-06-06: 114; 2016-06-07: 150; 2016-06-08: 150; 2016-06-09: 150; 2016-06-11: 144; 2016-06-12: 100; 2016-06-13: 100; 2016-06-14: 100; 2016-06-15: 100; 2016-06-16: 106; 2016-06-18: 114; 2016-06-19: 196; 2016-06-20: 200; 2016-06-21: 200; 2016-06-22: 218; 2016-06-23: 236; 2016-06-25: 212; 2016-06-26: 238; 2016-06-27: 250; 2016-06-28: 252; 2016-06-29: 252; 2016-06-30: 266; 2016-07-02: 282; 2016-07-03: 290; 2016-07-04: 284; 2016-07-05: 256; 2016-07-06: 154; 2016-07-12: 150; 2016-07-13: 150; 2016-07-14: 126; 2016-07-16: 92; 2016-07-17: 62; 2016-07-18: 20
Subcon - Plumbing | 2015-03-24: 4; 2015-03-25: 4; 2015-03-26: 4; 2015-03-28: 4; 2015-03-29: 4; 2015-03-30: 4; 2015-03-31: 4; 2015-04-01: 4; 2015-04-02: 4; 2015-04-04: 4; 2015-04-05: 4; 2015-04-06: 4; 2015-04-07: 4; 2015-04-08: 4; 2015-04-09: 5; 2015-04-11: 5; 2015-04-12: 5; 2015-04-13: 5; 2015-04-14: 5; 2015-04-15: 5; 2015-04-16: 5; 2015-04-18: 5; 2015-04-21: 4; 2015-04-22: 4; 2015-04-23: 4; 2015-04-25: 4; 2015-04-26: 4; 2015-04-27: 4; 2015-04-28: 4; 2015-04-29: 4; 2015-04-30: 4; 2015-05-02: 4; 2015-05-03: 4; 2015-05-04: 4; 2015-05-05: 4; 2015-05-06: 4; 2015-05-12: 5; 2015-05-13: 5; 2015-05-14: 10; 2015-05-16: 10; 2015-05-17: 10; 2015-05-18: 10; 2015-05-19: 10; 2015-05-20: 10; 2015-05-21: 10; 2015-05-23: 10; 2015-05-24: 10; 2015-05-25: 10; 2015-05-26: 10; 2015-05-27: 10; 2015-05-28: 10; 2015-05-30: 5; 2015-05-31: 5; 2015-07-26: 10; 2015-07-27: 10; 2015-07-28: 10; 2015-07-29: 10; 2015-07-30: 10; 2015-08-01: 20; 2015-08-02: 20; 2015-08-03: 20; 2015-08-04: 30; 2015-08-05: 30; 2015-08-06: 30; 2015-08-08: 30; 2015-08-09: 30; 2015-08-10: 40; 2015-08-11: 40; 2015-08-12: 30; 2015-08-13: 30; 2015-08-15: 30; 2015-08-16: 30; 2015-08-17: 30; 2015-08-18: 20; 2015-08-19: 33; 2015-08-20: 33; 2015-08-22: 33; 2015-08-23: 33; 2015-08-24: 33; 2015-08-25: 53; 2015-08-26: 53; 2015-08-27: 53; 2015-08-29: 53; 2015-08-30: 53; 2015-08-31: 53; 2015-09-01: 53; 2015-09-02: 53; 2015-09-03: 53; 2015-09-05: 53; 2015-09-06: 40; 2015-09-07: 40; 2015-09-08: 43; 2015-09-09: 43; 2015-09-10: 43; 2015-09-12: 23; 2015-09-13: 23; 2015-09-14: 33; 2015-09-15: 33; 2015-09-16: 33; 2015-09-17: 33; 2015-09-19: 47; 2015-09-20: 47; 2015-09-21: 47; 2015-09-22: 47; 2015-09-28: 47; 2015-09-29: 47; 2015-09-30: 67; 2015-10-01: 53; 2015-10-03: 53; 2015-10-04: 73; 2015-10-05: 73; 2015-10-06: 73; 2015-10-07: 53; 2015-10-08: 53; 2015-10-10: 73; 2015-10-11: 73; 2015-10-12: 79; 2015-10-13: 99; 2015-10-14: 111; 2015-10-15: 119; 2015-10-17: 127; 2015-10-18: 107; 2015-10-19: 127; 2015-10-20: 139; 2015-10-21: 143; 2015-10-22: 186; 2015-10-24: 186; 2015-10-25: 186; 2015-10-26: 186; 2015-10-27: 194; 2015-10-28: 220; 2015-10-29: 249; 2015-10-31: 251; 2015-11-01: 259; 2015-11-02: 258; 2015-11-03: 258; 2015-11-04: 278; 2015-11-05: 280; 2015-11-07: 333; 2015-11-08: 297; 2015-11-09: 255; 2015-11-10: 258; 2015-11-11: 253; 2015-11-12: 252; 2015-11-14: 236; 2015-11-15: 212; 2015-11-16: 192; 2015-11-17: 202; 2015-11-18: 160; 2015-11-19: 141; 2015-11-21: 167; 2015-11-22: 191; 2015-11-23: 203; 2015-11-24: 165; 2015-11-25: 200; 2015-11-26: 220; 2015-11-28: 217; 2015-11-29: 241; 2015-11-30: 241; 2015-12-01: 251; 2015-12-02: 259; 2015-12-03: 227; 2015-12-05: 218; 2015-12-06: 250; 2015-12-07: 262; 2015-12-08: 270; 2015-12-09: 254; 2015-12-10: 242; 2015-12-12: 270; 2015-12-13: 300; 2015-12-14: 264; 2015-12-15: 308; 2015-12-16: 304; 2015-12-17: 300; 2015-12-19: 288; 2015-12-20: 268; 2015-12-21: 266; 2015-12-22: 252; 2015-12-23: 230; 2015-12-24: 160; 2015-12-26: 172; 2015-12-27: 202; 2015-12-28: 200; 2015-12-29: 207; 2015-12-30: 239; 2015-12-31: 243; 2016-01-02: 264; 2016-01-03: 242; 2016-01-04: 222; 2016-01-05: 242; 2016-01-06: 260; 2016-01-07: 278; 2016-01-09: 304; 2016-01-10: 315; 2016-01-11: 323; 2016-01-12: 333; 2016-01-13: 319; 2016-01-14: 335; 2016-01-16: 305; 2016-01-17: 290; 2016-01-18: 310; 2016-01-19: 336; 2016-01-20: 356; 2016-01-21: 346; 2016-01-23: 348; 2016-01-24: 378; 2016-01-25: 406; 2016-01-26: 401; 2016-01-27: 441; 2016-01-28: 446; 2016-01-30: 446; 2016-01-31: 456; 2016-02-01: 446; 2016-02-02: 440; 2016-02-03: 406; 2016-02-04: 416; 2016-02-06: 359; 2016-02-07: 355; 2016-02-08: 350; 2016-02-09: 350; 2016-02-10: 324; 2016-02-11: 344; 2016-02-13: 366; 2016-02-14: 362; 2016-02-15: 382; 2016-02-16: 390; 2016-02-17: 432; 2016-02-18: 400; 2016-02-20: 358; 2016-02-21: 362; 2016-02-22: 356; 2016-02-23: 341; 2016-02-24: 333; 2016-02-25: 320; 2016-02-27: 284; 2016-02-28: 260; 2016-02-29: 190; 2016-03-01: 174; 2016-03-02: 178; 2016-03-03: 150; 2016-03-05: 165; 2016-03-06: 165; 2016-03-07: 145; 2016-03-08: 145; 2016-03-09: 205; 2016-03-10: 205; 2016-03-12: 205; 2016-03-13: 205; 2016-03-14: 205; 2016-03-15: 241; 2016-03-16: 219; 2016-03-17: 217; 2016-03-19: 219; 2016-03-20: 223; 2016-03-21: 239; 2016-03-22: 243; 2016-03-23: 205; 2016-03-24: 201; 2016-03-26: 203; 2016-03-27: 151; 2016-03-28: 167; 2016-03-29: 175; 2016-03-30: 175; 2016-03-31: 177; 2016-04-02: 152; 2016-04-03: 187; 2016-04-04: 184; 2016-04-05: 184; 2016-04-06: 183; 2016-04-07: 185; 2016-04-09: 189; 2016-04-10: 189; 2016-04-11: 189; 2016-04-12: 189; 2016-04-13: 189; 2016-04-14: 135; 2016-04-16: 125; 2016-04-17: 125; 2016-04-18: 128; 2016-04-19: 122; 2016-04-20: 82; 2016-04-21: 83; 2016-04-23: 78; 2016-04-24: 100; 2016-04-25: 104; 2016-04-26: 110; 2016-04-27: 118; 2016-04-28: 118; 2016-04-30: 118; 2016-05-01: 94; 2016-05-02: 98; 2016-05-03: 150; 2016-05-04: 158; 2016-05-05: 144; 2016-05-07: 148; 2016-05-08: 160; 2016-05-09: 168; 2016-05-10: 180; 2016-05-11: 166; 2016-05-12: 160; 2016-05-14: 148; 2016-05-15: 140; 2016-05-16: 140; 2016-05-17: 134; 2016-05-18: 124; 2016-05-19: 120; 2016-05-21: 68; 2016-05-22: 60; 2016-05-23: 60; 2016-05-24: 60; 2016-05-25: 48; 2016-05-26: 20; 2016-05-28: 8; 2016-05-29: 6; 2016-05-30: 10; 2016-05-31: 10; 2016-06-01: 10; 2016-06-02: 10; 2016-06-04: 10; 2016-06-05: 10; 2016-06-06: 10; 2016-06-07: 10; 2016-06-08: 10; 2016-06-09: 4; 2016-07-14: 14; 2016-07-16: 14; 2016-07-17: 14; 2016-07-18: 14; 2016-07-19: 14; 2016-07-20: 14; 2016-07-21: 14; 2016-07-23: 14; 2016-07-24: 14; 2016-07-25: 14; 2016-07-26: 14; 2016-07-27: 14; 2016-07-28: 14; 2016-07-30: 14
Subcon - HVAC | 2015-09-30: 10; 2015-10-01: 10; 2015-10-03: 10; 2015-10-04: 10; 2015-10-05: 10; 2015-10-06: 30; 2015-10-07: 30; 2015-10-08: 30; 2015-10-10: 30; 2015-10-11: 40; 2015-10-12: 40; 2015-10-13: 40; 2015-10-14: 40; 2015-10-15: 40; 2015-10-17: 40; 2015-10-18: 70; 2015-10-19: 70; 2015-10-20: 70; 2015-10-21: 70; 2015-10-22: 70; 2015-10-24: 60; 2015-10-25: 60; 2015-10-26: 80; 2015-10-27: 80; 2015-10-28: 90; 2015-10-29: 80; 2015-10-31: 80; 2015-11-01: 90; 2015-11-02: 110; 2015-11-03: 110; 2015-11-04: 80; 2015-11-05: 90; 2015-11-07: 90; 2015-11-08: 100; 2015-11-09: 98; 2015-11-10: 96; 2015-11-11: 96; 2015-11-12: 126; 2015-11-14: 126; 2015-11-15: 126; 2015-11-16: 126; 2015-11-17: 116; 2015-11-18: 102; 2015-11-19: 72; 2015-11-21: 98; 2015-11-22: 118; 2015-11-23: 128; 2015-11-24: 108; 2015-11-25: 118; 2015-11-26: 124; 2015-11-28: 124; 2015-11-29: 120; 2015-11-30: 82; 2015-12-01: 82; 2015-12-02: 104; 2015-12-03: 104; 2015-12-05: 120; 2015-12-06: 136; 2015-12-07: 162; 2015-12-08: 172; 2015-12-09: 152; 2015-12-10: 160; 2015-12-12: 180; 2015-12-13: 180; 2015-12-14: 172; 2015-12-15: 156; 2015-12-16: 156; 2015-12-17: 176; 2015-12-19: 164; 2015-12-20: 104; 2015-12-21: 112; 2015-12-22: 126; 2015-12-23: 136; 2015-12-24: 154; 2015-12-26: 182; 2015-12-27: 182; 2015-12-28: 182; 2015-12-29: 142; 2015-12-30: 142; 2015-12-31: 138; 2016-01-02: 204; 2016-01-03: 200; 2016-01-04: 200; 2016-01-05: 200; 2016-01-06: 200; 2016-01-07: 214; 2016-01-09: 220; 2016-01-10: 228; 2016-01-11: 224; 2016-01-12: 260; 2016-01-13: 248; 2016-01-14: 262; 2016-01-16: 282; 2016-01-17: 270; 2016-01-18: 292; 2016-01-19: 278; 2016-01-20: 292; 2016-01-21: 317; 2016-01-23: 330; 2016-01-24: 330; 2016-01-25: 332; 2016-01-26: 315; 2016-01-27: 292; 2016-01-28: 298; 2016-01-30: 238; 2016-01-31: 229; 2016-02-01: 270; 2016-02-02: 256; 2016-02-03: 262; 2016-02-04: 322; 2016-02-06: 288; 2016-02-07: 298; 2016-02-08: 291; 2016-02-09: 290; 2016-02-10: 306; 2016-02-11: 292; 2016-02-13: 237; 2016-02-14: 235; 2016-02-15: 260; 2016-02-16: 242; 2016-02-17: 253; 2016-02-18: 244; 2016-02-20: 245; 2016-02-21: 237; 2016-02-22: 181; 2016-02-23: 185; 2016-02-24: 195; 2016-02-25: 202; 2016-02-27: 241; 2016-02-28: 260; 2016-02-29: 257; 2016-03-01: 283; 2016-03-02: 287; 2016-03-03: 269; 2016-03-05: 274; 2016-03-06: 259; 2016-03-07: 265; 2016-03-08: 258; 2016-03-09: 245; 2016-03-10: 215; 2016-03-12: 228; 2016-03-13: 194; 2016-03-14: 204; 2016-03-15: 190; 2016-03-16: 190; 2016-03-17: 178; 2016-03-19: 170; 2016-03-20: 154; 2016-03-21: 182; 2016-03-22: 182; 2016-03-23: 182; 2016-03-24: 168; 2016-03-26: 168; 2016-03-27: 168; 2016-03-28: 178; 2016-03-29: 156; 2016-03-30: 162; 2016-03-31: 132; 2016-04-02: 130; 2016-04-03: 122; 2016-04-04: 132; 2016-04-05: 152; 2016-04-06: 172; 2016-04-07: 146; 2016-04-09: 142; 2016-04-10: 140; 2016-04-11: 140; 2016-04-12: 148; 2016-04-13: 138; 2016-04-14: 128; 2016-04-16: 126; 2016-04-17: 106; 2016-04-18: 116; 2016-04-19: 116; 2016-04-20: 122; 2016-04-21: 98; 2016-04-23: 108; 2016-04-24: 60; 2016-04-25: 60; 2016-04-26: 60; 2016-04-27: 70; 2016-04-28: 60; 2016-04-30: 60; 2016-05-01: 74; 2016-05-02: 70; 2016-05-03: 60; 2016-05-04: 60; 2016-05-05: 58; 2016-05-07: 58; 2016-05-08: 52; 2016-05-09: 38; 2016-05-10: 28; 2016-05-11: 28; 2016-05-12: 28; 2016-05-14: 28; 2016-05-15: 28; 2016-05-16: 28; 2016-05-25: 12; 2016-05-26: 20; 2016-05-28: 32; 2016-05-29: 40; 2016-05-30: 40; 2016-05-31: 40; 2016-06-01: 40; 2016-06-02: 40; 2016-06-04: 40; 2016-06-05: 40; 2016-06-06: 40; 2016-06-07: 40; 2016-06-08: 40; 2016-06-09: 40; 2016-06-11: 40; 2016-06-12: 28; 2016-06-13: 20; 2016-06-14: 8
Subcon - Fire Fighting | 2015-10-24: 40; 2015-10-25: 40; 2015-10-26: 40; 2015-10-27: 40; 2015-10-28: 40; 2015-10-29: 40; 2015-10-31: 40; 2015-11-01: 40; 2015-11-02: 40; 2015-11-03: 40; 2015-11-04: 90; 2015-11-05: 90; 2015-11-07: 90; 2015-11-08: 90; 2015-11-09: 90; 2015-11-10: 50; 2015-11-11: 50; 2015-11-12: 50; 2015-11-14: 50; 2015-11-15: 50; 2015-11-16: 60; 2015-11-17: 60; 2015-11-18: 100; 2015-11-19: 140; 2015-11-21: 140; 2015-11-22: 100; 2015-11-23: 100; 2015-11-24: 100; 2015-11-25: 100; 2015-11-26: 108; 2015-11-28: 98; 2015-11-29: 98; 2015-11-30: 108; 2015-12-01: 108; 2015-12-02: 108; 2015-12-03: 108; 2015-12-05: 108; 2015-12-06: 68; 2015-12-07: 28; 2015-12-08: 28; 2015-12-09: 58; 2015-12-10: 58; 2015-12-12: 58; 2015-12-13: 58; 2015-12-14: 50; 2015-12-15: 50; 2015-12-16: 58; 2015-12-17: 58; 2015-12-19: 58; 2015-12-20: 98; 2015-12-21: 98; 2015-12-22: 98; 2015-12-23: 88; 2015-12-24: 88; 2015-12-26: 88; 2015-12-27: 56; 2015-12-28: 56; 2015-12-29: 96; 2015-12-30: 96; 2015-12-31: 96; 2016-01-02: 96; 2016-01-03: 88; 2016-01-04: 88; 2016-01-05: 98; 2016-01-06: 58; 2016-01-07: 58; 2016-01-09: 58; 2016-01-10: 58; 2016-01-11: 58; 2016-01-12: 58; 2016-01-13: 50; 2016-01-14: 50; 2016-01-16: 10; 2016-01-17: 50; 2016-01-18: 50; 2016-01-19: 130; 2016-01-20: 130; 2016-01-21: 130; 2016-01-23: 120; 2016-01-24: 130; 2016-01-25: 140; 2016-01-26: 190; 2016-01-27: 190; 2016-01-28: 210; 2016-01-30: 210; 2016-01-31: 226; 2016-02-01: 250; 2016-02-02: 260; 2016-02-03: 240; 2016-02-04: 240; 2016-02-06: 160; 2016-02-07: 176; 2016-02-08: 180; 2016-02-09: 180; 2016-02-10: 190; 2016-02-11: 236; 2016-02-13: 186; 2016-02-14: 210; 2016-02-15: 206; 2016-02-16: 206; 2016-02-17: 194; 2016-02-18: 200; 2016-02-20: 190; 2016-02-21: 222; 2016-02-22: 232; 2016-02-23: 216; 2016-02-24: 216; 2016-02-25: 217; 2016-02-27: 214; 2016-02-28: 194; 2016-02-29: 154; 2016-03-01: 154; 2016-03-02: 174; 2016-03-03: 174; 2016-03-05: 192; 2016-03-06: 192; 2016-03-07: 162; 2016-03-08: 173; 2016-03-09: 108; 2016-03-10: 104; 2016-03-12: 100; 2016-03-13: 104; 2016-03-14: 104; 2016-03-15: 104; 2016-03-16: 104; 2016-03-17: 104; 2016-03-19: 116; 2016-03-20: 108; 2016-03-21: 88; 2016-03-22: 86; 2016-03-23: 72; 2016-03-24: 56; 2016-03-26: 48; 2016-03-27: 48; 2016-03-28: 48; 2016-03-29: 50; 2016-03-30: 56; 2016-03-31: 56; 2016-04-02: 52; 2016-04-03: 52; 2016-04-04: 50; 2016-04-05: 40; 2016-04-06: 12; 2016-04-07: 26; 2016-04-09: 24; 2016-04-10: 40; 2016-04-11: 40; 2016-04-12: 40; 2016-04-13: 40; 2016-04-14: 40; 2016-04-16: 40; 2016-04-17: 42; 2016-04-18: 52; 2016-04-19: 70; 2016-04-20: 76; 2016-04-21: 76; 2016-04-23: 76; 2016-04-24: 72; 2016-04-25: 60; 2016-04-26: 71; 2016-04-27: 50; 2016-04-28: 48; 2016-04-30: 42; 2016-05-01: 43; 2016-05-02: 46; 2016-05-03: 46; 2016-05-04: 48; 2016-05-05: 44; 2016-05-07: 28; 2016-05-08: 28; 2016-05-09: 26; 2016-05-10: 26; 2016-05-11: 30; 2016-05-12: 42; 2016-05-14: 26; 2016-05-15: 25; 2016-05-16: 20; 2016-05-17: 20; 2016-05-18: 20; 2016-05-19: 20; 2016-05-21: 22; 2016-05-22: 22; 2016-05-23: 22; 2016-05-24: 23; 2016-05-25: 38; 2016-05-26: 46; 2016-05-28: 46; 2016-05-29: 42; 2016-05-30: 26; 2016-05-31: 37; 2016-06-01: 56; 2016-06-02: 60; 2016-06-04: 60; 2016-06-05: 60; 2016-06-06: 60; 2016-06-07: 76; 2016-06-08: 80; 2016-06-09: 80; 2016-06-11: 80; 2016-06-12: 68; 2016-06-13: 60; 2016-06-14: 48; 2016-06-15: 40; 2016-06-16: 40; 2016-06-18: 40; 2016-06-19: 24; 2016-06-20: 20; 2016-06-21: 4
Subcon - Lift & Esc. | 2016-01-02: 20; 2016-01-03: 20; 2016-01-04: 20; 2016-01-05: 20; 2016-01-06: 20; 2016-01-07: 20; 2016-01-09: 40; 2016-01-10: 40; 2016-01-11: 40; 2016-01-12: 40; 2016-01-13: 40; 2016-01-14: 40; 2016-01-16: 60; 2016-01-17: 60; 2016-01-18: 60; 2016-01-19: 40; 2016-01-20: 40; 2016-01-21: 40; 2016-01-23: 40; 2016-01-24: 40; 2016-01-25: 40; 2016-01-26: 20; 2016-01-27: 20; 2016-01-28: 20; 2016-01-30: 20; 2016-01-31: 20; 2016-02-01: 20; 2016-02-02: 8; 2016-02-03: 8; 2016-02-04: 8; 2016-02-06: 8; 2016-02-07: 8; 2016-02-08: 8; 2016-02-09: 8; 2016-02-10: 8; 2016-02-11: 8; 2016-02-13: 8; 2016-02-14: 8; 2016-02-15: 8; 2016-02-16: 8; 2016-02-17: 8
Subcon - Water Proofing | 2015-09-01: 4; 2015-09-02: 4; 2015-09-03: 4; 2015-09-05: 4; 2015-09-06: 4; 2015-09-07: 4; 2015-09-08: 4; 2015-09-09: 4; 2015-09-10: 8; 2015-09-12: 8; 2015-09-13: 4; 2015-09-14: 4; 2015-09-15: 4; 2015-09-16: 4; 2015-09-17: 4; 2015-09-19: 4; 2015-09-20: 4; 2015-09-21: 4; 2015-10-01: 6; 2015-10-03: 10; 2015-10-04: 10; 2015-10-05: 10; 2015-10-06: 10; 2015-10-07: 10; 2015-10-08: 10; 2015-10-10: 10; 2015-10-11: 10; 2015-10-12: 10; 2015-10-13: 4; 2015-10-21: 6; 2015-10-22: 6; 2015-10-24: 6; 2015-10-25: 6; 2015-10-26: 6; 2015-10-27: 6; 2015-10-28: 6; 2015-10-29: 6; 2015-10-31: 6; 2015-11-01: 12; 2015-11-02: 6; 2015-11-03: 6; 2015-11-04: 6; 2015-11-05: 6; 2015-11-07: 6; 2015-11-08: 6; 2015-11-09: 6; 2015-11-10: 12; 2015-11-11: 12; 2015-11-12: 6; 2015-11-14: 6; 2015-11-15: 6; 2015-11-16: 6; 2015-11-17: 6; 2015-11-18: 6; 2015-11-19: 6; 2015-11-21: 6; 2015-11-29: 6; 2015-11-30: 6; 2015-12-01: 32; 2015-12-02: 32; 2015-12-03: 32; 2015-12-05: 32; 2015-12-06: 32; 2015-12-07: 38; 2015-12-08: 62; 2015-12-09: 62; 2015-12-10: 56; 2015-12-12: 56; 2015-12-13: 30; 2015-12-14: 38; 2015-12-15: 40; 2015-12-16: 40; 2015-12-17: 40; 2015-12-19: 40; 2015-12-20: 20; 2015-12-21: 20; 2015-12-22: 20; 2015-12-23: 20; 2015-12-24: 34; 2015-12-26: 30; 2015-12-27: 30; 2015-12-28: 30; 2015-12-29: 30; 2015-12-30: 30; 2015-12-31: 22; 2016-01-02: 20; 2016-01-03: 20; 2016-01-04: 20; 2016-01-16: 40; 2016-01-17: 40; 2016-01-18: 40; 2016-01-19: 40; 2016-01-20: 40; 2016-01-21: 44; 2016-01-23: 44; 2016-01-24: 46; 2016-01-25: 58; 2016-01-26: 58; 2016-01-27: 64; 2016-01-28: 68; 2016-01-30: 68; 2016-01-31: 78; 2016-02-01: 78; 2016-02-02: 40; 2016-02-03: 44; 2016-02-04: 42; 2016-02-06: 60; 2016-02-07: 60; 2016-02-08: 60; 2016-02-09: 100; 2016-02-10: 100; 2016-02-11: 90; 2016-02-13: 90; 2016-02-14: 124; 2016-02-15: 120; 2016-02-16: 120; 2016-02-17: 110; 2016-02-18: 120; 2016-02-20: 114; 2016-02-21: 116; 2016-02-22: 140; 2016-02-23: 130; 2016-02-24: 140; 2016-02-25: 146; 2016-02-27: 116; 2016-02-28: 120; 2016-02-29: 130; 2016-03-01: 150; 2016-03-02: 126; 2016-03-03: 130; 2016-03-05: 124; 2016-03-06: 148; 2016-03-07: 138; 2016-03-08: 148; 2016-03-09: 142; 2016-03-10: 144; 2016-03-12: 130; 2016-03-13: 120; 2016-03-14: 114; 2016-03-15: 104; 2016-03-16: 94; 2016-03-17: 80; 2016-03-19: 64; 2016-03-20: 48; 2016-03-21: 44; 2016-03-22: 38; 2016-03-23: 14; 2016-03-24: 14; 2016-03-26: 8; 2016-03-27: 8; 2016-03-28: 12; 2016-03-29: 12; 2016-03-30: 8; 2016-03-31: 8; 2016-04-09: 2; 2016-04-10: 2; 2016-04-11: 2; 2016-04-12: 2; 2016-04-13: 2; 2016-04-14: 2; 2016-04-16: 2; 2016-04-17: 2; 2016-04-18: 4; 2016-04-19: 4; 2016-04-20: 2; 2016-04-21: 2
Subcon - Anti-termite | 2014-12-30: 8; 2014-12-31: 8; 2015-01-10: 8; 2015-01-11: 8; 2015-01-31: 10; 2015-02-01: 10; 2015-02-02: 2; 2015-02-03: 2; 2015-02-04: 2; 2015-02-05: 2; 2015-02-07: 4; 2015-02-08: 4; 2015-02-09: 4; 2015-02-10: 4; 2015-02-11: 4; 2015-02-12: 4; 2015-02-14: 4; 2015-02-15: 4; 2015-02-16: 2; 2015-02-17: 2; 2015-02-18: 2; 2015-02-19: 2; 2015-02-21: 2; 2015-02-22: 2; 2015-03-01: 8; 2015-03-02: 8; 2015-03-03: 8; 2015-03-10: 8; 2015-03-11: 8; 2015-03-12: 8; 2015-03-26: 12; 2015-03-28: 12; 2015-03-29: 20; 2015-03-30: 20; 2015-03-31: 20; 2015-04-01: 12; 2015-04-02: 12; 2015-04-04: 12; 2015-04-05: 12; 2015-04-06: 12; 2015-04-07: 8; 2015-04-08: 8; 2015-04-15: 8; 2015-04-16: 8; 2015-04-21: 4; 2015-04-22: 4; 2015-04-23: 4; 2015-04-25: 4; 2015-05-09: 16; 2015-05-10: 16; 2015-05-31: 8; 2015-06-01: 8; 2015-06-02: 8; 2015-06-03: 8
Subcon - GRC Works | 2016-05-01: 16; 2016-05-02: 16; 2016-05-03: 16; 2016-05-04: 16; 2016-05-05: 16; 2016-05-07: 16; 2016-05-08: 16; 2016-05-09: 16; 2016-05-10: 16; 2016-05-11: 16; 2016-05-12: 26; 2016-05-14: 26; 2016-05-15: 26; 2016-05-16: 26; 2016-05-17: 26; 2016-05-18: 26; 2016-05-19: 26; 2016-05-21: 26; 2016-05-22: 26; 2016-05-23: 26; 2016-05-24: 26; 2016-05-25: 26; 2016-05-26: 26; 2016-05-28: 26; 2016-05-29: 26; 2016-05-30: 26; 2016-05-31: 26; 2016-06-01: 26; 2016-06-02: 26; 2016-06-04: 26; 2016-06-05: 26; 2016-06-06: 26; 2016-06-07: 26; 2016-06-08: 26; 2016-06-09: 26; 2016-06-11: 26; 2016-06-12: 26; 2016-06-13: 26; 2016-06-14: 26; 2016-06-15: 26; 2016-06-16: 25; 2016-06-18: 25; 2016-06-19: 25; 2016-06-20: 25; 2016-06-21: 25; 2016-06-22: 25; 2016-06-23: 25; 2016-06-25: 25; 2016-06-26: 25; 2016-06-27: 25; 2016-06-28: 25; 2016-06-29: 25; 2016-06-30: 25; 2016-07-02: 25; 2016-07-03: 25; 2016-07-04: 25; 2016-07-05: 25; 2016-07-06: 25; 2016-07-12: 15; 2016-07-13: 15; 2016-07-14: 5; 2016-07-16: 5; 2016-07-17: 5; 2016-07-18: 5; 2016-07-19: 5; 2016-07-20: 5; 2016-07-21: 5; 2016-07-23: 5; 2016-07-24: 5; 2016-07-25: 5; 2016-07-26: 5; 2016-07-27: 5
Subcon - Kitchen Equipment | 2016-05-10: 8; 2016-05-11: 10; 2016-05-12: 10; 2016-05-14: 10; 2016-05-15: 10; 2016-05-16: 10; 2016-05-17: 20; 2016-05-18: 20; 2016-05-19: 20; 2016-05-21: 20; 2016-05-22: 20; 2016-05-23: 20; 2016-05-24: 20; 2016-05-25: 20; 2016-05-26: 20; 2016-05-28: 20; 2016-05-29: 20; 2016-05-30: 20; 2016-05-31: 20; 2016-06-01: 20; 2016-06-02: 20; 2016-06-04: 20; 2016-06-05: 20; 2016-06-06: 20; 2016-06-07: 20; 2016-06-08: 20; 2016-06-09: 20; 2016-06-11: 20; 2016-06-12: 20; 2016-06-13: 20; 2016-06-14: 12; 2016-06-15: 10; 2016-06-16: 10; 2016-06-18: 10; 2016-06-19: 10; 2016-06-20: 10
Subcon - Swimming Pool Equipment | 2016-04-30: 6; 2016-05-01: 8; 2016-05-02: 8; 2016-05-03: 8; 2016-05-04: 8; 2016-05-05: 14; 2016-05-07: 24; 2016-05-08: 24; 2016-05-09: 24; 2016-05-10: 24; 2016-05-11: 18; 2016-05-12: 24; 2016-05-14: 24; 2016-05-15: 24; 2016-05-16: 24; 2016-05-17: 18; 2016-05-18: 8; 2016-05-19: 8; 2016-05-21: 8; 2016-05-22: 8; 2016-05-23: 8
Subcon - Landscape | 2016-02-22: 5; 2016-02-23: 5; 2016-02-24: 5; 2016-02-25: 5; 2016-02-27: 5; 2016-02-28: 5; 2016-02-29: 5; 2016-03-01: 5; 2016-03-02: 5; 2016-03-03: 5; 2016-03-05: 5; 2016-03-06: 5; 2016-03-07: 5; 2016-03-08: 5; 2016-03-09: 5; 2016-03-10: 10; 2016-03-12: 10; 2016-03-13: 10; 2016-03-14: 10; 2016-03-15: 10; 2016-03-16: 10; 2016-03-17: 10; 2016-03-19: 20; 2016-03-20: 20; 2016-03-21: 20; 2016-03-22: 20; 2016-03-23: 20; 2016-03-24: 20; 2016-03-26: 20; 2016-03-27: 20; 2016-04-12: 5; 2016-04-13: 8; 2016-04-14: 8; 2016-04-16: 38; 2016-04-17: 38; 2016-04-18: 38; 2016-04-19: 38; 2016-04-20: 38; 2016-04-21: 43; 2016-04-23: 40; 2016-04-24: 42; 2016-04-25: 44; 2016-04-26: 44; 2016-04-27: 44; 2016-04-28: 44; 2016-04-30: 44; 2016-05-01: 44; 2016-05-02: 44; 2016-05-03: 14; 2016-05-04: 14; 2016-05-05: 14; 2016-05-07: 14; 2016-05-08: 14; 2016-05-09: 24; 2016-05-10: 24; 2016-05-11: 24; 2016-05-12: 24; 2016-05-14: 30; 2016-05-15: 34; 2016-05-16: 34; 2016-05-17: 34; 2016-05-18: 34; 2016-05-19: 34; 2016-05-21: 34; 2016-05-22: 34; 2016-05-23: 34; 2016-05-24: 34; 2016-05-25: 32; 2016-05-26: 32; 2016-05-28: 32; 2016-05-29: 32; 2016-05-30: 32; 2016-05-31: 26; 2016-06-01: 22; 2016-06-02: 22; 2016-06-04: 22; 2016-06-05: 22; 2016-06-06: 22; 2016-06-07: 40; 2016-06-08: 40; 2016-06-09: 40; 2016-06-11: 40; 2016-06-12: 40; 2016-06-13: 40; 2016-06-14: 40; 2016-06-15: 40; 2016-06-16: 40; 2016-06-18: 40; 2016-06-19: 40; 2016-06-20: 40; 2016-06-21: 40; 2016-06-22: 40; 2016-06-23: 40; 2016-06-25: 20; 2016-06-26: 20; 2016-06-27: 20; 2016-06-28: 20; 2016-06-29: 20; 2016-06-30: 20; 2016-07-02: 20; 2016-07-03: 20; 2016-07-04: 20; 2016-07-05: 20; 2016-07-06: 20; 2016-07-12: 20; 2016-07-13: 20; 2016-07-14: 20; 2016-07-16: 20; 2016-07-17: 20; 2016-07-18: 20; 2016-07-19: 20; 2016-07-20: 20; 2016-07-21: 20; 2016-07-23: 20; 2016-07-24: 20; 2016-07-25: 20; 2016-07-26: 20; 2016-07-27: 20; 2016-07-28: 20; 2016-07-30: 20; 2016-07-31: 20; 2016-08-01: 20; 2016-08-02: 27; 2016-08-03: 27; 2016-08-04: 27; 2016-08-06: 27; 2016-08-07: 27; 2016-08-08: 27; 2016-08-09: 27; 2016-08-10: 27; 2016-08-11: 27; 2016-08-13: 27; 2016-08-14: 27; 2016-08-15: 27; 2016-08-16: 27; 2016-08-17: 27; 2016-08-18: 27; 2016-08-20: 22; 2016-08-21: 2; 2016-08-22: 2; 2016-08-23: 2; 2016-08-24: 2; 2016-08-25: 2; 2016-08-27: 2; 2016-08-28: 2; 2016-08-29: 10; 2016-08-30: 10; 2016-08-31: 10; 2016-09-01: 10; 2016-09-03: 10; 2016-09-04: 10; 2016-09-05: 10; 2016-09-06: 10; 2016-09-07: 10; 2016-09-13: 10; 2016-09-14: 13; 2016-09-15: 13; 2016-09-17: 13; 2016-09-18: 13; 2016-09-19: 13; 2016-09-20: 3; 2016-09-21: 3; 2016-09-22: 3; 2016-09-24: 3; 2016-09-25: 3; 2016-10-05: 4; 2016-10-06: 4; 2016-10-08: 4; 2016-10-09: 4; 2016-10-10: 4; 2016-10-11: 4; 2016-10-12: 4; 2016-10-13: 4
Subcon - Irrigation | 2016-01-24: 20; 2016-01-25: 20; 2016-01-26: 20; 2016-01-27: 20; 2016-01-28: 20; 2016-01-30: 20; 2016-01-31: 20; 2016-02-01: 20; 2016-02-02: 20; 2016-02-03: 20; 2016-03-29: 6; 2016-03-30: 10; 2016-03-31: 10; 2016-04-02: 10; 2016-04-03: 10; 2016-04-04: 10; 2016-04-05: 10; 2016-04-06: 10; 2016-04-07: 10; 2016-04-09: 10; 2016-04-10: 4; 2016-05-21: 10; 2016-05-22: 10; 2016-05-23: 10; 2016-05-24: 10; 2016-05-25: 10; 2016-05-26: 30; 2016-05-28: 30; 2016-05-29: 30; 2016-05-30: 30; 2016-05-31: 30; 2016-06-01: 30; 2016-06-02: 30; 2016-06-04: 30; 2016-06-05: 30; 2016-06-06: 30; 2016-06-07: 40; 2016-06-08: 40; 2016-06-09: 40; 2016-06-11: 40; 2016-06-12: 40; 2016-06-13: 29; 2016-06-14: 29; 2016-06-15: 29; 2016-06-16: 29; 2016-06-18: 29; 2016-06-19: 19; 2016-06-20: 19; 2016-06-21: 19; 2016-06-22: 19; 2016-06-23: 19; 2016-06-25: 19; 2016-06-26: 19; 2016-06-27: 19; 2016-06-28: 19; 2016-06-29: 14; 2016-06-30: 6; 2016-07-02: 6; 2016-07-03: 6; 2016-07-04: 6; 2016-07-05: 6; 2016-07-06: 6; 2016-07-12: 6; 2016-07-13: 6; 2016-07-14: 4

## Daily Manpower - Mitigation R4
Activity Name | time axis 2014-10-15 to 2016-10-13
MANPOWER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 11 | 11 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 0 | 11 | 11 | 11 | 11 | 11 | 17 | 0 | 17 | 17 | 17 | 17 | 17 | 0 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 34 | 34 | 34 | 36 | 36 | 61 | 0 | 85 | 80 | 80 | 88 | 60 | 60 | 0 | 79 | 123 | 120 | 115 | 102 | 102 | 0 | 98 | 106 | 106 | 110 | 116 | 96 | 0 | 90 | 70 | 70 | 76 | 96 | 90 | 0 | 82 | 92 | 89 | 85 | 80 | 98 | 0 | 76 | 78 | 123 | 102 | 110 | 92 | 0 | 70 | 70 | 95 | 98 | 98 | 139 | 0 | 96 | 114 | 131 | 141 | 100 | 133 | 0 | 161 | 133 | 145 | 171 | 122 | 114 | 0 | 122 | 102 | 92 | 58 | 57 | 53 | 0 | 24 | 38 | 32 | 32 | 22 | 22 | 0 | 30 | 32 | 34 | 36 | 38 | 44 | 0 | 20 | 20 | 28 | 28 | 28 | 28 | 0 | 28 | 34 | 60 | 52 | 42 | 34 | 0 | 53 | 59 | 60 | 52 | 46 | 40 | 0 | 39 | 78 | 49 | 51 | 111 | 82 | 0 | 107 | 143 | 155 | 126 | 111 | 47 | 0 | 103 | 114 | 127 | 149 | 132 | 118 | 0 | 41 | 34 | 49 | 51 | 40 | 62 | 0 | 31 | 51 | 154 | 167 | 157 | 141 | 0 | 141 | 31 | 19 | 67 | 102 | 47 | 0 | 89 | 79 | 92 | 121 | 135 | 135 | 0 | 121 | 163 | 133 | 153 | 157 | 167 | 0 | 159 | 127 | 121 | 160 | 155 | 150 | 0 | 156 | 140 | 159 | 144 | 97 | 86 | 0 | 89 | 87 | 77 | 83 | 128 | 160 | 0 | 172 | 155 | 120 | 103 | 74 | 77 | 16 | 66 | 60 | 73 | 80 | 141 | 172 | 0 | 0 | 0 | 0 | 0 | 178 | 172 | 0 | 152 | 170 | 150 | 106 | 108 | 134 | 0 | 182 | 190 | 187 | 173 | 161 | 158 | 0 | 154 | 148 | 146 | 188 | 217 | 211 | 0 | 179 | 174 | 142 | 124 | 100 | 96 | 0 | 157 | 204 | 224 | 217 | 247 | 256 | 22 | 217 | 196 | 294 | 263 | 233 | 255 | 0 | 248 | 308 | 368 | 428 | 503 | 488 | 4 | 426 | 343 | 244 | 174 | 172 | 162 | 0 | 164 | 194 | 235 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 290 | 283 | 16 | 269 | 258 | 280 | 298 | 311 | 371 | 20 | 433 | 437 | 436 | 419 | 389 | 446 | 86 | 564 | 584 | 540 | 651 | 685 | 660 | 95 | 660 | 624 | 588 | 606 | 650 | 721 | 145 | 715 | 669 | 707 | 644 | 658 | 576 | 168 | 575 | 581 | 713 | 809 | 814 | 779 | 189 | 847 | 869 | 877 | 832 | 824 | 797 | 170 | 846 | 796 | 906 | 888 | 846 | 725 | 158 | 744 | 744 | 705 | 699 | 763 | 740 | 127 | 746 | 804 | 844 | 918 | 880 | 906 | 160 | 991 | 1009 | 1041 | 1033 | 1067 | 1064 | 89 | 1063 | 970 | 1022 | 1013 | 1008 | 1093 | 44 | 1128 | 1088 | 1103 | 1062 | 1082 | 1118 | 25 | 1115 | 1116 | 1139 | 1158 | 1232 | 1280 | 0 | 1320 | 1409 | 1539 | 1616 | 1661 | 1636 | 0 | 1593 | 1553 | 1518 | 1506 | 1563 | 1503 | 0 | 1418 | 1467 | 1471 | 1446 | 1402 | 1365 | 0 | 1450 | 1582 | 1652 | 1730 | 1779 | 1865 | 0 | 1861 | 1831 | 1775 | 1782 | 1737 | 1728 | 0 | 1661 | 1634 | 1681 | 1788 | 1803 | 1786 | 0 | 1805 | 1832 | 1785 | 1800 | 1784 | 1850 | 0 | 1840 | 1800 | 1763 | 1726 | 1667 | 1629 | 0 | 1505 | 1523 | 1589 | 1573 | 1636 | 1646 | 0 | 1644 | 1677 | 1684 | 1670 | 1655 | 1614 | 0 | 1636 | 1661 | 1676 | 1760 | 1745 | 1760 | 0 | 1814 | 1790 | 1824 | 1895 | 1853 | 1815 | 0 | 1776 | 1788 | 1823 | 1787 | 1782 | 1778 | 0 | 1829 | 1763 | 1734 | 1795 | 1793 | 1802 | 0 | 1801 | 1780 | 1817 | 1805 | 1800 | 1744 | 0 | 1659 | 1572 | 1582 | 1469 | 1430 | 1396 | 0 | 1360 | 1350 | 1323 | 1245 | 1219 | 1107 | 0 | 1106 | 1074 | 1025 | 1004 | 972 | 887 | 0 | 853 | 803 | 813 | 823 | 815 | 809 | 0 | 832 | 828 | 896 | 923 | 911 | 880 | 0 | 892 | 870 | 887 | 891 | 833 | 782 | 0 | 655 | 646 | 627 | 572 | 570 | 551 | 0 | 533 | 536 | 547 | 513 | 515 | 490 | 0 | 422 | 412 | 435 | 402 | 406 | 401 | 0 | 383 | 355 | 336 | 342 | 308 | 262 | 0 | 250 | 239 | 230 | 215 | 212 | 0 | 0 | 0 | 0 | 0 | 197 | 197 | 170 | 0 | 176 | 176 | 176 | 150 | 129 | 125 | 0 | 122 | 113 | 95 | 86 | 86 | 86 | 0 | 86 | 68 | 68 | 68 | 68 | 68 | 0 | 68 | 69 | 77 | 77 | 77 | 77 | 0 | 77 | 72 | 72 | 72 | 72 | 72 | 0 | 72 | 72 | 72 | 79 | 70 | 36 | 0 | 36 | 36 | 36 | 36 | 39 | 39 | 0 | 39 | 40 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 44 | 35 | 30 | 0 | 9 | 9 | 9 | 8 | 4 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Carpenter-Conc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 13 | 3 | 0 | 3 | 3 | 3 | 3 | 13 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 10 | 10 | 0 | 4 | 4 | 4 | 9 | 5 | 5 | 0 | 15 | 15 | 15 | 20 | 20 | 20 | 0 | 20 | 20 | 15 | 15 | 5 | 5 | 0 | 5 | 12 | 9 | 9 | 9 | 9 | 0 | 13 | 11 | 9 | 9 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 5 | 6 | 5 | 5 | 5 | 6 | 0 | 12 | 30 | 30 | 29 | 23 | 0 | 0 | 5 | 28 | 29 | 34 | 34 | 34 | 0 | 11 | 5 | 5 | 5 | 3 | 3 | 0 | 2 | 4 | 13 | 14 | 14 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 25 | 25 | 0 | 25 | 40 | 26 | 34 | 34 | 46 | 0 | 30 | 30 | 30 | 37 | 30 | 30 | 0 | 30 | 25 | 27 | 29 | 29 | 29 | 0 | 29 | 27 | 25 | 25 | 36 | 54 | 0 | 54 | 48 | 34 | 21 | 15 | 17 | 4 | 16 | 14 | 12 | 18 | 38 | 55 | 0 | 0 | 0 | 0 | 0 | 55 | 49 | 0 | 40 | 37 | 25 | 16 | 16 | 17 | 0 | 27 | 33 | 33 | 33 | 33 | 33 | 0 | 33 | 36 | 33 | 41 | 48 | 41 | 0 | 40 | 39 | 39 | 34 | 18 | 22 | 0 | 38 | 57 | 59 | 51 | 54 | 45 | 1 | 33 | 33 | 54 | 58 | 58 | 69 | 0 | 65 | 71 | 94 | 121 | 132 | 130 | 2 | 106 | 57 | 33 | 26 | 39 | 37 | 0 | 31 | 19 | 15 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 41 | 4 | 41 | 38 | 67 | 78 | 72 | 70 | 0 | 61 | 85 | 98 | 87 | 88 | 101 | 30 | 102 | 107 | 70 | 90 | 97 | 85 | 26 | 98 | 90 | 103 | 97 | 110 | 155 | 53 | 131 | 122 | 132 | 124 | 119 | 89 | 52 | 103 | 96 | 111 | 119 | 131 | 112 | 50 | 126 | 131 | 114 | 92 | 91 | 106 | 53 | 95 | 112 | 134 | 126 | 103 | 68 | 47 | 76 | 78 | 42 | 46 | 23 | 33 | 41 | 61 | 80 | 73 | 60 | 53 | 62 | 51 | 80 | 69 | 78 | 55 | 40 | 41 | 16 | 58 | 65 | 55 | 48 | 51 | 50 | 13 | 58 | 35 | 36 | 30 | 32 | 34 | 12 | 20 | 20 | 24 | 24 | 26 | 23 | 0 | 20 | 10 | 17 | 37 | 37 | 39 | 0 | 46 | 45 | 39 | 23 | 31 | 31 | 0 | 28 | 30 | 21 | 9 | 9 | 7 | 0 | 3 | 3 | 4 | 14 | 14 | 16 | 0 | 25 | 28 | 21 | 32 | 30 | 20 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 13 | 10 | 10 | 10 | 10 | 8 | 0 | 0 | 0 | 0 | 2 | 10 | 10 | 0 | 10 | 12 | 20 | 20 | 20 | 21 | 0 | 24 | 24 | 24 | 24 | 24 | 26 | 0 | 32 | 23 | 20 | 26 | 38 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 31 | 42 | 52 | 44 | 44 | 44 | 0 | 38 | 24 | 23 | 20 | 20 | 20 | 0 | 34 | 39 | 47 | 48 | 43 | 31 | 0 | 31 | 32 | 35 | 31 | 31 | 31 | 0 | 31 | 31 | 27 | 14 | 12 | 3 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 0 | 4 | 8 | 8 | 10 | 10 | 12 | 0 | 14 | 12 | 10 | 12 | 12 | 8 | 0 | 7 | 6 | 6 | 2 | 0 | 1 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Steel Fixer - Conc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 12 | 4 | 4 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 4 | 4 | 4 | 0 | 4 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 12 | 12 | 12 | 12 | 0 | 12 | 12 | 0 | 0 | 5 | 9 | 0 | 9 | 9 | 9 | 9 | 14 | 14 | 0 | 14 | 14 | 14 | 10 | 5 | 7 | 0 | 7 | 7 | 7 | 7 | 2 | 2 | 0 | 2 | 0 | 0 | 1 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 1 | 1 | 4 | 4 | 4 | 0 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 2 | 2 | 2 | 2 | 0 | 1 | 0 | 11 | 11 | 11 | 11 | 2 | 12 | 0 | 14 | 14 | 14 | 14 | 4 | 2 | 0 | 0 | 0 | 3 | 4 | 4 | 4 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 27 | 29 | 27 | 9 | 0 | 16 | 9 | 9 | 11 | 13 | 6 | 0 | 6 | 6 | 6 | 11 | 19 | 25 | 0 | 33 | 35 | 31 | 23 | 16 | 7 | 0 | 5 | 4 | 4 | 12 | 23 | 23 | 0 | 23 | 23 | 15 | 6 | 8 | 8 | 4 | 6 | 4 | 8 | 12 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 19 | 22 | 0 | 20 | 19 | 19 | 19 | 24 | 29 | 0 | 26 | 19 | 20 | 25 | 19 | 12 | 0 | 12 | 12 | 13 | 26 | 22 | 22 | 0 | 24 | 26 | 13 | 8 | 8 | 10 | 0 | 12 | 16 | 28 | 37 | 37 | 34 | 0 | 30 | 16 | 6 | 17 | 19 | 20 | 0 | 20 | 22 | 13 | 11 | 20 | 25 | 0 | 21 | 22 | 27 | 28 | 20 | 22 | 0 | 22 | 23 | 21 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 53 | 49 | 4 | 45 | 36 | 15 | 16 | 32 | 33 | 0 | 58 | 54 | 55 | 53 | 43 | 22 | 13 | 36 | 62 | 68 | 71 | 73 | 77 | 22 | 66 | 45 | 43 | 35 | 46 | 61 | 18 | 49 | 66 | 75 | 59 | 48 | 50 | 21 | 38 | 33 | 70 | 75 | 66 | 73 | 31 | 73 | 69 | 80 | 66 | 49 | 32 | 16 | 44 | 57 | 67 | 65 | 62 | 53 | 29 | 53 | 51 | 51 | 46 | 26 | 28 | 12 | 36 | 48 | 41 | 41 | 37 | 22 | 11 | 15 | 35 | 37 | 35 | 37 | 40 | 13 | 28 | 18 | 15 | 8 | 9 | 12 | 5 | 8 | 11 | 14 | 14 | 13 | 9 | 1 | 13 | 10 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 5 | 5 | 9 | 12 | 12 | 0 | 12 | 21 | 16 | 13 | 13 | 13 | 0 | 13 | 10 | 0 | 0 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mason - Conc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 11 | 19 | 0 | 11 | 17 | 27 | 27 | 17 | 15 | 0 | 15 | 10 | 10 | 15 | 5 | 5 | 0 | 5 | 5 | 5 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 1 | 19 | 0 | 0 | 0 | 0 | 16 | 4 | 10 | 0 | 0 | 10 | 0 | 0 | 5 | 10 | 5 | 0 | 2 | 3 | 3 | 2 | 0 | 10 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14 | 34 | 4 | 0 | 6 | 3 | 3 | 0 | 0 | 15 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 4 | 16 | 10 | 1 | 0 | 1 | 1 | 11 | 11 | 1 | 5 | 0 | 7 | 7 | 5 | 0 | 0 | 0 | 0 | 6 | 4 | 4 | 10 | 6 | 6 | 0 | 4 | 4 | 7 | 2 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 14 | 14 | 4 | 2 | 2 | 0 | 8 | 10 | 8 | 2 | 2 | 8 | 0 | 7 | 3 | 1 | 4 | 14 | 15 | 0 | 4 | 4 | 4 | 12 | 13 | 3 | 0 | 11 | 4 | 0 | 0 | 4 | 10 | 8 | 9 | 5 | 24 | 11 | 0 | 0 | 0 | 0 | 5 | 14 | 12 | 19 | 11 | 0 | 5 | 16 | 13 | 3 | 3 | 3 | 0 | 3 | 5 | 14 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 13 | 14 | 0 | 11 | 14 | 13 | 11 | 3 | 6 | 8 | 14 | 8 | 0 | 3 | 6 | 20 | 0 | 22 | 7 | 10 | 10 | 10 | 12 | 0 | 13 | 21 | 13 | 23 | 18 | 6 | 2 | 26 | 4 | 12 | 13 | 30 | 22 | 8 | 18 | 25 | 6 | 22 | 18 | 4 | 10 | 14 | 16 | 12 | 8 | 22 | 18 | 14 | 44 | 4 | 10 | 12 | 18 | 21 | 2 | 14 | 9 | 17 | 10 | 25 | 25 | 8 | 5 | 11 | 17 | 26 | 11 | 15 | 16 | 17 | 7 | 10 | 12 | 17 | 5 | 8 | 3 | 4 | 10 | 22 | 6 | 6 | 0 | 3 | 4 | 7 | 7 | 11 | 17 | 0 | 9 | 6 | 6 | 5 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 4 | 0 | 12 | 10 | 10 | 15 | 21 | 23 | 0 | 25 | 31 | 22 | 19 | 19 | 19 | 0 | 19 | 16 | 26 | 16 | 16 | 16 | 0 | 15 | 16 | 14 | 24 | 15 | 19 | 0 | 22 | 22 | 22 | 22 | 22 | 22 | 0 | 22 | 22 | 22 | 23 | 25 | 26 | 0 | 29 | 25 | 24 | 19 | 22 | 22 | 0 | 21 | 18 | 16 | 16 | 19 | 19 | 0 | 17 | 11 | 11 | 8 | 8 | 4 | 0 | 11 | 8 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labour - BTCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 14 | 14 | 14 | 18 | 4 | 4 | 0 | 8 | 30 | 30 | 30 | 26 | 26 | 0 | 22 | 26 | 26 | 30 | 33 | 23 | 0 | 20 | 8 | 8 | 11 | 21 | 18 | 0 | 18 | 23 | 23 | 21 | 21 | 30 | 0 | 30 | 36 | 56 | 48 | 52 | 43 | 0 | 33 | 33 | 41 | 42 | 42 | 60 | 0 | 41 | 47 | 51 | 56 | 41 | 58 | 0 | 72 | 61 | 67 | 77 | 58 | 54 | 0 | 58 | 48 | 43 | 29 | 24 | 24 | 0 | 12 | 19 | 16 | 16 | 11 | 11 | 0 | 15 | 11 | 9 | 10 | 11 | 11 | 0 | 2 | 2 | 6 | 6 | 6 | 6 | 0 | 6 | 9 | 18 | 17 | 13 | 9 | 0 | 16 | 16 | 14 | 15 | 15 | 12 | 0 | 11 | 17 | 16 | 17 | 43 | 36 | 0 | 48 | 59 | 71 | 62 | 53 | 25 | 0 | 45 | 53 | 53 | 63 | 59 | 53 | 0 | 15 | 12 | 15 | 16 | 11 | 19 | 0 | 6 | 13 | 22 | 18 | 18 | 10 | 0 | 10 | 0 | 2 | 14 | 39 | 22 | 0 | 44 | 41 | 46 | 58 | 67 | 61 | 0 | 52 | 61 | 37 | 47 | 49 | 54 | 0 | 46 | 36 | 40 | 66 | 65 | 65 | 0 | 72 | 67 | 73 | 67 | 50 | 42 | 0 | 40 | 33 | 29 | 34 | 57 | 74 | 0 | 80 | 72 | 54 | 46 | 37 | 39 | 8 | 34 | 31 | 36 | 37 | 61 | 77 | 0 | 0 | 0 | 0 | 0 | 79 | 76 | 0 | 66 | 72 | 60 | 40 | 45 | 59 | 0 | 82 | 83 | 83 | 85 | 79 | 76 | 0 | 74 | 72 | 68 | 88 | 97 | 92 | 0 | 84 | 88 | 71 | 56 | 41 | 37 | 0 | 59 | 84 | 99 | 99 | 113 | 117 | 9 | 99 | 82 | 113 | 116 | 107 | 117 | 0 | 114 | 142 | 166 | 190 | 210 | 204 | 2 | 168 | 123 | 87 | 71 | 76 | 76 | 0 | 70 | 65 | 74 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 109 | 123 | 8 | 120 | 111 | 120 | 130 | 134 | 135 | 8 | 161 | 192 | 195 | 184 | 190 | 210 | 43 | 234 | 247 | 210 | 234 | 243 | 237 | 49 | 242 | 221 | 230 | 230 | 242 | 289 | 75 | 273 | 257 | 277 | 251 | 265 | 228 | 82 | 235 | 240 | 301 | 332 | 338 | 336 | 94 | 370 | 370 | 365 | 331 | 317 | 300 | 87 | 318 | 309 | 362 | 354 | 329 | 262 | 81 | 261 | 267 | 249 | 247 | 269 | 282 | 64 | 296 | 315 | 316 | 333 | 305 | 301 | 80 | 324 | 326 | 324 | 299 | 313 | 308 | 38 | 288 | 234 | 232 | 233 | 222 | 234 | 20 | 274 | 253 | 257 | 236 | 226 | 225 | 15 | 206 | 193 | 182 | 186 | 202 | 205 | 0 | 210 | 211 | 242 | 247 | 275 | 274 | 0 | 273 | 275 | 269 | 259 | 285 | 249 | 0 | 222 | 248 | 284 | 283 | 300 | 314 | 0 | 326 | 368 | 372 | 372 | 384 | 385 | 0 | 361 | 334 | 329 | 338 | 339 | 336 | 0 | 300 | 292 | 308 | 320 | 302 | 305 | 0 | 305 | 295 | 306 | 330 | 336 | 357 | 0 | 357 | 344 | 305 | 297 | 289 | 278 | 0 | 261 | 260 | 258 | 267 | 272 | 273 | 0 | 286 | 271 | 272 | 254 | 249 | 243 | 0 | 241 | 234 | 226 | 263 | 246 | 228 | 0 | 221 | 224 | 224 | 230 | 234 | 221 | 0 | 211 | 216 | 221 | 210 | 210 | 208 | 0 | 172 | 158 | 157 | 154 | 153 | 149 | 0 | 153 | 153 | 140 | 141 | 136 | 124 | 0 | 124 | 123 | 125 | 120 | 107 | 107 | 0 | 121 | 122 | 133 | 123 | 121 | 114 | 0 | 111 | 110 | 112 | 122 | 123 | 123 | 0 | 106 | 110 | 111 | 103 | 101 | 92 | 0 | 95 | 100 | 107 | 117 | 114 | 111 | 0 | 121 | 120 | 120 | 118 | 111 | 106 | 0 | 100 | 100 | 97 | 93 | 101 | 92 | 0 | 86 | 93 | 89 | 67 | 64 | 64 | 0 | 64 | 65 | 73 | 73 | 73 | 72 | 0 | 65 | 52 | 66 | 62 | 58 | 60 | 0 | 65 | 70 | 70 | 70 | 73 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 65 | 0 | 65 | 65 | 65 | 51 | 51 | 49 | 0 | 47 | 42 | 32 | 32 | 32 | 32 | 0 | 32 | 32 | 32 | 32 | 32 | 32 | 0 | 32 | 33 | 39 | 39 | 39 | 39 | 0 | 39 | 39 | 39 | 39 | 39 | 39 | 0 | 39 | 39 | 39 | 39 | 34 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mason - Block | 2015-02-01: 5; 2015-02-02: 5; 2015-02-03: 5; 2015-02-04: 5; 2015-02-05: 5; 2015-02-07: 5; 2015-02-08: 5; 2015-02-09: 5; 2015-02-10: 5; 2015-02-11: 5; 2015-02-12: 5; 2015-02-14: 5; 2015-02-15: 5; 2015-02-16: 5; 2015-02-17: 5; 2015-02-18: 5; 2015-02-19: 5; 2015-02-26: 5; 2015-02-28: 5; 2015-03-01: 5; 2015-03-02: 5; 2015-03-03: 5; 2015-03-04: 5; 2015-03-05: 5; 2015-03-07: 5; 2015-03-08: 5; 2015-03-09: 5; 2015-04-13: 3; 2015-04-14: 4; 2015-04-15: 4; 2015-04-16: 4; 2015-04-18: 4; 2015-04-19: 5; 2015-04-20: 8; 2015-04-21: 8; 2015-04-22: 8; 2015-04-23: 8; 2015-04-25: 5; 2015-04-26: 4; 2015-04-27: 4; 2015-04-28: 4; 2015-04-29: 4; 2015-04-30: 3; 2015-07-30: 6; 2015-08-01: 16; 2015-08-02: 16; 2015-08-03: 16; 2015-08-04: 16; 2015-08-05: 16; 2015-08-06: 16; 2015-08-08: 16; 2015-08-09: 16; 2015-08-10: 16; 2015-08-11: 16; 2015-08-12: 16; 2015-08-13: 16; 2015-08-15: 16; 2015-08-16: 16; 2015-08-17: 10; 2015-08-23: 8; 2015-08-24: 10; 2015-08-25: 10; 2015-08-26: 16; 2015-08-27: 26; 2015-08-29: 26; 2015-08-30: 26; 2015-08-31: 26; 2015-09-01: 26; 2015-09-02: 26; 2015-09-03: 26; 2015-09-05: 26; 2015-09-06: 42; 2015-09-07: 42; 2015-09-08: 42; 2015-09-09: 34; 2015-09-10: 32; 2015-09-12: 32; 2015-09-13: 26; 2015-09-14: 16; 2015-09-15: 16; 2015-09-16: 16; 2015-09-17: 16; 2015-09-19: 16; 2015-09-20: 16; 2015-09-21: 16; 2015-09-22: 16; 2015-09-30: 5; 2015-10-01: 10; 2015-10-03: 10; 2015-10-04: 10; 2015-10-05: 10; 2015-10-06: 10; 2015-10-07: 10; 2015-10-08: 10; 2015-10-10: 10; 2015-10-11: 20; 2015-10-12: 20; 2015-10-13: 20; 2015-10-14: 20; 2015-10-15: 23; 2015-10-17: 35; 2015-10-18: 30; 2015-10-19: 25; 2015-10-20: 25; 2015-10-21: 25; 2015-10-22: 25; 2015-10-24: 25; 2015-10-25: 25; 2015-10-26: 25; 2015-10-27: 28; 2015-10-28: 30; 2015-10-29: 30; 2015-10-31: 30; 2015-11-01: 30; 2015-11-02: 29; 2015-11-03: 25; 2015-11-04: 25; 2015-11-05: 25; 2015-11-07: 25; 2015-11-08: 28; 2015-11-09: 55; 2015-11-10: 55; 2015-11-11: 61; 2015-11-12: 86; 2015-11-14: 83; 2015-11-15: 71; 2015-11-16: 74; 2015-11-17: 87; 2015-11-18: 87; 2015-11-19: 85; 2015-11-21: 79; 2015-11-22: 79; 2015-11-23: 79; 2015-11-24: 79; 2015-11-25: 78; 2015-11-26: 59; 2015-11-28: 59; 2015-11-29: 61; 2015-11-30: 70; 2015-12-01: 79; 2015-12-02: 128; 2015-12-03: 127; 2015-12-05: 122; 2015-12-06: 122; 2015-12-07: 124; 2015-12-08: 142; 2015-12-09: 142; 2015-12-10: 144; 2015-12-12: 152; 2015-12-13: 150; 2015-12-14: 144; 2015-12-15: 144; 2015-12-16: 156; 2015-12-17: 138; 2015-12-19: 129; 2015-12-20: 78; 2015-12-21: 79; 2015-12-22: 84; 2015-12-23: 84; 2015-12-24: 90; 2015-12-26: 112; 2015-12-27: 112; 2015-12-28: 110; 2015-12-29: 102; 2015-12-30: 102; 2015-12-31: 102; 2016-01-02: 102; 2016-01-03: 92; 2016-01-04: 76; 2016-01-05: 78; 2016-01-06: 86; 2016-01-07: 83; 2016-01-09: 70; 2016-01-10: 76; 2016-01-11: 95; 2016-01-12: 65; 2016-01-13: 85; 2016-01-14: 85; 2016-01-16: 85; 2016-01-17: 85; 2016-01-18: 85; 2016-01-19: 85; 2016-01-20: 75; 2016-01-21: 69; 2016-01-23: 40; 2016-01-24: 26; 2016-01-25: 53; 2016-01-26: 64; 2016-01-27: 64; 2016-01-28: 64; 2016-01-30: 64; 2016-01-31: 64; 2016-02-01: 64; 2016-02-02: 64; 2016-02-03: 64; 2016-02-04: 58; 2016-02-06: 31; 2016-02-07: 20; 2016-02-08: 20; 2016-02-09: 20; 2016-02-10: 20; 2016-02-11: 20; 2016-02-13: 20; 2016-02-14: 20; 2016-02-15: 20; 2016-02-16: 20
Mason - Plaster | 2015-07-25: 1; 2015-07-26: 1; 2015-07-27: 1; 2015-07-28: 1; 2015-07-29: 1; 2015-07-30: 1; 2015-08-01: 1; 2015-08-02: 1; 2015-08-25: 0; 2015-08-26: 1; 2015-08-27: 1; 2015-08-29: 1; 2015-08-30: 1; 2015-08-31: 1; 2015-09-01: 1; 2015-09-02: 1; 2015-09-03: 1; 2015-09-05: 1; 2015-09-06: 1; 2015-09-07: 1; 2015-09-08: 1; 2015-09-09: 1; 2015-09-10: 1; 2015-09-12: 1; 2015-09-13: 1; 2015-09-20: 4; 2015-09-21: 11; 2015-09-22: 11; 2015-09-29: 11; 2015-09-30: 11; 2015-10-01: 11; 2015-10-03: 11; 2015-10-04: 11; 2015-10-05: 11; 2015-10-06: 11; 2015-10-07: 11; 2015-10-08: 11; 2015-10-10: 15; 2015-10-11: 17; 2015-10-12: 17; 2015-10-13: 17; 2015-10-14: 17; 2015-10-15: 17; 2015-10-17: 17; 2015-10-18: 17; 2015-10-19: 15; 2015-10-20: 15; 2015-10-21: 15; 2015-10-22: 15; 2015-10-24: 17; 2015-10-25: 17; 2015-10-26: 23; 2015-10-27: 22; 2015-10-28: 13; 2015-10-29: 13; 2015-10-31: 13; 2015-11-01: 13; 2015-11-02: 11; 2015-11-03: 11; 2015-11-04: 22; 2015-11-05: 22; 2015-11-07: 27; 2015-11-08: 30; 2015-11-09: 32; 2015-11-10: 34; 2015-11-11: 34; 2015-11-12: 34; 2015-11-14: 37; 2015-11-15: 37; 2015-11-16: 36; 2015-11-17: 32; 2015-11-18: 33; 2015-11-19: 33; 2015-11-21: 33; 2015-11-22: 33; 2015-11-23: 30; 2015-11-24: 30; 2015-11-25: 30; 2015-11-26: 24; 2015-11-28: 23; 2015-11-29: 31; 2015-11-30: 34; 2015-12-01: 34; 2015-12-02: 34; 2015-12-03: 34; 2015-12-05: 34; 2015-12-06: 20; 2015-12-07: 15; 2015-12-08: 15; 2015-12-09: 15; 2015-12-10: 14; 2015-12-12: 16; 2015-12-13: 19; 2015-12-14: 19; 2015-12-15: 17; 2015-12-16: 17; 2015-12-17: 17; 2015-12-19: 18; 2015-12-20: 22; 2015-12-21: 26; 2015-12-22: 26; 2015-12-23: 26; 2015-12-24: 28; 2015-12-26: 35; 2015-12-27: 37; 2015-12-28: 54; 2015-12-29: 48; 2015-12-30: 38; 2015-12-31: 38; 2016-01-02: 38; 2016-01-03: 39; 2016-01-04: 42; 2016-01-05: 44; 2016-01-06: 52; 2016-01-07: 61; 2016-01-09: 72; 2016-01-10: 72; 2016-01-11: 78; 2016-01-12: 92; 2016-01-13: 92; 2016-01-14: 90; 2016-01-16: 82; 2016-01-17: 82; 2016-01-18: 82; 2016-01-19: 89; 2016-01-20: 122; 2016-01-21: 111; 2016-01-23: 115; 2016-01-24: 129; 2016-01-25: 133; 2016-01-26: 133; 2016-01-27: 149; 2016-01-28: 158; 2016-01-30: 158; 2016-01-31: 158; 2016-02-01: 147; 2016-02-02: 147; 2016-02-03: 147; 2016-02-04: 147; 2016-02-06: 140; 2016-02-07: 114; 2016-02-08: 114; 2016-02-09: 114; 2016-02-10: 113; 2016-02-11: 108; 2016-02-13: 87; 2016-02-14: 77; 2016-02-15: 82; 2016-02-16: 84; 2016-02-17: 84; 2016-02-18: 84; 2016-02-20: 83; 2016-02-21: 76; 2016-02-22: 73; 2016-02-23: 71; 2016-02-24: 53; 2016-02-25: 72; 2016-02-27: 68; 2016-02-28: 66; 2016-02-29: 53; 2016-03-01: 50; 2016-03-02: 39; 2016-03-03: 39; 2016-03-05: 39; 2016-03-06: 39; 2016-03-07: 39; 2016-03-08: 39; 2016-03-09: 39; 2016-03-10: 39; 2016-03-12: 39; 2016-03-13: 39; 2016-03-14: 39; 2016-03-15: 39; 2016-03-16: 39; 2016-03-17: 39; 2016-03-19: 37; 2016-03-20: 37; 2016-03-21: 37; 2016-03-22: 37; 2016-03-23: 37; 2016-03-24: 37; 2016-03-26: 37; 2016-03-27: 37; 2016-03-28: 37; 2016-03-29: 37; 2016-03-30: 37; 2016-03-31: 17; 2016-04-02: 17; 2016-04-03: 17; 2016-04-04: 17; 2016-04-05: 17; 2016-04-06: 17; 2016-04-07: 17; 2016-04-09: 17; 2016-04-10: 17; 2016-04-11: 17; 2016-04-12: 17; 2016-04-13: 17; 2016-04-14: 17; 2016-04-16: 17; 2016-04-17: 17; 2016-04-18: 17; 2016-04-19: 17; 2016-04-20: 17; 2016-04-21: 17; 2016-04-23: 17; 2016-04-24: 17; 2016-04-25: 17; 2016-04-26: 17; 2016-04-27: 17; 2016-04-28: 17; 2016-04-30: 17; 2016-05-01: 17; 2016-05-02: 17; 2016-05-03: 17; 2016-05-04: 17; 2016-05-05: 17; 2016-05-07: 17; 2016-05-08: 17; 2016-05-09: 17; 2016-05-10: 17; 2016-05-11: 17; 2016-05-12: 17; 2016-05-14: 17; 2016-05-15: 17; 2016-05-16: 17; 2016-05-17: 17; 2016-05-18: 17; 2016-05-19: 17; 2016-05-21: 17; 2016-05-22: 17; 2016-05-23: 17; 2016-05-24: 17; 2016-05-25: 17; 2016-05-26: 17; 2016-05-28: 17; 2016-05-29: 17; 2016-05-30: 17; 2016-05-31: 17; 2016-06-01: 17; 2016-06-02: 17; 2016-06-04: 17; 2016-06-05: 17; 2016-06-06: 17; 2016-06-07: 17; 2016-06-08: 17; 2016-06-09: 17; 2016-06-11: 17; 2016-06-12: 17; 2016-06-13: 17; 2016-06-14: 17; 2016-06-15: 17; 2016-06-16: 17; 2016-06-18: 17; 2016-06-19: 17; 2016-06-20: 17; 2016-06-21: 17; 2016-06-22: 17; 2016-06-23: 17; 2016-06-25: 17; 2016-06-26: 17; 2016-06-27: 17; 2016-06-28: 17; 2016-06-29: 17; 2016-06-30: 17; 2016-07-02: 17; 2016-07-03: 17; 2016-07-04: 17; 2016-07-05: 17; 2016-07-06: 17; 2016-07-12: 17; 2016-07-13: 17; 2016-07-14: 17; 2016-07-16: 17; 2016-07-17: 17; 2016-07-18: 17; 2016-07-19: 17; 2016-07-20: 17; 2016-07-21: 17; 2016-07-23: 17; 2016-07-24: 17; 2016-07-25: 17; 2016-07-26: 17; 2016-07-27: 17; 2016-07-28: 17; 2016-07-30: 17; 2016-07-31: 17; 2016-08-01: 17; 2016-08-02: 17; 2016-08-03: 17; 2016-08-04: 17; 2016-08-06: 17; 2016-08-07: 17; 2016-08-08: 17; 2016-08-09: 17; 2016-08-10: 17; 2016-08-11: 17; 2016-08-13: 17; 2016-08-14: 17; 2016-08-15: 17; 2016-08-16: 17; 2016-08-17: 17; 2016-08-18: 17; 2016-08-20: 17; 2016-08-21: 17; 2016-08-22: 17; 2016-08-23: 17; 2016-08-24: 14
Painter - BTCC | 2015-01-06: 4; 2015-01-07: 4; 2015-01-08: 4; 2015-01-10: 4; 2015-01-11: 4; 2015-01-12: 4; 2015-01-13: 4; 2015-01-18: 3; 2015-01-19: 3; 2015-01-20: 3; 2015-01-21: 3; 2015-01-22: 3; 2015-02-05: 9; 2015-02-07: 9; 2015-02-08: 9; 2015-02-09: 9; 2015-02-10: 9; 2015-02-11: 9; 2015-02-18: 4; 2015-02-19: 14; 2015-02-21: 14; 2015-02-22: 14; 2015-02-23: 20; 2015-02-24: 20; 2015-02-25: 14; 2015-02-26: 24; 2015-02-28: 28; 2015-03-01: 22; 2015-03-02: 28; 2015-03-03: 28; 2015-03-04: 14; 2015-03-05: 10; 2015-03-07: 14; 2015-03-08: 4; 2015-03-09: 4; 2015-03-10: 4; 2015-03-11: 4; 2015-03-12: 4; 2015-03-29: 0; 2015-03-30: 4; 2015-03-31: 4; 2015-04-01: 4; 2015-04-02: 4; 2015-04-04: 4; 2015-04-05: 8; 2015-04-06: 8; 2015-04-07: 8; 2015-04-08: 4; 2015-04-21: 1; 2015-04-22: 11; 2015-04-23: 15; 2015-04-25: 15; 2015-04-26: 10; 2015-04-27: 10; 2015-04-28: 14; 2015-04-29: 10; 2015-04-30: 5; 2015-05-02: 11; 2015-05-03: 10; 2015-05-04: 10; 2015-05-05: 10; 2015-05-06: 11; 2015-05-07: 12; 2015-05-09: 2; 2015-05-10: 2; 2015-05-11: 1; 2015-05-12: 3; 2015-05-13: 3; 2015-05-14: 2; 2015-05-17: 4; 2015-05-18: 4; 2015-05-19: 4; 2015-05-20: 4; 2015-05-21: 0; 2015-05-26: 0; 2015-05-27: 4; 2015-05-28: 11; 2015-05-30: 11; 2015-05-31: 8; 2015-06-01: 8; 2015-06-02: 6; 2015-06-03: 6; 2015-06-04: 6; 2015-06-06: 5; 2015-06-07: 2; 2015-06-08: 1; 2015-06-09: 1; 2015-06-10: 1; 2015-06-11: 1; 2015-06-16: 2; 2015-06-17: 6; 2015-06-18: 8; 2015-06-20: 8; 2015-06-21: 6; 2015-06-22: 2; 2015-06-29: 0; 2015-06-30: 2; 2015-07-01: 2; 2015-07-02: 2; 2015-07-04: 2; 2015-07-05: 2; 2015-07-06: 2; 2015-07-07: 2; 2015-07-29: 2; 2015-07-30: 3; 2015-08-01: 3; 2015-08-02: 4; 2015-08-03: 6; 2015-08-04: 8; 2015-08-05: 8; 2015-08-06: 6; 2015-08-08: 5; 2015-08-09: 5; 2015-08-10: 4; 2015-08-11: 2; 2015-08-17: 4; 2015-08-18: 4; 2015-08-19: 4; 2015-08-20: 4; 2015-10-03: 4; 2015-10-04: 4; 2015-10-05: 4; 2015-10-06: 4; 2015-10-07: 4; 2015-10-08: 4; 2015-10-10: 4; 2015-10-11: 4; 2015-10-14: 8; 2015-10-15: 20; 2015-10-17: 20; 2015-10-18: 20; 2015-10-19: 20; 2015-10-20: 20; 2015-10-21: 20; 2015-10-22: 20; 2015-10-24: 20; 2015-10-25: 20; 2015-10-26: 20; 2015-10-27: 20; 2015-10-28: 20; 2015-10-29: 20; 2015-10-31: 20; 2015-11-01: 18; 2015-11-02: 15; 2015-11-03: 15; 2015-11-04: 15; 2015-11-05: 15; 2015-11-07: 15; 2015-11-08: 15; 2015-11-09: 15; 2015-11-10: 15; 2015-11-11: 15; 2015-11-12: 15; 2015-11-14: 25; 2015-11-15: 35; 2015-11-16: 35; 2015-11-17: 35; 2015-11-18: 31; 2015-11-19: 24; 2015-11-21: 24; 2015-11-22: 24; 2015-11-23: 44; 2015-11-24: 44; 2015-11-25: 42; 2015-11-26: 40; 2015-11-28: 40; 2015-11-29: 40; 2015-11-30: 40; 2015-12-01: 38; 2015-12-02: 35; 2015-12-03: 35; 2015-12-05: 35; 2015-12-06: 35; 2015-12-07: 35; 2015-12-08: 35; 2015-12-09: 35; 2015-12-10: 30; 2015-12-12: 30; 2015-12-13: 30; 2015-12-14: 30; 2015-12-15: 30; 2015-12-16: 34; 2015-12-17: 50; 2015-12-19: 43; 2015-12-20: 35; 2015-12-21: 35; 2015-12-22: 35; 2015-12-23: 35; 2015-12-24: 38; 2015-12-26: 39; 2015-12-27: 39; 2015-12-28: 24; 2015-12-29: 24; 2015-12-30: 24; 2015-12-31: 21; 2016-01-02: 21; 2016-01-03: 20; 2016-01-04: 19; 2016-01-05: 19; 2016-01-06: 19; 2016-01-07: 23; 2016-01-09: 38; 2016-01-10: 35; 2016-01-11: 35; 2016-01-12: 39; 2016-01-13: 55; 2016-01-14: 55; 2016-01-16: 55; 2016-01-17: 55; 2016-01-18: 55; 2016-01-19: 55; 2016-01-20: 55; 2016-01-21: 40; 2016-01-23: 40; 2016-01-24: 44; 2016-01-25: 59; 2016-01-26: 55; 2016-01-27: 55; 2016-01-28: 61; 2016-01-30: 83; 2016-01-31: 123; 2016-02-01: 131; 2016-02-02: 131; 2016-02-03: 133; 2016-02-04: 139; 2016-02-06: 139; 2016-02-07: 145; 2016-02-08: 145; 2016-02-09: 148; 2016-02-10: 159; 2016-02-11: 162; 2016-02-13: 150; 2016-02-14: 152; 2016-02-15: 158; 2016-02-16: 144; 2016-02-17: 121; 2016-02-18: 123; 2016-02-20: 125; 2016-02-21: 126; 2016-02-22: 130; 2016-02-23: 142; 2016-02-24: 143; 2016-02-25: 143; 2016-02-27: 141; 2016-02-28: 138; 2016-02-29: 126; 2016-03-01: 125; 2016-03-02: 120; 2016-03-03: 110; 2016-03-05: 100; 2016-03-06: 91; 2016-03-07: 84; 2016-03-08: 84; 2016-03-09: 82; 2016-03-10: 76; 2016-03-12: 82; 2016-03-13: 78; 2016-03-14: 82; 2016-03-15: 81; 2016-03-16: 82; 2016-03-17: 71; 2016-03-19: 66; 2016-03-20: 66; 2016-03-21: 66; 2016-03-22: 109; 2016-03-23: 99; 2016-03-24: 99; 2016-03-26: 99; 2016-03-27: 99; 2016-03-28: 99; 2016-03-29: 103; 2016-03-30: 103; 2016-03-31: 104; 2016-04-02: 104; 2016-04-03: 104; 2016-04-04: 102; 2016-04-05: 98; 2016-04-06: 97; 2016-04-07: 94; 2016-04-09: 64; 2016-04-10: 64; 2016-04-11: 64; 2016-04-12: 64; 2016-04-13: 64; 2016-04-14: 64; 2016-04-16: 65; 2016-04-17: 66; 2016-04-18: 62; 2016-04-19: 62; 2016-04-20: 62; 2016-04-21: 62; 2016-04-23: 62; 2016-04-24: 62; 2016-04-25: 62; 2016-04-26: 61; 2016-04-27: 45; 2016-04-28: 45; 2016-04-30: 62; 2016-05-01: 62; 2016-05-02: 78; 2016-05-03: 78; 2016-05-04: 78; 2016-05-05: 78; 2016-05-07: 78; 2016-05-08: 78; 2016-05-09: 82; 2016-05-10: 90; 2016-05-11: 88; 2016-05-12: 88; 2016-05-14: 72; 2016-05-15: 72; 2016-05-16: 74; 2016-05-17: 67; 2016-05-18: 67; 2016-05-19: 52; 2016-05-21: 52; 2016-05-22: 52; 2016-05-23: 52; 2016-05-24: 52; 2016-05-25: 52; 2016-05-26: 52; 2016-05-28: 52; 2016-05-29: 52; 2016-05-30: 52; 2016-05-31: 52; 2016-06-01: 50; 2016-06-02: 49; 2016-06-04: 41; 2016-06-05: 41; 2016-06-06: 38; 2016-06-07: 31; 2016-06-08: 37; 2016-06-09: 37; 2016-06-11: 41; 2016-06-12: 48; 2016-06-13: 46; 2016-06-14: 37; 2016-06-15: 37; 2016-06-16: 37; 2016-06-18: 37; 2016-06-19: 38; 2016-06-20: 46; 2016-06-21: 46; 2016-06-22: 46; 2016-06-23: 45; 2016-06-25: 41; 2016-06-26: 35; 2016-06-27: 49; 2016-06-28: 45; 2016-06-29: 41; 2016-06-30: 43; 2016-07-02: 48; 2016-07-03: 53; 2016-07-04: 53; 2016-07-05: 53; 2016-07-06: 51; 2016-07-12: 43; 2016-07-13: 43; 2016-07-14: 43; 2016-07-16: 43; 2016-07-17: 43; 2016-07-18: 43; 2016-07-19: 29; 2016-07-20: 29; 2016-07-21: 27; 2016-07-23: 25; 2016-07-24: 20; 2016-07-25: 15; 2016-07-26: 15; 2016-07-27: 15; 2016-07-28: 15; 2016-07-30: 15; 2016-07-31: 15; 2016-08-01: 15; 2016-08-02: 15; 2016-08-03: 15; 2016-08-04: 15; 2016-08-06: 15; 2016-08-07: 15; 2016-08-08: 15; 2016-08-09: 15; 2016-08-10: 15; 2016-08-11: 15; 2016-08-13: 15; 2016-08-14: 15; 2016-08-15: 15; 2016-08-16: 15; 2016-08-17: 15; 2016-08-18: 15; 2016-08-20: 15; 2016-08-21: 15; 2016-08-22: 15; 2016-08-23: 15; 2016-08-24: 15; 2016-08-25: 15; 2016-08-27: 15; 2016-08-28: 15; 2016-08-29: 15; 2016-08-30: 15; 2016-08-31: 15; 2016-09-01: 15; 2016-09-03: 15; 2016-09-04: 15; 2016-09-05: 15; 2016-09-06: 15; 2016-09-07: 15; 2016-09-13: 15; 2016-09-14: 15; 2016-09-15: 12
Mason - Tile Sitter | 2015-11-07: 5; 2015-11-08: 8; 2015-11-09: 8; 2015-11-10: 8; 2015-11-11: 8; 2015-11-12: 8; 2015-11-14: 8; 2015-11-15: 8; 2015-11-16: 10; 2015-11-17: 10; 2015-11-18: 5; 2015-11-19: 2; 2015-11-21: 2; 2015-11-22: 2; 2015-11-23: 2; 2015-11-24: 2; 2015-11-25: 2; 2015-11-26: 2; 2015-12-07: 14; 2015-12-08: 16; 2015-12-09: 16; 2015-12-10: 16; 2015-12-12: 16; 2015-12-13: 17; 2015-12-14: 18; 2015-12-15: 20; 2015-12-16: 26; 2015-12-17: 26; 2015-12-19: 18; 2015-12-20: 20; 2015-12-21: 20; 2015-12-22: 22; 2015-12-23: 22; 2015-12-24: 21; 2015-12-26: 20; 2015-12-27: 18; 2015-12-28: 20; 2015-12-29: 20; 2015-12-30: 15; 2015-12-31: 13; 2016-01-02: 14; 2016-01-03: 14; 2016-01-04: 14; 2016-01-05: 14; 2016-01-06: 13; 2016-01-07: 12; 2016-01-09: 8; 2016-01-10: 16; 2016-01-11: 15; 2016-01-12: 14; 2016-01-13: 14; 2016-01-14: 14; 2016-01-16: 13; 2016-01-17: 18; 2016-01-18: 18; 2016-01-19: 18; 2016-01-20: 12; 2016-01-21: 6; 2016-01-23: 6; 2016-01-24: 6; 2016-01-25: 6; 2016-01-26: 6; 2016-01-27: 7; 2016-01-28: 10; 2016-01-30: 14; 2016-01-31: 24; 2016-02-01: 30; 2016-02-02: 30; 2016-02-03: 30; 2016-02-04: 30; 2016-02-06: 30; 2016-02-07: 31; 2016-02-08: 35; 2016-02-09: 30; 2016-02-10: 32; 2016-02-11: 37; 2016-02-13: 34; 2016-02-14: 34; 2016-02-15: 38; 2016-02-16: 49; 2016-02-17: 59; 2016-02-18: 60; 2016-02-20: 62; 2016-02-21: 61; 2016-02-22: 72; 2016-02-23: 84; 2016-02-24: 106; 2016-02-25: 106; 2016-02-27: 106; 2016-02-28: 101; 2016-02-29: 89; 2016-03-01: 87; 2016-03-02: 84; 2016-03-03: 83; 2016-03-05: 77; 2016-03-06: 86; 2016-03-07: 85; 2016-03-08: 94; 2016-03-09: 97; 2016-03-10: 98; 2016-03-12: 104; 2016-03-13: 100; 2016-03-14: 101; 2016-03-15: 107; 2016-03-16: 99; 2016-03-17: 107; 2016-03-19: 99; 2016-03-20: 104; 2016-03-21: 100; 2016-03-22: 92; 2016-03-23: 72; 2016-03-24: 66; 2016-03-26: 59; 2016-03-27: 62; 2016-03-28: 62; 2016-03-29: 64; 2016-03-30: 67; 2016-03-31: 72; 2016-04-02: 60; 2016-04-03: 53; 2016-04-04: 50; 2016-04-05: 51; 2016-04-06: 52; 2016-04-07: 53; 2016-04-09: 53; 2016-04-10: 53; 2016-04-11: 53; 2016-04-12: 53; 2016-04-13: 52; 2016-04-14: 48; 2016-04-16: 41; 2016-04-17: 34; 2016-04-18: 17; 2016-04-19: 17; 2016-04-20: 20; 2016-04-21: 33; 2016-04-23: 35; 2016-04-24: 43; 2016-04-25: 43; 2016-04-26: 44; 2016-04-27: 47; 2016-04-28: 46; 2016-04-30: 44; 2016-05-01: 46; 2016-05-02: 44; 2016-05-03: 44; 2016-05-04: 44; 2016-05-05: 46; 2016-05-07: 46; 2016-05-08: 40; 2016-05-09: 23; 2016-05-10: 22; 2016-05-11: 14; 2016-05-12: 15; 2016-05-14: 13; 2016-05-15: 13; 2016-05-16: 12; 2016-05-17: 9; 2016-05-18: 7; 2016-05-19: 10; 2016-05-21: 10; 2016-05-22: 17; 2016-05-23: 26; 2016-05-24: 34; 2016-05-25: 31; 2016-05-26: 30; 2016-05-28: 33; 2016-05-29: 33; 2016-05-30: 33; 2016-05-31: 37; 2016-06-01: 34; 2016-06-02: 29; 2016-06-04: 28; 2016-06-05: 28; 2016-06-06: 28; 2016-06-07: 28; 2016-06-08: 23; 2016-06-09: 14; 2016-06-11: 4; 2016-06-12: 4; 2016-06-13: 4; 2016-07-06: 5; 2016-07-12: 5; 2016-07-13: 5; 2016-07-14: 5; 2016-07-16: 5; 2016-07-17: 5; 2016-07-18: 5; 2016-07-19: 5; 2016-07-20: 5; 2016-07-21: 5; 2016-07-23: 5; 2016-07-24: 5; 2016-08-07: 1; 2016-08-08: 7; 2016-08-09: 7; 2016-08-10: 7; 2016-08-11: 7; 2016-08-13: 7; 2016-08-14: 7; 2016-08-15: 7; 2016-08-16: 7; 2016-08-17: 7; 2016-08-18: 7; 2016-08-20: 7; 2016-08-21: 7; 2016-08-22: 7; 2016-08-23: 7; 2016-08-24: 5
Heavy Equipment Operator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 7 | 7 | 7 | 7 | 7 | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 20 | 20 | 20 | 14 | 14 | 19 | 0 | 23 | 18 | 18 | 18 | 18 | 18 | 0 | 15 | 15 | 20 | 19 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 6 | 6 | 11 | 11 | 6 | 6 | 0 | 2 | 2 | 7 | 2 | 2 | 2 | 0 | 0 | 0 | 11 | 12 | 12 | 17 | 0 | 12 | 18 | 29 | 29 | 18 | 17 | 0 | 17 | 11 | 11 | 17 | 6 | 6 | 0 | 6 | 6 | 6 | 0 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 6 | 12 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 14 | 7 | 6 | 6 | 0 | 11 | 13 | 12 | 8 | 6 | 6 | 0 | 6 | 11 | 7 | 7 | 15 | 6 | 0 | 6 | 4 | 8 | 2 | 9 | 0 | 0 | 9 | 0 | 0 | 2 | 5 | 3 | 0 | 2 | 3 | 3 | 2 | 0 | 5 | 0 | 0 | 5 | 43 | 52 | 52 | 52 | 0 | 52 | 14 | 2 | 10 | 20 | 5 | 0 | 5 | 2 | 2 | 0 | 0 | 8 | 0 | 3 | 18 | 26 | 26 | 26 | 26 | 0 | 34 | 16 | 2 | 8 | 5 | 1 | 0 | 1 | 1 | 11 | 14 | 1 | 3 | 0 | 4 | 6 | 4 | 0 | 0 | 0 | 0 | 3 | 2 | 7 | 14 | 4 | 3 | 0 | 2 | 2 | 5 | 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 11 | 11 | 5 | 3 | 3 | 0 | 8 | 13 | 14 | 3 | 3 | 6 | 0 | 6 | 3 | 1 | 1 | 10 | 15 | 0 | 1 | 1 | 1 | 7 | 6 | 0 | 0 | 14 | 5 | 0 | 0 | 2 | 5 | 4 | 5 | 9 | 35 | 8 | 0 | 0 | 0 | 0 | 5 | 20 | 7 | 8 | 5 | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 17 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 13 | 0 | 9 | 12 | 18 | 14 | 0 | 2 | 4 | 9 | 6 | 0 | 3 | 5 | 20 | 0 | 27 | 6 | 7 | 18 | 15 | 7 | 0 | 19 | 25 | 6 | 19 | 12 | 4 | 1 | 22 | 1 | 8 | 20 | 31 | 22 | 14 | 16 | 20 | 2 | 12 | 18 | 1 | 7 | 21 | 19 | 9 | 6 | 18 | 18 | 9 | 34 | 0 | 3 | 5 | 8 | 18 | 4 | 14 | 2 | 7 | 6 | 25 | 15 | 14 | 0 | 0 | 4 | 10 | 2 | 7 | 18 | 10 | 0 | 0 | 1 | 3 | 4 | 14 | 0 | 1 | 8 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcon - Excavation | 2014-11-24: 4; 2014-11-25: 4; 2014-11-26: 4; 2014-11-27: 4; 2014-11-29: 4; 2014-11-30: 4; 2014-12-01: 4; 2014-12-02: 4; 2014-12-03: 4; 2014-12-04: 4; 2014-12-06: 4; 2014-12-07: 4; 2014-12-08: 4; 2014-12-09: 4; 2014-12-10: 4; 2014-12-11: 5; 2014-12-13: 5; 2014-12-14: 5; 2014-12-15: 5; 2014-12-16: 5; 2014-12-17: 5; 2014-12-20: 5; 2014-12-21: 5; 2014-12-22: 5; 2014-12-23: 5; 2014-12-24: 5; 2014-12-25: 5; 2014-12-27: 14; 2014-12-28: 14; 2014-12-29: 14; 2014-12-30: 14; 2014-12-31: 14; 2015-01-01: 14; 2015-01-03: 34; 2015-01-04: 34; 2015-01-05: 34; 2015-01-06: 34; 2015-01-07: 34; 2015-01-08: 34; 2015-01-10: 44; 2015-01-11: 44; 2015-01-12: 44; 2015-01-13: 40; 2015-01-14: 40; 2015-01-15: 40; 2015-01-17: 40; 2015-01-18: 40; 2015-01-19: 40; 2015-01-20: 40; 2015-01-21: 40; 2015-01-22: 40; 2015-01-24: 40; 2015-01-25: 40; 2015-01-26: 40; 2015-01-27: 40; 2015-01-28: 40; 2015-01-29: 40; 2015-01-31: 30; 2015-02-01: 30; 2015-02-02: 30; 2015-02-03: 30; 2015-02-04: 30; 2015-02-05: 30; 2015-02-07: 10; 2015-02-08: 10; 2015-02-09: 10; 2015-02-10: 10; 2015-02-11: 10; 2015-02-12: 10
Subcon - Backfilling | 2015-03-22: 6; 2015-03-23: 10; 2015-03-24: 10; 2015-03-25: 10; 2015-03-26: 10; 2015-03-28: 10; 2015-03-29: 10; 2015-03-30: 10; 2015-03-31: 10; 2015-04-01: 10; 2015-04-02: 10; 2015-04-04: 10; 2015-04-05: 10; 2015-04-06: 10; 2015-04-07: 10; 2015-04-08: 10; 2015-04-09: 10; 2015-04-11: 10; 2015-04-12: 14; 2015-04-13: 20; 2015-04-14: 14; 2015-04-15: 10; 2015-04-16: 10; 2015-04-18: 10; 2015-04-19: 10; 2015-04-20: 10; 2015-04-21: 10; 2015-04-22: 10; 2015-04-23: 10; 2015-04-25: 10; 2015-04-26: 6; 2015-04-30: 2; 2015-05-02: 5; 2015-05-03: 5; 2015-05-04: 5; 2015-05-05: 5; 2015-05-06: 5; 2015-05-07: 5; 2015-05-09: 5; 2015-05-10: 5; 2015-05-11: 15; 2015-05-12: 15; 2015-05-13: 15; 2015-05-14: 15; 2015-05-16: 15; 2015-05-17: 15; 2015-05-18: 43; 2015-05-19: 50; 2015-05-20: 40; 2015-05-21: 40; 2015-05-23: 40; 2015-05-24: 10; 2015-06-07: 8; 2015-06-08: 20; 2015-06-09: 20; 2015-06-10: 20; 2015-06-11: 20; 2015-06-13: 20; 2015-06-14: 12; 2015-07-02: 1; 2015-07-04: 4; 2015-07-05: 4; 2015-07-06: 4; 2015-07-07: 4; 2015-07-08: 4; 2015-07-09: 4; 2015-07-11: 4; 2015-07-12: 4; 2015-07-13: 4; 2015-07-14: 4; 2015-07-15: 4; 2015-07-16: 4; 2015-07-22: 4; 2015-07-23: 4; 2015-07-25: 4; 2015-07-26: 4; 2015-07-27: 4; 2015-07-28: 4; 2015-07-29: 4; 2015-07-30: 3; 2015-08-20: 10; 2015-08-22: 10; 2015-08-23: 10; 2015-08-24: 10; 2015-08-25: 10; 2015-08-26: 10; 2015-08-27: 10; 2015-08-29: 10; 2015-08-30: 10; 2015-08-31: 10
Subcon - Aluminium & Glass | 2016-01-06: 20; 2016-01-07: 20; 2016-01-09: 20; 2016-01-10: 20; 2016-01-11: 24; 2016-01-12: 50; 2016-01-13: 60; 2016-01-14: 60; 2016-01-16: 60; 2016-01-17: 60; 2016-01-18: 60; 2016-01-19: 60; 2016-01-20: 60; 2016-01-21: 60; 2016-01-23: 60; 2016-01-24: 60; 2016-01-25: 60; 2016-01-26: 66; 2016-01-27: 66; 2016-01-28: 66; 2016-01-30: 66; 2016-01-31: 67; 2016-02-01: 72; 2016-02-02: 72; 2016-02-03: 75; 2016-02-04: 78; 2016-02-06: 78; 2016-02-07: 52; 2016-02-08: 52; 2016-02-09: 52; 2016-02-10: 52; 2016-02-11: 47; 2016-02-13: 16; 2016-02-14: 6; 2016-02-15: 3; 2016-02-21: 4; 2016-02-22: 20; 2016-02-23: 20; 2016-02-24: 20; 2016-02-25: 20; 2016-02-27: 20; 2016-02-28: 20; 2016-02-29: 20; 2016-03-01: 20; 2016-03-02: 20; 2016-03-03: 20; 2016-03-05: 24; 2016-03-06: 40; 2016-03-07: 40; 2016-03-08: 40; 2016-03-09: 40; 2016-03-10: 40; 2016-03-12: 40; 2016-03-13: 40; 2016-03-14: 40; 2016-03-15: 40; 2016-03-16: 40; 2016-03-17: 44; 2016-03-19: 60; 2016-03-20: 60; 2016-03-21: 60; 2016-03-22: 62; 2016-03-23: 58; 2016-03-24: 42; 2016-03-26: 42; 2016-03-27: 42; 2016-03-28: 42; 2016-03-29: 42; 2016-03-30: 42; 2016-03-31: 42; 2016-04-02: 42; 2016-04-03: 54; 2016-04-04: 82; 2016-04-05: 81; 2016-04-06: 81; 2016-04-07: 98; 2016-04-09: 112; 2016-04-10: 112; 2016-04-11: 112; 2016-04-12: 112; 2016-04-13: 112; 2016-04-14: 112; 2016-04-16: 112; 2016-04-17: 112; 2016-04-18: 116; 2016-04-19: 114; 2016-04-20: 118; 2016-04-21: 130; 2016-04-23: 117; 2016-04-24: 109; 2016-04-25: 96; 2016-04-26: 96; 2016-04-27: 96; 2016-04-28: 104; 2016-04-30: 116; 2016-05-01: 137; 2016-05-02: 144; 2016-05-03: 168; 2016-05-04: 170; 2016-05-05: 134; 2016-05-07: 122; 2016-05-08: 124; 2016-05-09: 124; 2016-05-10: 117; 2016-05-11: 104; 2016-05-12: 100; 2016-05-14: 100; 2016-05-15: 92; 2016-05-16: 80; 2016-05-17: 80; 2016-05-18: 80; 2016-05-19: 80; 2016-05-21: 100; 2016-05-22: 105; 2016-05-23: 124; 2016-05-24: 124; 2016-05-25: 121; 2016-05-26: 102; 2016-05-28: 102; 2016-05-29: 100; 2016-05-30: 100; 2016-05-31: 100; 2016-06-01: 60; 2016-06-02: 52; 2016-06-04: 20; 2016-06-05: 20; 2016-06-06: 20; 2016-06-07: 20; 2016-06-08: 20; 2016-06-09: 20; 2016-06-11: 20; 2016-06-12: 20; 2016-06-13: 20; 2016-06-14: 20; 2016-06-15: 20; 2016-06-16: 14
Subcon - Wooden Door | 2015-11-28: 16; 2015-11-29: 16; 2015-11-30: 16; 2015-12-01: 16; 2015-12-02: 16; 2015-12-03: 16; 2015-12-05: 16; 2015-12-06: 16; 2015-12-07: 16; 2015-12-08: 16; 2015-12-09: 8; 2015-12-10: 8; 2015-12-12: 8; 2015-12-13: 8; 2015-12-14: 8; 2015-12-15: 8; 2015-12-16: 8; 2015-12-17: 8; 2015-12-19: 8; 2015-12-20: 8; 2015-12-24: 11; 2015-12-26: 16; 2015-12-27: 16; 2015-12-28: 16; 2015-12-29: 16; 2015-12-30: 16; 2015-12-31: 16; 2016-01-02: 39; 2016-01-03: 52; 2016-01-04: 52; 2016-01-05: 46; 2016-01-06: 44; 2016-01-07: 44; 2016-01-09: 44; 2016-01-10: 44; 2016-01-11: 44; 2016-01-12: 44; 2016-01-13: 42; 2016-01-14: 36; 2016-01-16: 16; 2016-01-17: 10; 2016-01-18: 8; 2016-01-19: 8; 2016-01-20: 8; 2016-01-21: 8; 2016-01-23: 8; 2016-01-24: 22; 2016-01-25: 26; 2016-01-26: 20; 2016-01-27: 23; 2016-01-28: 36; 2016-01-30: 36; 2016-01-31: 36; 2016-02-01: 40; 2016-02-02: 56; 2016-02-03: 56; 2016-02-04: 56; 2016-02-06: 56; 2016-02-07: 42; 2016-02-08: 36; 2016-02-09: 36; 2016-02-10: 36; 2016-02-11: 36; 2016-02-13: 36; 2016-02-14: 36; 2016-02-15: 32; 2016-02-16: 16; 2016-02-17: 16; 2016-02-18: 19; 2016-02-20: 29; 2016-02-21: 16; 2016-02-22: 16; 2016-02-23: 18; 2016-02-24: 24; 2016-02-25: 24; 2016-02-27: 24; 2016-02-28: 24; 2016-02-29: 24; 2016-03-01: 24; 2016-03-02: 28; 2016-03-03: 46; 2016-03-05: 52; 2016-03-06: 55; 2016-03-07: 68; 2016-03-08: 68; 2016-03-09: 68; 2016-03-10: 71; 2016-03-12: 76; 2016-03-13: 73; 2016-03-14: 58; 2016-03-15: 50; 2016-03-16: 56; 2016-03-17: 68; 2016-03-19: 68; 2016-03-20: 68; 2016-03-21: 68; 2016-03-22: 68; 2016-03-23: 68; 2016-03-24: 72; 2016-03-26: 88; 2016-03-27: 88; 2016-03-28: 88; 2016-03-29: 91; 2016-03-30: 74; 2016-03-31: 80; 2016-04-02: 80; 2016-04-03: 80; 2016-04-04: 80; 2016-04-05: 76; 2016-04-06: 60; 2016-04-07: 64; 2016-04-09: 80; 2016-04-10: 80; 2016-04-11: 80; 2016-04-12: 82; 2016-04-13: 88; 2016-04-14: 85; 2016-04-16: 80; 2016-04-17: 81; 2016-04-18: 88; 2016-04-19: 76; 2016-04-20: 54; 2016-04-21: 42; 2016-04-23: 42; 2016-04-24: 43; 2016-04-25: 50; 2016-04-26: 44; 2016-04-27: 44; 2016-04-28: 47; 2016-04-30: 52; 2016-05-01: 54; 2016-05-02: 57; 2016-05-03: 76; 2016-05-04: 73; 2016-05-05: 58; 2016-05-07: 70; 2016-05-08: 79; 2016-05-09: 92; 2016-05-10: 92; 2016-05-11: 91; 2016-05-12: 82; 2016-05-14: 92; 2016-05-15: 92; 2016-05-16: 89; 2016-05-17: 82; 2016-05-18: 74; 2016-05-19: 71; 2016-05-21: 44; 2016-05-22: 48; 2016-05-23: 64; 2016-05-24: 52; 2016-05-25: 43; 2016-05-26: 31; 2016-05-28: 40; 2016-05-29: 40; 2016-05-30: 40; 2016-05-31: 30; 2016-06-01: 30; 2016-06-02: 32; 2016-06-04: 32; 2016-06-05: 32; 2016-06-06: 32; 2016-06-07: 32; 2016-06-08: 28; 2016-06-09: 12; 2016-06-11: 12; 2016-06-12: 12; 2016-06-13: 11; 2016-06-14: 2; 2016-06-15: 12; 2016-06-16: 12; 2016-06-18: 14; 2016-06-19: 14; 2016-06-20: 12; 2016-06-21: 12; 2016-06-22: 12; 2016-06-23: 12; 2016-06-25: 12; 2016-06-26: 12; 2016-06-27: 12; 2016-06-28: 12; 2016-06-29: 12; 2016-06-30: 12; 2016-07-02: 12; 2016-07-03: 2; 2016-07-04: 2
Subcon - Veneer MDF | 2015-11-18: 2; 2015-11-19: 4; 2015-11-21: 4; 2015-11-22: 4; 2015-11-23: 4; 2015-11-24: 2; 2015-12-15: 3; 2015-12-16: 4; 2015-12-17: 4; 2015-12-19: 4; 2015-12-20: 4; 2015-12-21: 1; 2015-12-23: 1; 2015-12-24: 4; 2015-12-26: 4; 2015-12-27: 4; 2015-12-28: 4; 2015-12-29: 3; 2016-01-13: 1; 2016-01-14: 2; 2016-01-16: 2; 2016-01-17: 2; 2016-01-18: 2; 2016-01-19: 2; 2016-01-20: 2; 2016-01-21: 2; 2016-01-23: 1; 2016-02-04: 1; 2016-02-06: 2; 2016-02-07: 2; 2016-02-08: 2; 2016-02-09: 3; 2016-02-10: 4; 2016-02-11: 4; 2016-02-13: 4; 2016-02-14: 3; 2016-02-15: 2; 2016-02-16: 2; 2016-02-17: 4; 2016-02-18: 5; 2016-02-20: 4; 2016-02-21: 5; 2016-02-22: 6; 2016-02-23: 6; 2016-02-24: 6; 2016-02-25: 5; 2016-02-27: 9; 2016-02-28: 10; 2016-02-29: 10; 2016-03-01: 9; 2016-03-02: 8; 2016-03-03: 10; 2016-03-05: 12; 2016-03-06: 11; 2016-03-07: 9; 2016-03-08: 8; 2016-03-09: 8; 2016-03-10: 8; 2016-03-12: 8; 2016-03-13: 6; 2016-03-15: 1; 2016-03-16: 4; 2016-03-17: 5; 2016-03-19: 8; 2016-03-20: 8; 2016-03-21: 8; 2016-03-22: 8; 2016-03-23: 8; 2016-03-24: 9; 2016-03-26: 12; 2016-03-27: 11; 2016-03-28: 8; 2016-03-29: 8; 2016-03-30: 10; 2016-03-31: 14; 2016-04-02: 8; 2016-04-03: 8; 2016-04-04: 8; 2016-04-05: 8; 2016-04-06: 8; 2016-04-07: 8; 2016-04-09: 6; 2016-04-10: 2; 2016-04-11: 8; 2016-04-12: 8; 2016-04-13: 8; 2016-04-14: 8; 2016-04-16: 8; 2016-04-17: 6; 2016-04-18: 3; 2016-04-19: 14; 2016-04-20: 27; 2016-04-21: 27; 2016-04-23: 27; 2016-04-24: 27; 2016-04-25: 27; 2016-04-26: 26; 2016-04-27: 20; 2016-04-28: 12; 2016-04-30: 6; 2016-05-01: 6; 2016-05-02: 6; 2016-05-03: 6; 2016-05-04: 6; 2016-05-05: 5; 2016-05-07: 3; 2016-05-08: 3; 2016-05-09: 3; 2016-05-10: 3; 2016-05-11: 3; 2016-05-12: 3; 2016-05-14: 2
Subcon - Toilet Cubicle | 2016-01-02: 12; 2016-01-03: 12; 2016-01-04: 12; 2016-01-05: 12; 2016-01-06: 12; 2016-01-07: 12; 2016-01-09: 12; 2016-01-10: 12; 2016-01-28: 8; 2016-01-30: 12; 2016-01-31: 12; 2016-02-01: 12; 2016-02-02: 12; 2016-02-03: 12; 2016-02-04: 12; 2016-02-06: 14; 2016-02-07: 16; 2016-02-08: 12; 2016-02-09: 12; 2016-02-10: 12; 2016-02-11: 12; 2016-02-13: 12; 2016-02-14: 12; 2016-02-15: 10; 2016-03-02: 2; 2016-03-03: 10; 2016-03-05: 10; 2016-03-06: 10; 2016-03-07: 10; 2016-03-08: 10; 2016-03-09: 10; 2016-03-10: 10; 2016-03-12: 8; 2016-03-24: 2; 2016-03-26: 10; 2016-03-27: 10; 2016-03-28: 10; 2016-03-29: 10; 2016-03-30: 10; 2016-03-31: 10; 2016-04-02: 10; 2016-04-03: 8; 2016-04-10: 2; 2016-04-11: 10; 2016-04-12: 10; 2016-04-13: 10; 2016-04-14: 10; 2016-04-16: 10; 2016-04-17: 10; 2016-04-18: 10; 2016-04-19: 8
Subcon - Kitchen Cabinet | 2015-12-21: 10; 2015-12-22: 10; 2015-12-23: 10; 2015-12-24: 10; 2015-12-26: 10; 2015-12-27: 10; 2015-12-28: 10; 2015-12-29: 10; 2015-12-30: 10; 2015-12-31: 10; 2016-01-17: 7; 2016-01-18: 10; 2016-01-19: 10; 2016-01-20: 10; 2016-01-21: 10; 2016-01-23: 10; 2016-01-24: 10; 2016-01-25: 12; 2016-01-26: 20; 2016-01-27: 20; 2016-01-28: 13; 2016-01-30: 10; 2016-01-31: 10; 2016-02-01: 10; 2016-02-02: 10; 2016-02-03: 10; 2016-02-04: 10; 2016-02-06: 8; 2016-02-20: 4; 2016-02-21: 20; 2016-02-22: 20; 2016-02-23: 20; 2016-02-24: 20; 2016-02-25: 20; 2016-02-27: 20; 2016-02-28: 20; 2016-02-29: 20; 2016-03-01: 20; 2016-03-02: 16; 2016-03-13: 4; 2016-03-14: 20; 2016-03-15: 20; 2016-03-16: 20; 2016-03-17: 20; 2016-03-19: 20; 2016-03-20: 20; 2016-03-21: 20; 2016-03-22: 20; 2016-03-23: 20; 2016-03-24: 16; 2016-03-29: 6; 2016-03-30: 28; 2016-03-31: 29; 2016-04-02: 32; 2016-04-03: 32; 2016-04-04: 32; 2016-04-05: 32; 2016-04-06: 32; 2016-04-07: 36; 2016-04-09: 50; 2016-04-10: 50; 2016-04-11: 44; 2016-04-12: 42; 2016-04-13: 32; 2016-04-14: 35; 2016-04-16: 42; 2016-04-17: 52; 2016-04-18: 57; 2016-04-19: 64; 2016-04-20: 67; 2016-04-21: 70; 2016-04-23: 60; 2016-04-24: 60; 2016-04-25: 58; 2016-04-26: 52; 2016-04-27: 51; 2016-04-28: 39; 2016-04-30: 30; 2016-05-01: 22; 2016-05-02: 19; 2016-05-03: 20; 2016-05-04: 22; 2016-05-05: 30; 2016-05-07: 30; 2016-05-08: 25; 2016-05-09: 22; 2016-05-10: 23; 2016-05-11: 26; 2016-05-12: 26; 2016-05-14: 26; 2016-05-15: 26; 2016-05-16: 30; 2016-05-17: 30; 2016-05-18: 30; 2016-05-19: 30; 2016-05-21: 18; 2016-05-22: 15; 2016-05-23: 4; 2016-05-24: 6; 2016-05-25: 6; 2016-05-26: 6; 2016-05-28: 2; 2016-05-29: 2; 2016-05-30: 2; 2016-05-31: 2; 2016-06-01: 2; 2016-06-02: 2; 2016-06-04: 6; 2016-06-05: 6; 2016-06-06: 6; 2016-06-07: 6; 2016-06-08: 6; 2016-06-09: 6; 2016-06-11: 4; 2016-06-12: 4; 2016-06-13: 4; 2016-06-14: 4
Subcon - Steel Door | 2015-12-30: 8; 2015-12-31: 8; 2016-01-02: 8; 2016-01-03: 8; 2016-01-04: 8; 2016-01-05: 8; 2016-01-06: 8; 2016-01-07: 8; 2016-01-09: 14; 2016-01-10: 24; 2016-01-11: 24; 2016-01-12: 24; 2016-01-13: 16; 2016-01-14: 16; 2016-01-16: 16; 2016-01-17: 16; 2016-01-18: 16; 2016-01-19: 16; 2016-01-20: 16; 2016-01-21: 16; 2016-01-23: 10; 2016-02-20: 3; 2016-02-21: 16; 2016-02-22: 16; 2016-02-23: 16; 2016-02-24: 16; 2016-02-25: 16; 2016-02-27: 16; 2016-02-28: 16; 2016-02-29: 16; 2016-03-01: 16; 2016-03-02: 13; 2016-03-03: 3; 2016-03-05: 16; 2016-03-06: 16; 2016-03-07: 16; 2016-03-08: 16; 2016-03-09: 16; 2016-03-10: 17; 2016-03-12: 22; 2016-03-13: 30; 2016-03-14: 30; 2016-03-15: 27; 2016-03-16: 14; 2016-03-17: 14; 2016-03-19: 14; 2016-03-20: 17; 2016-03-21: 28; 2016-03-22: 20; 2016-03-23: 20; 2016-03-24: 20; 2016-03-26: 20; 2016-03-27: 24; 2016-03-28: 37; 2016-03-29: 34; 2016-03-30: 34; 2016-03-31: 31; 2016-04-02: 18; 2016-04-03: 20; 2016-04-04: 28; 2016-04-05: 26; 2016-04-06: 18; 2016-04-07: 18; 2016-04-09: 18; 2016-04-10: 18; 2016-04-11: 18; 2016-04-12: 20; 2016-04-13: 26; 2016-04-14: 20; 2016-04-16: 20; 2016-04-17: 21; 2016-04-18: 22; 2016-04-19: 22; 2016-04-20: 20; 2016-04-21: 10; 2016-04-23: 2; 2016-04-24: 2; 2016-04-25: 5; 2016-04-26: 12; 2016-04-27: 12; 2016-04-28: 11; 2016-04-30: 12; 2016-05-01: 12; 2016-05-02: 14; 2016-05-03: 14; 2016-05-04: 14; 2016-05-05: 14; 2016-05-07: 14; 2016-05-08: 14; 2016-05-09: 14; 2016-05-10: 15; 2016-05-11: 16; 2016-05-12: 13; 2016-05-14: 6; 2016-05-15: 7; 2016-05-16: 16; 2016-05-17: 16; 2016-05-18: 16; 2016-05-19: 16; 2016-05-21: 16; 2016-05-22: 15; 2016-05-23: 12; 2016-05-24: 12; 2016-05-25: 10; 2016-05-26: 9; 2016-05-28: 10; 2016-05-29: 10; 2016-05-30: 10; 2016-05-31: 10; 2016-06-01: 10; 2016-06-02: 10; 2016-06-04: 10; 2016-06-05: 10; 2016-06-06: 10; 2016-06-07: 10
Subcon - Steel Railing | 2015-12-30: 8; 2015-12-31: 8; 2016-01-02: 8; 2016-01-03: 8; 2016-01-04: 8; 2016-01-05: 8; 2016-01-06: 8; 2016-01-07: 8; 2016-01-09: 16; 2016-01-10: 16; 2016-01-11: 12; 2016-01-12: 16; 2016-01-13: 16; 2016-01-14: 16; 2016-01-16: 16; 2016-01-17: 16; 2016-01-18: 16; 2016-01-19: 16; 2016-01-20: 8; 2016-01-21: 8; 2016-01-23: 4; 2016-02-20: 2; 2016-02-21: 12; 2016-02-22: 12; 2016-02-23: 12; 2016-02-24: 12; 2016-02-25: 12; 2016-02-27: 12; 2016-02-28: 12; 2016-02-29: 12; 2016-03-01: 12; 2016-03-02: 10; 2016-03-03: 2; 2016-03-05: 12; 2016-03-06: 12; 2016-03-07: 12; 2016-03-08: 14; 2016-03-09: 20; 2016-03-10: 20; 2016-03-12: 20; 2016-03-13: 20; 2016-03-14: 20; 2016-03-15: 18; 2016-03-16: 8; 2016-03-17: 8; 2016-03-19: 8; 2016-03-20: 9; 2016-03-21: 12; 2016-03-22: 12; 2016-03-23: 12; 2016-03-24: 17; 2016-03-26: 28; 2016-03-27: 28; 2016-03-28: 28; 2016-03-29: 30; 2016-03-30: 38; 2016-03-31: 36; 2016-04-02: 26; 2016-04-03: 26; 2016-04-04: 26; 2016-04-05: 21; 2016-04-06: 10; 2016-04-07: 10; 2016-04-09: 10; 2016-04-10: 10; 2016-04-11: 10; 2016-04-12: 10; 2016-04-13: 10; 2016-04-14: 10; 2016-04-16: 10; 2016-04-17: 13; 2016-04-18: 18; 2016-04-19: 18; 2016-04-20: 18; 2016-04-21: 18; 2016-04-23: 18; 2016-04-24: 18; 2016-04-25: 21; 2016-04-26: 28; 2016-04-27: 28; 2016-04-28: 25; 2016-04-30: 28; 2016-05-01: 30; 2016-05-02: 36; 2016-05-03: 34; 2016-05-04: 27; 2016-05-05: 27; 2016-05-07: 27; 2016-05-08: 27; 2016-05-09: 27; 2016-05-10: 27; 2016-05-11: 19; 2016-05-12: 17; 2016-05-14: 11; 2016-05-15: 11; 2016-05-16: 11; 2016-05-17: 11; 2016-05-18: 11; 2016-05-19: 11; 2016-05-21: 11; 2016-05-22: 11; 2016-05-23: 11; 2016-05-24: 11; 2016-05-25: 12; 2016-05-26: 15; 2016-05-28: 14; 2016-05-29: 12; 2016-05-30: 9; 2016-05-31: 1; 2016-06-01: 1; 2016-06-02: 1; 2016-06-04: 1; 2016-06-05: 1; 2016-06-06: 1; 2016-06-07: 1; 2016-06-08: 1; 2016-06-09: 1; 2016-06-11: 1; 2016-06-12: 1; 2016-06-13: 1; 2016-06-14: 1; 2016-06-15: 1; 2016-06-16: 1; 2016-06-18: 1; 2016-06-19: 1; 2016-06-20: 1; 2016-06-21: 1; 2016-06-22: 1; 2016-07-16: 6; 2016-07-17: 6; 2016-07-18: 6; 2016-07-19: 6; 2016-07-20: 6; 2016-07-21: 6; 2016-07-23: 6; 2016-07-24: 6; 2016-07-25: 6; 2016-07-26: 6; 2016-09-04: 1; 2016-09-05: 6; 2016-09-06: 6; 2016-09-07: 6; 2016-09-13: 6; 2016-09-14: 6; 2016-09-15: 6; 2016-09-17: 6; 2016-09-18: 6; 2016-09-19: 6; 2016-09-20: 5
Subcon - Structural Steel & Metal Decking | 2015-12-19: 20; 2015-12-20: 20; 2015-12-21: 20; 2015-12-22: 20; 2015-12-23: 20; 2015-12-24: 20; 2015-12-26: 20; 2015-12-27: 20; 2015-12-28: 20; 2015-12-29: 20; 2015-12-30: 20; 2015-12-31: 20; 2016-01-02: 20; 2016-01-03: 20; 2016-01-04: 20; 2016-01-05: 40; 2016-01-06: 40; 2016-01-07: 40; 2016-01-09: 40; 2016-01-10: 40; 2016-01-11: 60; 2016-01-12: 60; 2016-01-13: 60; 2016-01-14: 60; 2016-01-16: 60; 2016-01-17: 40; 2016-01-18: 40; 2016-01-19: 40; 2016-01-20: 40; 2016-01-21: 40
Subcon - Vanity Counter | 2016-05-03: 2; 2016-05-04: 15; 2016-05-05: 20; 2016-05-07: 20; 2016-05-08: 20; 2016-05-09: 21; 2016-05-10: 30; 2016-05-11: 30; 2016-05-12: 30; 2016-05-14: 30; 2016-05-15: 31; 2016-05-16: 40; 2016-05-17: 40; 2016-05-18: 40; 2016-05-19: 40; 2016-05-21: 38; 2016-05-22: 25; 2016-05-23: 20; 2016-05-24: 30; 2016-05-25: 30; 2016-05-26: 29; 2016-05-28: 20; 2016-05-29: 20; 2016-05-30: 20; 2016-05-31: 30; 2016-06-01: 29; 2016-06-02: 20; 2016-06-04: 20; 2016-06-05: 20; 2016-06-06: 20; 2016-06-07: 20; 2016-06-08: 20; 2016-06-09: 20; 2016-06-11: 10; 2016-06-12: 10; 2016-06-13: 10; 2016-06-14: 10; 2016-06-15: 10; 2016-06-16: 10
Subcon - False Ceiling | 2016-01-17: 5; 2016-01-18: 10; 2016-01-19: 10; 2016-01-20: 10; 2016-01-21: 10; 2016-01-23: 10; 2016-01-24: 10; 2016-01-25: 14; 2016-01-26: 28; 2016-01-27: 28; 2016-01-28: 28; 2016-01-30: 38; 2016-01-31: 38; 2016-02-01: 38; 2016-02-02: 38; 2016-02-03: 35; 2016-02-04: 32; 2016-02-06: 28; 2016-02-07: 32; 2016-02-08: 32; 2016-02-09: 32; 2016-02-10: 32; 2016-02-11: 32; 2016-02-13: 26; 2016-02-14: 26; 2016-02-15: 28; 2016-02-16: 28; 2016-02-17: 26; 2016-02-18: 16; 2016-02-20: 16; 2016-02-21: 20; 2016-02-22: 20; 2016-02-23: 20; 2016-02-24: 24; 2016-02-25: 28; 2016-02-27: 40; 2016-02-28: 32; 2016-02-29: 32; 2016-03-01: 32; 2016-03-02: 33; 2016-03-03: 48; 2016-03-05: 48; 2016-03-06: 44; 2016-03-07: 48; 2016-03-08: 67; 2016-03-09: 84; 2016-03-10: 100; 2016-03-12: 96; 2016-03-13: 98; 2016-03-14: 104; 2016-03-15: 88; 2016-03-16: 88; 2016-03-17: 91; 2016-03-19: 107; 2016-03-20: 113; 2016-03-21: 104; 2016-03-22: 120; 2016-03-23: 128; 2016-03-24: 162; 2016-03-26: 168; 2016-03-27: 164; 2016-03-28: 150; 2016-03-29: 159; 2016-03-30: 161; 2016-03-31: 178; 2016-04-02: 185; 2016-04-03: 211; 2016-04-04: 220; 2016-04-05: 208; 2016-04-06: 230; 2016-04-07: 256; 2016-04-09: 285; 2016-04-10: 262; 2016-04-11: 220; 2016-04-12: 229; 2016-04-13: 244; 2016-04-14: 258; 2016-04-16: 272; 2016-04-17: 254; 2016-04-18: 246; 2016-04-19: 242; 2016-04-20: 229; 2016-04-21: 224; 2016-04-23: 192; 2016-04-24: 175; 2016-04-25: 154; 2016-04-26: 128; 2016-04-27: 118; 2016-04-28: 112; 2016-04-30: 87; 2016-05-01: 85; 2016-05-02: 80; 2016-05-03: 60; 2016-05-04: 60; 2016-05-05: 41; 2016-05-07: 39; 2016-05-08: 37; 2016-05-09: 19; 2016-05-10: 18; 2016-05-11: 17; 2016-05-12: 15; 2016-05-14: 14; 2016-05-15: 10; 2016-05-16: 10; 2016-05-17: 7; 2016-05-18: 10; 2016-05-19: 9; 2016-05-21: 9; 2016-05-22: 9; 2016-05-23: 9; 2016-05-24: 9; 2016-05-25: 9; 2016-05-26: 9; 2016-05-28: 10; 2016-05-29: 13; 2016-05-30: 13; 2016-05-31: 14; 2016-06-01: 12; 2016-06-02: 12; 2016-06-04: 9; 2016-06-05: 9; 2016-06-06: 7; 2016-06-07: 7; 2016-06-08: 7; 2016-06-09: 7; 2016-06-11: 6; 2016-06-12: 6; 2016-06-13: 7; 2016-06-14: 7; 2016-06-15: 4; 2016-06-16: 4; 2016-06-18: 2; 2016-06-19: 2; 2016-06-20: 1; 2016-06-21: 1
Subcon - Landscape | 2015-11-09: 20; 2015-11-10: 40; 2015-11-11: 40; 2015-11-12: 40; 2015-11-14: 40; 2015-11-15: 40; 2015-11-16: 60; 2015-11-17: 87; 2015-11-18: 93; 2015-11-19: 93; 2015-11-21: 93; 2015-11-22: 93; 2015-11-23: 93; 2015-11-24: 93; 2015-11-25: 93; 2015-11-26: 73; 2015-11-28: 53; 2015-11-29: 53; 2015-11-30: 53; 2015-12-01: 53; 2015-12-02: 53; 2015-12-03: 33; 2015-12-05: 27; 2015-12-06: 40; 2015-12-07: 40; 2015-12-08: 40; 2015-12-09: 40; 2015-12-10: 40; 2015-12-12: 40; 2015-12-13: 40; 2015-12-14: 40; 2015-12-15: 40; 2015-12-16: 40; 2015-12-17: 40; 2015-12-19: 40; 2015-12-20: 40; 2015-12-21: 40; 2015-12-22: 40; 2015-12-23: 40; 2015-12-24: 40; 2015-12-26: 40; 2015-12-27: 40; 2015-12-28: 40; 2015-12-29: 40; 2015-12-30: 40; 2015-12-31: 40; 2016-01-02: 40; 2016-01-03: 40; 2016-01-04: 40; 2016-01-05: 40; 2016-01-06: 40; 2016-01-07: 40; 2016-01-09: 40; 2016-01-10: 40; 2016-01-11: 40; 2016-01-12: 40; 2016-01-13: 40; 2016-01-14: 40; 2016-01-16: 40; 2016-01-17: 40; 2016-01-18: 40; 2016-01-19: 40; 2016-01-20: 40; 2016-01-21: 40; 2016-01-23: 40; 2016-01-24: 40; 2016-01-25: 40; 2016-01-26: 30; 2016-01-27: 20; 2016-01-28: 20; 2016-01-30: 20; 2016-01-31: 20; 2016-02-01: 20; 2016-02-02: 20; 2016-02-03: 20; 2016-02-04: 20; 2016-02-06: 20; 2016-02-07: 20; 2016-02-08: 20; 2016-02-09: 20; 2016-02-10: 20; 2016-02-11: 20; 2016-02-13: 10; 2016-03-08: 6; 2016-03-09: 30; 2016-03-10: 30; 2016-03-12: 30; 2016-03-13: 30; 2016-03-14: 30; 2016-03-15: 30; 2016-03-16: 31; 2016-03-17: 34; 2016-03-19: 34; 2016-03-20: 34; 2016-03-21: 34; 2016-03-22: 34; 2016-03-23: 34; 2016-03-24: 34; 2016-03-26: 34; 2016-03-27: 34; 2016-03-28: 34; 2016-03-29: 34; 2016-03-30: 34; 2016-03-31: 32; 2016-04-02: 24; 2016-04-03: 27; 2016-04-04: 40; 2016-04-05: 40; 2016-04-06: 40; 2016-04-07: 40; 2016-04-09: 40; 2016-04-10: 40; 2016-04-11: 40; 2016-04-12: 40; 2016-04-13: 40; 2016-04-14: 40; 2016-04-16: 40; 2016-04-17: 40; 2016-04-18: 42; 2016-04-19: 50; 2016-04-20: 48; 2016-04-21: 40; 2016-04-23: 40; 2016-04-24: 40; 2016-04-25: 40; 2016-04-26: 40; 2016-04-27: 40; 2016-04-28: 40; 2016-04-30: 40; 2016-05-01: 40; 2016-05-02: 38; 2016-05-03: 30; 2016-05-04: 30; 2016-05-05: 30; 2016-05-07: 30; 2016-05-08: 30; 2016-05-09: 30; 2016-05-10: 30; 2016-05-11: 27; 2016-05-12: 13; 2016-05-14: 13; 2016-05-15: 13; 2016-05-16: 15; 2016-05-17: 21; 2016-05-18: 22; 2016-05-19: 27; 2016-05-21: 27; 2016-05-22: 27; 2016-05-23: 27; 2016-05-24: 27; 2016-05-25: 24; 2016-05-26: 14; 2016-05-28: 12; 2016-05-29: 6; 2016-05-30: 6; 2016-05-31: 6; 2016-06-01: 6; 2016-06-02: 6; 2016-06-04: 5
Subcon - Mirror | 2016-05-26: 1; 2016-05-28: 6; 2016-05-29: 9; 2016-05-30: 9; 2016-05-31: 11; 2016-06-01: 13; 2016-06-02: 13; 2016-06-04: 13; 2016-06-05: 13; 2016-06-06: 13; 2016-06-07: 13; 2016-06-08: 7; 2016-06-09: 4; 2016-06-11: 9; 2016-06-12: 7; 2016-06-13: 5; 2016-06-14: 5; 2016-06-15: 5; 2016-06-16: 5; 2016-06-18: 5; 2016-06-19: 5; 2016-06-20: 5; 2016-06-21: 5
Subcon - Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 10 | 10 | 10 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 10 | 10 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 10 | 14 | 16 | 10 | 10 | 0 | 10 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 10 | 10 | 10 | 0 | 10 | 0 | 0 | 3 | 10 | 10 | 0 | 13 | 20 | 18 | 10 | 10 | 8 | 0 | 0 | 5 | 15 | 16 | 16 | 16 | 0 | 16 | 8 | 6 | 32 | 67 | 68 | 0 | 77 | 78 | 52 | 18 | 11 | 2 | 0 | 16 | 52 | 61 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 46 | 10 | 0 | 6 | 4 | 4 | 6 | 22 | 72 | 0 | 72 | 72 | 72 | 67 | 18 | 32 | 10 | 109 | 109 | 115 | 155 | 153 | 143 | 8 | 102 | 94 | 44 | 48 | 70 | 62 | 12 | 70 | 72 | 72 | 34 | 30 | 29 | 10 | 34 | 53 | 67 | 68 | 68 | 66 | 18 | 54 | 61 | 53 | 44 | 36 | 33 | 10 | 44 | 60 | 58 | 56 | 50 | 64 | 12 | 67 | 68 | 58 | 58 | 68 | 52 | 2 | 65 | 69 | 77 | 81 | 90 | 96 | 2 | 115 | 118 | 125 | 124 | 130 | 133 | 10 | 147 | 134 | 124 | 116 | 126 | 138 | 11 | 125 | 125 | 123 | 113 | 122 | 129 | 0 | 148 | 144 | 152 | 153 | 155 | 161 | 0 | 172 | 264 | 328 | 329 | 329 | 325 | 0 | 312 | 288 | 283 | 291 | 295 | 297 | 0 | 306 | 303 | 313 | 322 | 258 | 208 | 0 | 245 | 274 | 335 | 425 | 445 | 557 | 0 | 579 | 584 | 560 | 530 | 541 | 591 | 0 | 611 | 619 | 631 | 728 | 739 | 696 | 0 | 623 | 621 | 508 | 468 | 458 | 475 | 0 | 451 | 448 | 447 | 444 | 446 | 486 | 0 | 387 | 362 | 364 | 357 | 367 | 367 | 0 | 381 | 423 | 407 | 399 | 389 | 340 | 0 | 354 | 376 | 367 | 369 | 371 | 374 | 0 | 385 | 386 | 417 | 451 | 405 | 389 | 0 | 384 | 379 | 363 | 376 | 370 | 363 | 0 | 385 | 415 | 432 | 464 | 468 | 464 | 0 | 446 | 440 | 459 | 479 | 507 | 500 | 0 | 480 | 454 | 462 | 442 | 439 | 426 | 0 | 427 | 424 | 398 | 375 | 371 | 347 | 0 | 336 | 298 | 281 | 245 | 226 | 181 | 0 | 165 | 98 | 98 | 98 | 99 | 103 | 0 | 141 | 144 | 165 | 169 | 183 | 175 | 0 | 176 | 185 | 189 | 211 | 217 | 199 | 0 | 141 | 148 | 140 | 110 | 117 | 152 | 0 | 162 | 150 | 180 | 179 | 170 | 166 | 0 | 144 | 140 | 158 | 137 | 140 | 140 | 0 | 130 | 122 | 90 | 90 | 90 | 50 | 0 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcon - Plumbing | 2015-04-30: 0; 2015-05-02: 4; 2015-05-03: 4; 2015-05-04: 4; 2015-05-05: 4; 2015-05-06: 4; 2015-05-07: 4; 2015-05-09: 4; 2015-05-10: 4; 2015-05-11: 4; 2015-05-12: 4; 2015-05-13: 4; 2015-05-14: 4; 2015-05-16: 4; 2015-05-17: 4; 2015-05-18: 2; 2015-05-19: 5; 2015-05-20: 5; 2015-05-21: 5; 2015-05-23: 5; 2015-05-24: 5; 2015-05-25: 5; 2015-05-26: 5; 2015-05-27: 4; 2015-05-28: 4; 2015-05-30: 4; 2015-05-31: 4; 2015-06-01: 5; 2015-06-02: 9; 2015-06-03: 9; 2015-06-04: 10; 2015-06-06: 14; 2015-06-07: 14; 2015-06-08: 14; 2015-06-09: 14; 2015-06-10: 14; 2015-06-11: 14; 2015-06-13: 13; 2015-06-14: 10; 2015-06-15: 10; 2015-06-16: 10; 2015-06-17: 10; 2015-06-18: 10; 2015-06-20: 5; 2015-06-21: 5; 2015-06-22: 4; 2015-08-30: 5; 2015-08-31: 6; 2015-09-01: 6; 2015-09-02: 6; 2015-09-03: 6; 2015-09-05: 6; 2015-09-06: 12; 2015-09-07: 12; 2015-09-08: 12; 2015-09-09: 12; 2015-09-10: 12; 2015-09-12: 12; 2015-09-13: 12; 2015-09-14: 12; 2015-09-15: 12; 2015-09-16: 7; 2015-09-17: 6; 2015-09-19: 6; 2015-09-20: 6; 2015-09-21: 6; 2015-09-22: 6; 2015-09-29: 6; 2015-09-30: 6; 2015-10-01: 6; 2015-10-03: 6; 2015-10-04: 12; 2015-10-05: 12; 2015-10-06: 12; 2015-10-07: 17; 2015-10-08: 22; 2015-10-10: 23; 2015-10-11: 21; 2015-10-12: 21; 2015-10-13: 26; 2015-10-14: 31; 2015-10-15: 25; 2015-10-17: 25; 2015-10-18: 35; 2015-10-19: 35; 2015-10-20: 55; 2015-10-21: 74; 2015-10-22: 73; 2015-10-24: 85; 2015-10-25: 85; 2015-10-26: 85; 2015-10-27: 85; 2015-10-28: 85; 2015-10-29: 85; 2015-10-31: 85; 2015-11-01: 84; 2015-11-02: 84; 2015-11-03: 84; 2015-11-04: 78; 2015-11-05: 82; 2015-11-07: 62; 2015-11-08: 42; 2015-11-09: 52; 2015-11-10: 59; 2015-11-11: 54; 2015-11-12: 50; 2015-11-14: 50; 2015-11-15: 53; 2015-11-16: 60; 2015-11-17: 56; 2015-11-18: 56; 2015-11-19: 56; 2015-11-21: 46; 2015-11-22: 37; 2015-11-23: 37; 2015-11-24: 37; 2015-11-25: 43; 2015-11-26: 49; 2015-11-28: 61; 2015-11-29: 61; 2015-11-30: 61; 2015-12-01: 64; 2015-12-02: 73; 2015-12-03: 66; 2015-12-05: 64; 2015-12-06: 69; 2015-12-07: 88; 2015-12-08: 114; 2015-12-09: 136; 2015-12-10: 154; 2015-12-12: 174; 2015-12-13: 190; 2015-12-14: 190; 2015-12-15: 200; 2015-12-16: 202; 2015-12-17: 205; 2015-12-19: 209; 2015-12-20: 215; 2015-12-21: 241; 2015-12-22: 227; 2015-12-23: 246; 2015-12-24: 281; 2015-12-26: 275; 2015-12-27: 275; 2015-12-28: 275; 2015-12-29: 268; 2015-12-30: 270; 2015-12-31: 268; 2016-01-02: 282; 2016-01-03: 295; 2016-01-04: 299; 2016-01-05: 296; 2016-01-06: 305; 2016-01-07: 307; 2016-01-09: 294; 2016-01-10: 300; 2016-01-11: 292; 2016-01-12: 324; 2016-01-13: 296; 2016-01-14: 281; 2016-01-16: 273; 2016-01-17: 273; 2016-01-18: 282; 2016-01-19: 281; 2016-01-20: 288; 2016-01-21: 287; 2016-01-23: 276; 2016-01-24: 283; 2016-01-25: 265; 2016-01-26: 265; 2016-01-27: 247; 2016-01-28: 216; 2016-01-30: 194; 2016-01-31: 186; 2016-02-01: 172; 2016-02-02: 161; 2016-02-03: 170; 2016-02-04: 141; 2016-02-06: 165; 2016-02-07: 199; 2016-02-08: 209; 2016-02-09: 213; 2016-02-10: 201; 2016-02-11: 218; 2016-02-13: 240; 2016-02-14: 234; 2016-02-15: 241; 2016-02-16: 221; 2016-02-17: 213; 2016-02-18: 219; 2016-02-20: 264; 2016-02-21: 282; 2016-02-22: 297; 2016-02-23: 293; 2016-02-24: 295; 2016-02-25: 302; 2016-02-27: 304; 2016-02-28: 312; 2016-02-29: 317; 2016-03-01: 314; 2016-03-02: 306; 2016-03-03: 264; 2016-03-05: 264; 2016-03-06: 286; 2016-03-07: 314; 2016-03-08: 269; 2016-03-09: 284; 2016-03-10: 286; 2016-03-12: 295; 2016-03-13: 283; 2016-03-14: 291; 2016-03-15: 316; 2016-03-16: 325; 2016-03-17: 318; 2016-03-19: 302; 2016-03-20: 296; 2016-03-21: 312; 2016-03-22: 312; 2016-03-23: 333; 2016-03-24: 376; 2016-03-26: 387; 2016-03-27: 346; 2016-03-28: 356; 2016-03-29: 361; 2016-03-30: 335; 2016-03-31: 319; 2016-04-02: 316; 2016-04-03: 310; 2016-04-04: 293; 2016-04-05: 296; 2016-04-06: 295; 2016-04-07: 269; 2016-04-09: 273; 2016-04-10: 249; 2016-04-11: 223; 2016-04-12: 251; 2016-04-13: 227; 2016-04-14: 205; 2016-04-16: 184; 2016-04-17: 200; 2016-04-18: 200; 2016-04-19: 200; 2016-04-20: 188; 2016-04-21: 170; 2016-04-23: 170; 2016-04-24: 174; 2016-04-25: 186; 2016-04-26: 170; 2016-04-27: 170; 2016-04-28: 170; 2016-04-30: 136; 2016-05-01: 120; 2016-05-02: 112; 2016-05-03: 87; 2016-05-04: 65; 2016-05-05: 60; 2016-05-07: 76; 2016-05-08: 74; 2016-05-09: 58; 2016-05-10: 63; 2016-05-11: 82; 2016-05-12: 82; 2016-05-14: 92; 2016-05-15: 100; 2016-05-16: 100; 2016-05-17: 102; 2016-05-18: 101; 2016-05-19: 100; 2016-05-21: 100; 2016-05-22: 103; 2016-05-23: 123; 2016-05-24: 133; 2016-05-25: 133; 2016-05-26: 153; 2016-05-28: 148; 2016-05-29: 131; 2016-05-30: 149; 2016-05-31: 161; 2016-06-01: 145; 2016-06-02: 143; 2016-06-04: 135; 2016-06-05: 133; 2016-06-06: 126; 2016-06-07: 110; 2016-06-08: 111; 2016-06-09: 110; 2016-06-11: 100; 2016-06-12: 110; 2016-06-13: 100; 2016-06-14: 103; 2016-06-15: 114; 2016-06-16: 96; 2016-06-18: 73; 2016-06-19: 80; 2016-06-20: 80; 2016-06-21: 80; 2016-06-22: 90; 2016-06-23: 90; 2016-06-25: 90; 2016-06-26: 86; 2016-06-27: 70; 2016-06-28: 70; 2016-06-29: 55; 2016-06-30: 40; 2016-07-02: 37; 2016-07-03: 24; 2016-07-04: 14
Subcon - HVAC | 2015-09-22: 1; 2015-09-29: 6; 2015-09-30: 6; 2015-10-01: 6; 2015-10-03: 6; 2015-10-04: 6; 2015-10-05: 6; 2015-10-06: 6; 2015-10-07: 6; 2015-10-08: 6; 2015-10-10: 6; 2015-10-11: 6; 2015-10-12: 6; 2015-10-13: 6; 2015-10-14: 6; 2015-10-15: 5; 2015-10-18: 9; 2015-10-19: 25; 2015-10-20: 30; 2015-10-21: 36; 2015-10-22: 39; 2015-10-24: 42; 2015-10-25: 46; 2015-10-26: 57; 2015-10-27: 62; 2015-10-28: 72; 2015-10-29: 72; 2015-10-31: 71; 2015-11-01: 72; 2015-11-02: 66; 2015-11-03: 76; 2015-11-04: 68; 2015-11-05: 56; 2015-11-07: 51; 2015-11-08: 46; 2015-11-09: 43; 2015-11-10: 50; 2015-11-11: 43; 2015-11-12: 30; 2015-11-14: 30; 2015-11-15: 44; 2015-11-16: 52; 2015-11-17: 56; 2015-11-18: 61; 2015-11-19: 68; 2015-11-21: 66; 2015-11-22: 56; 2015-11-23: 66; 2015-11-24: 64; 2015-11-25: 64; 2015-11-26: 57; 2015-11-28: 76; 2015-11-29: 76; 2015-11-30: 71; 2015-12-01: 66; 2015-12-02: 59; 2015-12-03: 62; 2015-12-05: 58; 2015-12-06: 58; 2015-12-07: 68; 2015-12-08: 81; 2015-12-09: 78; 2015-12-10: 88; 2015-12-12: 88; 2015-12-13: 96; 2015-12-14: 118; 2015-12-15: 104; 2015-12-16: 102; 2015-12-17: 106; 2015-12-19: 106; 2015-12-20: 118; 2015-12-21: 158; 2015-12-22: 156; 2015-12-23: 160; 2015-12-24: 169; 2015-12-26: 152; 2015-12-27: 148; 2015-12-28: 154; 2015-12-29: 173; 2015-12-30: 194; 2015-12-31: 217; 2016-01-02: 220; 2016-01-03: 228; 2016-01-04: 271; 2016-01-05: 272; 2016-01-06: 263; 2016-01-07: 235; 2016-01-09: 252; 2016-01-10: 239; 2016-01-11: 249; 2016-01-12: 259; 2016-01-13: 266; 2016-01-14: 259; 2016-01-16: 235; 2016-01-17: 223; 2016-01-18: 192; 2016-01-19: 196; 2016-01-20: 192; 2016-01-21: 192; 2016-01-23: 203; 2016-01-24: 222; 2016-01-25: 221; 2016-01-26: 185; 2016-01-27: 189; 2016-01-28: 175; 2016-01-30: 170; 2016-01-31: 172; 2016-02-01: 178; 2016-02-02: 192; 2016-02-03: 197; 2016-02-04: 202; 2016-02-06: 188; 2016-02-07: 212; 2016-02-08: 188; 2016-02-09: 196; 2016-02-10: 175; 2016-02-11: 159; 2016-02-13: 163; 2016-02-14: 158; 2016-02-15: 170; 2016-02-16: 228; 2016-02-17: 276; 2016-02-18: 266; 2016-02-20: 258; 2016-02-21: 256; 2016-02-22: 265; 2016-02-23: 281; 2016-02-24: 274; 2016-02-25: 282; 2016-02-27: 287; 2016-02-28: 271; 2016-02-29: 288; 2016-03-01: 290; 2016-03-02: 274; 2016-03-03: 263; 2016-03-05: 226; 2016-03-06: 199; 2016-03-07: 216; 2016-03-08: 221; 2016-03-09: 213; 2016-03-10: 207; 2016-03-12: 152; 2016-03-13: 168; 2016-03-14: 168; 2016-03-15: 170; 2016-03-16: 179; 2016-03-17: 184; 2016-03-19: 189; 2016-03-20: 195; 2016-03-21: 199; 2016-03-22: 209; 2016-03-23: 253; 2016-03-24: 240; 2016-03-26: 239; 2016-03-27: 243; 2016-03-28: 243; 2016-03-29: 243; 2016-03-30: 220; 2016-03-31: 199; 2016-04-02: 204; 2016-04-03: 175; 2016-04-04: 171; 2016-04-05: 168; 2016-04-06: 138; 2016-04-07: 126; 2016-04-09: 158; 2016-04-10: 126; 2016-04-11: 134; 2016-04-12: 162; 2016-04-13: 146; 2016-04-14: 147; 2016-04-16: 156; 2016-04-17: 158; 2016-04-18: 164; 2016-04-19: 147; 2016-04-20: 162; 2016-04-21: 160; 2016-04-23: 150; 2016-04-24: 152; 2016-04-25: 159; 2016-04-26: 112; 2016-04-27: 120; 2016-04-28: 115; 2016-04-30: 95; 2016-05-01: 96; 2016-05-02: 99; 2016-05-03: 91; 2016-05-04: 95; 2016-05-05: 95; 2016-05-07: 97; 2016-05-08: 99; 2016-05-09: 98; 2016-05-10: 92; 2016-05-11: 87; 2016-05-12: 81; 2016-05-14: 85; 2016-05-15: 76; 2016-05-16: 71; 2016-05-17: 72; 2016-05-18: 71; 2016-05-19: 68; 2016-05-21: 65; 2016-05-22: 54; 2016-05-23: 59; 2016-05-24: 40; 2016-05-25: 40; 2016-05-26: 40; 2016-05-28: 40; 2016-05-29: 40; 2016-05-30: 40; 2016-05-31: 30; 2016-06-01: 30; 2016-06-02: 29; 2016-06-04: 20; 2016-06-05: 10; 2016-06-06: 10; 2016-06-07: 10; 2016-06-08: 10
Subcon - Fire Fighting | 2015-11-07: 10; 2015-11-08: 10; 2015-11-09: 10; 2015-11-10: 10; 2015-11-11: 10; 2015-11-12: 10; 2015-11-14: 10; 2015-11-15: 10; 2015-11-16: 10; 2015-11-17: 10; 2015-11-18: 10; 2015-11-19: 10; 2015-11-21: 10; 2015-11-22: 10; 2015-11-23: 10; 2015-11-24: 10; 2015-11-25: 10; 2015-11-26: 10; 2015-11-28: 10; 2015-11-29: 10; 2015-11-30: 10; 2015-12-01: 10; 2015-12-02: 10; 2015-12-03: 10; 2015-12-05: 10; 2015-12-06: 10; 2015-12-07: 10; 2015-12-08: 10; 2015-12-09: 10; 2015-12-10: 10; 2015-12-12: 16; 2015-12-13: 16; 2015-12-14: 16; 2015-12-15: 56; 2015-12-16: 56; 2015-12-17: 56; 2015-12-19: 56; 2015-12-20: 56; 2015-12-21: 56; 2015-12-22: 56; 2015-12-23: 56; 2015-12-24: 56; 2015-12-26: 56; 2015-12-27: 56; 2015-12-28: 56; 2015-12-29: 51; 2015-12-30: 51; 2015-12-31: 51; 2016-01-02: 19; 2016-01-03: 19; 2016-01-04: 13; 2016-01-05: 15; 2016-01-06: 51; 2016-01-07: 117; 2016-01-09: 117; 2016-01-10: 119; 2016-01-11: 127; 2016-01-12: 127; 2016-01-13: 127; 2016-01-14: 129; 2016-01-16: 137; 2016-01-17: 138; 2016-01-18: 139; 2016-01-19: 129; 2016-01-20: 130; 2016-01-21: 134; 2016-01-23: 134; 2016-01-24: 121; 2016-01-25: 70; 2016-01-26: 70; 2016-01-27: 72; 2016-01-28: 80; 2016-01-30: 80; 2016-01-31: 80; 2016-02-01: 78; 2016-02-02: 65; 2016-02-03: 65; 2016-02-04: 70; 2016-02-06: 86; 2016-02-07: 85; 2016-02-08: 81; 2016-02-09: 81; 2016-02-10: 78; 2016-02-11: 65; 2016-02-13: 65; 2016-02-14: 75; 2016-02-15: 75; 2016-02-16: 79; 2016-02-17: 95; 2016-02-18: 95; 2016-02-20: 118; 2016-02-21: 120; 2016-02-22: 116; 2016-02-23: 114; 2016-02-24: 96; 2016-02-25: 96; 2016-02-27: 96; 2016-02-28: 96; 2016-02-29: 106; 2016-03-01: 106; 2016-03-02: 97; 2016-03-03: 81; 2016-03-05: 83; 2016-03-06: 85; 2016-03-07: 85; 2016-03-08: 70; 2016-03-09: 67; 2016-03-10: 65; 2016-03-12: 65; 2016-03-13: 83; 2016-03-14: 91; 2016-03-15: 91; 2016-03-16: 91; 2016-03-17: 81; 2016-03-19: 81; 2016-03-20: 90; 2016-03-21: 106; 2016-03-22: 102; 2016-03-23: 86; 2016-03-24: 82; 2016-03-26: 60; 2016-03-27: 64; 2016-03-28: 65; 2016-03-29: 66; 2016-03-30: 50; 2016-03-31: 50; 2016-04-02: 50; 2016-04-03: 50; 2016-04-04: 50; 2016-04-05: 38; 2016-04-06: 66; 2016-04-07: 50; 2016-04-09: 50; 2016-04-10: 56; 2016-04-11: 68; 2016-04-12: 68; 2016-04-13: 76; 2016-04-14: 103; 2016-04-16: 103; 2016-04-17: 115; 2016-04-18: 119; 2016-04-19: 119; 2016-04-20: 123; 2016-04-21: 139; 2016-04-23: 131; 2016-04-24: 99; 2016-04-25: 103; 2016-04-26: 102; 2016-04-27: 87; 2016-04-28: 87; 2016-04-30: 83; 2016-05-01: 77; 2016-05-02: 51; 2016-05-03: 49; 2016-05-04: 39; 2016-05-05: 36; 2016-05-07: 37; 2016-05-08: 49; 2016-05-09: 37; 2016-05-10: 35; 2016-05-11: 29; 2016-05-12: 29; 2016-05-14: 29; 2016-05-15: 33; 2016-05-16: 37; 2016-05-17: 49; 2016-05-18: 49; 2016-05-19: 49; 2016-05-21: 49; 2016-05-22: 53; 2016-05-23: 52; 2016-05-24: 64; 2016-05-25: 48; 2016-05-26: 61; 2016-05-28: 66; 2016-05-29: 66; 2016-05-30: 66; 2016-05-31: 70; 2016-06-01: 82; 2016-06-02: 64; 2016-06-04: 42; 2016-06-05: 42; 2016-06-06: 44; 2016-06-07: 40; 2016-06-08: 40; 2016-06-09: 40; 2016-06-11: 40; 2016-06-12: 40; 2016-06-13: 40; 2016-06-14: 41; 2016-06-15: 44; 2016-06-16: 44; 2016-06-18: 38; 2016-06-19: 24; 2016-06-20: 18; 2016-06-21: 3
Subcon - Lift & Esc. | 2016-01-30: 20; 2016-01-31: 20; 2016-02-01: 20; 2016-02-02: 20; 2016-02-03: 20; 2016-02-04: 20; 2016-02-06: 20; 2016-02-07: 20; 2016-02-08: 20; 2016-02-09: 20; 2016-02-10: 20; 2016-02-11: 20; 2016-02-13: 20; 2016-02-14: 20; 2016-02-15: 20; 2016-02-16: 20; 2016-02-17: 20; 2016-02-18: 20; 2016-02-20: 20; 2016-02-21: 20; 2016-02-22: 20; 2016-02-23: 20; 2016-02-24: 20; 2016-02-25: 20; 2016-02-27: 20; 2016-02-28: 20; 2016-02-29: 20; 2016-03-01: 20; 2016-03-02: 20; 2016-03-03: 20; 2016-03-05: 7; 2016-03-06: 7; 2016-03-07: 7; 2016-03-08: 7; 2016-03-09: 7; 2016-03-10: 7; 2016-03-12: 7; 2016-03-13: 7; 2016-03-14: 7; 2016-03-15: 7; 2016-03-16: 7; 2016-03-17: 7; 2016-03-19: 7; 2016-03-20: 7; 2016-03-21: 7; 2016-03-22: 7; 2016-03-23: 7; 2016-03-24: 7; 2016-03-26: 7; 2016-03-27: 7; 2016-03-28: 7; 2016-03-29: 7; 2016-03-30: 7; 2016-03-31: 7; 2016-04-02: 7; 2016-04-03: 7; 2016-04-04: 7; 2016-04-05: 7; 2016-04-06: 7; 2016-04-07: 7; 2016-04-09: 7; 2016-04-10: 7; 2016-04-11: 7; 2016-04-12: 7; 2016-04-13: 7; 2016-04-14: 7; 2016-04-16: 7; 2016-04-17: 7; 2016-04-18: 7; 2016-04-19: 7; 2016-04-20: 7; 2016-04-21: 7; 2016-04-23: 7; 2016-04-24: 7; 2016-04-25: 7; 2016-04-26: 5; 2016-04-27: 5; 2016-04-28: 5; 2016-04-30: 5; 2016-05-01: 5; 2016-05-02: 5; 2016-05-03: 5; 2016-05-04: 5; 2016-05-05: 5; 2016-05-07: 5; 2016-05-08: 5; 2016-05-09: 5; 2016-05-10: 5; 2016-05-11: 5; 2016-05-12: 5; 2016-05-14: 5; 2016-05-15: 5; 2016-05-16: 5; 2016-05-17: 5; 2016-05-18: 5; 2016-05-19: 5
Subcon - Water Proofing | 2015-10-24: 4; 2015-10-25: 4; 2015-10-26: 4; 2015-10-27: 4; 2015-10-28: 4; 2015-10-29: 4; 2015-10-31: 4; 2015-11-01: 4; 2015-11-02: 4; 2015-11-03: 4; 2015-11-15: 2; 2015-11-16: 4; 2015-11-17: 4; 2015-11-18: 4; 2015-11-19: 4; 2015-11-21: 4; 2015-11-22: 4; 2015-11-23: 8; 2015-11-24: 8; 2015-11-25: 8; 2015-11-26: 6; 2015-11-28: 4; 2015-11-29: 4; 2015-11-30: 4; 2015-12-01: 4; 2015-12-02: 4; 2015-12-03: 4; 2015-12-17: 1; 2015-12-19: 6; 2015-12-20: 6; 2015-12-21: 6; 2015-12-22: 6; 2015-12-23: 6; 2015-12-24: 6; 2015-12-26: 6; 2015-12-27: 6; 2015-12-28: 6; 2015-12-29: 5; 2016-01-07: 1; 2016-01-09: 6; 2016-01-10: 6; 2016-01-11: 6; 2016-01-12: 7; 2016-01-13: 12; 2016-01-14: 12; 2016-01-16: 12; 2016-01-17: 12; 2016-01-18: 12; 2016-01-19: 12; 2016-01-20: 16; 2016-01-21: 16; 2016-01-23: 16; 2016-01-24: 15; 2016-01-25: 10; 2016-01-26: 10; 2016-01-27: 10; 2016-01-28: 12; 2016-01-30: 27; 2016-01-31: 48; 2016-02-01: 48; 2016-02-02: 48; 2016-02-03: 48; 2016-02-04: 48; 2016-02-06: 49; 2016-02-07: 48; 2016-02-08: 48; 2016-02-09: 46; 2016-02-10: 31; 2016-02-11: 10; 2016-02-13: 10; 2016-02-14: 10; 2016-02-15: 10; 2016-02-16: 10; 2016-02-17: 10; 2016-02-18: 38; 2016-02-20: 54; 2016-02-21: 54; 2016-02-22: 54; 2016-02-23: 52; 2016-02-24: 44; 2016-02-25: 44; 2016-02-27: 44; 2016-02-28: 44; 2016-02-29: 45; 2016-03-01: 26; 2016-03-02: 10; 2016-03-03: 10; 2016-03-05: 18; 2016-03-06: 54; 2016-03-07: 70; 2016-03-08: 70; 2016-03-09: 70; 2016-03-10: 70; 2016-03-12: 70; 2016-03-13: 70; 2016-03-14: 71; 2016-03-15: 80; 2016-03-16: 80; 2016-03-17: 79; 2016-03-19: 70; 2016-03-20: 70; 2016-03-21: 70; 2016-03-22: 72; 2016-03-23: 36; 2016-03-24: 31; 2016-03-26: 40; 2016-03-27: 40; 2016-03-28: 40; 2016-03-29: 49; 2016-03-30: 90; 2016-03-31: 97; 2016-04-02: 104; 2016-04-03: 112; 2016-04-04: 144; 2016-04-05: 148; 2016-04-06: 165; 2016-04-07: 175; 2016-04-09: 174; 2016-04-10: 174; 2016-04-11: 167; 2016-04-12: 171; 2016-04-13: 182; 2016-04-14: 190; 2016-04-16: 191; 2016-04-17: 150; 2016-04-18: 165; 2016-04-19: 140; 2016-04-20: 133; 2016-04-21: 110; 2016-04-23: 114; 2016-04-24: 88; 2016-04-25: 86; 2016-04-26: 82; 2016-04-27: 82; 2016-04-28: 82; 2016-04-30: 79; 2016-05-01: 74; 2016-05-02: 72; 2016-05-03: 50; 2016-05-04: 50; 2016-05-05: 30; 2016-05-07: 31; 2016-05-08: 24; 2016-05-09: 24; 2016-05-10: 16; 2016-05-11: 16; 2016-05-12: 6; 2016-05-14: 6; 2016-05-15: 6; 2016-05-16: 7; 2016-05-17: 10; 2016-05-18: 10; 2016-05-19: 8; 2016-05-21: 7; 2016-05-22: 2; 2016-05-23: 2
Subcon - Anti-termite | 2014-12-30: 8; 2014-12-31: 8; 2015-01-10: 8; 2015-01-11: 8; 2015-01-31: 10; 2015-02-01: 10; 2015-02-02: 2; 2015-02-03: 2; 2015-02-04: 2; 2015-02-05: 2; 2015-02-07: 4; 2015-02-08: 4; 2015-02-09: 4; 2015-02-10: 4; 2015-02-11: 4; 2015-02-12: 4; 2015-02-14: 4; 2015-02-15: 4; 2015-02-16: 2; 2015-02-17: 2; 2015-02-18: 2; 2015-02-19: 2; 2015-02-21: 2; 2015-02-22: 2; 2015-04-18: 1; 2015-04-19: 23; 2015-04-26: 19; 2015-04-27: 5; 2015-05-04: 12; 2015-05-05: 12; 2015-05-18: 22; 2015-05-19: 24; 2015-05-20: 24; 2015-05-21: 24; 2015-05-23: 24; 2015-05-24: 2; 2015-05-25: 8; 2015-05-26: 24; 2015-05-27: 1; 2015-05-28: 1; 2015-05-30: 1; 2015-05-31: 1; 2015-06-01: 1; 2015-06-02: 1; 2015-06-03: 1; 2015-06-04: 1; 2015-06-06: 1; 2015-06-07: 1; 2015-06-14: 13; 2015-06-15: 19; 2015-07-12: 1; 2015-07-13: 1; 2015-07-14: 1; 2015-07-15: 1; 2015-07-16: 1; 2015-07-22: 2; 2015-07-23: 2; 2015-07-25: 2; 2015-07-26: 2; 2015-07-27: 2; 2015-07-28: 1; 2015-07-29: 1; 2015-07-30: 1; 2015-08-01: 1; 2015-08-02: 1; 2015-08-03: 1; 2015-08-04: 1; 2015-08-05: 1; 2015-08-06: 1; 2015-08-08: 1; 2015-08-29: 4; 2015-08-30: 4; 2015-08-31: 4; 2015-09-01: 4
Subcon - GRC Works | 2016-04-27: 10; 2016-04-28: 10; 2016-04-30: 10; 2016-05-01: 10; 2016-05-02: 10; 2016-05-03: 10; 2016-05-04: 10; 2016-05-05: 10; 2016-05-07: 10; 2016-05-08: 10; 2016-05-09: 20; 2016-05-10: 21; 2016-05-11: 26; 2016-05-12: 26; 2016-05-14: 26; 2016-05-15: 26; 2016-05-16: 26; 2016-05-17: 26; 2016-05-18: 26; 2016-05-19: 26; 2016-05-21: 26; 2016-05-22: 26; 2016-05-23: 26; 2016-05-24: 26; 2016-05-25: 26; 2016-05-26: 26; 2016-05-28: 26; 2016-05-29: 26; 2016-05-30: 26; 2016-05-31: 26; 2016-06-01: 26; 2016-06-02: 26; 2016-06-04: 26; 2016-06-05: 26; 2016-06-06: 26; 2016-06-07: 26; 2016-06-08: 26; 2016-06-09: 26; 2016-06-11: 26; 2016-06-12: 26; 2016-06-13: 26; 2016-06-14: 26; 2016-06-15: 26; 2016-06-16: 26; 2016-06-18: 26; 2016-06-19: 26; 2016-06-20: 26; 2016-06-21: 26; 2016-06-22: 26; 2016-06-23: 26; 2016-06-25: 26; 2016-06-26: 26; 2016-06-27: 25; 2016-06-28: 25; 2016-06-29: 25; 2016-06-30: 25; 2016-07-02: 25; 2016-07-03: 25; 2016-07-04: 15; 2016-07-05: 15; 2016-07-06: 5; 2016-07-12: 5; 2016-07-13: 5; 2016-07-14: 5; 2016-07-16: 5; 2016-07-17: 5; 2016-07-18: 5; 2016-07-19: 5; 2016-07-20: 5; 2016-07-21: 5; 2016-07-23: 5; 2016-07-24: 5; 2016-07-25: 5; 2016-07-26: 5; 2016-07-27: 5; 2016-07-28: 5; 2016-07-30: 5; 2016-07-31: 5; 2016-08-01: 5; 2016-08-02: 5; 2016-08-03: 5; 2016-08-04: 5; 2016-08-06: 5; 2016-08-07: 4
Subcon - Kitchen Equipment | 2016-05-24: 5; 2016-05-25: 20; 2016-05-26: 20; 2016-05-28: 20; 2016-05-29: 20; 2016-05-30: 20; 2016-05-31: 20; 2016-06-01: 20; 2016-06-02: 20; 2016-06-04: 20; 2016-06-05: 20; 2016-06-06: 20; 2016-06-07: 20; 2016-06-08: 20; 2016-06-09: 20; 2016-06-11: 20; 2016-06-12: 20; 2016-06-13: 20; 2016-06-14: 20; 2016-06-15: 20; 2016-06-16: 20; 2016-06-18: 20; 2016-06-19: 20; 2016-06-20: 20; 2016-06-21: 20; 2016-06-22: 20; 2016-06-23: 20; 2016-06-25: 20; 2016-06-26: 20; 2016-06-27: 20; 2016-06-28: 15
Subcon - Swimming Pool Equipment | 2016-05-14: 4; 2016-05-15: 16; 2016-05-16: 16; 2016-05-17: 16; 2016-05-18: 16; 2016-05-19: 20; 2016-05-21: 32; 2016-05-22: 32; 2016-05-23: 32; 2016-05-24: 32; 2016-05-25: 28; 2016-05-26: 16; 2016-05-28: 16; 2016-05-29: 16; 2016-05-30: 16; 2016-05-31: 12
Subcon - Landscape | 2016-02-28: 1; 2016-02-29: 5; 2016-03-01: 5; 2016-03-02: 5; 2016-03-03: 5; 2016-03-05: 5; 2016-03-06: 5; 2016-03-07: 5; 2016-03-08: 5; 2016-03-09: 5; 2016-03-10: 5; 2016-03-12: 5; 2016-03-13: 5; 2016-03-14: 5; 2016-03-15: 5; 2016-03-16: 6; 2016-03-17: 10; 2016-03-19: 10; 2016-03-20: 10; 2016-03-21: 10; 2016-03-22: 10; 2016-03-23: 10; 2016-03-24: 12; 2016-03-26: 50; 2016-03-27: 50; 2016-03-28: 50; 2016-03-29: 50; 2016-03-30: 50; 2016-03-31: 60; 2016-04-02: 60; 2016-04-03: 56; 2016-04-04: 40; 2016-04-05: 40; 2016-04-06: 40; 2016-04-07: 40; 2016-04-09: 40; 2016-04-10: 40; 2016-04-11: 40; 2016-04-12: 10; 2016-04-13: 10; 2016-04-14: 10; 2016-04-16: 10; 2016-04-17: 10; 2016-04-18: 20; 2016-04-19: 20; 2016-04-20: 20; 2016-04-21: 20; 2016-04-23: 20; 2016-04-24: 20; 2016-04-25: 20; 2016-04-26: 20; 2016-04-27: 20; 2016-04-28: 20; 2016-04-30: 20; 2016-05-01: 20; 2016-05-02: 20; 2016-05-03: 20; 2016-05-04: 20; 2016-05-05: 20; 2016-05-07: 20; 2016-05-08: 20; 2016-05-09: 20; 2016-05-10: 20; 2016-05-11: 20; 2016-05-12: 20; 2016-05-14: 20; 2016-05-15: 20; 2016-05-16: 20; 2016-05-17: 20; 2016-05-18: 20; 2016-05-19: 20; 2016-05-21: 20; 2016-05-22: 20; 2016-05-23: 20; 2016-05-24: 20; 2016-05-25: 20; 2016-05-26: 20; 2016-05-28: 20; 2016-05-29: 20; 2016-05-30: 20; 2016-05-31: 20; 2016-06-01: 20; 2016-06-02: 28; 2016-06-04: 28; 2016-06-05: 28; 2016-06-06: 28; 2016-06-07: 28; 2016-06-08: 28; 2016-06-09: 28; 2016-06-11: 28; 2016-06-12: 22; 2016-06-13: 22; 2016-06-14: 26; 2016-06-15: 26; 2016-06-16: 26; 2016-06-18: 26; 2016-06-19: 26; 2016-06-20: 26; 2016-06-21: 26; 2016-06-22: 26; 2016-06-23: 24; 2016-06-25: 24; 2016-06-26: 24; 2016-06-27: 24; 2016-06-28: 44; 2016-06-29: 44; 2016-06-30: 44; 2016-07-02: 44; 2016-07-03: 44; 2016-07-04: 54; 2016-07-05: 54; 2016-07-06: 54; 2016-07-12: 54; 2016-07-13: 54; 2016-07-14: 54; 2016-07-16: 54; 2016-07-17: 54; 2016-07-18: 54; 2016-07-19: 54; 2016-07-20: 30; 2016-07-21: 30; 2016-07-23: 30; 2016-07-24: 30; 2016-07-25: 30; 2016-07-26: 20; 2016-07-27: 27; 2016-07-28: 27; 2016-07-30: 27; 2016-07-31: 7; 2016-08-01: 7; 2016-08-02: 7; 2016-08-03: 7; 2016-08-04: 7; 2016-08-06: 7; 2016-08-07: 7; 2016-08-08: 7; 2016-08-09: 7; 2016-08-10: 7; 2016-08-11: 7; 2016-08-13: 7; 2016-08-14: 2; 2016-08-15: 2; 2016-08-16: 2; 2016-08-17: 2; 2016-08-18: 2; 2016-08-20: 2; 2016-08-21: 2; 2016-08-22: 2; 2016-08-23: 10; 2016-08-24: 10; 2016-08-25: 10; 2016-08-27: 10; 2016-08-28: 10; 2016-08-29: 10; 2016-08-30: 10; 2016-08-31: 13; 2016-09-01: 13; 2016-09-03: 13; 2016-09-04: 13; 2016-09-05: 13; 2016-09-06: 13; 2016-09-07: 13; 2016-09-13: 13; 2016-09-14: 3; 2016-09-15: 3; 2016-09-17: 4; 2016-09-18: 4; 2016-09-19: 4; 2016-09-20: 4; 2016-09-21: 4; 2016-09-22: 4; 2016-09-24: 4; 2016-09-25: 4
Subcon - Irrigation | 2015-12-31: 10; 2016-01-02: 20; 2016-01-03: 20; 2016-01-04: 20; 2016-01-05: 20; 2016-01-06: 20; 2016-01-07: 20; 2016-01-09: 20; 2016-01-10: 20; 2016-01-11: 20; 2016-01-12: 20; 2016-01-13: 20; 2016-01-14: 20; 2016-01-16: 20; 2016-01-17: 20; 2016-01-18: 14; 2016-01-19: 9; 2016-01-20: 9; 2016-01-21: 9; 2016-01-23: 9; 2016-01-24: 9; 2016-01-25: 9; 2016-01-26: 9; 2016-01-27: 9; 2016-01-28: 9; 2016-01-30: 13; 2016-01-31: 29; 2016-02-01: 29; 2016-02-02: 29; 2016-02-03: 26; 2016-02-04: 24; 2016-02-06: 24; 2016-02-07: 24; 2016-02-08: 24; 2016-02-09: 24; 2016-02-10: 20; 2016-02-11: 4; 2016-02-13: 4; 2016-02-14: 4; 2016-02-15: 2; 2016-04-30: 10; 2016-05-01: 10; 2016-05-02: 10; 2016-05-03: 10; 2016-05-04: 10; 2016-05-05: 10; 2016-05-07: 10; 2016-05-08: 10; 2016-05-09: 10; 2016-05-10: 10; 2016-05-11: 10; 2016-05-12: 10; 2016-05-14: 10; 2016-05-15: 10; 2016-05-16: 10; 2016-05-17: 20; 2016-05-18: 20; 2016-05-19: 30; 2016-05-21: 30; 2016-05-22: 30; 2016-05-23: 30; 2016-05-24: 30; 2016-05-25: 30; 2016-05-26: 30; 2016-05-28: 30; 2016-05-29: 20; 2016-05-30: 20; 2016-05-31: 10; 2016-06-01: 10; 2016-06-02: 10; 2016-06-04: 10; 2016-06-05: 10; 2016-06-06: 10; 2016-06-07: 10; 2016-06-08: 10; 2016-06-09: 2; 2016-06-11: 2; 2016-06-12: 2; 2016-06-13: 2; 2016-06-14: 2; 2016-06-15: 2; 2016-06-16: 2; 2016-06-18: 2

## Initial
Activity ID | time axis 2014-12-01 to 2016-10-13
MANPOWER | 8 | 17 | 17 | 17 |  | 17 | 17 | 29 | 29 | 29 | 29 |  | 29 | 29 | 29 | 29 | 29 |  |  | 29 | 36 | 36 | 36 | 36 | 36 |  | 61 | 61 | 56 | 56 | 56 | 56 |  | 56 | 76 | 76 | 76 | 84 | 84 |  | 79 | 79 | 79 | 77 | 73 | 53 |  | 53 | 57 | 47 | 63 | 63 | 57 |  | 57 | 57 | 57 | 74 | 64 | 64 | 5 | 89 | 95 | 95 | 100 | 90 | 136 | 5 | 132 | 127 | 142 | 121 | 124 | 142 |  | 151 | 112 | 112 | 112 | 112 | 112 |  | 114 | 134 | 169 | 151 | 106 | 140 |  | 115 | 142 | 160 | 180 | 170 | 170 |  | 170 | 179 | 173 | 157 | 137 | 177 | 10 | 98 | 118 | 98 | 83 | 83 | 128 |  | 128 | 124 | 124 | 159 | 161 | 151 |  | 151 | 91 | 123 | 107 | 74 | 68 |  | 70 | 70 | 70 | 70 | 72 | 87 |  | 88 | 158 | 154 | 172 | 146 | 150 | 10 | 163 | 153 | 205 | 181 | 270 | 326 | 10 | 363 | 388 | 344 | 292 | 277 | 279 |  | 203 | 178 | 191 | 210 | 212 | 172 |  | 163 | 132 | 159 | 155 | 116 | 84 |  | 179 | 282 | 323 | 315 | 303 | 280 |  | 295 | 300 | 317 | 292 | 307 | 349 |  | 341 | 328 | 290 | 224 | 286 | 407 |  | 491 | 493 | 578 | 578 | 679 | 681 |  | 675 | 534 | 489 | 476 | 488 | 502 |  | 445 | 322 | 321 | 335 | 326 | 274 |  | 224 | 330 | 376 | 395 | 406 | 510 |  | 546 | 532 | 497 | 365 | 301 | 287 |  | 355 | 281 | 278 | 270 | 320 | 391 | [5 empty] | 351 | 320 |  | 245 | 347 | 432 | 482 | 508 | 520 |  | 529 | 522 | 550 | 470 | 425 | 415 |  | 418 | 420 | 478 | 476 | 430 | 464 |  | 453 | 437 | 403 | 482 | 540 | 580 |  | 634 | 622 | 616 | 596 | 628 | 504 |  | 455 | 414 | 402 | 402 | 455 | 461 |  | 511 | 617 | 597 | 611 | 612 | 609 |  | 628 | 550 | 604 | 593 | 594 | 579 |  | 593 | 570 | 573 | 536 | [6 empty] | 501 | 494 | 534 |  | 587 | 583 | 608 | 591 | 663 | 665 |  | 678 | 674 | 751 | 839 | 881 | 893 |  | 896 | 925 | 970 | 939 | 942 | 960 |  | 936 | 938 | 931 | 933 | 1018 | 982 | 4 | 1088 | 1096 | 1089 | 1114 | 1108 | 1081 | 4 | 1086 | 1228 | 1346 | 1354 | 1340 | 1379 | 30 | 1379 | 1392 | 1385 | 1330 | 1282 | 1303 | 30 | 1361 | 1315 | 1387 | 1402 | 1322 | 1285 | 38 | 1256 | 1198 | 1212 | 1217 | 1278 | 1353 | 38 | 1412 | 1415 | 1486 | 1477 | 1510 | 1507 | 62 | 1469 | 1458 | 1505 | 1480 | 1567 | 1533 | 20 | 1565 | 1547 | 1540 | 1534 | 1516 | 1479 | 40 | 1518 | 1547 | 1637 | 1693 | 1713 | 1690 | 20 | 1741 | 1647 | 1594 | 1614 | 1677 | 1699 | 72 | 1780 | 1778 | 1839 | 1753 | 1757 | 1678 | 86 | 1714 | 1773 | 1846 | 1786 | 1801 | 1865 | 62 | 1848 | 1794 | 1758 | 1790 | 1827 | 1903 | 100 | 1983 | 1987 | 1853 | 1888 | 1792 | 1729 | 56 | 1707 | 1777 | 1838 | 1901 | 2030 | 2023 | 45 | 1979 | 1830 | 1842 | 1748 | 1714 | 1955 | 55 | 1959 | 1934 | 1986 | 2072 | 2063 | 2018 | 110 | 1980 | 1846 | 1796 | 1869 | 1884 | 1865 | 139 | 1858 | 1868 | 1720 | 1683 | 1676 | 1568 | 91 | 1545 | 1427 | 1447 | 1381 | 1331 | 1384 | 100 | 1218 | 1152 | 1065 | 1021 | 1009 | 1004 | 59 | 994 | 936 | 966 | 994 | 861 | 842 | 88 | 846 | 826 | 844 | 874 | 909 | 901 | 98 | 932 | 976 | 922 | 1037 | 1110 | 1085 | 89 | 993 | 1001 | 1033 | 1027 | 1020 | 1005 | 97 | 982 | 982 | 1038 | 999 | 915 | 913 | 102 | 937 | 879 | 887 | 874 | 858 | 810 | 96 | 826 | 828 | 751 | 714 | 756 | 768 | 40 | 739 | 715 | 720 | 775 | 815 | 801 | 28 | 783 | 787 | 709 | 701 | 678 | 666 | 20 | 630 | 560 | 498 | 476 | 449 | 416 | 10 | 356 | 332 | 323 | 323 | 307 | 291 |  | 267 | 247 | 248 | 235 | 191 | 196 |  | 196 | 197 | 202 | 192 | 188 | 172 |  | 170 | 170 | 166 | 166 | 166 | 162 | 10 | 146 | 146 | 139 | 139 | 138 | 14 | 14 | 14 | 14 | 4 | 123 | 119 | 119 | 4 | 119 | 115 | 95 | 95 | 95 | 95 |  | 95 | 93 | 111 | 104 | 104 | 102 |  | 94 | 94 | 57 | 57 | 57 | 57 |  | 50 | 50 | 53 | 63 | 63 | 46 |  | 46 | 46 | 45 | 44 | 44 | 38 |  | 38 | 45 | 43 | 22 | 22 | 22 |  | 22 | 20 | 20 | 20 | 20 | 23 |  | 23 | 23 | 19 | 19 | 9 | [5 empty] | 9 | 9 | 9 |  | 8 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4
Carpenter-Conc | 2015-01-04: 10; 2015-01-05: 10; 2015-01-06: 10; 2015-01-07: 10; 2015-01-08: 10; 2015-01-10: 10; 2015-01-11: 10; 2015-01-12: 10; 2015-01-13: 10; 2015-01-14: 13; 2015-01-15: 3; 2015-01-17: 3; 2015-01-18: 3; 2015-01-19: 3; 2015-01-20: 11; 2015-01-21: 11; 2015-01-22: 8; 2015-01-24: 8; 2015-01-25: 8; 2015-01-26: 8; 2015-01-27: 8; 2015-01-28: 8; 2015-01-29: 8; 2015-01-31: 8; 2015-02-01: 11; 2015-02-02: 11; 2015-02-03: 3; 2015-02-04: 3; 2015-02-05: 3; 2015-02-07: 3; 2015-02-08: 3; 2015-02-11: 9; 2015-02-12: 9; 2015-02-14: 19; 2015-02-15: 19; 2015-02-16: 19; 2015-02-17: 19; 2015-02-18: 19; 2015-02-19: 19; 2015-02-21: 19; 2015-02-22: 29; 2015-02-23: 29; 2015-02-24: 20; 2015-02-25: 10; 2015-02-26: 10; 2015-02-28: 20; 2015-03-01: 30; 2015-03-02: 38; 2015-03-03: 48; 2015-03-04: 48; 2015-03-05: 48; 2015-03-07: 48; 2015-03-08: 38; 2015-03-09: 38; 2015-03-10: 38; 2015-03-11: 28; 2015-03-12: 8; 2015-03-14: 8; 2015-03-15: 8; 2015-03-30: 16; 2015-03-31: 16; 2015-04-01: 16; 2015-04-02: 16; 2015-04-04: 20; 2015-04-05: 20; 2015-04-06: 20; 2015-04-07: 20; 2015-04-08: 21; 2015-04-09: 21; 2015-04-11: 20; 2015-04-12: 53; 2015-04-13: 54; 2015-04-14: 38; 2015-04-15: 37; 2015-04-16: 37; 2015-04-18: 33; 2015-04-19: 33; 2015-04-20: 33; 2015-04-21: 12; 2015-04-22: 70; 2015-04-23: 70; 2015-04-25: 70; 2015-04-26: 70; 2015-04-27: 58; 2015-04-28: 58; 2015-04-29: 58; 2015-04-30: 59; 2015-05-02: 22; 2015-05-03: 22; 2015-05-04: 22; 2015-05-05: 48; 2015-05-06: 49; 2015-05-07: 28; 2015-05-09: 28; 2015-05-10: 27; 2015-05-11: 27; 2015-05-12: 27; 2015-05-13: 27; 2015-05-14: 11; 2015-05-16: 71; 2015-05-17: 93; 2015-05-18: 93; 2015-05-19: 93; 2015-05-20: 87; 2015-05-21: 88; 2015-05-23: 88; 2015-05-24: 83; 2015-05-25: 81; 2015-05-26: 85; 2015-05-27: 85; 2015-05-28: 106; 2015-05-30: 102; 2015-05-31: 82; 2015-06-01: 76; 2015-06-02: 78; 2015-06-03: 81; 2015-06-04: 139; 2015-06-06: 139; 2015-06-07: 126; 2015-06-08: 181; 2015-06-09: 181; 2015-06-10: 181; 2015-06-11: 183; 2015-06-13: 180; 2015-06-14: 122; 2015-06-15: 122; 2015-06-16: 119; 2015-06-17: 110; 2015-06-18: 116; 2015-06-20: 92; 2015-06-21: 57; 2015-06-22: 70; 2015-06-23: 60; 2015-06-24: 62; 2015-06-25: 62; 2015-06-27: 36; 2015-06-28: 91; 2015-06-29: 89; 2015-06-30: 94; 2015-07-01: 85; 2015-07-02: 146; 2015-07-04: 146; 2015-07-05: 138; 2015-07-06: 132; 2015-07-07: 66; 2015-07-08: 66; 2015-07-09: 67; 2015-07-11: 86; 2015-07-12: 49; 2015-07-13: 47; 2015-07-14: 46; 2015-07-15: 46; 2015-07-16: 45; 2015-07-22: 24; 2015-07-23: 24; 2015-07-25: 3; 2015-07-26: 62; 2015-07-27: 70; 2015-07-28: 74; 2015-07-29: 74; 2015-07-30: 80; 2015-08-01: 80; 2015-08-02: 80; 2015-08-03: 77; 2015-08-04: 28; 2015-08-05: 28; 2015-08-06: 25; 2015-08-08: 36; 2015-08-09: 36; 2015-08-10: 38; 2015-08-11: 37; 2015-08-12: 36; 2015-08-13: 34; 2015-08-15: 28; 2015-08-16: 24; 2015-08-17: 7; 2015-08-18: 62; 2015-08-19: 62; 2015-08-20: 62; 2015-08-22: 62; 2015-08-23: 62; 2015-08-24: 62; 2015-08-25: 65; 2015-08-26: 65; 2015-08-27: 8; 2015-08-29: 8; 2015-08-30: 5; 2015-08-31: 7; 2015-09-01: 7; 2015-09-02: 6; 2015-09-03: 6; 2015-09-05: 38; 2015-09-06: 41; 2015-09-07: 41; 2015-09-08: 41; 2015-09-09: 39; 2015-09-10: 44; 2015-09-12: 44; 2015-09-13: 13; 2015-09-14: 16; 2015-09-15: 20; 2015-09-16: 20; 2015-09-17: 23; 2015-09-19: 19; 2015-09-20: 11; 2015-09-21: 11; 2015-09-22: 8; 2015-09-29: 11; 2015-09-30: 10; 2015-10-01: 7; 2015-10-03: 7; 2015-10-04: 7; 2015-10-05: 7; 2015-10-06: 7; 2015-10-07: 7; 2015-10-08: 7; 2015-10-10: 4; 2015-10-11: 4; 2015-10-12: 14; 2015-10-13: 16; 2015-10-14: 17; 2015-10-15: 16; 2015-10-17: 19; 2015-10-18: 19; 2015-10-19: 29; 2015-10-20: 29; 2015-10-21: 27; 2015-10-22: 27; 2015-10-24: 21; 2015-10-25: 22; 2015-10-26: 24; 2015-10-27: 19; 2015-10-28: 21; 2015-10-29: 21; 2015-10-31: 33; 2015-11-01: 33; 2015-11-02: 29; 2015-11-03: 29; 2015-11-04: 29; 2015-11-05: 18; 2015-11-07: 15; 2015-11-08: 15; 2015-11-09: 17; 2015-11-10: 17; 2015-11-11: 29; 2015-11-12: 29; 2015-11-14: 25; 2015-11-15: 29; 2015-11-16: 29; 2015-11-17: 19; 2015-11-18: 19; 2015-11-19: 19; 2015-11-21: 21; 2015-11-22: 21; 2015-11-23: 21; 2015-11-24: 23; 2015-11-25: 26; 2015-11-26: 22; 2015-11-28: 22; 2015-11-29: 12; 2015-11-30: 12; 2015-12-01: 12; 2015-12-02: 12; 2015-12-03: 12; 2015-12-05: 16; 2015-12-06: 18; 2015-12-07: 26; 2015-12-08: 26; 2015-12-09: 26; 2015-12-10: 30; 2015-12-12: 28; 2015-12-13: 20; 2015-12-14: 20; 2015-12-15: 20; 2015-12-16: 20; 2015-12-17: 22; 2015-12-19: 30; 2015-12-20: 30; 2015-12-21: 30; 2015-12-22: 36; 2015-12-23: 34; 2015-12-24: 26; 2015-12-26: 26; 2015-12-27: 26; 2015-12-28: 26; 2015-12-29: 26; 2015-12-30: 26; 2015-12-31: 26; 2016-01-02: 26; 2016-01-03: 36; 2016-01-04: 34; 2016-01-05: 30; 2016-01-06: 30; 2016-01-07: 34; 2016-01-09: 30; 2016-01-10: 30; 2016-01-11: 28; 2016-01-12: 28; 2016-01-13: 28; 2016-01-14: 24; 2016-01-16: 24; 2016-01-17: 28; 2016-01-18: 28; 2016-01-19: 24; 2016-01-20: 24; 2016-01-21: 24; 2016-01-23: 24; 2016-01-24: 24; 2016-01-25: 24; 2016-01-26: 10; 2016-01-27: 10; 2016-01-28: 14; 2016-01-30: 14; 2016-01-31: 16; 2016-02-01: 16; 2016-02-02: 16; 2016-02-03: 17; 2016-02-04: 18; 2016-02-05: 1; 2016-02-06: 16; 2016-02-07: 6; 2016-02-08: 6; 2016-02-09: 6; 2016-02-10: 6; 2016-02-11: 6; 2016-02-13: 6; 2016-02-14: 4; 2016-02-15: 4; 2016-02-16: 4; 2016-02-17: 4; 2016-02-18: 4; 2016-02-20: 4; 2016-02-21: 4; 2016-02-22: 4; 2016-02-23: 4; 2016-02-24: 4; 2016-02-25: 4; 2016-02-27: 4; 2016-02-28: 4; 2016-02-29: 4; 2016-03-01: 4; 2016-03-02: 4; 2016-03-03: 4; 2016-03-05: 4; 2016-03-06: 4; 2016-03-07: 4; 2016-03-08: 4; 2016-03-09: 4; 2016-03-10: 4; 2016-03-12: 5; 2016-03-13: 4; 2016-03-14: 4; 2016-03-15: 4; 2016-03-16: 4; 2016-03-17: 4; 2016-03-19: 4; 2016-03-20: 4; 2016-03-21: 4; 2016-03-22: 4; 2016-03-23: 4; 2016-03-24: 4; 2016-03-26: 4; 2016-03-27: 4; 2016-03-28: 4; 2016-03-29: 4; 2016-03-30: 4; 2016-03-31: 4; 2016-04-02: 4; 2016-04-03: 4; 2016-04-04: 4; 2016-04-05: 4; 2016-04-06: 4; 2016-04-07: 4; 2016-04-09: 4; 2016-04-10: 4; 2016-04-11: 4; 2016-04-12: 4; 2016-04-13: 4; 2016-04-14: 4; 2016-04-16: 3
Steel Fixer - Conc | 2015-01-04: 12; 2015-01-05: 12; 2015-01-06: 12; 2015-01-07: 12; 2015-01-08: 12; 2015-01-10: 12; 2015-01-11: 12; 2015-01-12: 12; 2015-01-13: 12; 2015-01-14: 12; 2015-01-15: 12; 2015-01-17: 12; 2015-01-18: 4; 2015-01-19: 8; 2015-01-20: 8; 2015-01-21: 8; 2015-01-22: 8; 2015-01-24: 8; 2015-01-25: 8; 2015-01-26: 8; 2015-01-27: 4; 2015-01-28: 4; 2015-01-29: 4; 2015-01-31: 2; 2015-02-01: 2; 2015-02-02: 2; 2015-02-03: 2; 2015-02-04: 2; 2015-02-05: 2; 2015-02-12: 9; 2015-02-14: 21; 2015-02-15: 24; 2015-02-16: 24; 2015-02-17: 24; 2015-02-18: 24; 2015-02-19: 24; 2015-02-21: 30; 2015-02-22: 30; 2015-02-23: 30; 2015-02-24: 30; 2015-02-25: 30; 2015-02-26: 18; 2015-02-28: 19; 2015-03-01: 23; 2015-03-02: 29; 2015-03-03: 29; 2015-03-04: 23; 2015-03-05: 23; 2015-03-07: 23; 2015-03-08: 23; 2015-03-09: 13; 2015-03-10: 4; 2015-03-11: 4; 2015-03-25: 6; 2015-03-26: 6; 2015-03-28: 6; 2015-03-29: 11; 2015-03-30: 11; 2015-03-31: 11; 2015-04-01: 11; 2015-04-02: 13; 2015-04-04: 15; 2015-04-05: 15; 2015-04-06: 15; 2015-04-07: 15; 2015-04-08: 15; 2015-04-09: 10; 2015-04-11: 24; 2015-04-12: 18; 2015-04-13: 18; 2015-04-14: 15; 2015-04-15: 15; 2015-04-16: 14; 2015-04-18: 14; 2015-04-19: 14; 2015-04-20: 5; 2015-04-21: 5; 2015-04-22: 5; 2015-04-23: 33; 2015-04-25: 33; 2015-04-26: 28; 2015-04-27: 28; 2015-04-28: 28; 2015-04-29: 48; 2015-04-30: 48; 2015-05-02: 48; 2015-05-03: 31; 2015-05-04: 42; 2015-05-05: 42; 2015-05-06: 42; 2015-05-07: 48; 2015-05-09: 39; 2015-05-10: 39; 2015-05-11: 38; 2015-05-12: 38; 2015-05-13: 11; 2015-05-14: 11; 2015-05-16: 19; 2015-05-17: 46; 2015-05-18: 46; 2015-05-19: 42; 2015-05-20: 42; 2015-05-21: 42; 2015-05-23: 37; 2015-05-24: 51; 2015-05-25: 50; 2015-05-26: 32; 2015-05-27: 43; 2015-05-28: 43; 2015-05-30: 43; 2015-05-31: 43; 2015-06-01: 25; 2015-06-02: 11; 2015-06-03: 35; 2015-06-04: 51; 2015-06-06: 72; 2015-06-07: 72; 2015-06-08: 72; 2015-06-09: 72; 2015-06-10: 100; 2015-06-11: 98; 2015-06-13: 98; 2015-06-14: 98; 2015-06-15: 71; 2015-06-16: 82; 2015-06-17: 82; 2015-06-18: 93; 2015-06-20: 65; 2015-06-21: 50; 2015-06-22: 44; 2015-06-23: 51; 2015-06-24: 42; 2015-06-25: 31; 2015-06-27: 30; 2015-06-28: 30; 2015-06-29: 56; 2015-06-30: 50; 2015-07-01: 50; 2015-07-02: 51; 2015-07-04: 71; 2015-07-05: 65; 2015-07-06: 67; 2015-07-07: 67; 2015-07-08: 37; 2015-07-09: 47; 2015-07-11: 46; 2015-07-12: 46; 2015-07-13: 23; 2015-07-14: 23; 2015-07-15: 25; 2015-07-16: 25; 2015-07-22: 24; 2015-07-23: 3; 2015-07-25: 3; 2015-07-26: 4; 2015-07-27: 33; 2015-07-28: 32; 2015-07-29: 32; 2015-07-30: 32; 2015-08-01: 32; 2015-08-02: 32; 2015-08-03: 32; 2015-08-04: 34; 2015-08-05: 7; 2015-08-06: 15; 2015-08-08: 14; 2015-08-09: 15; 2015-08-10: 13; 2015-08-11: 13; 2015-08-12: 12; 2015-08-13: 11; 2015-08-15: 11; 2015-08-16: 2; 2015-08-17: 2; 2015-08-18: 2; 2015-08-19: 31; 2015-08-20: 31; 2015-08-22: 31; 2015-08-23: 31; 2015-08-24: 31; 2015-08-25: 31; 2015-08-26: 32; 2015-08-27: 32; 2015-08-29: 3; 2015-08-30: 4; 2015-08-31: 4; 2015-09-01: 4; 2015-09-02: 4; 2015-09-03: 3; 2015-09-05: 3; 2015-09-06: 21; 2015-09-07: 21; 2015-09-08: 20; 2015-09-09: 20; 2015-09-10: 20; 2015-09-12: 23; 2015-09-13: 23; 2015-09-14: 5; 2015-09-15: 5; 2015-09-16: 5; 2015-09-17: 5; 2015-09-19: 5; 2015-09-20: 5; 2015-09-21: 2; 2015-09-22: 2; 2015-09-29: 2; 2015-09-30: 2; 2015-10-01: 2; 2015-10-03: 2; 2015-10-04: 2; 2015-10-05: 2; 2015-10-06: 2; 2015-10-07: 2; 2015-10-08: 2; 2015-10-10: 2; 2015-10-11: 2; 2015-10-12: 8; 2015-10-13: 8; 2015-10-14: 8; 2015-10-15: 8; 2015-10-17: 8; 2015-10-18: 8; 2015-10-19: 9; 2015-10-20: 9; 2015-10-21: 9; 2015-10-22: 9; 2015-10-24: 3; 2015-10-25: 3; 2015-10-26: 3; 2015-10-27: 3; 2015-10-28: 3; 2015-10-29: 3; 2015-10-31: 5; 2015-11-01: 5; 2015-11-02: 3; 2015-11-03: 3; 2015-11-04: 3; 2015-11-05: 3; 2015-11-07: 3; 2015-11-08: 3; 2015-11-09: 3; 2015-11-10: 3; 2015-11-11: 5; 2015-11-12: 5; 2015-11-14: 3; 2015-11-15: 3; 2015-11-16: 3; 2015-11-17: 3; 2015-11-18: 3; 2015-11-19: 3; 2015-11-21: 3; 2015-11-22: 3; 2015-11-23: 3; 2015-11-24: 3; 2015-12-05: 2; 2015-12-06: 2; 2015-12-07: 2; 2015-12-08: 2; 2015-12-09: 2; 2015-12-10: 2; 2015-12-12: 2; 2015-12-13: 2; 2015-12-14: 2; 2015-12-15: 2; 2015-12-16: 2; 2015-12-17: 2; 2015-12-19: 2; 2015-12-20: 2; 2015-12-21: 2; 2015-12-22: 2; 2015-12-23: 2; 2015-12-24: 2; 2015-12-26: 2; 2015-12-27: 2; 2015-12-28: 2; 2015-12-29: 2; 2015-12-30: 2; 2015-12-31: 2; 2016-01-02: 2; 2016-01-03: 2; 2016-01-04: 2; 2016-01-05: 2; 2016-01-06: 2; 2016-01-07: 2; 2016-01-31: 1; 2016-02-01: 1; 2016-02-02: 1; 2016-02-03: 1; 2016-02-04: 1; 2016-02-06: 1; 2016-02-07: 1; 2016-02-08: 1; 2016-02-09: 1; 2016-02-10: 1; 2016-02-11: 1; 2016-02-13: 1
Mason - Conc | 2014-12-27: 10; 2014-12-28: 10; 2014-12-29: 10; 2014-12-30: 10; 2014-12-31: 10; 2015-01-01: 10; 2015-01-03: 10; 2015-01-18: 10; 2015-01-27: 10; 2015-01-31: 8; 2015-02-01: 8; 2015-02-02: 8; 2015-02-03: 16; 2015-02-04: 8; 2015-02-05: 16; 2015-02-07: 16; 2015-02-08: 16; 2015-02-09: 24; 2015-02-10: 16; 2015-02-11: 18; 2015-02-12: 18; 2015-02-14: 8; 2015-02-23: 10; 2015-02-24: 10; 2015-02-26: 20; 2015-02-28: 10; 2015-03-08: 10; 2015-03-12: 40; 2015-03-14: 10; 2015-03-15: 10; 2015-03-16: 8; 2015-03-19: 8; 2015-03-21: 8; 2015-03-22: 8; 2015-03-23: 8; 2015-03-24: 18; 2015-03-25: 18; 2015-03-26: 18; 2015-03-28: 18; 2015-04-09: 10; 2015-04-12: 2; 2015-04-14: 20; 2015-04-16: 2; 2015-04-18: 10; 2015-04-19: 10; 2015-04-20: 28; 2015-04-21: 18; 2015-04-22: 8; 2015-04-23: 8; 2015-04-25: 18; 2015-04-26: 28; 2015-04-27: 28; 2015-04-28: 8; 2015-05-03: 10; 2015-05-09: 10; 2015-05-11: 11; 2015-05-12: 10; 2015-05-13: 15; 2015-05-14: 15; 2015-05-17: 1; 2015-05-18: 10; 2015-05-19: 10; 2015-05-20: 10; 2015-05-23: 10; 2015-05-24: 4; 2015-05-25: 12; 2015-05-26: 20; 2015-05-27: 10; 2015-05-28: 10; 2015-05-30: 10; 2015-05-31: 20; 2015-06-01: 30; 2015-06-02: 16; 2015-06-03: 20; 2015-06-04: 10; 2015-06-06: 10; 2015-06-07: 10; 2015-06-10: 10; 2015-06-11: 12; 2015-06-13: 12; 2015-06-14: 2; 2015-06-15: 12; 2015-06-16: 2; 2015-06-17: 2; 2015-06-18: 2; 2015-06-20: 12; 2015-06-21: 8; 2015-06-22: 6; 2015-06-23: 15; 2015-06-24: 24; 2015-06-25: 14; 2015-06-27: 15; 2015-06-28: 14; 2015-06-29: 12; 2015-06-30: 12; 2015-07-01: 22; 2015-07-02: 13; 2015-07-04: 12; 2015-07-05: 22; 2015-07-06: 12; 2015-07-07: 12; 2015-07-08: 17; 2015-07-09: 4; 2015-07-11: 2; 2015-07-12: 2; 2015-07-13: 12; 2015-07-14: 2; 2015-07-16: 11; 2015-07-22: 11; 2015-07-23: 23; 2015-07-25: 12; 2015-07-26: 2; 2015-07-27: 2; 2015-07-28: 3; 2015-07-29: 2; 2015-07-30: 2; 2015-08-01: 2; 2015-08-02: 2; 2015-08-03: 2; 2015-08-04: 4; 2015-08-05: 14; 2015-08-06: 4; 2015-08-08: 4; 2015-08-09: 4; 2015-08-10: 2; 2015-08-11: 2; 2015-08-12: 2; 2015-08-13: 13; 2015-08-15: 12; 2015-08-16: 12; 2015-08-17: 12; 2015-08-18: 2; 2015-08-19: 2; 2015-08-20: 2; 2015-08-22: 2; 2015-08-23: 2; 2015-08-24: 2; 2015-08-25: 4; 2015-08-26: 4; 2015-08-27: 4; 2015-08-29: 14; 2015-08-30: 4; 2015-08-31: 4; 2015-09-01: 4; 2015-09-02: 4; 2015-09-03: 6; 2015-09-05: 4; 2015-09-06: 12; 2015-09-07: 12; 2015-09-08: 12; 2015-09-09: 12; 2015-09-10: 2; 2015-09-12: 2; 2015-09-13: 2; 2015-09-14: 12; 2015-09-15: 2; 2015-09-16: 2; 2015-09-17: 7; 2015-09-19: 10; 2015-09-20: 12; 2015-09-21: 22; 2015-09-22: 12; 2015-09-29: 12; 2015-09-30: 12; 2015-10-01: 12; 2015-10-03: 12; 2015-10-04: 12; 2015-10-05: 12; 2015-10-06: 14; 2015-10-07: 14; 2015-10-08: 14; 2015-10-10: 14; 2015-10-11: 14; 2015-10-12: 20; 2015-10-13: 20; 2015-10-14: 20; 2015-10-15: 20; 2015-10-17: 20; 2015-10-18: 18; 2015-10-19: 21; 2015-10-20: 21; 2015-10-21: 21; 2015-10-22: 21; 2015-10-24: 15; 2015-10-25: 13; 2015-10-26: 13; 2015-10-27: 13; 2015-10-28: 8; 2015-10-29: 5; 2015-10-31: 9; 2015-11-01: 9; 2015-11-02: 7; 2015-11-03: 7; 2015-11-04: 7; 2015-11-05: 5; 2015-11-07: 5; 2015-11-08: 5; 2015-11-09: 5; 2015-11-10: 5; 2015-11-11: 11; 2015-11-12: 11; 2015-11-14: 9; 2015-11-15: 9; 2015-11-16: 9; 2015-11-17: 7; 2015-11-18: 7; 2015-11-19: 7; 2015-11-21: 7; 2015-11-22: 7; 2015-11-23: 11; 2015-11-24: 11; 2015-11-25: 8; 2015-11-26: 8; 2015-11-28: 8; 2015-11-29: 4; 2015-11-30: 4; 2015-12-01: 4; 2015-12-02: 4; 2015-12-03: 4; 2015-12-04: 5; 2015-12-05: 17; 2015-12-06: 17; 2015-12-07: 17; 2015-12-08: 17; 2015-12-09: 17; 2015-12-10: 8; 2015-12-12: 8; 2015-12-13: 8; 2015-12-14: 8; 2015-12-15: 8; 2015-12-16: 12; 2015-12-17: 12; 2015-12-19: 12; 2015-12-20: 12; 2015-12-21: 12; 2015-12-22: 8; 2015-12-23: 8; 2015-12-24: 8; 2015-12-26: 8; 2015-12-27: 8; 2015-12-28: 12; 2015-12-29: 12; 2015-12-30: 12; 2015-12-31: 12; 2016-01-02: 12; 2016-01-03: 8; 2016-01-04: 8; 2016-01-05: 8; 2016-01-06: 8; 2016-01-07: 8; 2016-01-08: 2; 2016-01-09: 20; 2016-01-10: 20; 2016-01-11: 20; 2016-01-12: 20; 2016-01-13: 20; 2016-01-14: 16; 2016-01-16: 14; 2016-01-17: 14; 2016-01-18: 14; 2016-01-19: 14; 2016-01-20: 16; 2016-01-21: 16; 2016-01-22: 2; 2016-01-23: 6; 2016-01-24: 6; 2016-01-25: 6; 2016-01-26: 2; 2016-01-31: 2; 2016-02-01: 4; 2016-02-02: 4; 2016-02-03: 4; 2016-02-04: 4; 2016-02-05: 2; 2016-02-06: 4; 2016-02-07: 4; 2016-02-08: 2; 2016-02-09: 2; 2016-02-10: 2; 2016-02-11: 2; 2016-02-13: 2; 2016-03-01: 2; 2016-03-02: 2; 2016-03-13: 2; 2016-03-14: 2; 2016-03-25: 2; 2016-03-26: 2
Labour - BTCC | [26 empty] | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 22 | 22 | 22 | 22 | 22 |  | 22 | 22 | 22 | 22 | 25 | 15 |  | 15 | 17 | 16 | 24 | 24 | 21 |  | 21 | 21 | 21 | 27 | 22 | 22 |  | 23 | 26 | 26 | 26 | 18 | 21 |  | 19 | 19 | 24 | 16 | 27 | 36 |  | 48 | 43 | 43 | 43 | 43 | 43 |  | 49 | 59 | 69 | 60 | 40 | 48 |  | 49 | 66 | 80 | 90 | 84 | 84 |  | 84 | 84 | 64 | 55 | 45 | 48 |  | 18 | 18 | 8 |  |  | 8 |  | 8 | 8 | 8 | 18 | 24 | 24 |  | 24 | 11 | 27 | 27 | 27 | 29 |  | 35 | 35 | 35 | 35 | 36 | 41 |  | 44 | 73 | 72 | 73 | 52 | 53 |  | 57 | 57 | 66 | 35 | 83 | 111 |  | 121 | 126 | 114 | 94 | 106 | 107 |  | 70 | 63 | 64 | 90 | 91 | 76 |  | 77 | 66 | 76 | 75 | 53 | 37 |  | 90 | 140 | 149 | 145 | 139 | 130 |  | 135 | 138 | 143 | 137 | 139 | 160 |  | 156 | 146 | 132 | 106 | 137 | 201 |  | 237 | 224 | 269 | 269 | 307 | 307 |  | 304 | 236 | 219 | 217 | 223 | 240 |  | 197 | 143 | 147 | 152 | 154 | 133 |  | 107 | 161 | 185 | 184 | 185 | 238 |  | 257 | 238 | 225 | 159 | 133 | 131 |  | 150 | 113 | 117 | 108 | 135 | 162 | [5 empty] | 142 | 131 |  | 99 | 148 | 184 | 188 | 202 | 208 |  | 204 | 214 | 219 | 172 | 155 | 151 |  | 162 | 163 | 178 | 177 | 148 | 157 |  | 153 | 140 | 123 | 168 | 197 | 197 |  | 212 | 212 | 212 | 202 | 218 | 161 |  | 142 | 130 | 132 | 132 | 146 | 147 |  | 177 | 206 | 206 | 220 | 218 | 215 |  | 224 | 193 | 203 | 197 | 198 | 194 |  | 201 | 195 | 202 | 188 | [6 empty] | 169 | 168 | 180 |  | 180 | 181 | 192 | 179 | 204 | 204 |  | 202 | 202 | 213 | 237 | 236 | 234 |  | 231 | 230 | 244 | 244 | 242 | 243 |  | 244 | 220 | 222 | 217 | 222 | 227 |  | 258 | 258 | 251 | 249 | 226 | 213 |  | 210 | 210 | 213 | 213 | 237 | 239 | 15 | 232 | 236 | 244 | 223 | 214 | 212 | 15 | 214 | 213 | 228 | 231 | 228 | 223 | 12 | 221 | 192 | 190 | 190 | 190 | 194 | 15 | 200 | 200 | 208 | 209 | 210 | 195 | 2 | 182 | 173 | 169 | 171 | 168 | 170 |  | 178 | 179 | 181 | 176 | 173 | 164 |  | 158 | 158 | 147 | 147 | 144 | 147 |  | 153 | 150 | 147 | 142 | 138 | 142 | 4 | 134 | 132 | 135 | 136 | 156 | 156 | 10 | 150 | 154 | 154 | 147 | 136 | 136 | 16 | 128 | 128 | 135 | 121 | 124 | 128 | 14 | 128 | 105 | 97 | 104 | 106 | 106 | 6 | 105 | 91 | 99 | 99 | 99 | 98 | 2 | 90 | 75 | 75 | 75 | 74 | 70 | 2 | 69 | 69 | 69 | 69 | 69 | 54 | 2 | 54 | 50 | 49 | 68 | 72 | 70 | 10 | 70 | 70 | 85 | 91 | 91 | 87 | 10 | 88 | 104 | 103 | 101 | 93 | 91 | 6 | 76 | 75 | 69 | 65 | 65 | 65 | 2 | 70 | 68 | 68 | 68 | 53 | 45 |  | 45 | 41 | 40 | 47 | 47 | 49 | 2 | 49 | 49 | 44 | 42 | 71 | 71 |  | 71 | 66 | 66 | 68 | 68 | 68 | 2 | 68 | 66 | 76 | 76 | 76 | 62 |  | 62 | 52 | 52 | 52 | 52 | 67 |  | 69 | 70 | 70 | 70 | 70 | 60 |  | 60 | 60 | 60 | 73 | 73 | 73 |  | 73 | 73 | 63 | 63 | 63 | 63 |  | 46 | 56 | 56 | 55 | 55 | 55 |  | 45 | 45 | 45 | 45 | 50 | 42 |  | 40 | 40 | 40 | 34 | 24 | 24 |  | 24 | 24 | 24 | 24 | 24 | 24 |  | 24 | 24 | 19 | 19 | 19 | 19 |  | 19 | 19 | 19 | 19 | 19 | [5 empty] | 19 | 19 | 19 |  | 19 | 19 | 19 | 19 | 19 | 19 |  | 19 | 19 | 19 | 24 | 24 | 24 |  | 24 | 24 | 5 | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5
Mason - Block | 2015-01-19: 5; 2015-01-20: 5; 2015-01-21: 5; 2015-01-22: 5; 2015-01-24: 5; 2015-01-25: 5; 2015-01-26: 5; 2015-01-27: 5; 2015-01-28: 10; 2015-01-29: 10; 2015-01-31: 5; 2015-02-01: 5; 2015-02-02: 5; 2015-02-03: 5; 2015-02-04: 5; 2015-03-01: 13; 2015-03-02: 13; 2015-03-03: 13; 2015-03-04: 13; 2015-03-05: 13; 2015-03-07: 13; 2015-03-08: 13; 2015-03-09: 13; 2015-03-10: 13; 2015-03-11: 13; 2015-06-06: 15; 2015-06-07: 15; 2015-06-08: 15; 2015-06-09: 15; 2015-06-10: 15; 2015-06-11: 15; 2015-06-13: 15; 2015-06-14: 15; 2015-06-15: 15; 2015-06-16: 15; 2015-06-17: 30; 2015-06-18: 30; 2015-06-20: 30; 2015-06-21: 30; 2015-06-22: 30; 2015-06-23: 30; 2015-06-24: 30; 2015-06-25: 30; 2015-06-27: 30; 2015-06-28: 30; 2015-06-29: 30; 2015-06-30: 30; 2015-07-01: 30; 2015-07-02: 30; 2015-07-04: 30; 2015-07-05: 15; 2015-07-06: 15; 2015-07-07: 15; 2015-07-08: 15; 2015-07-09: 15; 2015-07-11: 15; 2015-07-12: 15; 2015-07-13: 30; 2015-07-14: 30; 2015-07-15: 57; 2015-07-16: 60; 2015-07-22: 60; 2015-07-23: 60; 2015-07-25: 60; 2015-07-26: 61; 2015-07-27: 62; 2015-07-28: 62; 2015-07-29: 77; 2015-07-30: 77; 2015-08-01: 77; 2015-08-02: 77; 2015-08-03: 77; 2015-08-04: 77; 2015-08-05: 77; 2015-08-06: 76; 2015-08-08: 75; 2015-08-09: 75; 2015-08-10: 90; 2015-08-11: 90; 2015-08-12: 63; 2015-08-13: 45; 2015-08-15: 45; 2015-08-16: 30; 2015-08-17: 30; 2015-08-18: 30; 2015-08-19: 30; 2015-08-20: 30; 2015-08-22: 45; 2015-08-23: 45; 2015-08-24: 45; 2015-08-25: 45; 2015-08-26: 45; 2015-08-27: 30; 2015-08-29: 30; 2015-08-30: 30; 2015-08-31: 30; 2015-09-01: 30; 2015-09-02: 45; 2015-09-03: 45; 2015-09-05: 45; 2015-09-06: 45; 2015-09-07: 45; 2015-09-08: 30; 2015-09-09: 30; 2015-09-10: 30; 2015-09-12: 30; 2015-09-13: 30; 2015-09-14: 45; 2015-09-15: 45; 2015-09-16: 45; 2015-09-17: 45; 2015-09-19: 45; 2015-09-20: 30; 2015-09-21: 30; 2015-09-22: 30; 2015-09-29: 30; 2015-09-30: 30; 2015-10-01: 45; 2015-10-03: 45; 2015-10-04: 45; 2015-10-05: 45; 2015-10-06: 45; 2015-10-07: 55; 2015-10-08: 55; 2015-10-10: 55; 2015-10-11: 55; 2015-10-12: 55; 2015-10-13: 70; 2015-10-14: 70; 2015-10-15: 70; 2015-10-17: 70; 2015-10-18: 70; 2015-10-19: 55; 2015-10-20: 55; 2015-10-21: 55; 2015-10-22: 55; 2015-10-24: 55; 2015-10-25: 45; 2015-10-26: 45; 2015-10-27: 45; 2015-10-28: 45; 2015-10-29: 45; 2015-10-31: 30; 2015-11-01: 30; 2015-11-02: 30; 2015-11-03: 30; 2015-11-04: 30; 2015-11-05: 45; 2015-11-07: 45; 2015-11-08: 45; 2015-11-09: 45; 2015-11-10: 45; 2015-11-11: 30; 2015-11-12: 30; 2015-11-14: 30; 2015-11-15: 30; 2015-11-16: 30; 2015-11-17: 30; 2015-11-18: 30; 2015-11-19: 30; 2015-11-21: 30; 2015-11-22: 30; 2015-11-23: 15; 2015-11-24: 15; 2015-11-25: 15; 2015-11-26: 15; 2015-11-28: 15; 2015-11-29: 25; 2015-11-30: 25; 2015-12-01: 25; 2015-12-02: 25; 2015-12-03: 25; 2015-12-05: 10; 2015-12-06: 10; 2015-12-07: 10; 2015-12-08: 10; 2015-12-09: 10; 2015-12-10: 20; 2015-12-12: 20; 2015-12-13: 20; 2015-12-14: 20; 2015-12-15: 20; 2015-12-16: 10; 2015-12-17: 10; 2015-12-19: 10; 2015-12-20: 10; 2015-12-21: 10; 2015-12-22: 20; 2015-12-23: 20; 2015-12-24: 20; 2015-12-26: 20; 2015-12-27: 20; 2015-12-28: 10; 2015-12-29: 10; 2015-12-30: 10; 2015-12-31: 10; 2016-01-02: 10; 2016-01-03: 10; 2016-01-04: 10; 2016-01-05: 10; 2016-01-06: 10; 2016-01-07: 10
Mason - Plaster | 2015-05-27: 1; 2015-05-28: 1; 2015-05-30: 1; 2015-05-31: 1; 2015-06-01: 1; 2015-06-02: 1; 2015-06-03: 1; 2015-06-04: 1; 2015-06-06: 1; 2015-06-07: 1; 2015-06-08: 1; 2015-06-09: 1; 2015-06-10: 1; 2015-06-11: 1; 2015-06-13: 1; 2015-06-14: 1; 2015-06-15: 1; 2015-06-16: 1; 2015-06-17: 1; 2015-06-18: 1; 2015-07-06: 1; 2015-07-07: 1; 2015-07-08: 1; 2015-07-09: 1; 2015-07-11: 1; 2015-07-12: 1; 2015-07-13: 5; 2015-07-14: 7; 2015-07-15: 7; 2015-07-16: 22; 2015-07-22: 23; 2015-07-23: 23; 2015-07-25: 23; 2015-07-26: 23; 2015-07-27: 23; 2015-07-28: 23; 2015-07-29: 23; 2015-07-30: 23; 2015-08-01: 19; 2015-08-02: 29; 2015-08-03: 37; 2015-08-04: 37; 2015-08-05: 37; 2015-08-06: 37; 2015-08-08: 37; 2015-08-09: 37; 2015-08-10: 37; 2015-08-11: 37; 2015-08-12: 37; 2015-08-13: 37; 2015-08-15: 37; 2015-08-16: 52; 2015-08-17: 52; 2015-08-18: 52; 2015-08-19: 52; 2015-08-20: 52; 2015-08-22: 52; 2015-08-23: 52; 2015-08-24: 52; 2015-08-25: 37; 2015-08-26: 52; 2015-08-27: 67; 2015-08-29: 67; 2015-08-30: 67; 2015-08-31: 67; 2015-09-01: 67; 2015-09-02: 67; 2015-09-03: 67; 2015-09-05: 67; 2015-09-06: 67; 2015-09-07: 67; 2015-09-08: 82; 2015-09-09: 82; 2015-09-10: 82; 2015-09-12: 82; 2015-09-13: 82; 2015-09-14: 82; 2015-09-15: 82; 2015-09-16: 82; 2015-09-17: 70; 2015-09-19: 62; 2015-09-20: 62; 2015-09-21: 62; 2015-09-22: 62; 2015-09-29: 62; 2015-09-30: 62; 2015-10-01: 62; 2015-10-03: 62; 2015-10-04: 62; 2015-10-05: 64; 2015-10-06: 49; 2015-10-07: 49; 2015-10-08: 49; 2015-10-10: 49; 2015-10-11: 49; 2015-10-12: 49; 2015-10-13: 49; 2015-10-14: 47; 2015-10-15: 47; 2015-10-17: 47; 2015-10-18: 47; 2015-10-19: 47; 2015-10-20: 47; 2015-10-21: 47; 2015-10-22: 47; 2015-10-24: 47; 2015-10-25: 47; 2015-10-26: 47; 2015-10-27: 47; 2015-10-28: 47; 2015-10-29: 47; 2015-10-31: 57; 2015-11-01: 57; 2015-11-02: 57; 2015-11-03: 57; 2015-11-04: 57; 2015-11-05: 57; 2015-11-07: 57; 2015-11-08: 57; 2015-11-09: 57; 2015-11-10: 57; 2015-11-11: 57; 2015-11-12: 57; 2015-11-14: 57; 2015-11-15: 57; 2015-11-16: 57; 2015-11-17: 57; 2015-11-18: 57; 2015-11-19: 57; 2015-11-21: 57; 2015-11-22: 57; 2015-11-23: 57; 2015-11-24: 57; 2015-11-25: 57; 2015-11-26: 57; 2015-11-28: 57; 2015-11-29: 57; 2015-11-30: 57; 2015-12-01: 57; 2015-12-02: 57; 2015-12-03: 57; 2015-12-05: 47; 2015-12-06: 47; 2015-12-07: 47; 2015-12-08: 47; 2015-12-09: 47; 2015-12-10: 47; 2015-12-12: 47; 2015-12-13: 47; 2015-12-14: 47; 2015-12-15: 47; 2015-12-16: 32; 2015-12-17: 32; 2015-12-19: 32; 2015-12-20: 32; 2015-12-21: 32; 2015-12-22: 34; 2015-12-23: 34; 2015-12-24: 34; 2015-12-26: 32; 2015-12-27: 32; 2015-12-28: 17; 2015-12-29: 17; 2015-12-30: 17; 2015-12-31: 17; 2016-01-02: 17; 2016-01-03: 19; 2016-01-04: 19; 2016-01-05: 19; 2016-01-06: 19; 2016-01-07: 19; 2016-01-08: 2; 2016-01-09: 21; 2016-01-10: 21; 2016-01-11: 21; 2016-01-12: 21; 2016-01-13: 21; 2016-01-14: 21; 2016-01-16: 21; 2016-01-17: 21; 2016-01-18: 21; 2016-01-19: 21; 2016-01-20: 21; 2016-01-21: 21; 2016-01-22: 2; 2016-01-23: 21; 2016-01-24: 21; 2016-01-25: 21; 2016-01-26: 19; 2016-01-27: 19; 2016-01-28: 19; 2016-01-30: 19; 2016-01-31: 19; 2016-02-01: 19; 2016-02-02: 19; 2016-02-03: 19; 2016-02-04: 19; 2016-02-05: 2; 2016-02-06: 19; 2016-02-07: 17; 2016-02-08: 17; 2016-02-09: 17; 2016-02-10: 17; 2016-02-11: 17; 2016-02-13: 17; 2016-02-14: 17; 2016-02-15: 17; 2016-02-16: 17; 2016-02-17: 17; 2016-02-18: 17; 2016-02-20: 17; 2016-02-21: 17; 2016-02-22: 17; 2016-02-23: 17; 2016-02-24: 17; 2016-02-25: 17; 2016-02-27: 17; 2016-02-28: 17; 2016-02-29: 17; 2016-03-01: 17; 2016-03-02: 17; 2016-03-03: 17; 2016-03-05: 17; 2016-03-06: 17; 2016-03-07: 17; 2016-03-08: 17; 2016-03-09: 17; 2016-03-10: 17; 2016-03-12: 17; 2016-03-13: 17; 2016-03-14: 17; 2016-03-15: 17; 2016-03-16: 17; 2016-03-17: 17; 2016-03-19: 17; 2016-03-20: 17; 2016-03-21: 17; 2016-03-22: 17; 2016-03-23: 17; 2016-03-24: 17; 2016-03-26: 17; 2016-03-27: 17; 2016-03-28: 17; 2016-03-29: 17; 2016-03-30: 17; 2016-03-31: 17; 2016-04-02: 17; 2016-04-03: 17; 2016-04-04: 17; 2016-04-05: 17; 2016-04-06: 17; 2016-04-07: 17; 2016-04-09: 17; 2016-04-10: 17; 2016-04-11: 17; 2016-04-12: 17; 2016-04-13: 17; 2016-04-14: 17; 2016-04-16: 17; 2016-04-17: 17; 2016-04-18: 17; 2016-04-19: 17; 2016-04-20: 17; 2016-04-21: 17; 2016-04-23: 17; 2016-04-24: 17; 2016-04-25: 17; 2016-04-26: 17; 2016-04-27: 17; 2016-04-28: 17; 2016-04-30: 17; 2016-05-01: 17; 2016-05-02: 17; 2016-05-03: 17; 2016-05-04: 17; 2016-05-05: 17; 2016-05-07: 17; 2016-05-08: 17; 2016-05-09: 17; 2016-05-10: 17; 2016-05-11: 17; 2016-05-12: 17; 2016-05-14: 17; 2016-05-15: 17; 2016-05-16: 17; 2016-05-17: 17; 2016-05-18: 17; 2016-05-19: 17; 2016-05-21: 17; 2016-05-22: 17; 2016-05-23: 17; 2016-05-24: 17; 2016-05-25: 17; 2016-05-26: 17
Painter - BTCC | 2015-08-13: 19; 2015-08-15: 22; 2015-08-16: 22; 2015-08-17: 22; 2015-08-18: 22; 2015-08-19: 22; 2015-08-20: 22; 2015-08-22: 22; 2015-08-23: 22; 2015-08-24: 22; 2015-08-25: 22; 2015-08-26: 22; 2015-08-27: 22; 2015-08-29: 22; 2015-08-30: 22; 2015-08-31: 22; 2015-09-01: 22; 2015-09-02: 22; 2015-09-03: 22; 2015-09-05: 22; 2015-09-06: 22; 2015-09-07: 22; 2015-09-08: 37; 2015-09-09: 37; 2015-09-10: 37; 2015-09-12: 37; 2015-09-13: 37; 2015-09-14: 37; 2015-09-15: 37; 2015-09-16: 37; 2015-09-17: 37; 2015-09-19: 52; 2015-09-20: 67; 2015-09-21: 67; 2015-09-22: 67; 2015-09-29: 52; 2015-09-30: 52; 2015-10-01: 52; 2015-10-03: 52; 2015-10-04: 52; 2015-10-05: 51; 2015-10-06: 50; 2015-10-07: 65; 2015-10-08: 65; 2015-10-10: 65; 2015-10-11: 65; 2015-10-12: 65; 2015-10-13: 65; 2015-10-14: 65; 2015-10-15: 65; 2015-10-17: 65; 2015-10-18: 65; 2015-10-19: 80; 2015-10-20: 80; 2015-10-21: 80; 2015-10-22: 80; 2015-10-24: 80; 2015-10-25: 65; 2015-10-26: 65; 2015-10-27: 66; 2015-10-28: 69; 2015-10-29: 69; 2015-10-31: 80; 2015-11-01: 80; 2015-11-02: 80; 2015-11-03: 79; 2015-11-04: 61; 2015-11-05: 46; 2015-11-07: 46; 2015-11-08: 46; 2015-11-09: 43; 2015-11-10: 41; 2015-11-11: 52; 2015-11-12: 52; 2015-11-14: 52; 2015-11-15: 52; 2015-11-16: 52; 2015-11-17: 41; 2015-11-18: 41; 2015-11-19: 41; 2015-11-21: 41; 2015-11-22: 42; 2015-11-23: 55; 2015-11-24: 55; 2015-11-25: 55; 2015-11-26: 55; 2015-11-28: 55; 2015-11-29: 39; 2015-11-30: 36; 2015-12-01: 36; 2015-12-02: 37; 2015-12-03: 40; 2015-12-05: 51; 2015-12-06: 51; 2015-12-07: 51; 2015-12-08: 51; 2015-12-09: 50; 2015-12-10: 37; 2015-12-12: 35; 2015-12-13: 35; 2015-12-14: 35; 2015-12-15: 35; 2015-12-16: 46; 2015-12-17: 46; 2015-12-19: 46; 2015-12-20: 46; 2015-12-21: 46; 2015-12-22: 36; 2015-12-23: 34; 2015-12-24: 34; 2015-12-26: 34; 2015-12-27: 34; 2015-12-28: 46; 2015-12-29: 46; 2015-12-30: 46; 2015-12-31: 49; 2016-01-02: 51; 2016-01-03: 41; 2016-01-04: 39; 2016-01-05: 39; 2016-01-06: 39; 2016-01-07: 40; 2016-01-09: 39; 2016-01-10: 39; 2016-01-11: 36; 2016-01-12: 35; 2016-01-13: 51; 2016-01-14: 45; 2016-01-16: 41; 2016-01-17: 41; 2016-01-18: 41; 2016-01-19: 42; 2016-01-20: 45; 2016-01-21: 45; 2016-01-23: 45; 2016-01-24: 45; 2016-01-25: 46; 2016-01-26: 36; 2016-01-27: 31; 2016-01-28: 31; 2016-01-30: 31; 2016-01-31: 17; 2016-02-01: 20; 2016-02-02: 20; 2016-02-03: 20; 2016-02-04: 20; 2016-02-06: 20; 2016-02-07: 10; 2016-02-08: 20; 2016-02-09: 20; 2016-02-10: 20; 2016-02-11: 20; 2016-02-13: 20; 2016-02-14: 20; 2016-02-15: 20; 2016-02-16: 20; 2016-02-17: 20; 2016-02-18: 20; 2016-02-20: 19; 2016-02-21: 19; 2016-02-22: 19; 2016-02-23: 19; 2016-02-24: 19; 2016-02-25: 4; 2016-02-27: 4; 2016-02-28: 4; 2016-02-29: 4; 2016-03-01: 19; 2016-03-02: 22; 2016-03-03: 25; 2016-03-05: 25; 2016-03-06: 25; 2016-03-07: 40; 2016-03-08: 40; 2016-03-09: 40; 2016-03-10: 36; 2016-03-12: 37; 2016-03-13: 52; 2016-03-14: 51; 2016-03-15: 54; 2016-03-16: 54; 2016-03-17: 54; 2016-03-19: 39; 2016-03-20: 39; 2016-03-21: 39; 2016-03-22: 35; 2016-03-23: 35; 2016-03-24: 35; 2016-03-26: 36; 2016-03-27: 39; 2016-03-28: 39; 2016-03-29: 39; 2016-03-30: 24; 2016-03-31: 24; 2016-04-02: 24; 2016-04-03: 20; 2016-04-04: 19; 2016-04-05: 26; 2016-04-06: 26; 2016-04-07: 26; 2016-04-09: 26; 2016-04-10: 26; 2016-04-11: 21; 2016-04-12: 21; 2016-04-13: 50; 2016-04-14: 50; 2016-04-16: 50; 2016-04-17: 49; 2016-04-18: 49; 2016-04-19: 49; 2016-04-20: 49; 2016-04-21: 49; 2016-04-23: 49; 2016-04-24: 49; 2016-04-25: 59; 2016-04-26: 59; 2016-04-27: 59; 2016-04-28: 45; 2016-04-30: 45; 2016-05-01: 35; 2016-05-02: 35; 2016-05-03: 35; 2016-05-04: 35; 2016-05-05: 50; 2016-05-07: 52; 2016-05-08: 53; 2016-05-09: 53; 2016-05-10: 53; 2016-05-11: 53; 2016-05-12: 43; 2016-05-14: 43; 2016-05-15: 43; 2016-05-16: 43; 2016-05-17: 56; 2016-05-18: 56; 2016-05-19: 56; 2016-05-21: 56; 2016-05-22: 56; 2016-05-23: 46; 2016-05-24: 46; 2016-05-25: 46; 2016-05-26: 46; 2016-05-28: 46; 2016-05-29: 56; 2016-05-30: 56; 2016-05-31: 55; 2016-06-01: 55; 2016-06-02: 55; 2016-06-04: 45; 2016-06-05: 45; 2016-06-06: 45; 2016-06-07: 45; 2016-06-08: 45; 2016-06-09: 37; 2016-06-11: 35; 2016-06-12: 35; 2016-06-13: 35; 2016-06-14: 29; 2016-06-15: 19; 2016-06-16: 19; 2016-06-18: 19; 2016-06-19: 19; 2016-06-20: 19; 2016-06-21: 19; 2016-06-22: 19; 2016-06-23: 19; 2016-06-25: 19; 2016-06-26: 19; 2016-06-27: 19; 2016-06-28: 19; 2016-06-29: 19; 2016-06-30: 19; 2016-07-02: 19; 2016-07-03: 19; 2016-07-04: 19; 2016-07-05: 19; 2016-07-06: 19; 2016-07-12: 19; 2016-07-13: 19; 2016-07-14: 19; 2016-07-16: 19; 2016-07-17: 19; 2016-07-18: 19; 2016-07-19: 19; 2016-07-20: 19; 2016-07-21: 19; 2016-07-23: 19; 2016-07-24: 19; 2016-07-25: 19; 2016-07-26: 19; 2016-07-27: 19; 2016-07-28: 19; 2016-07-30: 19; 2016-07-31: 19
Mason - Tile Sitter | 2015-09-10: 2; 2015-09-12: 8; 2015-09-13: 8; 2015-09-14: 8; 2015-09-15: 8; 2015-09-16: 8; 2015-09-17: 10; 2015-09-19: 10; 2015-09-20: 10; 2015-09-21: 10; 2015-09-22: 8; 2015-09-29: 2; 2015-09-30: 2; 2015-10-01: 2; 2015-10-03: 2; 2015-10-04: 3; 2015-10-05: 13; 2015-10-06: 15; 2015-10-07: 15; 2015-10-08: 15; 2015-10-10: 15; 2015-10-11: 15; 2015-10-12: 16; 2015-10-13: 23; 2015-10-14: 23; 2015-10-15: 21; 2015-10-17: 17; 2015-10-18: 17; 2015-10-19: 19; 2015-10-20: 19; 2015-10-21: 19; 2015-10-22: 20; 2015-10-24: 27; 2015-10-25: 29; 2015-10-26: 29; 2015-10-27: 28; 2015-10-28: 33; 2015-10-29: 40; 2015-10-31: 50; 2015-11-01: 50; 2015-11-02: 50; 2015-11-03: 49; 2015-11-04: 44; 2015-11-05: 44; 2015-11-07: 44; 2015-11-08: 44; 2015-11-09: 48; 2015-11-10: 50; 2015-11-11: 60; 2015-11-12: 62; 2015-11-13: 15; 2015-11-14: 62; 2015-11-15: 62; 2015-11-16: 70; 2015-11-17: 72; 2015-11-18: 63; 2015-11-19: 61; 2015-11-20: 15; 2015-11-21: 61; 2015-11-22: 59; 2015-11-23: 72; 2015-11-24: 73; 2015-11-25: 69; 2015-11-26: 68; 2015-11-27: 12; 2015-11-28: 66; 2015-11-29: 57; 2015-11-30: 58; 2015-12-01: 58; 2015-12-02: 58; 2015-12-03: 58; 2015-12-04: 10; 2015-12-05: 64; 2015-12-06: 62; 2015-12-07: 62; 2015-12-08: 63; 2015-12-09: 65; 2015-12-10: 59; 2015-12-11: 2; 2015-12-12: 49; 2015-12-13: 48; 2015-12-14: 44; 2015-12-15: 46; 2015-12-16: 52; 2015-12-17: 52; 2015-12-19: 52; 2015-12-20: 53; 2015-12-21: 55; 2015-12-22: 47; 2015-12-23: 47; 2015-12-24: 46; 2015-12-26: 42; 2015-12-27: 42; 2015-12-28: 40; 2015-12-29: 40; 2015-12-30: 37; 2015-12-31: 37; 2016-01-02: 41; 2016-01-03: 41; 2016-01-04: 41; 2016-01-05: 40; 2016-01-06: 36; 2016-01-07: 35; 2016-01-09: 24; 2016-01-10: 22; 2016-01-11: 30; 2016-01-12: 32; 2016-01-13: 36; 2016-01-14: 50; 2016-01-15: 10; 2016-01-16: 50; 2016-01-17: 50; 2016-01-18: 50; 2016-01-19: 46; 2016-01-20: 30; 2016-01-21: 30; 2016-01-22: 12; 2016-01-23: 32; 2016-01-24: 32; 2016-01-25: 38; 2016-01-26: 54; 2016-01-27: 64; 2016-01-28: 64; 2016-01-29: 14; 2016-01-30: 64; 2016-01-31: 52; 2016-02-01: 40; 2016-02-02: 45; 2016-02-03: 45; 2016-02-04: 44; 2016-02-05: 1; 2016-02-06: 46; 2016-02-07: 54; 2016-02-08: 54; 2016-02-09: 54; 2016-02-10: 54; 2016-02-11: 53; 2016-02-12: 2; 2016-02-13: 45; 2016-02-14: 34; 2016-02-15: 34; 2016-02-16: 34; 2016-02-17: 33; 2016-02-18: 29; 2016-02-19: 2; 2016-02-20: 29; 2016-02-21: 29; 2016-02-22: 29; 2016-02-23: 29; 2016-02-24: 29; 2016-02-25: 29; 2016-02-26: 2; 2016-02-27: 29; 2016-02-28: 25; 2016-02-29: 24; 2016-03-01: 18; 2016-03-02: 16; 2016-03-03: 24; 2016-03-05: 24; 2016-03-06: 24; 2016-03-07: 24; 2016-03-08: 30; 2016-03-09: 30; 2016-03-10: 30; 2016-03-12: 29; 2016-03-13: 29; 2016-03-14: 28; 2016-03-15: 36; 2016-03-16: 36; 2016-03-17: 36; 2016-03-18: 6; 2016-03-19: 36; 2016-03-20: 35; 2016-03-21: 19; 2016-03-22: 19; 2016-03-23: 19; 2016-03-24: 19; 2016-03-26: 20; 2016-03-27: 18; 2016-03-28: 28; 2016-03-29: 28; 2016-03-30: 28; 2016-03-31: 20; 2016-04-02: 10; 2016-04-03: 10; 2016-04-04: 10; 2016-04-05: 10; 2016-04-06: 10; 2016-04-07: 12; 2016-04-08: 2; 2016-04-09: 12; 2016-04-10: 12; 2016-04-11: 12; 2016-04-12: 10; 2016-04-13: 10; 2016-04-19: 2; 2016-04-20: 2; 2016-04-21: 2; 2016-04-22: 2; 2016-04-23: 2; 2016-06-08: 5; 2016-06-09: 5; 2016-06-11: 5; 2016-06-12: 5; 2016-06-13: 5; 2016-06-14: 5; 2016-06-15: 5; 2016-06-16: 5; 2016-06-18: 5; 2016-06-19: 5; 2016-06-20: 5; 2016-06-21: 5; 2016-06-22: 5; 2016-06-23: 5; 2016-06-25: 5; 2016-06-26: 5; 2016-07-26: 5; 2016-07-27: 5; 2016-07-28: 5; 2016-07-30: 5; 2016-07-31: 5; 2016-08-01: 5; 2016-08-02: 5; 2016-08-03: 5; 2016-08-04: 5; 2016-08-06: 5; 2016-08-07: 5; 2016-08-08: 5; 2016-08-09: 5; 2016-08-10: 5; 2016-08-11: 5; 2016-08-13: 5; 2016-08-14: 5; 2016-08-15: 5; 2016-08-16: 5; 2016-08-17: 5
Heavy Equipment Operator | 2014-12-01: 5; 2014-12-02: 10; 2014-12-03: 10; 2014-12-04: 10; 2014-12-06: 10; 2014-12-07: 10; 2014-12-08: 14; 2014-12-09: 14; 2014-12-10: 14; 2014-12-11: 14; 2014-12-13: 14; 2014-12-14: 14; 2014-12-15: 14; 2014-12-16: 14; 2014-12-17: 14; 2014-12-20: 14; 2014-12-21: 18; 2014-12-22: 18; 2014-12-23: 18; 2014-12-24: 18; 2014-12-25: 18; 2014-12-27: 19; 2014-12-28: 19; 2014-12-29: 14; 2014-12-30: 14; 2014-12-31: 14; 2015-01-01: 14; 2015-01-03: 14; 2015-01-04: 14; 2015-01-05: 14; 2015-01-06: 14; 2015-01-07: 15; 2015-01-08: 15; 2015-01-10: 10; 2015-01-11: 10; 2015-01-12: 10; 2015-01-13: 10; 2015-01-14: 10; 2015-01-15: 10; 2015-01-17: 10; 2015-01-18: 10; 2015-01-19: 5; 2015-01-20: 5; 2015-01-21: 5; 2015-01-22: 5; 2015-01-24: 5; 2015-01-25: 5; 2015-01-26: 5; 2015-01-27: 5; 2015-01-28: 5; 2015-01-29: 5; 2015-01-31: 14; 2015-02-01: 14; 2015-02-02: 14; 2015-02-03: 19; 2015-02-04: 20; 2015-02-05: 29; 2015-02-07: 29; 2015-02-08: 24; 2015-02-09: 29; 2015-02-10: 24; 2015-02-11: 20; 2015-02-12: 20; 2015-02-14: 15; 2015-02-15: 6; 2015-02-16: 6; 2015-02-17: 6; 2015-02-18: 6; 2015-02-19: 6; 2015-02-21: 6; 2015-02-22: 6; 2015-02-23: 11; 2015-02-24: 11; 2015-02-25: 6; 2015-02-26: 24; 2015-02-28: 7; 2015-03-08: 9; 2015-03-09: 13; 2015-03-10: 13; 2015-03-11: 13; 2015-03-12: 47; 2015-03-14: 18; 2015-03-15: 18; 2015-03-16: 18; 2015-03-17: 19; 2015-03-18: 19; 2015-03-19: 28; 2015-03-21: 28; 2015-03-22: 28; 2015-03-23: 28; 2015-03-24: 33; 2015-03-25: 33; 2015-03-26: 33; 2015-03-28: 33; 2015-03-29: 19; 2015-03-30: 19; 2015-03-31: 13; 2015-04-09: 5; 2015-04-12: 2; 2015-04-14: 14; 2015-04-16: 2; 2015-04-18: 7; 2015-04-19: 7; 2015-04-20: 21; 2015-04-21: 29; 2015-04-22: 22; 2015-04-23: 22; 2015-04-25: 29; 2015-04-26: 34; 2015-04-27: 34; 2015-04-28: 22; 2015-04-29: 13; 2015-04-30: 13; 2015-05-02: 13; 2015-05-03: 22; 2015-05-04: 13; 2015-05-09: 9; 2015-05-11: 7; 2015-05-12: 5; 2015-05-13: 10; 2015-05-14: 10; 2015-05-17: 2; 2015-05-18: 5; 2015-05-19: 5; 2015-05-20: 5; 2015-05-23: 5; 2015-05-24: 4; 2015-05-25: 11; 2015-05-26: 18; 2015-05-27: 9; 2015-05-28: 9; 2015-05-30: 9; 2015-05-31: 16; 2015-06-01: 25; 2015-06-02: 12; 2015-06-03: 12; 2015-06-04: 5; 2015-06-06: 5; 2015-06-07: 5; 2015-06-10: 5; 2015-06-11: 5; 2015-06-13: 5; 2015-06-15: 9; 2015-06-20: 9; 2015-06-21: 7; 2015-06-22: 4; 2015-06-23: 7; 2015-06-24: 14; 2015-06-25: 5; 2015-06-27: 7; 2015-06-28: 5; 2015-06-29: 5; 2015-06-30: 5; 2015-07-01: 15; 2015-07-02: 12; 2015-07-04: 10; 2015-07-05: 15; 2015-07-06: 5; 2015-07-07: 5; 2015-07-08: 13; 2015-07-09: 2; 2015-07-11: 5; 2015-07-12: 5; 2015-07-13: 14; 2015-07-14: 4; 2015-07-16: 6; 2015-07-22: 6; 2015-07-23: 16; 2015-07-25: 5; 2015-07-28: 2; 2015-08-05: 9; 2015-08-13: 7; 2015-08-15: 5; 2015-08-16: 5; 2015-08-17: 5; 2015-08-29: 9; 2015-09-03: 4; 2015-09-06: 5; 2015-09-07: 5; 2015-09-08: 5; 2015-09-09: 5; 2015-09-14: 9; 2015-09-21: 9
Subcon - Excavation | 2014-12-01: 3; 2014-12-02: 3; 2014-12-03: 3; 2014-12-04: 3; 2014-12-06: 3; 2014-12-07: 3; 2014-12-08: 11; 2014-12-09: 11; 2014-12-10: 11; 2014-12-11: 11; 2014-12-13: 11; 2014-12-14: 11; 2014-12-15: 11; 2014-12-16: 11; 2014-12-17: 11; 2014-12-20: 11; 2014-12-21: 11; 2014-12-22: 11; 2014-12-23: 11; 2014-12-24: 11; 2014-12-25: 11; 2014-12-27: 10; 2014-12-28: 10; 2014-12-29: 10; 2014-12-30: 10; 2014-12-31: 10; 2015-01-01: 10; 2015-01-03: 10; 2015-01-04: 10; 2015-01-05: 10; 2015-01-06: 10; 2015-01-07: 10; 2015-01-08: 10; 2015-01-10: 10; 2015-01-11: 10; 2015-01-12: 10; 2015-01-13: 3; 2015-01-14: 3; 2015-01-15: 3; 2015-01-17: 3; 2015-01-18: 3
Subcon - Backfilling | 2015-02-04: 10; 2015-02-05: 10; 2015-02-07: 10; 2015-02-08: 10; 2015-02-09: 10; 2015-02-10: 10; 2015-02-11: 10; 2015-02-12: 10; 2015-02-14: 10; 2015-02-15: 10; 2015-02-16: 10; 2015-02-17: 10; 2015-02-18: 10; 2015-02-19: 10; 2015-02-21: 10; 2015-02-22: 10; 2015-02-23: 10; 2015-02-24: 10; 2015-02-25: 10; 2015-02-26: 10; 2015-03-09: 10; 2015-03-10: 10; 2015-03-11: 10; 2015-03-12: 10; 2015-03-14: 10; 2015-03-15: 30; 2015-03-16: 30; 2015-03-17: 40; 2015-03-18: 40; 2015-03-19: 40; 2015-03-21: 40; 2015-03-22: 40; 2015-03-23: 40; 2015-03-24: 40; 2015-03-25: 40; 2015-03-26: 20; 2015-03-28: 20; 2015-03-29: 20; 2015-03-30: 20; 2015-03-31: 10; 2015-04-15: 20; 2015-04-16: 20; 2015-04-18: 20; 2015-04-19: 20; 2015-04-20: 20; 2015-04-21: 30; 2015-04-22: 30; 2015-04-23: 30; 2015-04-25: 30; 2015-04-26: 30; 2015-04-27: 10; 2015-04-28: 10; 2015-04-29: 10; 2015-04-30: 10; 2015-05-02: 10; 2015-05-03: 10; 2015-05-04: 10
Subcon - Aluminium & Glass | 2015-11-12: 8; 2015-11-14: 40; 2015-11-15: 40; 2015-11-16: 40; 2015-11-17: 41; 2015-11-18: 46; 2015-11-19: 46; 2015-11-21: 46; 2015-11-22: 46; 2015-11-23: 46; 2015-11-24: 46; 2015-11-25: 46; 2015-11-26: 38; 2015-11-28: 6; 2015-11-29: 5; 2015-12-08: 8; 2015-12-09: 40; 2015-12-10: 40; 2015-12-12: 40; 2015-12-13: 41; 2015-12-14: 46; 2015-12-15: 46; 2015-12-16: 46; 2015-12-17: 46; 2015-12-19: 54; 2015-12-20: 86; 2015-12-21: 86; 2015-12-22: 82; 2015-12-23: 67; 2015-12-24: 71; 2015-12-26: 66; 2015-12-27: 66; 2015-12-28: 66; 2015-12-29: 66; 2015-12-30: 66; 2015-12-31: 66; 2016-01-02: 58; 2016-01-03: 30; 2016-01-04: 45; 2016-01-05: 40; 2016-01-06: 40; 2016-01-07: 40; 2016-01-09: 40; 2016-01-10: 40; 2016-01-11: 60; 2016-01-12: 60; 2016-01-13: 60; 2016-01-14: 56; 2016-01-16: 40; 2016-01-17: 40; 2016-01-18: 40; 2016-01-19: 40; 2016-01-20: 44; 2016-01-21: 60; 2016-01-23: 60; 2016-01-24: 60; 2016-01-25: 72; 2016-01-26: 68; 2016-01-27: 52; 2016-01-28: 55; 2016-01-30: 66; 2016-01-31: 66; 2016-02-01: 70; 2016-02-02: 86; 2016-02-03: 66; 2016-02-04: 66; 2016-02-06: 66; 2016-02-07: 66; 2016-02-08: 66; 2016-02-09: 69; 2016-02-10: 82; 2016-02-11: 82; 2016-02-13: 82; 2016-02-14: 82; 2016-02-15: 79; 2016-02-16: 66; 2016-02-17: 66; 2016-02-18: 66; 2016-02-20: 66; 2016-02-21: 69; 2016-02-22: 82; 2016-02-23: 82; 2016-02-24: 78; 2016-02-25: 62; 2016-02-27: 59; 2016-02-28: 46; 2016-02-29: 36; 2016-03-01: 36; 2016-03-02: 36; 2016-03-03: 36; 2016-03-05: 36; 2016-03-06: 36; 2016-03-07: 32; 2016-03-08: 16; 2016-03-09: 17; 2016-03-10: 20; 2016-03-12: 20; 2016-03-13: 20; 2016-03-14: 20; 2016-03-15: 22; 2016-03-16: 22; 2016-03-17: 22; 2016-03-18: 2; 2016-03-19: 22; 2016-03-20: 22; 2016-03-21: 26; 2016-03-22: 42; 2016-03-23: 44; 2016-03-24: 60; 2016-03-26: 60; 2016-03-27: 62; 2016-03-28: 62; 2016-03-29: 62; 2016-03-30: 62; 2016-03-31: 62; 2016-04-01: 2; 2016-04-02: 62; 2016-04-03: 62; 2016-04-04: 62; 2016-04-05: 62; 2016-04-06: 62; 2016-04-07: 60; 2016-04-09: 62; 2016-04-10: 62; 2016-04-11: 62; 2016-04-12: 62; 2016-04-13: 58; 2016-04-14: 42; 2016-04-15: 4; 2016-04-16: 44; 2016-04-17: 42; 2016-04-18: 40; 2016-04-19: 40; 2016-04-20: 40; 2016-04-21: 40; 2016-04-23: 40; 2016-04-24: 40; 2016-04-25: 36; 2016-04-26: 20; 2016-04-27: 16; 2016-04-28: 2; 2016-04-29: 2; 2016-04-30: 2
Subcon - Wooden Door | 2015-10-04: 3; 2015-10-05: 16; 2015-10-06: 16; 2015-10-07: 16; 2015-10-08: 16; 2015-10-10: 16; 2015-10-11: 16; 2015-10-12: 16; 2015-10-13: 16; 2015-10-14: 16; 2015-10-15: 14; 2015-10-17: 8; 2015-10-18: 8; 2015-10-19: 8; 2015-10-20: 8; 2015-10-21: 8; 2015-10-22: 8; 2015-10-24: 8; 2015-10-25: 8; 2015-10-26: 8; 2015-10-27: 6; 2015-10-29: 3; 2015-10-31: 16; 2015-11-01: 16; 2015-11-02: 16; 2015-11-03: 16; 2015-11-04: 16; 2015-11-05: 16; 2015-11-07: 16; 2015-11-08: 36; 2015-11-09: 45; 2015-11-10: 60; 2015-11-11: 54; 2015-11-12: 54; 2015-11-14: 54; 2015-11-15: 54; 2015-11-16: 54; 2015-11-17: 54; 2015-11-18: 54; 2015-11-19: 54; 2015-11-21: 52; 2015-11-22: 28; 2015-11-23: 34; 2015-11-24: 34; 2015-11-25: 34; 2015-11-26: 34; 2015-11-28: 34; 2015-11-29: 34; 2015-11-30: 34; 2015-12-01: 34; 2015-12-02: 32; 2015-12-03: 49; 2015-12-05: 62; 2015-12-06: 62; 2015-12-07: 62; 2015-12-08: 62; 2015-12-09: 62; 2015-12-10: 62; 2015-12-12: 68; 2015-12-13: 78; 2015-12-14: 78; 2015-12-15: 76; 2015-12-16: 70; 2015-12-17: 50; 2015-12-19: 50; 2015-12-20: 50; 2015-12-21: 50; 2015-12-22: 50; 2015-12-23: 50; 2015-12-24: 50; 2015-12-26: 44; 2015-12-27: 38; 2015-12-28: 52; 2015-12-29: 52; 2015-12-30: 52; 2015-12-31: 72; 2016-01-02: 72; 2016-01-03: 72; 2016-01-04: 66; 2016-01-05: 56; 2016-01-06: 56; 2016-01-07: 58; 2016-01-09: 64; 2016-01-10: 64; 2016-01-11: 70; 2016-01-12: 74; 2016-01-13: 74; 2016-01-14: 54; 2016-01-16: 54; 2016-01-17: 56; 2016-01-18: 58; 2016-01-19: 64; 2016-01-20: 58; 2016-01-21: 58; 2016-01-23: 58; 2016-01-24: 58; 2016-01-25: 60; 2016-01-26: 74; 2016-01-27: 82; 2016-01-28: 76; 2016-01-30: 72; 2016-01-31: 70; 2016-02-01: 44; 2016-02-02: 44; 2016-02-03: 42; 2016-02-04: 40; 2016-02-06: 42; 2016-02-07: 56; 2016-02-08: 56; 2016-02-09: 56; 2016-02-10: 56; 2016-02-11: 46; 2016-02-13: 32; 2016-02-14: 32; 2016-02-15: 32; 2016-02-16: 32; 2016-02-17: 34; 2016-02-18: 48; 2016-02-20: 40; 2016-02-21: 40; 2016-02-22: 40; 2016-02-23: 40; 2016-02-24: 32; 2016-02-25: 32; 2016-02-27: 32; 2016-02-28: 32; 2016-02-29: 34; 2016-03-01: 44; 2016-03-02: 44; 2016-03-03: 44; 2016-03-05: 54; 2016-03-06: 54; 2016-03-07: 46; 2016-03-08: 46; 2016-03-09: 46; 2016-03-10: 50; 2016-03-12: 52; 2016-03-13: 62; 2016-03-14: 62; 2016-03-15: 62; 2016-03-16: 62; 2016-03-17: 58; 2016-03-19: 42; 2016-03-20: 42; 2016-03-21: 42; 2016-03-22: 32; 2016-03-23: 34; 2016-03-24: 44; 2016-03-26: 44; 2016-03-27: 44; 2016-03-28: 40; 2016-03-29: 36; 2016-03-30: 20; 2016-03-31: 20; 2016-04-02: 20; 2016-04-03: 20; 2016-04-04: 20; 2016-04-05: 20; 2016-04-06: 20; 2016-04-07: 20; 2016-04-09: 20; 2016-04-10: 16
Subcon - Veneer MDF | 2015-09-19: 1; 2015-09-20: 4; 2015-09-21: 4; 2015-09-22: 4; 2015-09-29: 4; 2015-09-30: 3; 2015-10-20: 1; 2015-10-21: 4; 2015-10-22: 4; 2015-10-24: 4; 2015-10-25: 4; 2015-10-26: 3; 2015-10-28: 0; 2015-10-29: 2; 2015-10-31: 3; 2015-11-01: 6; 2015-11-02: 6; 2015-11-03: 6; 2015-11-04: 6; 2015-11-05: 5; 2015-11-07: 2; 2015-11-09: 0; 2015-11-10: 2; 2015-11-11: 2; 2015-11-12: 2; 2015-11-14: 2; 2015-11-15: 2; 2015-11-16: 2; 2015-11-17: 2; 2015-11-18: 2; 2015-11-21: 0; 2015-11-22: 2; 2015-11-23: 2; 2015-11-24: 2; 2015-11-25: 2; 2015-11-26: 2; 2015-11-28: 2; 2015-11-29: 2; 2015-11-30: 2; 2015-12-02: 0; 2015-12-03: 2; 2015-12-05: 2; 2015-12-06: 2; 2015-12-07: 2; 2015-12-08: 2; 2015-12-09: 2; 2015-12-10: 2; 2015-12-12: 2; 2015-12-14: 0; 2015-12-15: 2; 2015-12-16: 2; 2015-12-17: 2; 2015-12-19: 2; 2015-12-20: 2; 2015-12-21: 2; 2015-12-22: 2; 2015-12-23: 2; 2015-12-26: 0; 2015-12-27: 2; 2015-12-28: 2; 2015-12-29: 2; 2015-12-30: 2; 2015-12-31: 2; 2016-01-02: 2; 2016-01-03: 2; 2016-01-04: 2; 2016-01-11: 4; 2016-01-12: 5; 2016-01-13: 8; 2016-01-14: 8; 2016-01-16: 8; 2016-01-17: 8; 2016-01-18: 8; 2016-01-19: 4; 2016-01-20: 4; 2016-01-21: 3; 2016-01-24: 1; 2016-01-25: 4; 2016-01-26: 4; 2016-01-27: 4; 2016-01-28: 4; 2016-01-30: 4; 2016-01-31: 4; 2016-02-01: 4; 2016-02-02: 3; 2016-02-04: 1; 2016-02-06: 8; 2016-02-07: 8; 2016-02-08: 8; 2016-02-09: 8; 2016-02-10: 8; 2016-02-11: 8; 2016-02-13: 8; 2016-02-14: 3; 2016-02-29: 8; 2016-03-01: 8; 2016-03-02: 16; 2016-03-03: 16; 2016-03-05: 20; 2016-03-06: 20; 2016-03-07: 12; 2016-03-08: 12; 2016-03-09: 4; 2016-03-10: 4; 2016-03-12: 4; 2016-03-14: 8; 2016-03-15: 8; 2016-03-16: 8; 2016-03-17: 8; 2016-03-19: 8; 2016-03-20: 8; 2016-03-31: 8; 2016-04-02: 8; 2016-04-03: 8; 2016-04-04: 14; 2016-04-05: 14; 2016-04-06: 14; 2016-04-07: 14; 2016-04-09: 14; 2016-04-10: 6; 2016-04-11: 6; 2016-04-12: 14; 2016-04-13: 14; 2016-04-14: 14; 2016-04-16: 14; 2016-04-17: 14; 2016-04-18: 14; 2016-04-19: 14; 2016-04-20: 14; 2016-04-24: 8; 2016-04-25: 8; 2016-04-26: 8; 2016-04-27: 8; 2016-04-28: 8; 2016-04-30: 8; 2016-05-01: 8; 2016-05-02: 8
Subcon - Toilet Cubicle | 2015-11-03: 2; 2015-11-04: 12; 2015-11-05: 12; 2015-11-07: 12; 2015-11-08: 12; 2015-11-09: 12; 2015-11-10: 12; 2015-11-11: 12; 2015-11-12: 10; 2015-11-29: 2; 2015-11-30: 12; 2015-12-01: 12; 2015-12-02: 12; 2015-12-03: 12; 2015-12-05: 12; 2015-12-06: 12; 2015-12-07: 12; 2015-12-08: 10; 2015-12-09: 2; 2015-12-10: 12; 2015-12-12: 12; 2015-12-13: 12; 2015-12-14: 12; 2015-12-15: 12; 2015-12-16: 12; 2015-12-17: 12; 2015-12-19: 10; 2015-12-22: 2; 2015-12-23: 10; 2015-12-24: 10; 2015-12-26: 10; 2015-12-27: 10; 2015-12-28: 10; 2015-12-29: 10; 2015-12-30: 10; 2015-12-31: 8; 2016-01-03: 2; 2016-01-04: 10; 2016-01-05: 10; 2016-01-06: 10; 2016-01-07: 10; 2016-01-09: 10; 2016-01-10: 10; 2016-01-11: 10; 2016-01-12: 8; 2016-01-23: 10; 2016-01-24: 10; 2016-01-25: 10; 2016-01-26: 10; 2016-01-27: 10; 2016-01-28: 10; 2016-01-30: 10; 2016-01-31: 10
Subcon - Kitchen Cabinet | 2015-10-27: 1; 2015-10-28: 6; 2015-10-29: 6; 2015-10-31: 6; 2015-11-01: 6; 2015-11-02: 6; 2015-11-03: 6; 2015-11-04: 6; 2015-11-05: 6; 2015-11-07: 6; 2015-11-08: 5; 2015-11-22: 1; 2015-11-23: 6; 2015-11-24: 6; 2015-11-25: 6; 2015-11-26: 6; 2015-11-28: 6; 2015-11-29: 6; 2015-11-30: 6; 2015-12-01: 6; 2015-12-02: 7; 2015-12-03: 11; 2015-12-05: 6; 2015-12-06: 6; 2015-12-07: 6; 2015-12-08: 6; 2015-12-09: 6; 2015-12-10: 6; 2015-12-12: 6; 2015-12-13: 6; 2015-12-14: 5; 2015-12-15: 3; 2015-12-16: 16; 2015-12-17: 16; 2015-12-19: 16; 2015-12-20: 21; 2015-12-21: 24; 2015-12-22: 24; 2015-12-23: 24; 2015-12-24: 24; 2015-12-26: 24; 2015-12-27: 24; 2015-12-28: 30; 2015-12-29: 34; 2015-12-30: 34; 2015-12-31: 34; 2016-01-02: 34; 2016-01-03: 34; 2016-01-04: 40; 2016-01-05: 50; 2016-01-06: 45; 2016-01-07: 39; 2016-01-09: 26; 2016-01-10: 26; 2016-01-11: 20; 2016-01-12: 16; 2016-01-13: 16; 2016-01-14: 16; 2016-01-16: 10; 2016-01-19: 2; 2016-01-20: 8; 2016-01-21: 8; 2016-01-23: 8; 2016-01-24: 8; 2016-01-25: 8; 2016-01-26: 8; 2016-01-27: 8; 2016-01-28: 8; 2016-01-30: 8; 2016-01-31: 10; 2016-02-01: 16; 2016-02-02: 14; 2016-02-03: 8; 2016-02-04: 8; 2016-02-06: 8; 2016-02-07: 8; 2016-02-08: 8; 2016-02-09: 8; 2016-02-10: 8; 2016-02-11: 14; 2016-02-13: 20; 2016-02-14: 18; 2016-02-15: 12; 2016-02-16: 12; 2016-02-17: 12; 2016-02-18: 12; 2016-02-20: 12; 2016-02-21: 12; 2016-02-22: 20; 2016-02-23: 20; 2016-02-24: 20; 2016-02-25: 18; 2016-02-27: 12; 2016-02-28: 12; 2016-02-29: 10; 2016-03-01: 16; 2016-03-02: 16; 2016-03-03: 16; 2016-03-05: 8; 2016-03-06: 8; 2016-03-07: 8; 2016-03-08: 8; 2016-03-09: 8; 2016-03-10: 8; 2016-03-12: 10; 2016-03-13: 16; 2016-03-14: 16; 2016-03-15: 16; 2016-03-16: 16; 2016-03-17: 14; 2016-03-19: 8; 2016-03-20: 8; 2016-03-21: 8; 2016-03-22: 8; 2016-03-23: 10; 2016-03-24: 16; 2016-03-26: 16; 2016-03-27: 16; 2016-03-28: 16; 2016-03-29: 14; 2016-03-30: 8; 2016-03-31: 8; 2016-04-02: 8; 2016-04-03: 8; 2016-04-04: 8; 2016-04-05: 8; 2016-04-06: 8; 2016-04-07: 8; 2016-04-09: 8; 2016-04-10: 6
Subcon - Steel Door | 2015-11-03: 2; 2015-11-04: 8; 2015-11-05: 8; 2015-11-07: 8; 2015-11-08: 8; 2015-11-09: 8; 2015-11-10: 8; 2015-11-11: 8; 2015-11-12: 8; 2015-11-14: 8; 2015-11-15: 8; 2015-11-16: 8; 2015-11-17: 6; 2015-11-29: 2; 2015-11-30: 8; 2015-12-01: 8; 2015-12-02: 8; 2015-12-03: 8; 2015-12-05: 8; 2015-12-06: 8; 2015-12-07: 8; 2015-12-08: 8; 2015-12-09: 10; 2015-12-10: 16; 2015-12-12: 16; 2015-12-13: 14; 2015-12-14: 8; 2015-12-15: 8; 2015-12-16: 8; 2015-12-17: 8; 2015-12-19: 8; 2015-12-20: 8; 2015-12-21: 8; 2015-12-22: 11; 2015-12-23: 22; 2015-12-24: 16; 2015-12-26: 16; 2015-12-27: 16; 2015-12-28: 16; 2015-12-29: 16; 2015-12-30: 16; 2015-12-31: 16; 2016-01-02: 16; 2016-01-03: 16; 2016-01-04: 16; 2016-01-05: 16; 2016-01-06: 16; 2016-01-07: 18; 2016-01-09: 26; 2016-01-10: 26; 2016-01-11: 42; 2016-01-12: 42; 2016-01-13: 52; 2016-01-14: 50; 2016-01-16: 40; 2016-01-17: 38; 2016-01-18: 30; 2016-01-19: 32; 2016-01-20: 40; 2016-01-21: 40; 2016-01-23: 24; 2016-01-24: 24; 2016-01-25: 24; 2016-01-26: 25; 2016-01-27: 38; 2016-01-28: 36; 2016-01-30: 28; 2016-01-31: 28; 2016-02-01: 27; 2016-02-02: 24; 2016-02-03: 24; 2016-02-04: 24; 2016-02-06: 4; 2016-02-07: 5; 2016-02-08: 8; 2016-02-09: 8; 2016-02-10: 8; 2016-02-11: 8; 2016-02-13: 7; 2016-02-14: 4; 2016-02-15: 4; 2016-02-16: 4; 2016-02-17: 4; 2016-02-18: 4; 2016-02-20: 4; 2016-02-21: 4; 2016-02-22: 4; 2016-02-23: 4; 2016-02-24: 3; 2016-03-09: 10; 2016-03-10: 12; 2016-03-12: 12; 2016-03-13: 12; 2016-03-14: 12; 2016-03-15: 12; 2016-03-16: 12; 2016-03-17: 12; 2016-03-19: 12; 2016-03-20: 12; 2016-03-21: 2; 2016-03-22: 2; 2016-03-23: 4; 2016-03-24: 4; 2016-03-26: 4; 2016-03-27: 4; 2016-03-28: 4; 2016-03-29: 4; 2016-03-30: 4; 2016-03-31: 4; 2016-04-02: 4; 2016-04-03: 4; 2016-04-04: 4; 2016-04-05: 4; 2016-04-06: 4; 2016-04-07: 4; 2016-04-09: 4; 2016-04-10: 4; 2016-04-11: 4; 2016-04-12: 4; 2016-04-13: 4; 2016-04-14: 2; 2016-04-17: 2; 2016-04-18: 2; 2016-04-19: 2; 2016-04-20: 2; 2016-04-21: 2; 2016-04-23: 2; 2016-04-24: 2; 2016-04-25: 2; 2016-04-26: 2; 2016-04-27: 2
Subcon - Steel Railing | 2015-10-27: 2; 2015-10-28: 8; 2015-10-29: 8; 2015-10-31: 8; 2015-11-01: 8; 2015-11-02: 8; 2015-11-03: 8; 2015-11-04: 8; 2015-11-05: 8; 2015-11-07: 8; 2015-11-08: 6; 2015-11-22: 2; 2015-11-23: 8; 2015-11-24: 8; 2015-11-25: 8; 2015-11-26: 8; 2015-11-28: 8; 2015-11-29: 8; 2015-11-30: 8; 2015-12-01: 8; 2015-12-02: 10; 2015-12-03: 17; 2015-12-05: 20; 2015-12-06: 20; 2015-12-07: 20; 2015-12-08: 20; 2015-12-09: 20; 2015-12-10: 20; 2015-12-12: 20; 2015-12-13: 20; 2015-12-14: 18; 2015-12-15: 12; 2015-12-16: 12; 2015-12-17: 12; 2015-12-19: 12; 2015-12-20: 12; 2015-12-21: 12; 2015-12-22: 12; 2015-12-23: 12; 2015-12-24: 12; 2015-12-26: 12; 2015-12-27: 12; 2015-12-28: 12; 2015-12-29: 12; 2015-12-30: 12; 2015-12-31: 12; 2016-01-02: 12; 2016-01-03: 12; 2016-01-04: 12; 2016-01-05: 12; 2016-01-06: 12; 2016-01-07: 11; 2016-01-09: 16; 2016-01-10: 18; 2016-01-11: 18; 2016-01-12: 18; 2016-01-13: 18; 2016-01-14: 18; 2016-01-16: 18; 2016-01-17: 18; 2016-01-18: 18; 2016-01-19: 18; 2016-01-20: 18; 2016-01-21: 18; 2016-01-23: 18; 2016-01-24: 18; 2016-01-25: 18; 2016-01-26: 16; 2016-01-27: 16; 2016-01-28: 16; 2016-01-29: 8; 2016-01-30: 16; 2016-01-31: 16; 2016-02-01: 16; 2016-02-02: 16; 2016-02-03: 16; 2016-02-04: 16; 2016-02-05: 8; 2016-02-06: 16; 2016-02-07: 16; 2016-02-08: 16; 2016-02-09: 16; 2016-02-10: 10; 2016-02-11: 7; 2016-02-12: 1; 2016-02-13: 1; 2016-02-14: 1; 2016-02-15: 1; 2016-02-16: 1; 2016-02-17: 1; 2016-02-18: 1; 2016-02-19: 1; 2016-02-20: 1; 2016-02-21: 1; 2016-02-22: 1; 2016-02-23: 1; 2016-02-24: 1; 2016-02-25: 1; 2016-02-26: 1; 2016-02-27: 1; 2016-02-28: 1; 2016-02-29: 1; 2016-03-01: 0; 2016-03-02: 2; 2016-03-03: 8; 2016-03-05: 8; 2016-03-06: 8; 2016-03-07: 8; 2016-03-08: 8; 2016-03-09: 8; 2016-03-10: 8; 2016-03-12: 8; 2016-03-13: 8; 2016-03-14: 8; 2016-03-15: 8; 2016-03-16: 8; 2016-03-17: 8; 2016-03-19: 8; 2016-03-20: 8; 2016-03-21: 8; 2016-03-22: 8; 2016-03-23: 8; 2016-03-24: 8; 2016-03-26: 8; 2016-03-27: 8; 2016-03-28: 8; 2016-03-29: 8; 2016-03-30: 8; 2016-03-31: 8; 2016-04-02: 8; 2016-04-03: 8; 2016-04-04: 8; 2016-04-05: 8; 2016-04-06: 6; 2016-04-07: 2; 2016-04-08: 2; 2016-04-18: 2; 2016-04-19: 2; 2016-05-01: 2; 2016-05-02: 2; 2016-06-27: 6; 2016-06-28: 6; 2016-06-29: 6; 2016-06-30: 6; 2016-07-02: 6; 2016-07-03: 6; 2016-07-04: 6; 2016-07-05: 6; 2016-07-06: 6; 2016-07-12: 6; 2016-08-18: 4; 2016-08-20: 4; 2016-08-21: 4; 2016-08-22: 4; 2016-08-23: 4; 2016-08-24: 4; 2016-08-25: 4; 2016-08-27: 4; 2016-08-28: 4; 2016-08-29: 4; 2016-08-30: 4; 2016-08-31: 4; 2016-09-01: 4; 2016-09-03: 4; 2016-09-04: 4
Subcon - Structural Steel & Metal Decking | 2015-07-28: 20; 2015-07-29: 20; 2015-07-30: 20; 2015-08-01: 20; 2015-08-02: 20; 2015-08-03: 20; 2015-08-04: 20; 2015-08-05: 20; 2015-08-06: 20; 2015-08-08: 20; 2015-08-09: 20; 2015-08-10: 20; 2015-08-11: 20; 2015-08-12: 20; 2015-08-13: 20; 2015-08-15: 20; 2015-08-16: 20; 2015-08-17: 20; 2015-08-18: 20; 2015-08-19: 20; 2015-08-20: 20; 2015-08-22: 20; 2015-08-23: 20; 2015-08-24: 20; 2015-08-25: 20; 2015-08-26: 20; 2015-08-27: 20; 2015-08-29: 20; 2015-08-30: 20; 2015-08-31: 20; 2015-09-01: 20; 2015-09-02: 20; 2015-09-03: 20; 2015-09-05: 20; 2015-09-06: 20; 2015-09-07: 20; 2015-09-08: 20; 2015-09-09: 20; 2015-09-10: 20; 2015-09-12: 20
Subcon - Vanity Counter | 2016-01-19: 6; 2016-01-20: 10; 2016-01-21: 10; 2016-01-23: 10; 2016-01-24: 10; 2016-01-25: 10; 2016-01-26: 10; 2016-01-27: 10; 2016-01-28: 10; 2016-01-30: 10; 2016-01-31: 10; 2016-02-01: 10; 2016-02-02: 10; 2016-02-03: 10; 2016-02-04: 10; 2016-02-06: 10; 2016-02-07: 10; 2016-02-08: 10; 2016-02-09: 4; 2016-02-11: 10; 2016-02-13: 10; 2016-02-14: 10; 2016-02-15: 10; 2016-02-16: 10; 2016-02-17: 10; 2016-02-18: 10; 2016-02-20: 10; 2016-02-21: 20; 2016-02-22: 20; 2016-02-23: 20; 2016-02-24: 20; 2016-02-25: 20; 2016-02-27: 20; 2016-02-28: 20; 2016-02-29: 20; 2016-03-01: 20; 2016-03-02: 20; 2016-03-03: 10; 2016-03-05: 10; 2016-03-06: 10; 2016-03-07: 10; 2016-03-08: 10; 2016-03-09: 10; 2016-03-10: 10; 2016-03-12: 10
Subcon - False Ceiling | 2015-12-17: 10; 2015-12-19: 10; 2015-12-20: 10; 2015-12-21: 10; 2015-12-22: 10; 2015-12-23: 10; 2015-12-24: 10; 2015-12-26: 10; 2015-12-27: 10; 2015-12-28: 10; 2015-12-29: 18; 2015-12-30: 18; 2015-12-31: 18; 2016-01-02: 18; 2016-01-03: 22; 2016-01-04: 12; 2016-01-05: 12; 2016-01-06: 12; 2016-01-07: 12; 2016-01-09: 12; 2016-01-10: 4; 2016-01-11: 8; 2016-01-12: 18; 2016-01-13: 18; 2016-01-14: 14; 2016-01-16: 18; 2016-01-17: 38; 2016-01-18: 38; 2016-01-19: 34; 2016-01-20: 34; 2016-01-21: 30; 2016-01-23: 30; 2016-01-24: 38; 2016-01-25: 38; 2016-01-26: 38; 2016-01-27: 38; 2016-01-28: 62; 2016-01-30: 52; 2016-01-31: 52; 2016-02-01: 52; 2016-02-02: 52; 2016-02-03: 52; 2016-02-04: 44; 2016-02-06: 48; 2016-02-07: 64; 2016-02-08: 64; 2016-02-09: 86; 2016-02-10: 90; 2016-02-11: 90; 2016-02-13: 106; 2016-02-14: 102; 2016-02-15: 118; 2016-02-16: 114; 2016-02-17: 114; 2016-02-18: 114; 2016-02-20: 114; 2016-02-21: 118; 2016-02-22: 134; 2016-02-23: 144; 2016-02-24: 144; 2016-02-25: 148; 2016-02-27: 138; 2016-02-28: 138; 2016-02-29: 140; 2016-03-01: 140; 2016-03-02: 132; 2016-03-03: 104; 2016-03-05: 92; 2016-03-06: 92; 2016-03-07: 84; 2016-03-08: 80; 2016-03-09: 60; 2016-03-10: 60; 2016-03-12: 82; 2016-03-13: 78; 2016-03-14: 70; 2016-03-15: 66; 2016-03-16: 66; 2016-03-17: 69; 2016-03-19: 53; 2016-03-20: 73; 2016-03-21: 65; 2016-03-22: 65; 2016-03-23: 77; 2016-03-24: 77; 2016-03-26: 77; 2016-03-27: 89; 2016-03-28: 89; 2016-03-29: 67; 2016-03-30: 67; 2016-03-31: 91; 2016-04-02: 91; 2016-04-03: 91; 2016-04-04: 105; 2016-04-05: 105; 2016-04-06: 105; 2016-04-07: 107; 2016-04-09: 107; 2016-04-10: 88; 2016-04-11: 88; 2016-04-12: 112; 2016-04-13: 112; 2016-04-14: 135; 2016-04-15: 3; 2016-04-16: 119; 2016-04-17: 121; 2016-04-18: 121; 2016-04-19: 123; 2016-04-20: 125; 2016-04-21: 103; 2016-04-22: 3; 2016-04-23: 103; 2016-04-24: 107; 2016-04-25: 107; 2016-04-26: 104; 2016-04-27: 104; 2016-04-28: 104; 2016-04-30: 106; 2016-05-01: 91; 2016-05-02: 73; 2016-05-03: 69; 2016-05-04: 72; 2016-05-05: 72; 2016-05-07: 68; 2016-05-08: 68; 2016-05-09: 69; 2016-05-10: 69; 2016-05-11: 69; 2016-05-12: 68; 2016-05-14: 47; 2016-05-15: 47; 2016-05-16: 50; 2016-05-17: 50; 2016-05-18: 47; 2016-05-19: 27; 2016-05-21: 27; 2016-05-22: 27; 2016-05-23: 27; 2016-05-24: 27; 2016-05-25: 4; 2016-05-26: 4; 2016-05-28: 7; 2016-05-29: 7; 2016-05-30: 5; 2016-05-31: 5; 2016-06-01: 5; 2016-06-02: 5; 2016-06-04: 3; 2016-06-05: 3
Subcon - Landscape | 2016-02-10: 20; 2016-02-11: 20; 2016-02-13: 20; 2016-02-14: 20; 2016-02-15: 20; 2016-02-16: 20; 2016-02-17: 20; 2016-02-18: 20; 2016-02-20: 20; 2016-02-21: 20; 2016-02-22: 20; 2016-02-23: 20; 2016-02-24: 20; 2016-02-25: 20; 2016-02-27: 20; 2016-02-28: 20; 2016-02-29: 20; 2016-03-01: 20; 2016-03-02: 20; 2016-03-03: 20; 2016-03-05: 20; 2016-03-06: 20; 2016-03-07: 20; 2016-03-08: 20; 2016-03-09: 20; 2016-03-10: 20; 2016-03-12: 20; 2016-03-13: 20; 2016-03-14: 20; 2016-03-15: 20; 2016-03-16: 13; 2016-03-17: 16; 2016-03-19: 27; 2016-03-20: 27; 2016-03-21: 27; 2016-03-22: 27; 2016-03-23: 27; 2016-03-24: 27; 2016-03-26: 27; 2016-03-27: 27; 2016-03-28: 27; 2016-03-29: 27; 2016-03-30: 27; 2016-03-31: 27; 2016-04-02: 27; 2016-04-03: 13; 2016-04-04: 19; 2016-04-05: 43; 2016-04-06: 43; 2016-04-07: 43; 2016-04-09: 43; 2016-04-10: 43; 2016-04-11: 43; 2016-04-12: 43; 2016-04-13: 43; 2016-04-14: 43; 2016-04-16: 43; 2016-04-17: 43; 2016-04-18: 43; 2016-04-19: 43; 2016-04-20: 43; 2016-04-21: 43; 2016-04-23: 43; 2016-04-24: 43; 2016-04-25: 43; 2016-04-26: 43; 2016-04-27: 39; 2016-04-28: 23; 2016-04-30: 23; 2016-05-01: 23; 2016-05-02: 23; 2016-05-03: 23; 2016-05-04: 23; 2016-05-05: 23; 2016-05-07: 23; 2016-05-08: 23; 2016-05-09: 25; 2016-05-10: 30; 2016-05-11: 30; 2016-05-12: 30; 2016-05-14: 30; 2016-05-15: 30; 2016-05-16: 30; 2016-05-17: 30; 2016-05-18: 30; 2016-05-19: 30; 2016-05-21: 30; 2016-05-22: 30; 2016-05-23: 30; 2016-05-24: 30; 2016-05-25: 30; 2016-05-26: 30; 2016-05-28: 30; 2016-05-29: 30; 2016-05-30: 30; 2016-05-31: 30; 2016-06-01: 27; 2016-06-02: 14; 2016-06-04: 14; 2016-06-05: 14; 2016-06-06: 14; 2016-06-07: 14; 2016-06-08: 14; 2016-06-09: 14; 2016-06-11: 14; 2016-06-12: 14; 2016-06-13: 14; 2016-06-14: 14; 2016-06-15: 14; 2016-06-16: 14; 2016-06-18: 14; 2016-06-19: 15; 2016-06-20: 20; 2016-06-21: 20; 2016-06-22: 20; 2016-06-23: 20; 2016-06-25: 20; 2016-06-26: 20; 2016-06-27: 20; 2016-06-28: 20; 2016-06-29: 20; 2016-06-30: 20; 2016-07-02: 20; 2016-07-03: 20; 2016-07-04: 20; 2016-07-05: 20; 2016-07-06: 20; 2016-07-12: 20; 2016-07-13: 20; 2016-07-14: 20; 2016-07-16: 20; 2016-07-17: 20; 2016-07-18: 20; 2016-07-19: 20; 2016-07-20: 20; 2016-07-21: 20; 2016-07-23: 20; 2016-07-24: 20; 2016-07-25: 20; 2016-07-26: 20; 2016-07-27: 20; 2016-07-28: 18; 2016-07-30: 10; 2016-07-31: 10; 2016-08-01: 10; 2016-08-02: 10; 2016-08-03: 10; 2016-08-04: 10; 2016-08-06: 10; 2016-08-07: 10; 2016-08-08: 13; 2016-08-09: 23; 2016-08-10: 23; 2016-08-11: 23; 2016-08-13: 23; 2016-08-14: 23; 2016-08-15: 23; 2016-08-16: 21; 2016-08-17: 21; 2016-08-18: 21; 2016-08-20: 21; 2016-08-21: 21; 2016-08-22: 19; 2016-08-23: 8; 2016-08-24: 8; 2016-08-25: 8; 2016-08-27: 8; 2016-08-28: 6; 2016-08-29: 6; 2016-08-30: 6; 2016-08-31: 6; 2016-09-01: 6; 2016-09-03: 6; 2016-09-04: 6; 2016-09-05: 6; 2016-09-06: 6; 2016-09-07: 6; 2016-09-13: 6; 2016-09-14: 6; 2016-09-15: 6; 2016-09-17: 5
Subcon - Mirror | 2016-02-21: 4; 2016-02-22: 6; 2016-02-23: 6; 2016-02-24: 6; 2016-02-25: 6; 2016-02-27: 6; 2016-02-28: 6; 2016-02-29: 6; 2016-03-01: 6; 2016-03-02: 6; 2016-03-03: 8; 2016-03-05: 6; 2016-03-06: 6; 2016-03-07: 6; 2016-03-08: 6; 2016-03-09: 6; 2016-03-10: 6; 2016-03-12: 6; 2016-03-13: 6; 2016-03-14: 6
Subcon - Electrical | 2015-04-25: 20; 2015-04-26: 20; 2015-04-27: 20; 2015-04-28: 20; 2015-04-29: 20; 2015-04-30: 20; 2015-05-02: 20; 2015-05-04: 20; 2015-05-05: 20; 2015-05-06: 20; 2015-05-07: 20; 2015-05-18: 20; 2015-05-19: 20; 2015-05-20: 20; 2015-05-21: 20; 2015-05-23: 20; 2015-05-24: 20; 2015-05-25: 20; 2015-05-27: 20; 2015-05-28: 20; 2015-05-30: 20; 2015-05-31: 20; 2015-06-06: 12; 2015-06-07: 40; 2015-06-08: 40; 2015-06-09: 40; 2015-06-10: 60; 2015-06-11: 60; 2015-06-13: 60; 2015-06-14: 60; 2015-06-15: 40; 2015-06-16: 40; 2015-06-17: 40; 2015-06-18: 20; 2015-06-20: 40; 2015-06-21: 28; 2015-06-22: 20; 2015-06-23: 20; 2015-06-30: 20; 2015-07-01: 20; 2015-07-02: 20; 2015-07-04: 20; 2015-07-05: 40; 2015-07-06: 40; 2015-07-07: 40; 2015-07-08: 20; 2015-07-09: 20; 2015-07-11: 40; 2015-07-12: 40; 2015-07-13: 20; 2015-07-14: 40; 2015-07-15: 40; 2015-07-16: 40; 2015-07-22: 40; 2015-07-23: 20; 2015-07-25: 20; 2015-07-26: 20; 2015-07-27: 28; 2015-07-28: 48; 2015-07-29: 48; 2015-07-30: 48; 2015-08-01: 48; 2015-08-02: 28; 2015-08-03: 46; 2015-08-04: 58; 2015-08-05: 38; 2015-08-06: 38; 2015-08-08: 30; 2015-08-09: 30; 2015-08-10: 50; 2015-08-11: 50; 2015-08-12: 62; 2015-08-13: 70; 2015-08-15: 70; 2015-08-16: 70; 2015-08-17: 70; 2015-08-18: 70; 2015-08-19: 70; 2015-08-20: 110; 2015-08-22: 120; 2015-08-23: 108; 2015-08-24: 108; 2015-08-25: 108; 2015-08-26: 108; 2015-08-27: 88; 2015-08-29: 68; 2015-08-30: 68; 2015-08-31: 56; 2015-09-01: 56; 2015-09-02: 78; 2015-09-03: 78; 2015-09-05: 78; 2015-09-06: 126; 2015-09-07: 106; 2015-09-08: 86; 2015-09-09: 91; 2015-09-10: 98; 2015-09-12: 98; 2015-09-13: 98; 2015-09-14: 130; 2015-09-15: 130; 2015-09-16: 130; 2015-09-17: 122; 2015-09-19: 122; 2015-09-20: 102; 2015-09-21: 82; 2015-09-22: 85; 2015-09-29: 85; 2015-09-30: 78; 2015-10-01: 98; 2015-10-03: 92; 2015-10-04: 82; 2015-10-05: 74; 2015-10-06: 82; 2015-10-07: 90; 2015-10-08: 90; 2015-10-10: 107; 2015-10-11: 107; 2015-10-12: 149; 2015-10-13: 191; 2015-10-14: 199; 2015-10-15: 211; 2015-10-17: 211; 2015-10-18: 221; 2015-10-19: 245; 2015-10-20: 245; 2015-10-21: 249; 2015-10-22: 251; 2015-10-24: 257; 2015-10-25: 289; 2015-10-26: 293; 2015-10-27: 293; 2015-10-28: 287; 2015-10-29: 241; 2015-10-31: 235; 2015-11-01: 241; 2015-11-02: 237; 2015-11-03: 250; 2015-11-04: 262; 2015-11-05: 263; 2015-11-07: 292; 2015-11-08: 343; 2015-11-09: 327; 2015-11-10: 319; 2015-11-11: 275; 2015-11-12: 275; 2015-11-14: 275; 2015-11-15: 278; 2015-11-16: 263; 2015-11-17: 270; 2015-11-18: 268; 2015-11-19: 280; 2015-11-21: 274; 2015-11-22: 265; 2015-11-23: 237; 2015-11-24: 255; 2015-11-25: 222; 2015-11-26: 233; 2015-11-28: 244; 2015-11-29: 261; 2015-11-30: 267; 2015-12-01: 267; 2015-12-02: 284; 2015-12-03: 309; 2015-12-05: 302; 2015-12-06: 310; 2015-12-07: 313; 2015-12-08: 317; 2015-12-09: 327; 2015-12-10: 358; 2015-12-11: 10; 2015-12-12: 349; 2015-12-13: 343; 2015-12-14: 353; 2015-12-15: 357; 2015-12-16: 415; 2015-12-17: 397; 2015-12-19: 403; 2015-12-20: 395; 2015-12-21: 382; 2015-12-22: 379; 2015-12-23: 372; 2015-12-24: 354; 2015-12-26: 374; 2015-12-27: 419; 2015-12-28: 443; 2015-12-29: 481; 2015-12-30: 483; 2015-12-31: 479; 2016-01-02: 515; 2016-01-03: 472; 2016-01-04: 446; 2016-01-05: 459; 2016-01-06: 471; 2016-01-07: 489; 2016-01-08: 24; 2016-01-09: 524; 2016-01-10: 532; 2016-01-11: 530; 2016-01-12: 502; 2016-01-13: 481; 2016-01-14: 436; 2016-01-15: 26; 2016-01-16: 447; 2016-01-17: 466; 2016-01-18: 493; 2016-01-19: 440; 2016-01-20: 481; 2016-01-21: 537; 2016-01-23: 523; 2016-01-24: 517; 2016-01-25: 507; 2016-01-26: 489; 2016-01-27: 525; 2016-01-28: 553; 2016-01-29: 34; 2016-01-30: 576; 2016-01-31: 573; 2016-02-01: 528; 2016-02-02: 542; 2016-02-03: 494; 2016-02-04: 488; 2016-02-05: 26; 2016-02-06: 501; 2016-02-07: 488; 2016-02-08: 490; 2016-02-09: 496; 2016-02-10: 540; 2016-02-11: 518; 2016-02-13: 490; 2016-02-14: 410; 2016-02-15: 406; 2016-02-16: 414; 2016-02-17: 429; 2016-02-18: 503; 2016-02-19: 20; 2016-02-20: 493; 2016-02-21: 473; 2016-02-22: 472; 2016-02-23: 500; 2016-02-24: 562; 2016-02-25: 575; 2016-02-26: 45; 2016-02-27: 569; 2016-02-28: 562; 2016-02-29: 563; 2016-03-01: 602; 2016-03-02: 604; 2016-03-03: 612; 2016-03-04: 35; 2016-03-05: 565; 2016-03-06: 559; 2016-03-07: 516; 2016-03-08: 493; 2016-03-09: 501; 2016-03-10: 485; 2016-03-11: 11; 2016-03-12: 440; 2016-03-13: 378; 2016-03-14: 375; 2016-03-15: 371; 2016-03-16: 325; 2016-03-17: 344; 2016-03-19: 305; 2016-03-20: 260; 2016-03-21: 280; 2016-03-22: 297; 2016-03-23: 280; 2016-03-24: 260; 2016-03-25: 11; 2016-03-26: 248; 2016-03-27: 244; 2016-03-28: 258; 2016-03-29: 282; 2016-03-30: 245; 2016-03-31: 210; 2016-04-01: 10; 2016-04-02: 218; 2016-04-03: 258; 2016-04-04: 271; 2016-04-05: 260; 2016-04-06: 260; 2016-04-07: 230; 2016-04-08: 10; 2016-04-09: 230; 2016-04-10: 270; 2016-04-11: 270; 2016-04-12: 310; 2016-04-13: 330; 2016-04-14: 330; 2016-04-15: 20; 2016-04-16: 314; 2016-04-17: 320; 2016-04-18: 340; 2016-04-19: 310; 2016-04-20: 260; 2016-04-21: 256; 2016-04-22: 10; 2016-04-23: 260; 2016-04-24: 292; 2016-04-25: 312; 2016-04-26: 292; 2016-04-27: 258; 2016-04-28: 292; 2016-04-29: 20; 2016-04-30: 312; 2016-05-01: 282; 2016-05-02: 282; 2016-05-03: 282; 2016-05-04: 282; 2016-05-05: 304; 2016-05-06: 40; 2016-05-07: 340; 2016-05-08: 320; 2016-05-09: 300; 2016-05-10: 260; 2016-05-11: 318; 2016-05-12: 348; 2016-05-13: 20; 2016-05-14: 348; 2016-05-15: 346; 2016-05-16: 338; 2016-05-17: 406; 2016-05-18: 450; 2016-05-19: 456; 2016-05-20: 20; 2016-05-21: 436; 2016-05-22: 436; 2016-05-23: 378; 2016-05-24: 378; 2016-05-25: 378; 2016-05-26: 378; 2016-05-27: 20; 2016-05-28: 378; 2016-05-29: 298; 2016-05-30: 228; 2016-05-31: 228; 2016-06-01: 206; 2016-06-02: 198; 2016-06-04: 160; 2016-06-05: 136; 2016-06-06: 130; 2016-06-07: 128; 2016-06-08: 120; 2016-06-09: 120; 2016-06-11: 100; 2016-06-12: 100; 2016-06-13: 100; 2016-06-14: 100; 2016-06-15: 76; 2016-06-16: 60; 2016-06-18: 60; 2016-06-19: 60; 2016-06-20: 60; 2016-06-21: 60; 2016-06-22: 56; 2016-06-23: 40; 2016-06-25: 40; 2016-06-26: 40; 2016-06-27: 40; 2016-06-28: 40; 2016-06-29: 40; 2016-06-30: 36; 2016-07-02: 20; 2016-07-03: 20; 2016-07-04: 20; 2016-07-05: 20; 2016-07-06: 20; 2016-07-12: 20; 2016-07-13: 20; 2016-07-14: 20; 2016-07-16: 20; 2016-07-17: 16
Subcon - Plumbing | 2015-03-04: 2; 2015-03-05: 2; 2015-03-07: 2; 2015-03-08: 2; 2015-03-09: 2; 2015-03-10: 4; 2015-03-11: 4; 2015-03-12: 4; 2015-03-14: 4; 2015-03-15: 4; 2015-03-16: 4; 2015-03-17: 4; 2015-03-18: 4; 2015-03-19: 4; 2015-03-21: 4; 2015-04-12: 10; 2015-04-13: 10; 2015-04-14: 12; 2015-04-15: 12; 2015-04-16: 12; 2015-04-18: 12; 2015-04-19: 12; 2015-04-20: 12; 2015-04-21: 12; 2015-04-22: 12; 2015-04-23: 12; 2015-04-25: 12; 2015-04-26: 12; 2015-04-27: 12; 2015-04-28: 12; 2015-04-29: 2; 2015-04-30: 2; 2015-07-11: 10; 2015-07-12: 10; 2015-07-13: 10; 2015-07-14: 10; 2015-07-15: 10; 2015-07-16: 20; 2015-07-22: 20; 2015-07-23: 20; 2015-07-25: 20; 2015-07-26: 26; 2015-07-27: 30; 2015-07-28: 30; 2015-07-29: 30; 2015-07-30: 30; 2015-08-01: 46; 2015-08-02: 40; 2015-08-03: 40; 2015-08-04: 40; 2015-08-05: 40; 2015-08-06: 50; 2015-08-08: 40; 2015-08-09: 40; 2015-08-10: 50; 2015-08-11: 50; 2015-08-12: 50; 2015-08-13: 50; 2015-08-15: 50; 2015-08-16: 60; 2015-08-17: 60; 2015-08-18: 50; 2015-08-19: 50; 2015-08-20: 50; 2015-08-22: 63; 2015-08-23: 63; 2015-08-24: 53; 2015-08-25: 53; 2015-08-26: 53; 2015-08-27: 63; 2015-08-29: 63; 2015-08-30: 57; 2015-08-31: 53; 2015-09-01: 53; 2015-09-02: 57; 2015-09-03: 57; 2015-09-05: 51; 2015-09-06: 47; 2015-09-07: 47; 2015-09-08: 53; 2015-09-09: 53; 2015-09-10: 53; 2015-09-12: 53; 2015-09-13: 53; 2015-09-14: 47; 2015-09-15: 47; 2015-09-16: 47; 2015-09-17: 47; 2015-09-19: 47; 2015-09-20: 53; 2015-09-21: 53; 2015-09-22: 53; 2015-09-29: 53; 2015-09-30: 53; 2015-10-01: 53; 2015-10-03: 72; 2015-10-04: 72; 2015-10-05: 72; 2015-10-06: 72; 2015-10-07: 87; 2015-10-08: 87; 2015-10-10: 87; 2015-10-11: 87; 2015-10-12: 87; 2015-10-13: 87; 2015-10-14: 91; 2015-10-15: 97; 2015-10-17: 101; 2015-10-18: 123; 2015-10-19: 115; 2015-10-20: 115; 2015-10-21: 115; 2015-10-22: 115; 2015-10-24: 96; 2015-10-25: 116; 2015-10-26: 112; 2015-10-27: 115; 2015-10-28: 132; 2015-10-29: 128; 2015-10-30: 4; 2015-10-31: 148; 2015-11-01: 148; 2015-11-02: 162; 2015-11-03: 166; 2015-11-04: 166; 2015-11-05: 157; 2015-11-06: 4; 2015-11-07: 155; 2015-11-08: 190; 2015-11-09: 208; 2015-11-10: 208; 2015-11-11: 192; 2015-11-12: 222; 2015-11-14: 214; 2015-11-15: 232; 2015-11-16: 232; 2015-11-17: 212; 2015-11-18: 193; 2015-11-19: 209; 2015-11-21: 221; 2015-11-22: 206; 2015-11-23: 234; 2015-11-24: 234; 2015-11-25: 228; 2015-11-26: 234; 2015-11-27: 4; 2015-11-28: 234; 2015-11-29: 218; 2015-11-30: 219; 2015-12-01: 218; 2015-12-02: 222; 2015-12-03: 226; 2015-12-04: 8; 2015-12-05: 234; 2015-12-06: 228; 2015-12-07: 228; 2015-12-08: 228; 2015-12-09: 228; 2015-12-10: 202; 2015-12-11: 18; 2015-12-12: 202; 2015-12-13: 200; 2015-12-14: 212; 2015-12-15: 212; 2015-12-16: 252; 2015-12-17: 242; 2015-12-19: 242; 2015-12-20: 243; 2015-12-21: 243; 2015-12-22: 259; 2015-12-23: 263; 2015-12-24: 263; 2015-12-25: 20; 2015-12-26: 253; 2015-12-27: 263; 2015-12-28: 311; 2015-12-29: 290; 2015-12-30: 290; 2015-12-31: 285; 2016-01-01: 20; 2016-01-02: 285; 2016-01-03: 277; 2016-01-04: 277; 2016-01-05: 277; 2016-01-06: 271; 2016-01-07: 257; 2016-01-08: 20; 2016-01-09: 293; 2016-01-10: 293; 2016-01-11: 282; 2016-01-12: 251; 2016-01-13: 241; 2016-01-14: 225; 2016-01-16: 245; 2016-01-17: 256; 2016-01-18: 248; 2016-01-19: 248; 2016-01-20: 234; 2016-01-21: 234; 2016-01-23: 242; 2016-01-24: 198; 2016-01-25: 188; 2016-01-26: 202; 2016-01-27: 230; 2016-01-28: 239; 2016-01-30: 272; 2016-01-31: 304; 2016-02-01: 302; 2016-02-02: 291; 2016-02-03: 290; 2016-02-04: 262; 2016-02-06: 244; 2016-02-07: 284; 2016-02-08: 312; 2016-02-09: 302; 2016-02-10: 346; 2016-02-11: 366; 2016-02-13: 356; 2016-02-14: 336; 2016-02-15: 351; 2016-02-16: 317; 2016-02-17: 289; 2016-02-18: 319; 2016-02-20: 327; 2016-02-21: 295; 2016-02-22: 329; 2016-02-23: 349; 2016-02-24: 339; 2016-02-25: 319; 2016-02-27: 311; 2016-02-28: 301; 2016-02-29: 273; 2016-03-01: 283; 2016-03-02: 283; 2016-03-03: 275; 2016-03-04: 20; 2016-03-05: 323; 2016-03-06: 323; 2016-03-07: 323; 2016-03-08: 303; 2016-03-09: 323; 2016-03-10: 278; 2016-03-11: 20; 2016-03-12: 259; 2016-03-13: 262; 2016-03-14: 272; 2016-03-15: 265; 2016-03-16: 264; 2016-03-17: 264; 2016-03-18: 20; 2016-03-19: 204; 2016-03-20: 204; 2016-03-21: 189; 2016-03-22: 159; 2016-03-23: 161; 2016-03-24: 157; 2016-03-26: 157; 2016-03-27: 127; 2016-03-28: 147; 2016-03-29: 147; 2016-03-30: 127; 2016-03-31: 117; 2016-04-01: 60; 2016-04-02: 137; 2016-04-03: 107; 2016-04-04: 108; 2016-04-05: 111; 2016-04-06: 111; 2016-04-07: 116; 2016-04-08: 80; 2016-04-09: 131; 2016-04-10: 129; 2016-04-11: 103; 2016-04-12: 133; 2016-04-13: 133; 2016-04-14: 113; 2016-04-15: 60; 2016-04-16: 95; 2016-04-17: 101; 2016-04-18: 101; 2016-04-19: 101; 2016-04-20: 106; 2016-04-21: 104; 2016-04-22: 40; 2016-04-23: 78; 2016-04-24: 78; 2016-04-25: 98; 2016-04-26: 98; 2016-04-27: 80; 2016-04-28: 88; 2016-04-29: 40; 2016-04-30: 78; 2016-05-01: 78; 2016-05-02: 78; 2016-05-03: 78; 2016-05-04: 80; 2016-05-05: 40; 2016-05-06: 20; 2016-05-07: 40; 2016-05-08: 40; 2016-05-09: 40; 2016-05-10: 20; 2016-05-11: 20; 2016-05-12: 20; 2016-05-14: 20; 2016-05-15: 20; 2016-05-16: 20; 2016-05-17: 20; 2016-05-18: 20; 2016-05-19: 20; 2016-05-21: 20; 2016-05-22: 20; 2016-05-23: 20; 2016-05-24: 20; 2016-05-25: 20; 2016-05-26: 20; 2016-05-28: 20; 2016-05-29: 20; 2016-05-30: 20; 2016-05-31: 20; 2016-06-01: 18; 2016-06-02: 10; 2016-06-04: 10; 2016-06-05: 10; 2016-06-06: 10; 2016-06-07: 8; 2016-06-26: 10; 2016-06-27: 10; 2016-06-28: 10; 2016-06-29: 10; 2016-06-30: 10; 2016-07-01: 10; 2016-07-02: 10; 2016-07-03: 10; 2016-07-04: 14; 2016-07-05: 14; 2016-07-06: 14; 2016-07-07: 14; 2016-07-08: 14; 2016-07-09: 14; 2016-07-10: 14; 2016-07-11: 4; 2016-07-12: 4; 2016-07-13: 4; 2016-07-14: 4; 2016-07-15: 4; 2016-07-16: 4; 2016-07-17: 4
Subcon - HVAC | 2015-09-15: 10; 2015-09-16: 10; 2015-09-17: 10; 2015-09-19: 10; 2015-09-20: 10; 2015-09-21: 10; 2015-09-22: 10; 2015-09-29: 10; 2015-09-30: 10; 2015-10-01: 10; 2015-10-03: 30; 2015-10-04: 30; 2015-10-05: 30; 2015-10-06: 30; 2015-10-07: 30; 2015-10-08: 32; 2015-10-10: 32; 2015-10-11: 32; 2015-10-12: 32; 2015-10-13: 32; 2015-10-14: 64; 2015-10-15: 64; 2015-10-17: 74; 2015-10-18: 74; 2015-10-19: 74; 2015-10-20: 42; 2015-10-21: 42; 2015-10-22: 54; 2015-10-24: 54; 2015-10-25: 54; 2015-10-26: 42; 2015-10-27: 52; 2015-10-28: 92; 2015-10-29: 92; 2015-10-31: 104; 2015-11-01: 92; 2015-11-02: 92; 2015-11-03: 88; 2015-11-04: 92; 2015-11-05: 100; 2015-11-07: 108; 2015-11-08: 128; 2015-11-09: 240; 2015-11-10: 240; 2015-11-11: 240; 2015-11-12: 240; 2015-11-14: 242; 2015-11-15: 206; 2015-11-16: 198; 2015-11-17: 198; 2015-11-18: 190; 2015-11-19: 190; 2015-11-21: 238; 2015-11-22: 238; 2015-11-23: 254; 2015-11-24: 254; 2015-11-25: 222; 2015-11-26: 156; 2015-11-28: 152; 2015-11-29: 148; 2015-11-30: 148; 2015-12-01: 156; 2015-12-02: 214; 2015-12-03: 234; 2015-12-05: 264; 2015-12-06: 264; 2015-12-07: 306; 2015-12-08: 266; 2015-12-09: 246; 2015-12-10: 242; 2015-12-11: 10; 2015-12-12: 234; 2015-12-13: 260; 2015-12-14: 302; 2015-12-15: 284; 2015-12-16: 274; 2015-12-17: 274; 2015-12-19: 278; 2015-12-20: 248; 2015-12-21: 248; 2015-12-22: 236; 2015-12-23: 224; 2015-12-24: 228; 2015-12-26: 270; 2015-12-27: 258; 2015-12-28: 278; 2015-12-29: 306; 2015-12-30: 340; 2015-12-31: 310; 2016-01-02: 330; 2016-01-03: 304; 2016-01-04: 272; 2016-01-05: 284; 2016-01-06: 336; 2016-01-07: 340; 2016-01-09: 345; 2016-01-10: 325; 2016-01-11: 349; 2016-01-12: 319; 2016-01-13: 299; 2016-01-14: 271; 2016-01-16: 275; 2016-01-17: 275; 2016-01-18: 335; 2016-01-19: 335; 2016-01-20: 329; 2016-01-21: 335; 2016-01-23: 359; 2016-01-24: 339; 2016-01-25: 311; 2016-01-26: 368; 2016-01-27: 368; 2016-01-28: 380; 2016-01-29: 10; 2016-01-30: 422; 2016-01-31: 442; 2016-02-01: 394; 2016-02-02: 394; 2016-02-03: 376; 2016-02-04: 356; 2016-02-06: 356; 2016-02-07: 438; 2016-02-08: 438; 2016-02-09: 486; 2016-02-10: 490; 2016-02-11: 464; 2016-02-13: 416; 2016-02-14: 416; 2016-02-15: 394; 2016-02-16: 354; 2016-02-17: 354; 2016-02-18: 480; 2016-02-20: 486; 2016-02-21: 490; 2016-02-22: 470; 2016-02-23: 478; 2016-02-24: 426; 2016-02-25: 422; 2016-02-26: 20; 2016-02-27: 406; 2016-02-28: 346; 2016-02-29: 346; 2016-03-01: 344; 2016-03-02: 344; 2016-03-03: 332; 2016-03-04: 40; 2016-03-05: 312; 2016-03-06: 316; 2016-03-07: 209; 2016-03-08: 209; 2016-03-09: 229; 2016-03-10: 209; 2016-03-11: 20; 2016-03-12: 213; 2016-03-13: 163; 2016-03-14: 179; 2016-03-15: 151; 2016-03-16: 151; 2016-03-17: 155; 2016-03-18: 20; 2016-03-19: 135; 2016-03-20: 135; 2016-03-21: 135; 2016-03-22: 135; 2016-03-23: 130; 2016-03-24: 104; 2016-03-25: 20; 2016-03-26: 120; 2016-03-27: 100; 2016-03-28: 100; 2016-03-29: 116; 2016-03-30: 96; 2016-03-31: 96; 2016-04-02: 92; 2016-04-03: 92; 2016-04-04: 72; 2016-04-05: 70; 2016-04-06: 106; 2016-04-07: 106; 2016-04-09: 124; 2016-04-10: 142; 2016-04-11: 142; 2016-04-12: 152; 2016-04-13: 152; 2016-04-14: 152; 2016-04-16: 132; 2016-04-17: 132; 2016-04-18: 152; 2016-04-19: 172; 2016-04-20: 202; 2016-04-21: 230; 2016-04-22: 40; 2016-04-23: 230; 2016-04-24: 190; 2016-04-25: 190; 2016-04-26: 170; 2016-04-27: 166; 2016-04-28: 182; 2016-04-29: 40; 2016-04-30: 172; 2016-05-01: 180; 2016-05-02: 198; 2016-05-03: 198; 2016-05-04: 178; 2016-05-05: 118; 2016-05-06: 36; 2016-05-07: 118; 2016-05-08: 118; 2016-05-09: 98; 2016-05-10: 114; 2016-05-11: 106; 2016-05-12: 98; 2016-05-13: 20; 2016-05-14: 90; 2016-05-15: 64; 2016-05-16: 64; 2016-05-17: 24; 2016-05-18: 24; 2016-05-19: 24; 2016-05-20: 8; 2016-05-21: 24; 2016-05-22: 24; 2016-05-23: 24; 2016-05-24: 16; 2016-05-25: 16
Subcon - Fire Fighting | 2015-10-03: 20; 2015-10-04: 20; 2015-10-05: 20; 2015-10-06: 20; 2015-10-07: 20; 2015-10-08: 20; 2015-10-10: 20; 2015-10-11: 20; 2015-10-12: 20; 2015-10-13: 20; 2015-10-14: 20; 2015-10-15: 20; 2015-10-17: 20; 2015-10-18: 20; 2015-10-19: 20; 2015-10-20: 20; 2015-10-21: 20; 2015-10-22: 20; 2015-10-24: 20; 2015-10-25: 20; 2015-10-26: 20; 2015-10-27: 20; 2015-10-28: 40; 2015-10-29: 40; 2015-10-31: 40; 2015-11-01: 50; 2015-11-02: 50; 2015-11-03: 62; 2015-11-04: 70; 2015-11-05: 70; 2015-11-07: 50; 2015-11-08: 70; 2015-11-09: 70; 2015-11-10: 70; 2015-11-11: 70; 2015-11-12: 70; 2015-11-14: 70; 2015-11-15: 90; 2015-11-16: 90; 2015-11-17: 90; 2015-11-18: 90; 2015-11-19: 90; 2015-11-21: 90; 2015-11-22: 90; 2015-11-23: 90; 2015-11-24: 80; 2015-11-25: 80; 2015-11-26: 110; 2015-11-28: 110; 2015-11-29: 110; 2015-11-30: 110; 2015-12-01: 110; 2015-12-02: 90; 2015-12-03: 90; 2015-12-05: 90; 2015-12-06: 90; 2015-12-07: 90; 2015-12-08: 110; 2015-12-09: 110; 2015-12-10: 110; 2015-12-12: 110; 2015-12-13: 90; 2015-12-14: 86; 2015-12-15: 78; 2015-12-16: 78; 2015-12-17: 78; 2015-12-19: 78; 2015-12-20: 68; 2015-12-21: 68; 2015-12-22: 68; 2015-12-23: 68; 2015-12-24: 68; 2015-12-26: 76; 2015-12-27: 76; 2015-12-28: 76; 2015-12-29: 76; 2015-12-30: 76; 2015-12-31: 68; 2016-01-02: 68; 2016-01-03: 68; 2016-01-04: 68; 2016-01-05: 68; 2016-01-06: 76; 2016-01-07: 76; 2016-01-09: 76; 2016-01-10: 96; 2016-01-11: 96; 2016-01-12: 88; 2016-01-13: 118; 2016-01-14: 138; 2016-01-16: 138; 2016-01-17: 138; 2016-01-18: 148; 2016-01-19: 148; 2016-01-20: 148; 2016-01-21: 148; 2016-01-23: 148; 2016-01-24: 156; 2016-01-25: 156; 2016-01-26: 156; 2016-01-27: 136; 2016-01-28: 136; 2016-01-30: 130; 2016-01-31: 130; 2016-02-01: 132; 2016-02-02: 132; 2016-02-03: 132; 2016-02-04: 142; 2016-02-06: 132; 2016-02-07: 112; 2016-02-08: 112; 2016-02-09: 112; 2016-02-10: 122; 2016-02-11: 122; 2016-02-13: 160; 2016-02-14: 160; 2016-02-15: 180; 2016-02-16: 170; 2016-02-17: 150; 2016-02-18: 166; 2016-02-20: 166; 2016-02-21: 166; 2016-02-22: 156; 2016-02-23: 156; 2016-02-24: 140; 2016-02-25: 140; 2016-02-27: 170; 2016-02-28: 140; 2016-02-29: 120; 2016-03-01: 120; 2016-03-02: 120; 2016-03-03: 140; 2016-03-04: 10; 2016-03-05: 150; 2016-03-06: 150; 2016-03-07: 150; 2016-03-08: 154; 2016-03-09: 144; 2016-03-10: 114; 2016-03-12: 114; 2016-03-13: 94; 2016-03-14: 94; 2016-03-15: 74; 2016-03-16: 84; 2016-03-17: 116; 2016-03-19: 116; 2016-03-20: 120; 2016-03-21: 100; 2016-03-22: 70; 2016-03-23: 58; 2016-03-24: 58; 2016-03-26: 58; 2016-03-27: 38; 2016-03-28: 38; 2016-03-29: 54; 2016-03-30: 54; 2016-03-31: 54; 2016-04-02: 50; 2016-04-03: 40; 2016-04-04: 40; 2016-04-05: 40; 2016-04-06: 40; 2016-04-07: 60; 2016-04-09: 68; 2016-04-10: 88; 2016-04-11: 88; 2016-04-12: 88; 2016-04-13: 88; 2016-04-14: 88; 2016-04-16: 68; 2016-04-17: 68; 2016-04-18: 60; 2016-04-19: 60; 2016-04-20: 68; 2016-04-21: 68; 2016-04-23: 68; 2016-04-24: 68; 2016-04-25: 68; 2016-04-26: 88; 2016-04-27: 68; 2016-04-28: 68; 2016-04-30: 80; 2016-05-01: 80; 2016-05-02: 88; 2016-05-03: 88; 2016-05-04: 88; 2016-05-05: 88; 2016-05-07: 68; 2016-05-08: 88; 2016-05-09: 48; 2016-05-10: 50; 2016-05-11: 42; 2016-05-12: 42; 2016-05-14: 42; 2016-05-15: 46; 2016-05-16: 46; 2016-05-17: 46; 2016-05-18: 46; 2016-05-19: 46; 2016-05-21: 46; 2016-05-22: 42; 2016-05-23: 42; 2016-05-24: 42; 2016-05-25: 42; 2016-05-26: 46; 2016-05-28: 46; 2016-05-29: 46; 2016-05-30: 46; 2016-05-31: 26; 2016-06-01: 26; 2016-06-02: 22; 2016-06-04: 22; 2016-06-05: 22; 2016-06-06: 22; 2016-06-07: 26; 2016-06-08: 26; 2016-06-09: 26; 2016-06-11: 26; 2016-06-12: 6; 2016-06-13: 6
Subcon - Lift & Esc. | 2016-01-09: 20; 2016-01-10: 20; 2016-01-11: 20; 2016-01-12: 20; 2016-01-13: 20; 2016-01-14: 40; 2016-01-16: 40; 2016-01-17: 40; 2016-01-18: 40; 2016-01-19: 40; 2016-01-20: 40; 2016-01-21: 40; 2016-01-23: 40; 2016-01-24: 40; 2016-01-25: 40; 2016-01-26: 40; 2016-01-27: 40; 2016-01-28: 40; 2016-01-30: 40; 2016-01-31: 40; 2016-02-01: 40; 2016-02-02: 40; 2016-02-03: 40; 2016-02-04: 40; 2016-02-06: 40; 2016-02-07: 20; 2016-02-08: 20; 2016-02-09: 20; 2016-02-10: 20; 2016-02-11: 20; 2016-02-13: 20; 2016-02-14: 20; 2016-02-15: 20; 2016-02-16: 20; 2016-02-17: 20; 2016-02-18: 8; 2016-02-20: 8; 2016-02-21: 8; 2016-02-22: 8; 2016-02-23: 8; 2016-02-24: 8; 2016-02-25: 8; 2016-02-27: 8; 2016-02-28: 8; 2016-02-29: 8; 2016-03-01: 8; 2016-03-02: 8; 2016-03-03: 8; 2016-03-05: 8
Subcon - Water Proofing | 2014-12-02: 3; 2014-12-03: 3; 2014-12-04: 3; 2014-12-06: 3; 2014-12-07: 3; 2014-12-08: 3; 2014-12-09: 3; 2014-12-10: 3; 2014-12-11: 3; 2014-12-13: 3; 2014-12-14: 3; 2014-12-15: 3; 2014-12-16: 3; 2014-12-17: 3; 2014-12-20: 3; 2014-12-21: 4; 2014-12-22: 4; 2014-12-23: 4; 2014-12-24: 4; 2014-12-25: 4; 2014-12-27: 5; 2014-12-28: 5; 2014-12-29: 5; 2014-12-30: 5; 2014-12-31: 5; 2015-01-01: 5; 2015-01-03: 5; 2015-01-04: 1; 2015-01-05: 1; 2015-01-06: 1; 2015-01-07: 10; 2015-01-08: 10; 2015-01-10: 10; 2015-01-11: 10; 2015-01-12: 10; 2015-01-13: 13; 2015-01-14: 3; 2015-01-15: 3; 2015-01-17: 3; 2015-01-18: 3; 2015-01-19: 3; 2015-01-20: 3; 2015-01-21: 3; 2015-01-22: 3; 2015-01-24: 3; 2015-01-25: 3; 2015-01-26: 3; 2015-01-27: 8; 2015-01-28: 8; 2015-01-29: 8; 2015-01-30: 5; 2015-01-31: 28; 2015-02-01: 28; 2015-02-02: 28; 2015-02-03: 28; 2015-02-04: 23; 2015-02-05: 55; 2015-02-06: 5; 2015-02-07: 55; 2015-02-08: 55; 2015-02-09: 55; 2015-02-10: 55; 2015-02-11: 40; 2015-02-12: 40; 2015-02-14: 30; 2015-02-15: 10; 2015-02-16: 10; 2015-02-17: 10; 2015-02-18: 10; 2015-02-19: 10; 2015-02-23: 10; 2015-02-24: 10; 2015-02-25: 10; 2015-02-26: 10; 2015-02-28: 10; 2015-03-01: 10; 2015-03-09: 10; 2015-03-10: 10; 2015-03-11: 10; 2015-03-12: 10; 2015-03-13: 10; 2015-03-14: 20; 2015-03-15: 20; 2015-03-16: 20; 2015-03-17: 10; 2015-03-18: 10; 2015-03-19: 30; 2015-03-21: 30; 2015-03-22: 30; 2015-03-23: 40; 2015-03-24: 50; 2015-03-25: 40; 2015-03-26: 50; 2015-03-28: 50; 2015-03-29: 30; 2015-03-30: 30; 2015-03-31: 30; 2015-04-01: 20; 2015-04-02: 10; 2015-04-15: 10; 2015-04-16: 10; 2015-04-17: 10; 2015-04-18: 10; 2015-04-20: 20; 2015-04-21: 40; 2015-04-22: 40; 2015-04-23: 40; 2015-04-24: 10; 2015-04-25: 30; 2015-04-26: 40; 2015-04-27: 40; 2015-04-28: 40; 2015-04-29: 20; 2015-04-30: 20; 2015-05-02: 20; 2015-05-03: 20; 2015-05-04: 20; 2015-05-05: 10; 2015-05-06: 10; 2015-08-18: 4; 2015-08-19: 4; 2015-08-20: 4; 2015-08-22: 4; 2015-08-23: 4; 2015-08-24: 8; 2015-08-25: 10; 2015-08-26: 10; 2015-08-27: 10; 2015-08-29: 10; 2015-08-30: 6; 2015-08-31: 6; 2015-09-01: 6; 2015-09-02: 6; 2015-09-03: 6; 2015-09-05: 6; 2015-09-06: 6; 2015-09-07: 6; 2015-09-08: 6; 2015-09-09: 6; 2015-09-10: 6; 2015-09-12: 6; 2015-09-13: 10; 2015-09-14: 10; 2015-09-15: 10; 2015-09-16: 10; 2015-09-17: 10; 2015-09-19: 10; 2015-09-20: 10; 2015-09-21: 10; 2015-09-22: 6; 2015-09-29: 8; 2015-09-30: 10; 2015-10-01: 10; 2015-10-03: 10; 2015-10-04: 10; 2015-10-05: 10; 2015-10-06: 10; 2015-10-07: 10; 2015-10-08: 10; 2015-10-10: 10; 2015-10-11: 6; 2015-10-12: 6; 2015-10-13: 6; 2015-10-14: 6; 2015-10-15: 6; 2015-10-17: 6; 2015-10-18: 6; 2015-10-19: 6; 2015-10-20: 6; 2015-10-21: 6; 2015-10-22: 6; 2015-10-24: 6; 2015-10-25: 6; 2015-10-26: 6; 2015-10-27: 6; 2015-10-28: 6; 2015-10-29: 6; 2015-10-31: 6; 2015-11-01: 6; 2015-11-02: 6; 2015-11-03: 6; 2015-11-04: 6; 2015-11-05: 6; 2015-11-07: 6; 2015-11-08: 6; 2015-11-09: 6; 2015-11-10: 6; 2015-11-11: 6; 2015-11-12: 6; 2015-11-14: 6; 2015-11-15: 6; 2015-11-16: 6; 2015-11-17: 6; 2015-11-18: 6; 2015-11-19: 6; 2015-11-21: 6; 2015-11-22: 6; 2015-11-23: 16; 2015-11-24: 16; 2015-11-25: 16; 2015-11-26: 16; 2015-11-27: 10; 2015-11-28: 16; 2015-11-29: 16; 2015-11-30: 16; 2015-12-01: 16; 2015-12-02: 16; 2015-12-03: 6; 2015-12-05: 6; 2015-12-06: 6; 2015-12-07: 16; 2015-12-08: 16; 2015-12-09: 30; 2015-12-10: 40; 2015-12-11: 20; 2015-12-12: 40; 2015-12-13: 40; 2015-12-14: 40; 2015-12-15: 40; 2015-12-16: 40; 2015-12-17: 40; 2015-12-18: 20; 2015-12-19: 40; 2015-12-20: 40; 2015-12-21: 40; 2015-12-22: 40; 2015-12-23: 40; 2015-12-24: 40; 2015-12-25: 20; 2015-12-26: 40; 2015-12-27: 30; 2015-12-28: 30; 2015-12-29: 30; 2015-12-30: 20; 2015-12-31: 20; 2016-01-02: 20; 2016-01-03: 30; 2016-01-04: 30; 2016-01-05: 40; 2016-01-06: 50; 2016-01-07: 60; 2016-01-08: 20; 2016-01-09: 60; 2016-01-10: 60; 2016-01-11: 60; 2016-01-12: 60; 2016-01-13: 40; 2016-01-14: 40; 2016-01-15: 40; 2016-01-16: 60; 2016-01-17: 70; 2016-01-18: 60; 2016-01-19: 60; 2016-01-20: 60; 2016-01-21: 50; 2016-01-22: 30; 2016-01-23: 40; 2016-01-24: 40; 2016-01-25: 20; 2016-01-26: 20; 2016-01-27: 20; 2016-01-28: 20; 2016-01-29: 20; 2016-01-30: 20; 2016-01-31: 20; 2016-02-01: 20; 2016-02-02: 20; 2016-02-03: 20; 2016-02-04: 10; 2016-02-05: 10; 2016-02-06: 10; 2016-02-07: 10; 2016-02-08: 20; 2016-02-09: 20; 2016-02-10: 20; 2016-02-11: 40; 2016-02-12: 40; 2016-02-13: 60; 2016-02-14: 60; 2016-02-15: 60; 2016-02-16: 50; 2016-02-17: 50; 2016-02-18: 50; 2016-02-19: 30; 2016-02-20: 50; 2016-02-21: 50; 2016-02-22: 60; 2016-02-23: 80; 2016-02-24: 100; 2016-02-25: 100; 2016-02-26: 40; 2016-02-27: 80; 2016-02-28: 70; 2016-02-29: 70; 2016-03-01: 50; 2016-03-02: 50; 2016-03-03: 44; 2016-03-04: 24; 2016-03-05: 54; 2016-03-06: 74; 2016-03-07: 74; 2016-03-08: 94; 2016-03-09: 70; 2016-03-10: 70; 2016-03-11: 30; 2016-03-12: 70; 2016-03-13: 50; 2016-03-14: 50; 2016-03-15: 44; 2016-03-16: 46; 2016-03-17: 46; 2016-03-18: 36; 2016-03-19: 56; 2016-03-20: 56; 2016-03-21: 32; 2016-03-22: 32; 2016-03-23: 32; 2016-03-24: 34; 2016-03-25: 14; 2016-03-26: 12; 2016-03-27: 16; 2016-03-28: 6; 2016-03-29: 6; 2016-03-30: 6; 2016-03-31: 6; 2016-04-01: 6; 2016-04-02: 2; 2016-04-03: 2; 2016-04-04: 2; 2016-04-05: 4; 2016-04-06: 4; 2016-04-07: 2; 2016-04-08: 2; 2016-04-09: 2; 2016-04-10: 2; 2016-04-11: 2; 2016-04-12: 2; 2016-04-13: 2; 2016-04-14: 2; 2016-04-15: 2; 2016-04-16: 2; 2016-04-17: 4; 2016-04-18: 4; 2016-04-19: 2; 2016-04-20: 2
Subcon - Anti-termite | 2014-12-02: 2; 2014-12-03: 2; 2014-12-04: 2; 2014-12-06: 2; 2014-12-07: 2; 2014-12-08: 2; 2014-12-09: 2; 2014-12-10: 2; 2014-12-11: 2; 2014-12-13: 2; 2014-12-14: 2; 2014-12-15: 2; 2014-12-16: 2; 2014-12-17: 2; 2014-12-20: 2; 2014-12-21: 3; 2014-12-22: 3; 2014-12-23: 3; 2014-12-24: 3; 2014-12-25: 3; 2014-12-27: 6; 2014-12-28: 6; 2014-12-29: 6; 2014-12-30: 6; 2014-12-31: 6; 2015-01-01: 6; 2015-01-03: 6; 2015-01-04: 6; 2015-01-05: 6; 2015-01-06: 6; 2015-01-07: 5; 2015-01-08: 5; 2015-01-10: 5; 2015-01-11: 5; 2015-01-12: 5; 2015-01-13: 7; 2015-01-14: 7; 2015-01-15: 7; 2015-01-17: 7; 2015-01-18: 7; 2015-01-19: 7; 2015-01-20: 7; 2015-01-21: 7; 2015-01-22: 7; 2015-01-24: 7; 2015-01-25: 7; 2015-01-26: 7; 2015-01-27: 7; 2015-01-28: 7; 2015-01-29: 7; 2015-01-31: 2; 2015-02-01: 2; 2015-02-02: 2; 2015-02-03: 2; 2015-02-04: 2; 2015-03-09: 10; 2015-03-10: 10; 2015-03-11: 10; 2015-03-12: 10; 2015-03-14: 10; 2015-03-15: 10; 2015-03-16: 10; 2015-03-17: 10; 2015-03-18: 10; 2015-03-19: 10; 2015-03-21: 10; 2015-03-22: 10
Subcon - GRC Works | 2016-04-11: 5; 2016-04-12: 5; 2016-04-13: 5; 2016-04-14: 5; 2016-04-16: 5; 2016-04-17: 5; 2016-04-18: 5; 2016-04-19: 5; 2016-04-20: 5; 2016-04-21: 5; 2016-04-23: 5; 2016-04-24: 5; 2016-04-25: 5; 2016-04-26: 5; 2016-04-27: 5; 2016-04-28: 5; 2016-04-30: 5; 2016-05-01: 5; 2016-05-02: 5; 2016-05-03: 5; 2016-05-04: 5; 2016-05-05: 5; 2016-05-07: 5; 2016-05-08: 5; 2016-05-09: 5; 2016-05-10: 5; 2016-05-11: 5; 2016-05-12: 16; 2016-05-14: 16; 2016-05-15: 16; 2016-05-16: 26; 2016-05-17: 26; 2016-05-18: 26; 2016-05-19: 26; 2016-05-21: 26; 2016-05-22: 26; 2016-05-23: 26; 2016-05-24: 26; 2016-05-25: 26; 2016-05-26: 26; 2016-05-28: 21; 2016-05-29: 21; 2016-05-30: 21; 2016-05-31: 21; 2016-06-01: 21; 2016-06-02: 21; 2016-06-04: 21; 2016-06-05: 21; 2016-06-06: 21; 2016-06-07: 21; 2016-06-08: 11; 2016-06-09: 11; 2016-06-11: 11; 2016-06-12: 11; 2016-06-13: 11; 2016-06-14: 11; 2016-06-15: 11; 2016-06-16: 28; 2016-06-18: 28; 2016-06-19: 28; 2016-06-20: 28; 2016-06-21: 28; 2016-06-22: 28; 2016-06-23: 28; 2016-06-25: 28; 2016-06-26: 28; 2016-06-27: 28; 2016-06-28: 28; 2016-06-29: 28; 2016-06-30: 28; 2016-07-02: 28; 2016-07-03: 28; 2016-07-04: 17; 2016-07-05: 17; 2016-07-06: 17; 2016-07-12: 17; 2016-07-13: 17; 2016-07-14: 17; 2016-07-16: 17; 2016-07-17: 17; 2016-07-18: 17; 2016-07-19: 17; 2016-07-20: 17; 2016-07-21: 17; 2016-07-23: 17; 2016-07-24: 17; 2016-07-25: 17
Subcon - Kitchen Equipment | 2016-03-02: 12; 2016-03-03: 15; 2016-03-05: 15; 2016-03-06: 15; 2016-03-07: 15; 2016-03-08: 15; 2016-03-09: 15; 2016-03-10: 15; 2016-03-12: 15; 2016-03-13: 15; 2016-03-14: 15; 2016-03-15: 15; 2016-03-16: 15; 2016-03-17: 15; 2016-03-19: 15; 2016-03-20: 3
Subcon - Swimming Pool Equipment | 2016-02-20: 10; 2016-02-21: 12; 2016-02-22: 12; 2016-02-23: 12; 2016-02-24: 12; 2016-02-25: 22; 2016-02-27: 24; 2016-02-28: 24; 2016-02-29: 24; 2016-03-01: 24; 2016-03-02: 14; 2016-03-03: 12; 2016-03-05: 12; 2016-03-06: 12; 2016-03-07: 12; 2016-03-08: 2
Subcon - Landscape | 2016-02-14: 5; 2016-02-15: 5; 2016-02-16: 13; 2016-02-17: 13; 2016-02-18: 13; 2016-02-20: 13; 2016-02-21: 13; 2016-02-22: 13; 2016-02-23: 13; 2016-02-24: 13; 2016-02-25: 15; 2016-02-27: 15; 2016-02-28: 19; 2016-02-29: 19; 2016-03-01: 19; 2016-03-02: 24; 2016-03-03: 24; 2016-03-05: 24; 2016-03-06: 24; 2016-03-07: 24; 2016-03-08: 24; 2016-03-09: 24; 2016-03-10: 24; 2016-03-12: 34; 2016-03-13: 34; 2016-03-14: 34; 2016-03-15: 34; 2016-03-16: 34; 2016-03-17: 34; 2016-03-18: 10; 2016-03-19: 34; 2016-03-20: 4; 2016-03-21: 4; 2016-03-22: 4; 2016-03-23: 4; 2016-03-24: 14; 2016-03-25: 10; 2016-03-26: 14; 2016-03-27: 14; 2016-03-28: 14; 2016-03-29: 14; 2016-03-30: 10; 2016-03-31: 20; 2016-04-01: 10; 2016-04-02: 20; 2016-04-03: 20; 2016-04-04: 20; 2016-04-05: 20; 2016-04-06: 20; 2016-04-07: 20; 2016-04-09: 10; 2016-04-10: 10; 2016-04-11: 10; 2016-04-12: 16; 2016-04-13: 16; 2016-04-14: 16; 2016-04-16: 16; 2016-04-17: 16; 2016-04-18: 16; 2016-04-19: 16; 2016-04-20: 16; 2016-04-21: 16; 2016-04-23: 16; 2016-04-24: 16; 2016-04-25: 16; 2016-04-26: 16; 2016-04-27: 16; 2016-04-28: 16; 2016-04-30: 16; 2016-05-01: 16; 2016-05-02: 16; 2016-05-03: 16; 2016-05-04: 16; 2016-05-05: 16; 2016-05-07: 16; 2016-05-08: 16; 2016-05-09: 16; 2016-05-10: 16; 2016-05-11: 16; 2016-05-12: 16; 2016-05-14: 16; 2016-05-15: 16; 2016-05-16: 16; 2016-05-17: 16; 2016-05-18: 16; 2016-05-19: 16; 2016-05-21: 16; 2016-05-22: 16; 2016-05-23: 16; 2016-05-24: 16; 2016-05-25: 16; 2016-05-26: 16; 2016-05-28: 16; 2016-05-29: 16; 2016-05-30: 16; 2016-05-31: 16; 2016-06-01: 16; 2016-06-02: 16; 2016-06-04: 16; 2016-06-05: 16; 2016-06-06: 16; 2016-06-07: 16; 2016-06-08: 16; 2016-06-09: 16; 2016-06-11: 16; 2016-06-12: 16; 2016-06-13: 16; 2016-06-14: 16; 2016-06-15: 16; 2016-06-16: 16; 2016-06-18: 16; 2016-06-19: 16; 2016-06-20: 16; 2016-06-21: 16; 2016-06-22: 16; 2016-06-23: 16; 2016-06-25: 16; 2016-06-26: 16; 2016-06-27: 16; 2016-06-28: 16; 2016-06-29: 16; 2016-06-30: 16; 2016-07-02: 16; 2016-07-03: 16; 2016-07-04: 16; 2016-07-05: 16; 2016-07-06: 16; 2016-07-12: 16; 2016-07-13: 18; 2016-07-14: 18; 2016-07-16: 18; 2016-07-17: 18; 2016-07-18: 18; 2016-07-19: 19; 2016-07-20: 19; 2016-07-21: 19; 2016-07-23: 19; 2016-07-24: 19; 2016-07-25: 37; 2016-07-26: 37; 2016-07-27: 37; 2016-07-28: 37; 2016-07-30: 37; 2016-07-31: 37; 2016-08-01: 37; 2016-08-02: 37; 2016-08-03: 37; 2016-08-04: 37; 2016-08-06: 30; 2016-08-07: 30; 2016-08-08: 30; 2016-08-09: 30; 2016-08-10: 30; 2016-08-11: 13; 2016-08-13: 13; 2016-08-14: 13; 2016-08-15: 13; 2016-08-16: 13; 2016-08-17: 13; 2016-08-18: 13; 2016-08-20: 13; 2016-08-21: 20; 2016-08-22: 20; 2016-08-23: 10; 2016-08-24: 10; 2016-08-25: 10; 2016-08-27: 10; 2016-08-28: 10; 2016-08-29: 10; 2016-08-30: 10; 2016-08-31: 10; 2016-09-01: 13; 2016-09-03: 13; 2016-09-04: 13; 2016-09-05: 13; 2016-09-06: 13; 2016-09-07: 3; 2016-09-13: 3; 2016-09-14: 3; 2016-09-15: 3; 2016-09-17: 3; 2016-09-18: 4; 2016-09-19: 4; 2016-09-20: 4; 2016-09-21: 4; 2016-09-22: 4; 2016-09-24: 4; 2016-09-25: 4; 2016-09-26: 4
Subcon - Irrigation | 2016-01-16: 20; 2016-01-17: 20; 2016-01-18: 20; 2016-01-19: 20; 2016-01-20: 20; 2016-01-21: 20; 2016-01-23: 20; 2016-01-24: 20; 2016-01-25: 20; 2016-01-26: 20; 2016-02-02: 10; 2016-02-03: 10; 2016-02-04: 10; 2016-02-06: 10; 2016-02-07: 10; 2016-02-08: 10; 2016-02-09: 10; 2016-02-10: 10; 2016-02-11: 10; 2016-02-13: 10; 2016-04-30: 10; 2016-05-01: 10; 2016-05-02: 10; 2016-05-03: 10; 2016-05-04: 10; 2016-05-05: 10; 2016-05-07: 10; 2016-05-08: 10; 2016-05-09: 10; 2016-05-10: 10; 2016-05-11: 10; 2016-05-12: 10; 2016-05-14: 10; 2016-05-15: 10; 2016-05-16: 10; 2016-05-17: 10; 2016-05-18: 10; 2016-05-19: 10; 2016-05-21: 12; 2016-05-22: 20; 2016-05-23: 20; 2016-05-24: 20; 2016-05-25: 20; 2016-05-26: 20; 2016-05-28: 20; 2016-05-29: 10; 2016-05-30: 20; 2016-05-31: 20; 2016-06-01: 20; 2016-06-02: 20; 2016-06-03: 10; 2016-06-04: 20; 2016-06-05: 20; 2016-06-06: 20; 2016-06-07: 20; 2016-06-08: 20; 2016-06-09: 20; 2016-06-11: 20; 2016-06-12: 20; 2016-06-13: 21; 2016-06-14: 26; 2016-06-15: 26; 2016-06-16: 30; 2016-06-18: 30; 2016-06-19: 30; 2016-06-20: 30; 2016-06-21: 20; 2016-06-22: 20; 2016-06-23: 20; 2016-06-25: 18; 2016-06-26: 8; 2016-06-27: 8; 2016-06-28: 8; 2016-06-29: 8; 2016-06-30: 8; 2016-07-02: 8; 2016-07-03: 8; 2016-07-04: 8; 2016-07-05: 8; 2016-07-06: 7; 2016-07-12: 2; 2016-07-13: 2; 2016-07-14: 2; 2016-07-16: 2; 2016-07-17: 2; 2016-07-18: 2; 2016-07-19: 2; 2016-07-20: 2; 2016-07-21: 2; 2016-07-23: 2

## Sheet3
Activity ID | Activity Name | Resource Name | time axis 2014-10-12 to 2016-10-09
PRELIMINARIES |  |  | 47671 | 138809 | 612326 | 798040 | 1084524 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 59589
PRE.PDBC.002 | Preliminaries for Contract Period | Running Cost | 47671 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 83425 | 59589
PRE.PDBC.009 | Taking Over of Site | Running Cost | 2014-11-09: 760000
PRE.PDBC.007 | Execution Temporary Site Facilities | Civil Materials | 2014-10-19: 55385; 2014-10-26: 64615; 2014-11-02: 64615; 2014-11-09: 55385
PRE.PDBC.008 | Submission of Performance Bond & Insurances | Civil Materials | 2014-10-26: 464286; 2014-11-02: 650000; 2014-11-09: 185714
C1-OFFICERS BUILDING-1 | [6 empty] | 2653 | 15919 | 15919 | 20733 | 18718 | 16468 | 24977 | 49534 | 92024 | 257161 | 204227 | 157810 | 153488 | 81069 | 178638 | 286447 | 200753 | 306450 | 178856 | 99168 | 155313 | 205776 | 363456 | 345155 | 376691 | 559816 | 617044 | 452621 | 616763 | 796700 | 738425 | 748528 | 862492 | 798091 | 779777 | 638349 | 529684 | 749348 | 642106 | 403986 | 505067 | 860354 | 318042 | 297005 | 415203 | 247561 | 376678 | 547533 | 807022 | 1194633 | 1300891 | 1565978 | 1887499 | 1959139 | 1962861 | 1855170 | 2095381 | 2154428 | 2013407 | 2145904 | 2258889 | 2607463 | 2592894 | 2681643 | 2683028 | 3215943 | 3075652 | 3641146 | 3285954 | 3041314 | 2510434 | 2174295 | 1695551 | 1697115 | 1856594 | 1792348 | 1661248 | 1456273 | 1238168 | 1133437 | 1051539 | 901613 | 779954 | 755098 | 620792 | 320693 | 144983 | 136353 | 130105 | 110476 | 75879 | 74054 | 36396 | 10963 | 43585 | 26593 | 24483
SUBSTRUCTURE WORK |  |  | 2014-11-09: 2653; 2014-11-16: 15919; 2014-11-23: 15919; 2014-11-30: 20733; 2014-12-07: 18718; 2014-12-14: 16468; 2014-12-21: 24977; 2014-12-28: 49534; 2015-01-04: 92024; 2015-01-11: 257161; 2015-01-18: 204227; 2015-01-25: 157810; 2015-02-01: 153488; 2015-02-08: 81069; 2015-02-15: 178638; 2015-02-22: 286447; 2015-03-01: 200753; 2015-03-08: 306450; 2015-03-15: 178856; 2015-03-22: 99168; 2015-03-29: 155313; 2015-04-05: 205776; 2015-04-12: 363456; 2015-04-19: 150518; 2015-04-26: 74919; 2015-05-03: 86814; 2015-05-10: 68209; 2015-05-17: 183429; 2015-05-24: 4740
CIVIL WORKS |  |  | 2014-11-09: 2653; 2014-11-16: 15919; 2014-11-23: 15919; 2014-11-30: 20733; 2014-12-07: 18718; 2014-12-14: 16468; 2014-12-21: 24977; 2014-12-28: 49534; 2015-01-04: 92024; 2015-01-11: 257161; 2015-01-18: 204227; 2015-01-25: 157810; 2015-02-01: 153488; 2015-02-08: 81069; 2015-02-15: 178638; 2015-02-22: 286447; 2015-03-01: 200753; 2015-03-08: 300168; 2015-03-15: 160011; 2015-03-22: 80322; 2015-03-29: 127829; 2015-04-05: 189286; 2015-04-12: 360315; 2015-04-19: 131673; 2015-04-26: 56074; 2015-05-03: 83674; 2015-05-10: 68209; 2015-05-17: 183429; 2015-05-24: 4740
AREA-1 (EARTHWORKS & CONCRETE WORKS) |  |  | 2014-11-09: 2653; 2014-11-16: 15919; 2014-11-23: 15919; 2014-11-30: 20733; 2014-12-07: 9874; 2014-12-14: 6017; 2014-12-21: 8657; 2014-12-28: 28792; 2015-01-04: 65145; 2015-01-11: 221123; 2015-01-18: 173706; 2015-01-25: 81300; 2015-02-01: 111970; 2015-02-08: 20678; 2015-02-15: 13327; 2015-02-22: 16552; 2015-03-01: 102465; 2015-03-08: 163919; 2015-03-15: 63925; 2015-03-22: 46622; 2015-03-29: 73701; 2015-04-05: 68941; 2015-04-12: 183429; 2015-04-19: 4740
EARTHWORK |  |  | 2014-11-09: 2653; 2014-11-16: 15919; 2014-11-23: 15919; 2014-11-30: 20733; 2014-12-07: 9874; 2014-12-14: 6017; 2014-12-21: 8657; 2014-12-28: 2640
SUB.A1.EW.03 | Preparation & Apply Termite Control below Footings at Area-1 | Civil Materials | 2014-12-21: 2640; 2014-12-28: 2640
SUB.A1.EW.02 | Disposal of Excavated Materials at Area-1 | Civil Materials | 2014-11-30: 4814; 2014-12-07: 7220; 2014-12-14: 6017; 2014-12-21: 6017
SUB.A1.EW.01 | Excavation for Area-1 up to bottom of Footings Blinding | Civil Materials | 2014-11-09: 2653; 2014-11-16: 15919; 2014-11-23: 15919; 2014-11-30: 15919; 2014-12-07: 2653
FOOTINGS & LIFT BASES |  |  | 2014-12-28: 26152; 2015-01-04: 65145; 2015-01-11: 221123; 2015-01-18: 151675
SUB.A1.FT.02 | Horizontal Rubberized above Blinding for Footings & Lift Bases | Civil Materials | 2014-12-28: 1098; 2015-01-04: 6588
SUB.A1.FT.01 | Blinding for Footings & Lift Bases | Civil Materials | 2014-12-28: 25054
SUB.A1.FT.04 | Shuttering for Footings & Lift Bases | Civil Materials | 2015-01-04: 14600; 2015-01-11: 29201; 2015-01-18: 4867
SUB.A1.FT.04 | Shuttering for Footings & Lift Bases | Civil Materials | 2015-01-04: 2352; 2015-01-11: 4705; 2015-01-18: 784
SUB.A1.FT.04 | Shuttering for Footings & Lift Bases | Civil Materials | 2015-01-04: 344; 2015-01-11: 689; 2015-01-18: 115
SUB.A1.FT.05 | Reinforcing Bars for Footings & Lift Bases | Civil Materials | 2015-01-04: 33929; 2015-01-11: 67859; 2015-01-18: 33929
SUB.A1.FT.05 | Reinforcing Bars for Footings & Lift Bases | Civil Materials | 2015-01-04: 3208; 2015-01-11: 6415; 2015-01-18: 3207
SUB.A1.FT.05 | Reinforcing Bars for Footings & Lift Bases | Civil Materials | 2015-01-04: 2842; 2015-01-11: 5685; 2015-01-18: 2842
SUB.A1.FT.06 | Pouring for Footings & Lift Bases | Civil Materials | 2015-01-11: 94248; 2015-01-18: 94248
SUB.A1.FT.06 | Pouring for Footings & Lift Bases | Civil Materials | 2015-01-11: 5940; 2015-01-18: 5940
SUB.A1.FT.06 | Pouring for Footings & Lift Bases | Civil Materials | 2015-01-11: 5742; 2015-01-18: 5742
SUB.A1.FT.03 | Polythene Sheet above Blinding for Footings & Lift Bases | Civil Materials | 2015-01-04: 1281; 2015-01-11: 641
NECK COLUMNS & SOLID BLOCKS |  |  | 2015-01-18: 22031; 2015-01-25: 81300; 2015-02-01: 111970; 2015-02-08: 12632
SUB.A1.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 7525; 2015-02-08: 3763
SUB.A1.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 9031; 2015-02-08: 4515
SUB.A1.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 896; 2015-02-08: 448
SUB.A1.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 1075; 2015-02-08: 537
SUB.A1.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 5375
SUB.A1.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 6450
SUB.A1.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-01-18: 5474; 2015-01-25: 16423; 2015-02-01: 5474
SUB.A1.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-01-18: 714; 2015-01-25: 2143; 2015-02-01: 714
SUB.A1.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-01-18: 1340; 2015-01-25: 4020; 2015-02-01: 1340
SUB.A1.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-01-18: 2372; 2015-01-25: 14232; 2015-02-01: 7116
SUB.A1.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-01-18: 455; 2015-01-25: 2732; 2015-02-01: 1366
SUB.A1.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-01-18: 2241; 2015-01-25: 13448; 2015-02-01: 6724
SUB.A1.NC.06 | Pouring for Neck Columns | Civil Materials | 2015-02-01: 25344
SUB.A1.NC.06 | Pouring for Neck Columns | Civil Materials | 2015-02-01: 3762
SUB.A1.NC.06 | Pouring for Neck Columns | Civil Materials | 2015-02-01: 9306
SUB.A1.NC.01 | Installation of Solid Block | Civil Materials | 2015-01-18: 9434; 2015-01-25: 28301; 2015-02-01: 9434
SUB.A1.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 4300
SUB.A1.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 6021; 2015-02-08: 3010
SUB.A1.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-01: 717; 2015-02-08: 358
AREA-2 (EARTHWORKS & CONCRETE WORKS) |  |  | 2014-12-07: 8844; 2014-12-14: 10451; 2014-12-21: 13666; 2014-12-28: 4822; 2015-01-04: 10959; 2015-01-11: 15305; 2015-01-18: 20647; 2015-01-25: 69290; 2015-02-01: 31424; 2015-02-08: 31109; 2015-02-15: 18896; 2015-02-22: 7979; 2015-03-01: 9124; 2015-03-08: 33732; 2015-03-15: 27316; 2015-03-22: 21002; 2015-03-29: 35805; 2015-04-05: 45201; 2015-04-12: 28153; 2015-04-19: 38323
EARTHWORK |  |  | 2014-12-07: 8844; 2014-12-14: 10451; 2014-12-21: 13666; 2014-12-28: 4822; 2015-01-04: 3444
SUB.A2.EW.02 | Disposal of Excavated Materials at Area-2 | Civil Materials | 2014-12-14: 1607; 2014-12-21: 4822; 2014-12-28: 4822; 2015-01-04: 804
SUB.A2.EW.03 | Preparation & Apply Termite Control below Footings at Area-2 | Civil Materials | 2015-01-04: 2640
SUB.A2.EW.01 | Excavation for Area-2 up to bottom of footings blinding | Civil Materials | 2014-12-07: 8844; 2014-12-14: 8844; 2014-12-21: 8844
FOOTINGS |  |  | 2015-01-04: 7516; 2015-01-11: 15305; 2015-01-18: 20647; 2015-01-25: 69290
SUB.A2.FT.02 | Horizontal Rubberized above Blinding for Footings | Civil Materials | 2015-01-11: 3844
SUB.A2.FT.06 | Pouring for Footings | Civil Materials | 2015-01-25: 41888
SUB.A2.FT.06 | Pouring for Footings | Civil Materials | 2015-01-25: 2640
SUB.A2.FT.06 | Pouring for Footings | Civil Materials | 2015-01-25: 2552
SUB.A2.FT.05 | Reinforcing Bars for Footings | Civil Materials | 2015-01-18: 11310; 2015-01-25: 18849
SUB.A2.FT.05 | Reinforcing Bars for Footings | Civil Materials | 2015-01-18: 1069; 2015-01-25: 1782
SUB.A2.FT.05 | Reinforcing Bars for Footings | Civil Materials | 2015-01-18: 947; 2015-01-25: 1579
SUB.A2.FT.01 | Blinding for Footings | Civil Materials | 2015-01-04: 7516; 2015-01-11: 5010
SUB.A2.FT.04 | Shuttering for Footings | Civil Materials | 2015-01-11: 4635; 2015-01-18: 6180
SUB.A2.FT.04 | Shuttering for Footings | Civil Materials | 2015-01-11: 747; 2015-01-18: 995
SUB.A2.FT.04 | Shuttering for Footings | Civil Materials | 2015-01-11: 109; 2015-01-18: 146
SUB.A2.FT.03 | Polythene Sheet above Blinding for Footings | Civil Materials | 2015-01-11: 960
NECK COLUMNS & SOLID BLOCKS |  |  | 2015-02-01: 31424; 2015-02-08: 31109; 2015-02-15: 16227
SUB.A2.NC.06 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 1693; 2015-02-15: 5080
SUB.A2.NC.06 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 168; 2015-02-15: 504
SUB.A2.NC.06 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 202; 2015-02-15: 605
SUB.A2.NC.06 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 1411; 2015-02-15: 4233
SUB.A2.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 2016; 2015-02-15: 672
SUB.A2.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 2419; 2015-02-15: 806
SUB.A2.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-02-01: 4055; 2015-02-08: 2028
SUB.A2.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-02-01: 529; 2015-02-08: 265
SUB.A2.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-02-01: 993; 2015-02-08: 496
SUB.A2.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-02-01: 2636; 2015-02-08: 2636
SUB.A2.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-02-01: 506; 2015-02-08: 506
SUB.A2.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-02-01: 2491; 2015-02-08: 2490
SUB.A2.NC.05 | Pouring for Neck Columns | Civil Materials | 2015-02-08: 5632
SUB.A2.NC.05 | Pouring for Neck Columns | Civil Materials | 2015-02-08: 836
SUB.A2.NC.05 | Pouring for Neck Columns | Civil Materials | 2015-02-08: 2068
SUB.A2.NC.01 | Installation of Solid Block | Civil Materials | 2015-02-01: 20215; 2015-02-08: 3369
SUB.A2.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 1612; 2015-02-15: 537
SUB.A2.NC.06 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 1129; 2015-02-15: 3386
SUB.A2.NC.06 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-02-08: 134; 2015-02-15: 403
AREA-3 (EARTHWORKS & CONCRETE WORKS) |  |  | 2014-12-21: 2653; 2014-12-28: 15919; 2015-01-04: 15919; 2015-01-11: 20733; 2015-01-18: 9874; 2015-01-25: 7220; 2015-02-01: 10094; 2015-02-08: 29281; 2015-02-15: 146415; 2015-02-22: 261916; 2015-03-01: 89164; 2015-03-08: 102517; 2015-03-15: 68770; 2015-03-22: 12698; 2015-03-29: 18323; 2015-04-05: 75144; 2015-04-12: 148733; 2015-04-19: 88610; 2015-04-26: 56074; 2015-05-03: 83674; 2015-05-10: 68209; 2015-05-17: 183429; 2015-05-24: 4740
EARTHWORK |  |  | 2014-12-21: 2653; 2014-12-28: 15919; 2015-01-04: 15919; 2015-01-11: 20733; 2015-01-18: 9874; 2015-01-25: 7220; 2015-02-01: 10094
SUB.A3.EW.03 | Preparation & Apply Termite Control below Footings at Area-3 | Civil Materials | 2015-02-01: 5280
SUB.A3.EW.01 | Excavation for Area-3 up to bottom of footings blinding | Civil Materials | 2014-12-21: 2653; 2014-12-28: 15919; 2015-01-04: 15919; 2015-01-11: 15919; 2015-01-18: 2653
SUB.A3.EW.02 | Disposal of Excavated Materials at Area-3 | Civil Materials | 2015-01-11: 4814; 2015-01-18: 7220; 2015-01-25: 7220; 2015-02-01: 4814
FOOTINGS & LIFT BASES |  |  | 2015-02-08: 29281; 2015-02-15: 146415; 2015-02-22: 261916; 2015-03-01: 26482
SUB.A3.FT.02 | Horizontal Rubberized above Blinding for Footings & Lift Bases | Civil Materials | 2015-02-08: 3843; 2015-02-15: 3843
SUB.A3.FT.01 | Blinding for Footings & Lift Bases | Civil Materials | 2015-02-08: 25054
SUB.A3.FT.04 | Shuttering for Footings & Lift Bases | Civil Materials | 2015-02-15: 29201; 2015-02-22: 19467
SUB.A3.FT.04 | Shuttering for Footings & Lift Bases | Civil Materials | 2015-02-15: 4705; 2015-02-22: 3136
SUB.A3.FT.04 | Shuttering for Footings & Lift Bases | Civil Materials | 2015-02-15: 689; 2015-02-22: 459
SUB.A3.FT.05 | Reinforcing Bars for Footings & Lift Bases | Civil Materials | 2015-02-15: 67859; 2015-02-22: 67859
SUB.A3.FT.05 | Reinforcing Bars for Footings & Lift Bases | Civil Materials | 2015-02-15: 6415; 2015-02-22: 6415
SUB.A3.FT.05 | Reinforcing Bars for Footings & Lift Bases | Civil Materials | 2015-02-15: 5685; 2015-02-22: 5684
SUB.A3.FT.06 | Pouring for Footings & Lift Bases | Civil Materials | 2015-02-15: 23562; 2015-02-22: 141372; 2015-03-01: 23562
SUB.A3.FT.06 | Pouring for Footings & Lift Bases | Civil Materials | 2015-02-15: 1485; 2015-02-22: 8910; 2015-03-01: 1485
SUB.A3.FT.06 | Pouring for Footings & Lift Bases | Civil Materials | 2015-02-15: 1436; 2015-02-22: 8613; 2015-03-01: 1436
SUB.A3.FT.03 | Polythene Sheet above Blinding for Footings & Lift Bases | Civil Materials | 2015-02-08: 384; 2015-02-15: 1538
NECK COLUMNS & SOLID BLOCKS |  |  | 2015-03-01: 62681; 2015-03-08: 102517; 2015-03-15: 62735
SUB.A3.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 5644; 2015-03-15: 5644
SUB.A3.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 6773; 2015-03-15: 6773
SUB.A3.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 672; 2015-03-15: 672
SUB.A3.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 806; 2015-03-15: 806
SUB.A3.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 3583; 2015-03-15: 1792
SUB.A3.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 4300; 2015-03-15: 2150
SUB.A3.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-03-01: 13686; 2015-03-08: 13686
SUB.A3.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-03-01: 1786; 2015-03-08: 1786
SUB.A3.NC.02 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-03-01: 3350; 2015-03-08: 3350
SUB.A3.NC.06 | Pouring for Neck Columns | Civil Materials | 2015-03-15: 25344
SUB.A3.NC.06 | Pouring for Neck Columns | Civil Materials | 2015-03-15: 3762
SUB.A3.NC.06 | Pouring for Neck Columns | Civil Materials | 2015-03-15: 9306
SUB.A3.NC.01 | Installation of Solid Block | Civil Materials | 2015-03-01: 23584; 2015-03-08: 23584
SUB.A3.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-03-01: 9488; 2015-03-08: 14232
SUB.A3.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-03-01: 1822; 2015-03-08: 2732
SUB.A3.NC.03 | Shuttering for Neck Columns | Civil Materials | 2015-03-01: 8966; 2015-03-08: 13448
SUB.A3.NC.04 | Rubberized Waterproofing for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 2867; 2015-03-15: 1433
SUB.A3.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 4516; 2015-03-15: 4515
SUB.A3.NC.05 | Hard Board Cover & Polythene Sheet for Footing, Neck Column & Solid Block | Civil Materials | 2015-03-08: 538; 2015-03-15: 537
F1-OFFICERS BUILDING-2 | [10 empty] | 22995 | 31957 | 45519 | 45519 | 46179 | 31083 | 12923 | 44302 | 122603 | 131427 | 256991 | 192618 | 98996 | 141069 | 17441 | 25819 | 75251 | 145390 | 173775 | 40832 | 100030 | 165498 | 127706 | 126336 | 395042 | 194549 | 219298 | 485579 | 514408 | 792861 | 95218 | 172418 | 42923 | 60454 | 228858 | 570376 | 621216 | 492843 | 438480 | 413246 | 523072 | 310712 | 158499 | 39331 | 38660 | 202574 | 284348 | 226814 | 208063 | 342507 | 519078 | 590388 | 660523 | 825270 | 679949 | 562529 | 839183 | 771572 | 838889 | 1017079 | 1395852 | 1628538 | 932523 | 736890 | 645963 | 680330 | 1658788 | 1813817 | 1980379 | 1678551 | 1159304 | 929024 | 838784 | 876483 | 711317 | 737605 | 986647 | 1242756 | 914431 | 431532 | 164198 | 176692 | 147088 | 128707 | 103819 | 101570 | 104854 | 87103 | 69388 | 29062 | 8270 | 6445 | 3080 | 6600 | 2200
SUBSTRUCTURE WORK |  |  | 2014-12-07: 22995; 2014-12-14: 31957; 2014-12-21: 45519; 2014-12-28: 45519; 2015-01-04: 46179; 2015-01-11: 31083; 2015-01-18: 12923; 2015-01-25: 44302; 2015-02-01: 122603; 2015-02-08: 131427; 2015-02-15: 256991; 2015-02-22: 192618; 2015-03-01: 98996; 2015-03-08: 141069; 2015-03-15: 17441; 2015-03-22: 25819; 2015-03-29: 75251; 2015-04-05: 145390; 2015-04-12: 173775; 2015-04-19: 40832; 2015-04-26: 100030; 2015-05-03: 165498; 2015-05-10: 127706; 2015-05-17: 126336; 2015-05-24: 304040
CIVIL WORKS |  |  | 2014-12-07: 22995; 2014-12-14: 31957; 2014-12-21: 45519; 2014-12-28: 45519; 2015-01-04: 46179; 2015-01-11: 31083; 2015-01-18: 12923; 2015-01-25: 44302; 2015-02-01: 122603; 2015-02-08: 131427; 2015-02-15: 256991; 2015-02-22: 192618; 2015-03-01: 98996; 2015-03-08: 141069; 2015-03-15: 17441; 2015-03-22: 25819; 2015-03-29: 75251; 2015-04-05: 145390; 2015-04-12: 168585; 2015-04-19: 34604; 2015-04-26: 95878; 2015-05-03: 165498; 2015-05-10: 127706; 2015-05-17: 126336; 2015-05-24: 304040
EARTHWORK |  |  | 2014-12-07: 22995; 2014-12-14: 31957; 2014-12-21: 45519; 2014-12-28: 45519; 2015-01-04: 46179; 2015-01-11: 31083; 2015-01-18: 12923; 2015-01-25: 1320
SUB.B2.EW.3 | Preparation & Termite Control for Blinding of Footing | Civil Materials | 2015-01-04: 660; 2015-01-11: 3960; 2015-01-18: 3960; 2015-01-25: 1320
SUB.B2.EW.1 | Excavation for up to bottom of Blinding for Footings | Civil Materials | 2014-12-07: 22995; 2014-12-14: 22995; 2014-12-21: 27594; 2014-12-28: 27594; 2015-01-04: 27594; 2015-01-11: 9198
SUB.B2.EW.2 | Disposal of Excavated Materials | Civil Materials | 2014-12-14: 8963; 2014-12-21: 17926; 2014-12-28: 17926; 2015-01-04: 17926; 2015-01-11: 17926; 2015-01-18: 8963
FOOTINGS |  |  | 2015-01-25: 37985; 2015-02-01: 79291; 2015-02-08: 80221; 2015-02-15: 196156
SUB.B2.FT.01 | Blinding for Footings | Concrete Pump
SUB.B2.FT.01 | Blinding for Footings | Civil Materials | 2015-01-25: 27483; 2015-02-01: 9161
SUB.B2.FT.04 | Shuttering for Footings | Civil Materials | 2015-02-01: 25240; 2015-02-08: 30288
SUB.B2.FT.04 | Shuttering for Footings | Civil Materials | 2015-02-01: 1120; 2015-02-08: 1344
SUB.B2.FT.05 | Reinforcing Bars for Footings | Civil Materials | 2015-02-01: 713; 2015-02-08: 1069; 2015-02-15: 356
SUB.B2.FT.05 | Reinforcing Bars for Footings | Civil Materials | 2015-02-01: 31680; 2015-02-08: 47520; 2015-02-15: 15840
SUB.B2.FT.06 | Pouring for Footings | Civil Materials | 2015-02-15: 176000
SUB.B2.FT.06 | Pouring for Footings | Civil Materials | 2015-02-15: 3960
SUB.B2.FT.02 | Horizontal Rubberized Waterproofing above Blinding for Footings | Civil Materials | 2015-01-25: 10502; 2015-02-01: 7001
SUB.B2.FT.03 | Polythene Sheet above Blinding for Footings | Civil Materials | 2015-02-01: 4376
SWIMMING POOL SLAB & BALANCE TANK |  |  | 2015-01-25: 4997; 2015-02-01: 43312; 2015-02-08: 51206; 2015-02-15: 30365; 2015-02-22: 98781
SUB.B2.SPS.01 | Blinding for Swimming Pool Slab & Balance Tank | Civil Materials | 2015-01-25: 4997; 2015-02-01: 24984
SUB.B2.SPS.05 | Reinforcing Bars for Swimming Pool Slab & Balance Tank | Civil Materials | 2015-02-08: 15183; 2015-02-15: 30365; 2015-02-22: 5061
SUB.B2.SPS.06 | Pouring for Swimming Pool Slab & Balance Tank | Civil Materials | 2015-02-22: 93720
SUB.B2.SPS.02 | Horizontal Rubberized Waterproofing for Swimming Pool Slab & Balance Tank | Civil Materials | 2015-02-01: 5834
SUB.B2.SPS.04 | Screed Works above Blinding for Swimming Pool Slab & Balance Tank | Civil Materials | 2015-02-01: 11765; 2015-02-08: 35294
SUB.B2.SPS.03 | Polytene Sheet for Swimming Pool Slab & Balance Tank | Civil Materials | 2015-02-01: 730; 2015-02-08: 730
SWIMMING POOL WALL & BALANCE TANK |  |  | 2015-02-22: 28521; 2015-03-01: 48264; 2015-03-08: 47406
SUB.B2.SPW.1 | Reinforcing Bars for Swimming Pool Walls & Balance Tank | Civil Materials | 2015-02-22: 11704; 2015-03-01: 14630
SUB.B2.SPW.2 | Shuttering for Swimming Pool Walls & Balance Tank | Civil Materials | 2015-02-22: 16817; 2015-03-01: 33634; 2015-03-08: 5606
SUB.B2.SPW.3 | Pouring for Swimming Pool Walls & Balance Tank | Civil Materials | 2015-03-08: 41800
NECK COLUMNS & SOLID BLOCKS |  |  | 2015-02-15: 30469; 2015-02-22: 65317; 2015-03-01: 50733; 2015-03-08: 90756
SUB.B2.NC.01 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-02-15: 6757; 2015-02-22: 11261
SUB.B2.NC.01 | Reinforcing Bars for Neck Columns | Civil Materials | 2015-02-15: 912; 2015-02-22: 1519
SUB.B2.NC.04 | Pouring for Neck Columns | Civil Materials | 2015-03-01: 3960
SUB.B2.NC.04 | Pouring for Neck Columns | Civil Materials | 2015-03-01: 28600
SUB.B2.NC.03 | Installation of Solid Block | Civil Materials | 2015-02-15: 6934; 2015-02-22: 20803; 2015-03-01: 6934
SUB.B2.NC.02 | Shuttering for Neck Columns | Civil Materials | 2015-02-15: 14282; 2015-02-22: 28565; 2015-03-01: 4761
SUB.B2.NC.02 | Shuttering for Neck Columns | Civil Materials | 2015-02-15: 1584; 2015-02-22: 3168; 2015-03-01: 528
SUB.B2.NC.05 | Rubberized Waterproofing & Polythene Sheet for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-01: 952; 2015-03-08: 4760
SUB.B2.NC.05 | Rubberized Waterproofing & Polythene Sheet for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-01: 1269; 2015-03-08: 6347
SUB.B2.NC.05 | Rubberized Waterproofing & Polythene Sheet for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-01: 952; 2015-03-08: 4760
SUB.B2.NC.05 | Rubberized Waterproofing & Polythene Sheet for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-01: 1587; 2015-03-08: 7933
SUB.B2.NC.05 | Rubberized Waterproofing & Polythene Sheet for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-01: 397; 2015-03-08: 1983
SUB.B2.NC.05 | Rubberized Waterproofing & Polythene Sheet for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-01: 238; 2015-03-08: 1190
SUB.B2.NC.05 | Rubberized Waterproofing & Polythene Sheet for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-01: 317; 2015-03-08: 1586
SUB.B2.NC.05 | Rubberized Waterproofing & Polythene Sheet for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-01: 238; 2015-03-08: 1190
SUB.B2.NC.06 | Hard Board Cover for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-08: 15252
SUB.B2.NC.06 | Hard Board Cover for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-08: 15252
SUB.B2.NC.06 | Hard Board Cover for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-08: 15252
SUB.B2.NC.06 | Hard Board Cover for Footings, Solid Block, Pool, Tank & Neck Columns | Civil Materials | 2015-03-08: 15252

## Sheet1
Activity ID | Activity Name | Start | Finish | Resource Name | Budgeted Cost | Spreadsheet Field | time axis 2014-10-12 to 2016-10-09
CONSTRUCTION, COMPLETION & MAINTENANCE OF OFFICER'S BUILDING 1&2 AT BARZAN CAMP |  | 15-Oct-14 A | 2016-10-13 |  | 142221534 | Budgeted Cost | 45808.22 | 98625.92 | 144779.77 | 144779.77 | 1001922.63 | 1307856.69 | 440709.53 | 101389.98 | 101946.02 | 99242.47 | 107688.73 | 143518.65 | 165527.85 | 272470.38 | 407521.31 | 251602.5 | 274046.92 | 296237.96 | 355499.08 | 307344.49 | 276062.07 | 316609.35 | 159536.78 | 158277.81 | 106492.28 | 249209.66 | 164513.89 | 182737.79 | 304947.43 | 358920.41 | 283773.59 | 389589.68 | 309899.98 | 563205.33 | 416111.76 | 460683.7 | 547797.48 | 316488.5 | 320862.16 | 224390.05 | 229881.53 | 421547.15 | 517935.91 | 524304.23 | 497614.74 | 546478.62 | 607243.46 | 689472.15 | 445202.55 | 551576.66 | 564277.1 | 762616.9 | 1165244.23 | 1600819.98 | 1565129.03 | 1430043.46 | 1620274.54 | 1847791.74 | 1542471.1 | 1548548.09 | 1977559.5 | 2200552.31 | 2317423.01 | 2454830.61 | 2959593.44 | 4866809.74 | 4505032.17 | 3952426.94 | 5448956.03 | 5385659.63 | 5009673.59 | 4605550.15 | 4239264.27 | 5541464.2 | 6008507.79 | 4840463.59 | 4140554.69 | 4103139.54 | 4245019.35 | 4561888.88 | 4232052.82 | 3456283 | 2295461.49 | 1759259.75 | 2881573.43 | 3167398.98 | 2370329.99 | 2014820.07 | 1659590.48 | 1004151.43 | 372766.07 | 361801.54 | 486247.83 | 423931.08 | 276012.94 | 256274.35 | 204251.43 | 155544.4 | 113565.7 | 102582.52 | 97260.52 | 90213.98 | 81264.38 | 80164.38 | 57260.27
CONSTRUCTION, COMPLETION & MAINTENANCE OF OFFICER'S BUILDING 1&2 AT BARZAN CAMP |  | 15-Oct-14 A | 2016-10-13 |  | 142221534 | Cum Budgeted Cost | 45808.22 | 144434.14 | 289213.91 | 433993.68 | 1435916.3 | 2743772.99 | 3184482.52 | 3285872.5 | 3387818.52 | 3487060.99 | 3594749.72 | 3738268.37 | 3903796.22 | 4176266.61 | 4583787.91 | 4835390.41 | 5109437.33 | 5405675.29 | 5761174.37 | 6068518.86 | 6344580.92 | 6661190.27 | 6820727.06 | 6979004.87 | 7085497.15 | 7334706.81 | 7499220.7 | 7681958.49 | 7986905.92 | 8345826.33 | 8629599.92 | 9019189.6 | 9329089.58 | 9892294.91 | 10308406.67 | 10769090.37 | 11316887.85 | 11633376.34 | 11954238.5 | 12178628.56 | 12408510.09 | 12830057.23 | 13347993.14 | 13872297.38 | 14369912.12 | 14916390.74 | 15523634.2 | 16213106.35 | 16658308.9 | 17209885.56 | 17774162.66 | 18536779.56 | 19702023.79 | 21302843.77 | 22867972.8 | 24298016.26 | 25918290.8 | 27766082.54 | 29308553.64 | 30857101.72 | 32834661.22 | 35035213.54 | 37352636.55 | 39807467.16 | 42767060.6 | 47633870.34 | 52138902.52 | 56091329.45 | 61540285.48 | 66925945.11 | 71935618.71 | 76541168.86 | 80780433.12 | 86321897.32 | 92330405.11 | 97170868.7 | 101311423.39 | 105414562.93 | 109659582.28 | 114221471.16 | 118453523.98 | 121909806.99 | 124205268.48 | 125964528.23 | 128846101.66 | 132013500.64 | 134383830.63 | 136398650.7 | 138058241.17 | 139062392.61 | 139435158.67 | 139796960.22 | 140283208.05 | 140707139.13 | 140983152.07 | 141239426.42 | 141443677.85 | 141599222.25 | 141712787.95 | 141815370.46 | 141912630.98 | 142002844.96 | 142084109.35 | 142164273.73 | 142221534
No Type of work-8 |  | 08-Nov-14 A | 2016-03-08 |  | 0 | Budgeted Cost
No Type of work-8 |  | 08-Nov-14 A | 2016-03-08 |  | 0 | Cum Budgeted Cost