## Dashboard
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
PROJECT NAME - MIDREX TOLEDO HBI, OHIO USA | [10 empty] | CLIENT NAME - MIDREX INT | [6 empty] | STEEL CONTRACTOR - WH | [6 empty] | DATE | 2018-02-15
PROJECT SUMMARY |  |  |  | PROGRESS CURVE | [13 empty] | CURRENT PROGRESS
Contract Commencement |  | 2017-01-01 | [15 empty] | 1
Contract Completion |  | 2017-12-30 | [15 empty] | 2
Contract Duration |  | 345 | [15 empty] | 3
Elapsed Duration |  | 150 | [15 empty] | 4
Remaining Duration |  | 195 | [15 empty] | 5
Planned Progress (%) |  | 43% | [15 empty] | 6
Actual Progress (%) |  | 48% | [15 empty] | 7
Variation (%) |  | -5% | [15 empty] | 8
Slippage to Baseline |  | -14 | [15 empty] | 9
Forecast Completion | [17 empty] | 10
PROJECT SUMMARY |  |  |  | RESOURCE HISTOGRAM | [13 empty] | CRITICAL ISSUE
PROJECT STATUS | [17 empty] | 1
2
3
4
5
TIME CHART | [17 empty] | 6
7
8
9
10
TECHNICAL SUBMITALS SUMMARY | [6 empty] | PROGRESS PHOTO'S
Description | Total | Planned till date | Submitted till date | Approved | Rejected | Under Review
Prequalification | 24 | 0 | 0 | 0 | 0 | 0
Materials | 67 | 0 | 0 | 0 | 0 | 0
Shop Drawings | 112 | 0 | 0 | 0 | 0 | 0
RFI'S & NCR
Description | Raised |  | Replied |  | Status
RFI
NCR

## Project Summary
Progress Curve
Contract Commencement | 2017-01-01 | Month | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01
Contract Completion | 2017-12-30 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract Duration | 345 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elapsed Duration | 150 | Planned Cum. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Duration | 195 | Actual Cum. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned Progress (%) | 43%
Actual Progress (%) | 48%
Variation (%) | -5%
Slippage to Baseline | -14 | Resource Histogram
Forecast Completion |  | Month | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01
|  | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Planned Cum. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Cum. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elapsed Dur % | 0.2205%
Remaining Dur % | 0.2462%
Planned Progress (%) | 43%
Actual Progress (%) | 48%
345
150
195
Planned Progress (%) | 0%
Actual Progress (%) | 0%
Variation (%) | 0%
Slippage to Baseline | 14

## Daily Manpower
Date | Steel Fixer | Carpenter | Mason | Welder | Helper | Rigger | Electrician | Plumber | Painter | Guinter | Waterproof Tech. | Actual | Plan
2017-01-01
2017-01-02
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07
2017-01-08
2017-01-09
2017-01-10
2017-01-11
2017-01-12
2017-01-13
2017-01-14
2017-01-15
2017-01-16
2017-01-17
2017-01-18
2017-01-19
2017-01-20
2017-01-21
2017-01-22
2017-01-23
2017-01-24
2017-01-25
2017-01-26
2017-01-27
2017-01-28
2017-01-29
2017-01-30
2017-01-31 | [11 empty] | 0 | 0
2017-02-01
2017-02-02
2017-02-03
2017-02-04
2017-02-05
2017-02-06
2017-02-07
2017-02-08
2017-02-09
2017-02-10
2017-02-11
2017-02-12
2017-02-13
2017-02-14
2017-02-15
2017-02-16
2017-02-17
2017-02-18
2017-02-19
2017-02-20
2017-02-21
2017-02-22
2017-02-23
2017-02-24
2017-02-25
2017-02-26
2017-02-27
2017-02-28 | [11 empty] | 0 | 0
2017-03-01
2017-03-02
2017-03-03
2017-03-04
2017-03-05
2017-03-06
2017-03-07
2017-03-08
2017-03-09
2017-03-10
2017-03-11
2017-03-12
2017-03-13
2017-03-14
2017-03-15
2017-03-16
2017-03-17
2017-03-18
2017-03-19
2017-03-20
2017-03-21
2017-03-22
2017-03-23
2017-03-24
2017-03-25
2017-03-26
2017-03-27
2017-03-28
2017-03-29
2017-03-30
2017-03-31 | [11 empty] | 0
2017-04-01
2017-04-02
2017-04-03
2017-04-04
2017-04-05
2017-04-06
2017-04-07
2017-04-08
2017-04-09
2017-04-10
2017-04-11
2017-04-12
2017-04-13
2017-04-14
2017-04-15
2017-04-16
2017-04-17
2017-04-18
2017-04-19
2017-04-20
2017-04-21
2017-04-22
2017-04-23
2017-04-24
2017-04-25
2017-04-26
2017-04-27
2017-04-28
2017-04-29
2017-04-30 | [11 empty] | 0
2017-05-01
2017-05-02
2017-05-03
2017-05-04
2017-05-05
2017-05-06
2017-05-07
2017-05-08
2017-05-09
2017-05-10
2017-05-11
2017-05-12
2017-05-13
2017-05-14
2017-05-15
2017-05-16
2017-05-17
2017-05-18
2017-05-19
2017-05-20
2017-05-21
2017-05-22
2017-05-23
2017-05-24
2017-05-25
2017-05-26
2017-05-27
2017-05-28
2017-05-29
2017-05-30
2017-05-31 | [11 empty] | #DIV/0!
2017-06-01
2017-06-02
2017-06-03
2017-06-04
2017-06-05
2017-06-06
2017-06-07
2017-06-08
2017-06-09
2017-06-10
2017-06-11
2017-06-12
2017-06-13
2017-06-14
2017-06-15
2017-06-16
2017-06-17
2017-06-18
2017-06-19
2017-06-20
2017-06-21
2017-06-22
2017-06-23
2017-06-24
2017-06-25
2017-06-26
2017-06-27
2017-06-28
2017-06-29
2017-06-30 | [11 empty] | #DIV/0!
2017-07-01
2017-07-02
2017-07-03
2017-07-04
2017-07-05
2017-07-06
2017-07-07
2017-07-08
2017-07-09
2017-07-10
2017-07-11
2017-07-12
2017-07-13
2017-07-14
2017-07-15
2017-07-16
2017-07-17
2017-07-18
2017-07-19
2017-07-20
2017-07-21
2017-07-22
2017-07-23
2017-07-24
2017-07-25
2017-07-26
2017-07-27
2017-07-28
2017-07-29
2017-07-30
2017-07-31 | [11 empty] | #DIV/0!
2017-08-01
2017-08-02
2017-08-03
2017-08-04
2017-08-05
2017-08-06
2017-08-07
2017-08-08
2017-08-09
2017-08-10
2017-08-11
2017-08-12
2017-08-13
2017-08-14
2017-08-15
2017-08-16
2017-08-17
2017-08-18
2017-08-19
2017-08-20
2017-08-21
2017-08-22
2017-08-23
2017-08-24
2017-08-25
2017-08-26
2017-08-27
2017-08-28
2017-08-29
2017-08-30
2017-08-31 | [11 empty] | #DIV/0!
2017-09-01
2017-09-02
2017-09-03
2017-09-04
2017-09-05
2017-09-06
2017-09-07
2017-09-08
2017-09-09
2017-09-10
2017-09-11
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16
2017-09-17
2017-09-18
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23
2017-09-24
2017-09-25
2017-09-26
2017-09-27
2017-09-28
2017-09-29
2017-09-30 | [11 empty] | #DIV/0!
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09
2017-10-10
2017-10-11
2017-10-12
2017-10-13
2017-10-14
2017-10-15
2017-10-16
2017-10-17
2017-10-18
2017-10-19
2017-10-20
2017-10-21
2017-10-22
2017-10-23
2017-10-24
2017-10-25
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31 | [11 empty] | #DIV/0!
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30 | [11 empty] | #DIV/0!
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31 | [11 empty] | #DIV/0!
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31 | [11 empty] | #DIV/0!
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28 | [11 empty] | #DIV/0!
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31 | [11 empty] | #DIV/0!
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30 | [11 empty] | #DIV/0!
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30
2018-05-31 | [11 empty] | #DIV/0!
2018-06-01
2018-06-02
2018-06-03
2018-06-04
2018-06-05
2018-06-06
2018-06-07
2018-06-08
2018-06-09
2018-06-10
2018-06-11
2018-06-12
2018-06-13
2018-06-14
2018-06-15
2018-06-16
2018-06-17
2018-06-18
2018-06-19
2018-06-20
2018-06-21
2018-06-22
2018-06-23
2018-06-24
2018-06-25
2018-06-26
2018-06-27
2018-06-28
2018-06-29
2018-06-30 | [11 empty] | #DIV/0!
2018-07-01
2018-07-02
2018-07-03
2018-07-04
2018-07-05
2018-07-06
2018-07-07
2018-07-08
2018-07-09
2018-07-10
2018-07-11
2018-07-12
2018-07-13
2018-07-14
2018-07-15
2018-07-16
2018-07-17
2018-07-18
2018-07-19
2018-07-20
2018-07-21
2018-07-22
2018-07-23
2018-07-24
2018-07-25
2018-07-26
2018-07-27
2018-07-28
2018-07-29
2018-07-30
2018-07-31 | [11 empty] | #DIV/0!
2018-08-01
2018-08-02
2018-08-03
2018-08-04
2018-08-05
2018-08-06
2018-08-07
2018-08-08
2018-08-09
2018-08-10
2018-08-11
2018-08-12
2018-08-13
2018-08-14
2018-08-15
2018-08-16
2018-08-17
2018-08-18
2018-08-19
2018-08-20
2018-08-21
2018-08-22
2018-08-23
2018-08-24
2018-08-25
2018-08-26
2018-08-27
2018-08-28
2018-08-29
2018-08-30
2018-08-31 | [11 empty] | 0
2018-09-01
2018-09-02
2018-09-03
2018-09-04
2018-09-05
2018-09-06
2018-09-07
2018-09-08
2018-09-09
2018-09-10
2018-09-11
2018-09-12
2018-09-13
2018-09-14
2018-09-15
2018-09-16
2018-09-17
2018-09-18
2018-09-19
2018-09-20
2018-09-21
2018-09-22
2018-09-23
2018-09-24
2018-09-25
2018-09-26
2018-09-27
2018-09-28
2018-09-29
2018-09-30 | [11 empty] | 0