## Monthly Dashboard Report
| Engineering Enterprises MONTHLY PROJECT DASHBOARD | [15 empty] | Doc. No. |  | REE/OPR/05
[17 empty] | Rev.: |  | 0
[17 empty] | Date: |  | 2016-03-31
Project: | AL JASASSIYA SOUTH HOUSE PROJECT (PROJECT #R67-M1-15) | [15 empty] | Report for the Month of: |  | 2016-03-31
Client: | PRIVATE ENGINEERING OFFICE | [7 empty] | Consultant: |  | M/S DORSCH QATAR |  |  |  | Main Contractor |  | URBACON TRADING & CONTRACTING
1. Schedule | [9 empty] | 7. Scope Management
Program Details | Plan Start | Completion Date |  | Plan % | Actual % | Variance % | Target (Next Month) |  |  | Current Scope Value (CSV) |  |  | Expected Contract Value |  |  | Project Revenue
|  | Plan | Projected
MEP Base Line | 2015-03-23 | 2015-11-30 | 2016-05-28 | 100% | 94.95% | -5.05% | 98.5% |  |  | Original Contract Value |  | 49200000 | Current Scope Value |  | 52051338.9626 | Planned Claim upto this month |  |  | 49354913.84
MEP Revised | 2015-03-23 | 2016-02-24 | 2016-05-28 | 100% | 94.95% | -5.05% | 98.5% |  |  | B O Q Adjustment (Revised BOQ) |  | 0 | Exp. Re-measured Qty |  |  | Actual Claim (EV) upto this month |  |  | 44408504.4651
[10 empty] | Approved Variations |  | 154913.84 | Variations Awaiting Approval (not Under Execution) |  | 0 | Certified |  |  | 40992023.6433
[10 empty] | Approved Deletions |  | 0 | EOT- (Submitted) |  |  | Planned Claim of this month |  |  | 154913.84
[10 empty] | Additions due to re- measurement |  | 0 | Expected New Variations (not Under Execution) |  | 0 | Actual Claim of this month |  |  | 3416480.8218
VO Scope | [9 empty] | Variations under execution & awaiting Approval |  | 2696425.1226 | Expected back charges |  | 0
Variance Analysis | [9 empty] | Total (QAR) |  | 52051338.9626 | Total (QAR) |  | 52051338.9626
2. Engineering | [9 empty] | 8. HSE - Health Safety Environment
| Total | Plan-Approval | Actual-Approval |  | Rejected | Under Review | Balance to Submit | EDC to 100% Approval | [5 empty] | Man-Hours Worked | Man-Hours without LTI | Man-Hours without LTA | First Aid Case | Major Injuries | Medical Case
Design Drawings | [9 empty] | This Month |  |  |  | 51440 | 51440 | 51440 | 3 | 0 | 5
Shop Drawings | 514 | 514 | 514 | 100% | 0 | 0 | 0 |  |  | Till Last Month |  |  |  | 11380000 | 11380000 | 11380000 | 39 | 0 | 36
[10 empty] | Total |  |  |  | 11431440 | 11431440 | 11431440 | 42 | 0 | 41
3. Procurement | [9 empty] | 9. Cost Control
Material Submission |  |  | Material Purchase Order |  |  | Material Delivery | [6 empty] | BAC- Budget At Completion (Including under execution) |  | AC- Actual Cost | ETC- Estimate To Complete | EAC-Estimate At Completion = ETC+AC | Expected Gross Profit/ Loss
[13 empty] | Original Contract | VO + Add. Qty |  |  |  | CSV - EAC
Total |  | 109 | Total |  | 109 | Total |  | 109 |  | Material |  |  | 25830769 | 1123129.3772 | 26667132 | 260000 | 26927132 | CSV | 52051338.9626
Plan-Approval |  | 109 | Plan - PO's |  | 109 | Plan-Delivery |  | 109 |  | Labour |  |  | 6180000 | 1306043.654 | 14217600.26 | 514800 | 14732400.26 | EAC | 49996901.7
Actual-Approval |  | 109 | PR-Released |  | 109 | Actual-Delivered |  | 109 |  | Preliminaries/ Staff |  |  | 6222000 | 222829.5916 | 3721391.28 | 150000 | 3871391.28
|  |  | Actual- PO's |  | 109 | Delivery-Confirmed |  | 109 |  | Sub-contract/Site Over Head |  |  | 2434887.28 |  | 3315978.16 | 150000 | 3465978.16
Variance |  | 0 | Variance |  | 0 | Variance |  | 0 |  | Total -Budget |  |  | 40667656.28 | 2652002.6228 | 47922101.7 | 1074800 | 48996901.7
Expected Date to 100% Approval | [9 empty] | <Back Charges/ Scope Deleation> (if any) | [5 empty] | 1000000 | 1000000
[10 empty] | G. Total Budget (QAR) |  |  |  | 43319658.9028 | 47922101.7 | 2074800 | 49996901.7 | 3.947% | 2054437.2626
4. QA/ QC | [9 empty] | 10. Resources
Inspection By the Engineer |  |  |  |  | NCR- Non Conformance Report | [6 empty] | Manpower (This Month) |  |  | Man Hours (Cumulative) |  |  | Mob/ DE Mob Plan (Next Month)
| Installation Inspection |  | Material Inspection |  |  |  | Internal | External |  |  |  | Plan | Actual | Variance | Plan | Actual | Variance | Mobilization | Demobilization
Total | 1131 |  | 57 |  | Total-Received |  | 0 | 29 |  | Staff |  | 15 | 10 | -5 |  | 74776 | -74776 |  | 4
Approved | 672 | 59.42% | 57 | 100% | Closed |  | 0 | 11 |  | Manpower |  | 40 | 141 | -101 | 9490000 | 11348124 | -1858124 |  | 65
Open | 407 | 35.99% | 0 | 0% | Open |  | 0 | 18 |  | Sub Con. | [5 empty] | 0 |  |  | 0
Rejected | 52 | 4.598% | 0 | 0%
5. Construction |  |  |  | 6. Areas of Concern | [5 empty] | 11. Close-out
Milestones and Major Ongoing Activities Status |  |  |  | Areas of Concern (Critical only) | [6 empty] | Installation Inspection | Material Inspection | Red Line Drw | As-Built | T&C Procedure | O&M Manual | Training Manual | Warranties | Spare Parts
Testing & Commissioning of Fire fighting system in progress. |  |  |  | Delivery of Emergency lights for staircase in Palace, chalets & Ancillary buildings | [5 empty] | Total | 1131 | 64 |  | 457 | 15 | 21
Pretesting of HVAC Equipment in progress |  |  |  | Delivery of wiring devices | [5 empty] | Submitted | 1131 | 25 |  | 17 | 15 | 0
Testing & Commissioning of Electrical Equipment in progress |  |  |  | Civil clearance for Bath Tub Installation in Chalets | [5 empty] | Approved (A) | 672 | 25 |  | 0 | 14 | 0
Pretesting of panels in progress. |  |  |  | Doors & Windows Installation are delaying | [5 empty] | Handed Over
Installation of Wiring Devices & Light Fixture in Palace & Chalets. | [9 empty] | Exp. Date to Complete
Isolator Installation & termination for equipment in progress | [9 empty] | Sub-Con.
Sanitary ware installation in chalet & palace in progress | [9 empty] | Total
Grills & Diffuser Installation in palace in progress parallel with civil. | [9 empty] | Submitted
Approved
Handed Over
Exp. Date to Complete
Remarks
Prepared by: Mehsan Muhmmed |  | Project Manager |  | Mohanned Hanna |  |  | Date: | 2016-03-31 | Reviewed by: |  |  | Operations Director |  |  | Name: Signature: |  |  | Date:
Formulas:
PRIVATE ENGINEERING OFFICE = +[PRIVATE ENGINEERING OFFICE, row above]

## Cover
Doc. No.: | REE/OPR/05
Rev.: | 0
Date: | 2016-03-31
AL JASASSIYA SOUTH HOUSE PROJECT
Proejct # R67-M1-15
Client:
PRIVATE ENGINEERING OFFICE (PEO)
Consultant:
M/S DORSCH QATAR
Main Contractor:
M/S UCC
In house Sub Contractor:
Consolidated Engineering System CO. W.L.L (CESCO)
Al Mana Networks Solutions & Security Services
Asian Insulation Co.

## Index
INDEX
1 | 1 |  |  | Executive Project Summary
2 | 2 |  |  | Schedule
§ Program
§ Progress
2 | 3 |  |  | Engineering
§ Shop Drawings
§ Technical Queries (TQ/ SCR/ RFI )
3 | 4 |  |  | Procurement
§ Material Submittals
§ Material Purchase Orders
|  | 4.1 |  | § Logs
|  | 4.12 |  | § Long Lead Tracking
4 | 5 |  |  | QA/QC Status
§ Material Inspection
§ Installation Inspection
§ Non-conformance Report
5 | 6 |  |  | Construction
§ Progress Accomplished This Month (Major Activities only)
§ One Month Look Ahead Plan (Major Activities only)
§ Progress S-Curve
§ Site Photos
6 | 7 |  |  | Commercial
|  | 7.1 |  | § Payment Application Detail
|  | 7.2 |  | § Scope Management Matrix (VO)
|  | 7.3 |  | § Sub-contractor
|  | 7.4 |  | § 7.4-Back Chargs detail
7 | 8 |  |  | HSE - Report
§ HSE Report
§ PPE Update
8 | 9 |  |  | Earned Value Management
§ Budget / Cost Comparison
§ ETC - Estimate to Complete + EAC -Estimate At Completion
9 | 10 |  |  | Resources
§ Man-hours
§ STB Update
§ Histogram
10 | 11 |  |  | Accounts
11 | 12 |  |  | Store
12 | 13 |  |  | Areas of Concern
13 | 14 |  |  | Close-out

## 1-Executive Project Summary
EXECUTIVE PROJECT SUMMARY - R67-M1-15
Project Name |  |  | Project Scope | Report Date
AL JASASSIYA SOUTH HOUSE PROJECT |  |  | MEP | 2016-03-31
Project Overview
The project is a palace on a beautiful site to the north of Qatar. The project consist of Palace, 6 No of Chalets, Main Gate, Service Gate, Staff Quarter, Main Kitchen and Garage, Service Yard, Horse Stable, Covered Traces and External Works.
1:Progress/Schedule:
MEP Over all progress is 94.95% as of 31-Mar-16 against planned progress of 100.00%
Compared to last Month progress 92.88% against planned 100.00%.
Over all progress Engineering - 100.00%, Procurement - 100.00%, Construction - 98.37% and T&C - 24%.
Ongoing key works-Progress:
The Following is a List the major works that are under progress on site.
Ø Testing & Commissioning of Fire fighting system in progress
Ø Pretesting of HVAC Equipment in progress
Ø Testing & Commissioning of Electrical Equipment in progress
Ø Pretesting of panels in progress.
Ø Installation of Wiring Devices & Light Fixture in Palace & Chalets.
Ø Isolator Installation & termination for equipment in progress
Ø Sanitary ware installation in chalet & palace in progress
Ø Grills & Diffuser Installation in palace in progress parallel with civil.
2- Engineering Progress:
Shop drawing progress: planned submission & approval 100 % & actual submission .100.00% Approved 100.00%.
3- Procurement
Procurement progress is 100.00%
4- QA/QC:
Ø Number of open and closed NCR’s |  | 29
Ø Number of IR thismonth
5- Construction
Construction Progress:
Building / Area | Planned % | Actual % | Variance
Chalets – 6nos | 100% | 98.88% | -1.12%
Main Palace | 100% | 98.18% | -1.82%
Main Gate | 100% | 98.46% | -1.54%
Service Gate | 100% | 98.77% | -1.23%
Staff Quarter | 100% | 98.43% | -1.57%
Horse Stable | 100% | 98.82% | -1.18%
Garage & Kitchen | 100% | 95.43% | -4.57%
Service Yard | 100% | 97.77% | -2.23%
Substation | 100% | 99.13% | -0.87%
External | 100% | 99.57% | -0.43%
Over All | 100% | 98.37% | -1.63%
Testing & Commissioning Progress
Project | Planned % | Actual % | Variance
AJSH | 100% | 24% | -76%
6- Commercial
Gross Certified Amount up to date |  | 40992023.6433
7- HSE
No Safety Issues
8- Earned Value Management
Estimate at Completion for the project is QAR 49,996,901.70 & the total budget is QAR 43,319,658.90 (Variance QAR -6,677,242.80). The overall gross profit is 2,054,437.26 (3.95%).
Note : An expected scope deletion of 1,000000.00 is considered.
9- Resources:
Staff | 10
Manpower | 155
10- Accounts
11- Store :
Total amount of material available at store is |  | 1230269.34
12- Area of concern:
Delivery of Emergency Lights, Wiring Devices Shortage, Civil Clearance for Bath tub Installation in Chalets and Doors & Windows Installation are delying the MEP work progres..
13- Close-out
As Built drawing in progress.

## 2-Schedule
| R67-M1-15 - Monthly Project Report SCHEDULE | [9 empty] | Doc. No.: |  | REE/OPR/05.1
[11 empty] | Rev.: | Rev.: | 0
[11 empty] | Date: |  | 2016-03-31
Project Overview
Program Details
Program Detail |  | Rev | Status |  | Start Date |  |  | Plan Completion Date |  |  |  | Projected Completion Date
MEP Baseline |  | 1 | Approved |  | 2015-03-23 |  |  | 2015-11-30
MEP Revised (Target) |  | 2 | Submitted |  | 2015-03-23 |  |  | 2016-02-24 |  |  |  | 2016-05-28
Delay Period | [7 empty] | -94days (As per MEP Revised Program-2)
(A)- Approved, (F) - Followed, (S)-Submitted/under review
Progress Details
Month |  | Progress Type |  | Plan |  | Actual |  | Variance
[8 empty] | Total | Engineering |  |  | Procurement |  | Construction
Previous | 2016-01-31 | Physical |  | 100% |  | 92.88% | #VALUE! | -7.12% | 0% | 4.36% |  | -0.02% |  | -4.12%
|  | Financial |  |  |  | 85.81% |  | -14.19%
Current | 2016-02-29 | Physical |  | 100% |  | 94.95% | #VALUE! | -5.05% | 0% | 4.36% |  | 0% |  | -1.63%
|  | Financial |  |  |  | 90% |  | -10%
Forecast | 2016-03-30 | Physical |  | 100%
Financial
Remarks

## 3-Engineering
| R6-M1-15 - Monthly Project Report ENGINEERING | [5 empty] | Doc. No.: | REE/OPR/05.2
[7 empty] | Rev.: | 0
[7 empty] | Date: | 2016-03-31
As of: | 2016-03-31
Shop Drawings
Description | No. of Drawings | Submitted (On This Month) | Total Submitted | Approved | Rejected | Under Review | Balance to Submit | Remarks
Electrical | 190 | 0 | 190 | 190 | 0 | 0 | 0
HVAC | 39 | 0 | 39 | 39 | 0 | 0 | 0
Plumbing | 97 | 0 | 97 | 97 | 0 | 0 | 0
Fire Fighting | 34 | 0 | 34 | 34 | 0 | 0 | 0
Builders work | 25 | 0 | 25 | 25 | 0 | 0 | 0
Coordination | 42 | 0 | 42 | 42 | 0 | 0 | 0
BMS | 35 | 0 | 35 | 35 | 0 | 0 | 0
External | 52 | 0 | 52 | 52 | 0 | 0 | 0
Total | 514 | 0 | 514 | 514 | 0 | 0 | 0 |  | 1
Technical Queries ( TQ/ SCR/ RFC)
Description | Submitted |  |  | Answered / Close |  |  | Open
Mechanical | 0 |  |  | 0 |  |  | 0
Electrical | 0 |  |  | 0 |  |  | 0
Total | 0 |  |  | 0 |  |  | 0
Open TQ's
Description | Sl No. | Ref. No. |  | Description |  |  |  | Status
Mechanical
Electrical

## 4-Procurement
|  | R67-M1-15 - Monthly Project Report PROCUREMENT | [8 empty] | Doc. No.: |  | REE/OPR/05.3
[11 empty] | Rev.: |  | 0
[11 empty] | Date.: |  | 2016-03-31
As of: | 2016-03-31
Material Submittal
Description |  |  | No. of Submittal | Planned Submission (On This Month) |  | Actual Submitted |  | Approved | Rejected |  |  | Under Review |  |  | Balance to Submit
HVAC |  |  | 23 | 0 |  | 23 |  | 23 | 0 |  |  | 0 |  |  | 0
Plumbing |  |  | 31 | 0 |  | 31 |  | 31 | 0 |  |  | 0 |  |  | 0
Fire Fighting |  |  | 25 | 0 |  | 25 |  | 25 | 0 |  |  | 0 |  |  | 0
Electrical |  |  | 29 | 0 |  | 29 |  | 29 | 0 |  |  | 0 |  |  | 0
Total |  |  | 108 | 0 |  | 108 |  | 108 | 0 |  |  | 0 |  |  | 0
Material Purchase Order - Long Lead
Description |  |  | No. of PO upto Last Month (Up to Jan-16) |  | Plan PO to be issued This Month (Feb-16) |  | MR Released This month (Feb-16) |  |  | Actual - PO issued This Month (Feb-16) |  |  |  | Remaining POs This Month
HVAC |  |  | 23 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Plumbing |  |  | 31 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Fire Fighting |  |  | 25 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Electrical |  |  | 29 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Others |  |  | 1 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Total |  |  | 109 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0

## 4.1-Logs
| R67-M1-15 - Monthly Project Report PROCUREMENT | Doc. No.: | REE/OPR/05.3
|  | Rev.: | 0
|  | Date.: | 2016-03-31
2016-03-31
Procurement Log Sheet Attached

## 4.2-Long Lead Tracking
|  | R67-M1-15 - Monthly Project Report PROCUREMENT | [8 empty] | Doc. No.: | REE/OPR/05.3.2
[11 empty] | Rev.: | 0
[11 empty] | Date: | 2016-03-31
Long Lead Material Track Sheet (Delivery Period more than 8 Weeks)
S.No | Item Description |  | Required at Site | Material Approval Status | MR Date | PO release Date | Delivery |  |  | Material Inspection | Installation @ Site | Remarks
[7 empty] | Deliver Period | Confirm by Sup | Actual
1 | Air Handling Units (AHU's) |  | 2015-11-01 | Approved | 2015-09-14 | 2015-09-17 | 60 | 81 | 83 | Done | Done | Delivered
2 | Air Terminals |  | 2015-09-10 | Approved | 2015-08-25 | 2015-09-01 | 50 | 75 | 121 | Done | In Progress | Delivered
3 | VRF Units |  | 2015-10-15 | Approved | 2015-08-11 | 2015-08-15 | 45 | 61 | 75 | Done | Done | Delivered
4 | Fans |  | 2015-09-20 | Approved | 2015-05-19 | 2015-08-11 | 80 | 80 | 95 | Done | Done | Delivered
5 | DX-Split Unit |  | 2015-10-15 | Approved | 2015-08-11 | 2015-08-15 | 45 | 61 | 65 | Done | Done | Delivered
6 | Water Filters |  | 2015-09-10 | Approved | 2015-05-23 | 2015-07-30 | 90 | 112 | 120 | Done | Done | Delivered
7 | Water Heaters |  | 2015-09-10 | Approved | 2015-05-23 | 2015-05-24 | 90 | 112 | 145 | Done | Done | Delivered
8 | Booster Pumps |  | 2015-09-10 | Approved | 2015-08-08 | 2015-08-09 | 30 | 30 | 35 | Done | Done | Delivered
9 | Sump Pumps |  | 2015-09-10 | Approved | 2015-09-06 | 2015-09-14 | 60 | 30 | 35 | Done | Done | Delivered
10 | Hot Water Circulation Pumps |  | 2015-09-10 | Approved | 2015-05-17 | 2015-05-19 | 100 | 115 | 105 | Done | Done | Delivered
11 | Water Cooler |  | 2015-10-03 | Approved | 2015-08-05 | 2015-08-09 | 50 | 60 | 75 | Done | Done | Delivered
12 | Oil/Grease Intercepter |  | 2015-10-03 | Approved | 2015-06-02 | 2015-06-03 | 90 | 90 | 104 | Done | Done | Delivered
13 | FM 200 System |  | 2015-11-10 | Approved | 2015-07-04 | 2015-07-08 | 90 | 90 | 125 | Done | Done | Delivered
14 | Foam Fire Supression System |  | 2015-11-10 | Approved | 2015-07-04 | 2015-07-08 | 90 | 90 | 125 | Done | Done | Delivered
15 | Fire Hose Reel & Cabinet |  | 2015-09-01 | Approved | 2015-07-04 | 2015-07-08 | 90 | 90 | 115 | Done | Done | Delivered
16 | Firefighting Pump |  | 2015-10-15 | Approved | 2015-07-04 | 2015-07-08 | 120 | 120 | 160 | Done | Done | Delivered
17 | Aerosol Fire Supression System |  | 2015-11-10 | Approved | 2015-07-04 | 2015-07-08 | 90 | 90 | 115 | Done | Done | Delivered
18 | Generator |  | 2015-10-10 | Approved | 2015-08-04 | 2015-08-10 | 60 | 60 | 68 | Done | Done | Delivered
19 | Transformer |  | 2015-09-15 | Approved | 2015-05-21 | 2015-05-23 | 90 | 90 | 104 | Done | Done | Delivered
20 | Power Cables |  | 2015-08-03 | Approved | 2015-08-18 | 2015-08-23 | 45 | 45 | 65 | Done | Done | Delivered
21 | CBS Equipment |  | 2015-11-14 | Approved | 2015-08-24 | 2015-08-25 | 80 | 80 | 138 | Done | In Progress | Delivered
22 | DB's |  | 2015-10-05 | Approved | 2015-06-22 | 2015-08-03 | 45 | 45 | 65 | Done | In Progress | Delivered
23 | MCC Panels |  | 2015-10-05 | Rejected | 2015-06-22 | 2015-10-26 | 25 | 25 | 94 | Done | Done | Delivered
24 | SMDB's |  | 2015-10-05 | Approved | 2015-06-22 | 2015-08-03 | 45 | 45 | 65 | Done | Done | Delivered
25 | Capacitor Bank |  | 2015-10-05 | Approved | 2015-06-22 | 2015-08-03 | 45 | 45 | 65 | Done | Done | Delivered
26 | LV Panels |  | 2015-10-05 | Approved | 2015-06-29 | 2015-08-03 | 45 | 45 | 65 | Done | Done | Delivered

## 5-QA-QC
|  | R67-M1-15 - Monthly Project Report QA/QC | [5 empty] | Doc. No.: |  | REE/OPR/05.4
[8 empty] | Rev.: |  | 0 | 0
[8 empty] | Date: |  | 2016-03-31
As of: |  | 2016-03-31
Material Inspection
Description |  |  | Total | Approved |  | Rejected |  |  | Open
HVAC |  |  | 30 | 30 |  | 0 |  |  | 0
Plumbing
Fire Fighting
Electrical |  |  | 27 | 27 |  | 0 |  |  | 0
Total |  |  | 57 | 57 |  | 0 |  |  | 0
Installation Inspection
Description |  |  | Total | Approved |  | Rejected |  |  | Open
HVAC |  |  | 608 | 344 |  | 221 |  |  | 43
Plumbing
Fire Fighting
Electrical |  |  | 523 | 328 |  | 186 |  |  | 9
Total |  |  | 1131 | 672 |  | 407 |  |  | 52
NCR- Non Conformance Report
Description |  |  | Total - Received |  | Closed |  | Open
External |  |  | 29 |  | 11 |  | 18
Internal |  |  | 0 |  | 0 |  | 0
Total |  |  | 29 |  | 11 |  | 18
Open NCR Details:
Sl NO. | Description | [5 empty] | Status
1 | It has been noticed that installations of HVAC duct and pipes supports are done with an unapproved anchot bolt (unifix) in Chalets, Main Kitchen and Garage Building (Photos attached for your reference. You are hereby instructed to immediately stop the fixation of the mentioned works using the unacceptable material and replace it with the approved (Hilti) material. The contractor will bear all the contractual consequences in case he continue the works without the approved material and the contractual clauses will be applied in this case. | [5 empty] | Open
2 | It was noticed that contractor is using rejected material for water supply system instead of approved materials "MUELLER" You are hreby instructed to replaced executed works with approved materials you are immediate corrective action is required. | [5 empty] | Open
3 | Contractor is proceeding with external sewage network without approved IFC drawings & with unapproved material. | [5 empty] | Open
4 | It was noticed that the contractor proceed the work (Floor Concrete) In Palace G.F. (Part # 03) Before inspection of Electrical works (Floor conduits) | [5 empty] | Open
5 | Contractor is proceeding with works related to external drainage without submitting wor inspection request for manhole works for external drainage. | [5 empty] | Open
6 | Contractor is proceeding with works related to external drainage without submitting wor inspection request for manhole works for external drainage. | [5 empty] | Open
7 | UPVC piping infront of Staff Quarter have already concreted without the approved installation inspection and without rectifying the slope which is not accepted | [5 empty] | Open
8 | With reference NCR 21, 29, & 31 Contractor is proceeding with works related to external Drainage drainage woithput approved work inspectio0nrequest for manhole & Sewage Networks for External Drainage. | [5 empty] | Open
9 | 1. Spacing between Electrical PVC conduit pipes & Mechanical water pipes are not as per standard and regulation (Conduits in touch with water line) 2. Spacing between backwash pipes and power sleeves is must and either of them must be closed 3. Slab on Grade done without raising inspection request in Kitchen & Garage area | [5 empty] | Open
10 | Backwash UPVC pipe line and water supply HDPE for pump room were backfilled and concreted before the time of inspection | [5 empty] | Open
11 | UPVC Piping infront of Palace which is already inspected and backfilled, have been exposed due to some excavation in the area, resulting that the pipes are exposed and bended which will affect the drainage systems | [5 empty] | Open
12 | Copper tape for lightening protection is casted in concrete prior to our inspection for installation (photo attached). Earth wire has been used for connection between two copper tape lenghts (phot attached). | [5 empty] | Open
13 | Referring to material submittal #U747414-AJSH/DORSCH/MAS/0166 for the MITSUBISHI ELECTRIC AC/DX units which is Japan/UK manufactured. It was noticed that the material delivered and installed at site is different from the approved material. The contractor did not comply with the approved material submittal. Your immediate corrective action is required. | [5 empty] | Open
14 | Contractor backfilled the underground UPVC pipes before the end of inspection and without visual checking. | [5 empty] | Open
15 | The contractor has backfilled and concreted the area where the Underground HDPE pipes was installed before the inspection time and without visual installation checking, please find the attached photos for reference. | [5 empty] | Open
16 | It was noticed that , material deliverd and installed at site is different from from the approved materials. | [5 empty] | Open
17 | Installing drainage pipes planters beside showers | [5 empty] | Open
18 | Using Improper fittings for back wash line in chalet 2 | [5 empty] | Open

## 6-Construction
|  | R67-M1-15 - Monthly Project Report CONSTRUCTION |  | Doc. No.: | REE/OPR/05.5
|  |  |  | Rev.: | 0
|  |  |  | Date: | 2016-03-31
Progress Accomplished This Month (Major Activities only)
S.No | Activity Description |  |  | Remarks
1 | Testing & Commissioning of Fire fighting system in progress.
2 | Pretesting of HVAC Equipment in progress
3 | Testing & Commissioning of Electrical Equipment in progress
4 | Pretesting of panels in progress.
5 | Installation of Wiring Devices & Light Fixture in Palace & Chalets.
6 | Isolator Installation & termination for equipment in progress
7 | Sanitary ware installation in chalet & palace in progress
8 | Grills & Diffuser Installation in palace in progress parallel with civil.
One Month Look Ahead Plan (Major Activities only)
S.No | Activity Description |  | Tentative Start Date | Remarks
1 | Final Testing & Commissioning |  | 2016-04-18
2 | Project Close Out |  | 2016-04-24

## 7-Project Scope +Revenue Detail
| R67-M1-15 - Monthly Project Report COMMERICAL | [5 empty] | Doc. No. | REE/OPR/05.6
[7 empty] | Rev.: | 1
[7 empty] | Date: | 2016-03-31
Project Scope Value Details
Current Scope Value |  |  | VO Breakdown |  |  | Expected Contract Value
Original Contract Value |  | 49200000 | Submitted |  | 3614250.695 | Current Scope Value | 52051338.9626
Revised / Adjustment B O Q |  | 0 | Approved |  | 154913.84 | Exp. Re-measured Qty | 0
Approved VO |  | 154913.84 | Rejected / Cancalled |  | 762911.7324 | Not- Approved Variations | 0
Scope Deletion |  | 0 | Under Revise |  | - | EOT- (Submitted) | 0
Not Approved Under Execution |  | 2696425.1226 | Not Approved, Under Execution |  | 2696425.1226 | Expected New Variations | 0
Additonal QTY |  | 0 |  |  |  | Domestic Claim | 0
52051338.9626 |  |  | 3614250.695 |  |  | 52051338.9626
Project Revenue Details
|  | Previous |  | Current |  |  | Forecast
|  | 2016-02-29 |  | 2016-03-31 |  |  | 2016-04-28
Plan | Monthly | 1254600 |  | 154913.84 |  |  | 2696425.1226
| Camulative | 49200000 |  | 49354913.84 |  |  | 52051338.9626
Actual | Monthly | 2459235.93 |  | 3416480.8218
| Camulative | 40992023.6433 |  | 44408504.4651
Variance | Monthly | 1204635.93 |  | 3261566.9818
| Camulative | -8207976.3567 |  | -4946409.3749
0.90261
Formulas:
Forecast = [Current]+28

## 7.1-Payment-Detail
| R67-M1-15 - Monthly Project Report COMMERICAL |  |  |  | Doc. No. | REE/OPR/05.6
[5 empty] | Rev.: | 0
[5 empty] | Date: | 2016-03-31
Payment Application Details
Payment Application Details |  |  | Certification Details |  | Outstanding Amount
Application No | Application Month | Gross Application Amount | Certified Amount | Back Charges
Application # 01 | 2015-06-01 | 2996167.93 | 1938041.27 | 0 | 1938041.27
Application # 02 | 2015-08-01 | 5186175.73 | 5202842.39 | 0 | 5202842.39
Application # 03 | 2015-09-01 | 7538395.71 | 7538395.71 | 0 | 7538395.71
Application # 04 | 2015-10-01 | 4743047.62 | 4743047.62 | 717523.49 | 4025524.13
Application # 05 | 2015-11-01 | 16848141 | 12499872.7833 | 0 | 12499872.7833
Application # 06 | 2015-12-01 | 6292070.9 | 2965648.9 | 1174841.31 | 1790807.59
Application # 07 | 2016-01-01 | 5597711.15 | 3644939.04 | 535277.25 | 3109661.79
Application # 08 | 2016-02-01 | 3687342.029 | 2459235.93
Application # 09 | 2016-03-01 | 3416480.8218
G. Total: |  | 44408504.4651 | 40992023.6433 | 2427642.05 | 36105145.6633

## 7.2-Scope Management
| R67-M1-15 - Monthly Project Report COMMERCIAL | [10 empty] | Doc No.: | REE/OPR/05.6
[12 empty] | Rev.: | 0
[12 empty] | Date: | 2016-03-31
Scope Management Matrix
VO # / Client Ref. | Description | VO Value Breakdown (Acual Cost) |  |  |  | Value of VO |  |  |  | Current Status (%) |  |  | Remarks
|  | Material | Manpower | Indirect Cost | O/H, M-Res + Profit | Submitted | Agreed | Approved | Status | Progress | Claim | Certification
VO.1 | Modification of FM200 System in Main Gate. | 39738.436 | 13246.1453 | 3311.5363 | 9934.609 | 66230.7266 | 48481.3 |  | Agreed |  |  |  | Action Required By UCC | 48481.3 | 73.2% | 29088.78 | 9696.26 | 2424.065 | 7272.195
VO.2 Rev.01 | Additional Swimming Pool Filling Line, Pumps & Backwash system. | 103099.38 | 43354.3644 | 12569.8064 | 23981.2383 | 183004.7892 |  | 128037.44 | Approved |  |  |  | - | 128037.44 | 69.96% | 72132.4329 | 30332.4403 | 8794.3372 | 16778.2296
VO.3 Rev.01 | Additional VAV System & Related BMS Items | 12847.2035 | 7208.7617 | 5647.8965 | 3591.4143 | 29295.276 |  | 26876.4 | Approved |  |  |  | - | 26876.4 | 91.74% | 11786.4252 | 6613.5429 | 5181.5564 | 3294.8755
VO.4 | Additional Centarl Battery System | 418245.1522 | 127374.2946 | 29177.6742 | 56620.834 | 631417.955 | 450000 |  | Agreed |  |  |  | Action Required By UCC | 450000 | 71.27% | 298075.6518 | 90777.3245 | 20794.3934 | 40352.6303
VO.5 | Additional Shoower Grating, Pipe Workd & Floor Drain | 48399.3153 | 5052.5792 | 2780.7554 | 5453.3501 | 61686 | 49000 |  | Agreed |  |  |  | Action Required By UCC | 49000 | 79.43% | 38445.7811 | 4013.4938 | 2208.8807 | 4331.8444
VO.6 | Additional External Containment for ELV Cables | 145281.0692 | 291410.1634 | 26221.0345 | 48055.5961 | 510967.8633 | 426109.8226 |  | Agreed |  |  |  | Action Required By UCC | 426109.8226 | 83.39% | 121153.785 | 243014.7607 | 21866.4248 | 40074.8521
VO.7 | Additional DBs, SMDBs With Feeder Cable & Cable Containment | 225897.6826 | 58994.43 | 44129.6373 | 29056.335 | 358078.0849 | 270538 |  | Agreed |  |  |  | Action Required By UCC | 270538 | 75.55% | 170672.0121 | 44571.9405 | 33341.1742 | 21952.8731
VO.8 | Additional Lighting For External Area | 466229.8981 | 1071037.3525 | 156583.056 | 79719.6934 | 1773570 | 1452296 |  | Agreed |  |  |  | Action Required By UCC | 1452296 | 81.89% | 381774.5091 | 877023.8913 | 128218.7598 | 65278.8398
Total: |  | 1459738.1369 | 1617678.0912 | 280421.3965 | 256413.0703 | 3614250.695 | 2696425.1226 | 154913.84 | [7 empty] | 0.32103
| V.O clasifications | Value
| Approved Variation orders (by client) | 154913.84
| Variation orders that already agreed by UCC - Work already executed at site | 2696425.1226
| Cancelled and / or rejected Variation orders | 762911.7324
| Variation orders that still under review by Client and work not yet executed | 0
| Total Value of the Variation orders | 3614250.695
Executed, Approved & Agreed
|  |  | Material | Manpower | Indirect Cost | O/H, M-Res + Profit
|  | VO.1 | 29088.78 | 9696.26 | 2424.065 | 7272.195 | 48481.3
|  | VO.2 | 72132.4329 | 30332.4403 | 8794.3372 | 16778.2296 | 128037.44
|  | VO.3 | 11786.4252 | 6613.5429 | 5181.5564 | 3294.8755 | 26876.4
|  | VO.4 | 298075.6518 | 90777.3245 | 20794.3934 | 40352.6303 | 450000
|  | VO.5 | 38445.7811 | 4013.4938 | 2208.8807 | 4331.8444 | 49000
|  | VO.6 | 121153.785 | 243014.7607 | 21866.4248 | 40074.8521 | 426109.8226
|  | VO.7 | 170672.0121 | 44571.9405 | 33341.1742 | 21952.8731 | 270538
|  | VO.8 | 381774.5091 | 877023.8913 | 128218.7598 | 65278.8398 | 1452296
|  |  | 1123129.3772 | 1306043.654 | 222829.5916 | 199336.3398 | 2851338.9626
Executed & Submitted
0
0
0
0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 1123129.3772 | 1306043.654 | 222829.5916 | 199336.3398 | 2851338.9626

## 7.3-sub-con
| R67-M1-15 - Monthly Project Report CONSTRUCTION | [8 empty] | Doc. No.: | REE/OPR/05.5
[10 empty] | Rev.: | 0
[10 empty] | Date: | 2016-03-31
Sub Contractor- 1 Status
SubCon Name: |  |  | Consolidated Engineering System CO. W.L.L |  |  |  | Scope: |  | Fire Fighting
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
608040 |  |  |  | 302409.24 |  | 910449.24 |  |  |  | 710614.3 |  |  | 685096.99
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan |  | 12 |  | 5 | 19 | 5 |  | 100%
Actual |  | 12 |  | 3 | 19 | 5 |  | 95%
Variance |  | 0 |  | -2 | 0 | 0 |  | -5%
Remarks
Sub Contractor- 2 Status
SubCon Name: |  |  | Al Mana Networks Solutions & Security Services |  |  |  | Scope: |  | BMS
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
620000 | [5 empty] | 620000 |  |  |  | 620314.93 |  |  | 558018.52
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan |  | 32 |  | 7 | 2 | 1 |  | 100%
Actual |  | 32 |  | 5 | 2 | 1 |  | 88%
Variance |  | 0 |  | -2 | 0 | 0 |  | -12%
Remarks
Sub Contractor- 3 Status
SubCon Name: |  |  | Asian Insulation Co. |  |  |  | Scope: |  | Aluminium Clading on External Duct Work
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
424800 | [5 empty] | 424800 |  |  |  | 349973.94 |  |  | 286253.94
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan |  | N/A |  | 9 | 1 | 1 |  | 75%
Actual |  | N/A |  | 5 | 1 | 1 |  | 67.39%
Variance |  | N/A |  | -4 | 0 | 0 |  | -7.614%
Remarks
Sub Contractor- 4 Status
SubCon Name: |  |  | Al Marshal Trading & Contracting |  |  |  | Scope: |  | Cable Pulling & PVC Sleeve Pipe Istallation
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
OPEN | [5 empty] | OPEN |  |  |  | 701691 |  |  | 701691
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan |  | N/A |  | 21 | N/A | N/A |  | 100%
Actual |  | N/A |  | 23 | N/A | N/A |  | 100%
Variance |  | N/A |  | 2 | N/A | N/A |  | 0%
Remarks |  | Work Completed
Sub Contractor- 5 Status
SubCon Name: |  |  | Asian Insulation Co. |  |  |  | Scope: |  | Installation Of Duct
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
OPEN | [5 empty] | OPEN |  |  |  | 314568.91 |  |  | 306784.85
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan | [7 empty] | 100%
Actual | [7 empty] | 100%
Variance | [7 empty] | 0%
Remarks |  | Work Completed
Sub Contractor- 6 Status
SubCon Name: |  |  | URUK Constructions Trade & Services WLL |  |  |  | Scope: |  | Installation Of Duct With Insulation
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
OPEN | [5 empty] | OPEN |  |  |  | 165894 |  |  | 165894
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan | [7 empty] | 100%
Actual | [7 empty] | 100%
Variance | [7 empty] | 0%
Remarks |  | Scope of work already Completed and this subcontractor already demobilized from site
Sub Contractor- 7 Status
SubCon Name: |  |  | Safty Committee For Safty Security |  |  |  | Scope: |  | Installation Of Sprinkler System
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
OPEN | [5 empty] | OPEN |  |  |  | 58369 |  |  | 55980.5
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan | [7 empty] | 100%
Actual | [7 empty] | 100%
Variance | [7 empty] | 0%
Remarks |  | Scope of work already Completed and this subcontractor already demobilized from site
Sub Contractor- 8 Status
SubCon Name: |  |  | ACACIA Intermational Group |  |  |  | Scope: |  | Installation Of Duct
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
OPEN | [5 empty] | OPEN |  |  |  | 20250 |  |  | 19237.5
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan | [7 empty] | 100%
Actual | [7 empty] | 100%
Variance | [7 empty] | 0%
Remarks |  | Work Completed
Sub Contractor- 9 Status
SubCon Name: |  |  | CONTROMET |  |  |  | Scope: |  | Termination Of DB, SMDB & LV Panels
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
116730 |  |  |  | 6480 |  | 123210 |  |  |  | 90677.5 |  |  | 90677.5
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan |  | N/A |  |  | N/A | N/A |  | 100%
Actual |  | N/A |  |  | N/A | N/A |  | 95%
Variance |  | N/A |  |  | N/A | N/A |  | -5%
Remarks |  | Already Contromat pepole demobilized from site and if any rework REE only doing
Sub Contractor- 10 Status
SubCon Name: |  |  | Raymond Nahra For Electrical & Mechnical Works |  |  |  | Scope: |  | Installation of DX AHUl's & FAHU's Copper Pipes
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
140000 | [5 empty] | 140000 |  |  |  | 132978.3 |  |  | 97978.3
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan |  | N/A |  | 6 | N/A | N/A |  | 100%
Actual |  | N/A |  | 3 | N/A | N/A |  | 75%
Variance |  | N/A |  | -3 | N/A | N/A |  | -25%
Remarks
Sub Contractor- 11 Status
SubCon Name: |  |  | JEDI Balancing Middle East |  |  |  | Scope: |  | Testing & Commissioning for All HVAC Machines & All Systems
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
40000 | [5 empty] | 40000
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan |  | N/A |  | 8 | N/A | N/A |  | 100%
Actual |  | N/A |  | 5 | N/A | N/A |  | 40%
Variance |  | N/A |  | -3 | N/A | N/A |  | -60%
Remarks
Sub Contractor- 12 Status
SubCon Name: |  |  | Desionic Contracting & Trading |  |  |  | Scope: |  | Manpower Sypply - Draftsman
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
QAR 9000/Month | [5 empty] | QAR 9000/Month |  |  |  | 265058.38 |  |  | 261079.15
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan
Actual
Variance
Remarks
Sub Contractor- 13 Status
SubCon Name: |  |  | Manpower Sypply - Technician |  |  |  | Scope: |  | Manpower Sypply - Technician
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
OPEN | [5 empty] | OPEN |  |  |  | 6188308.38 |  |  | 6178205.63
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan
Actual
Variance
Remarks
Sub Contractor- 14 Status
SubCon Name: |  |  | Mohammad Aurangjeb Ansari |  |  |  | Scope: |  | 6 Months Extendable Rental For 3 Ton
Sub-Contract Value |  |  |  | Approved VO |  | Total Scope Value |  |  |  | Claim |  |  | Certified as of
QAR 7750 | [5 empty] | QAR 7750 |  |  |  | 13442.31 |  |  | 13200.56
Progress |  | Engineering |  | Manpower | Material | Long Lead Items |  | Progress |  | Inspection |  | Claim by MEP (%)
Plan |  | N/A |  | 0 | N/A | N/A |  | N/A
Actual |  | N/A |  | 0 | N/A | N/A |  | N/A
Variance |  | N/A |  | 0 | N/A | N/A |  | N/A
Remarks
Draftsmen Supply Only
Manpower Supply Only
Manpower Supply Only
Note on BR27: Citadel: Advance Payment

## 7.4-Back Chargs detail
| R67-M1-15 - Monthly Project Report COMMERICAL | [5 empty] | Doc. No. | REE/OPR/05.6
[7 empty] | Rev.: | 0
[7 empty] | Date: | 2016-03-31
Back Charges Details
Back Charges Details |  |  |  | MEP Acceptance on Back Charges | Fair Amount for Back Charges | Cost Code/ BOQ Section for Back charges | Remarks
Application No | Application Month | Back Charges Amount | Back Charges for
4 | 2015-10-01 | 717523.49 | Materials & Labour Supply | 717523.49
6 | 2015-12-01 | 1174841.31 | Materials, Staff & Labour Supply | 1174841.31
7 | 2016-01-31 | 535277.25 | LRD Labour Supply | 535277.25
G. Total: |  | 2427642.05 |  | 2427642.05 | 0 | 0 | 0

## 8-HSE
| R67-M1-15 - Monthly Project Report HSE & PPE | [9 empty] | Doc. No.: |  |  | REE/OPR/05.7
[11 empty] | Rev.: | 0 |  | 0
[11 empty] | Date: | 41922 |  | 2016-03-31
HSE Report
|  |  |  | Upto Last Month (Cumulative) |  |  | This Month | [5 empty] | Total
Total Number of Employees (Manmonth) |  |  |  | 4644 |  |  | 165 | [5 empty] | 4809
Man-hours Worked |  |  |  | 11380000 |  |  | 51440 | [5 empty] | 11431440
Man-hours Without LTI |  |  |  | 11380000 |  |  | 51440 | [5 empty] | 11431440
Man-hours Without LTA |  |  |  | 11380000 |  |  | 51440 | [5 empty] | 11431440
First Aid Case |  |  |  | 39 |  |  | 3 | [5 empty] | 42
Major Injuries |  |  |  | 0 |  |  | 0 | [5 empty] | 0
Medical Case |  |  |  | 36 |  |  | 5 | [5 empty] | 41
Occupational Illness
Incident Reports |  |  | Near Miss |  | Unsafe Act. |  |  | Unsafe Condition |  |  |  |  | Damage Report
This Month |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0
Last Month |  |  | 1 |  | 18 |  |  | 7 |  |  |  |  | 1
Induction / Training |  |  | HSE Induction |  | In house Training |  |  | Tool Box Talks |  |  |  |  | Tool Box Topics
This Month |  |  | 0 |  | 2 |  |  | 3 |  |  |  |  | Hot work - Work on live electrical equipment , LOTO - Confined Space
Last Month |  |  | 3 |  | 1 |  |  | 7 |  |  |  |  | Electrical Safety -PPE , Manual Hand Work at Height
PPE
|  | Safety Shoes |  | Helmet | Jacket | Cover |  |  | Gloves | Goggles
Issued This Month |  | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
Available In Store |  | 20 |  | 14 | 23 | 0 |  |  | 0 | 8
New Requirement |  | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
Remarks

## 9-Budget-Cost-ETC-EAC
| R67-M1-15 - Monthly Project Report Cost Control |  |  |  |  | Doc. No. | REE/OPR/05.8
[6 empty] | Rev.: | 0
[6 empty] | Date: | 2016-03-31
EARNED VALUE MANAGEMENT
Description |  | Budget | Actual Cost | ETC - Estimate To Complete Cost | EAC - Estimate At Completion Cost |  | Variances (Budget- EAC)
Material Cost | HVAC | 7430548 | 8321542.587 | 30000 | 8351542.587 |  |  | 8321542.587 |  | 415170.837 | 7906371.75
| Fire Fighting | 3359591 | 3259443.529 | 30000 | 3289443.529 |  |  | 3259443.529 |  | 138390.279 | 666791.84 | 3121053.25
| Plumbing | [9 empty] | 2454261.41
| Electrical | 15040630 | 15086145.884 | 200000 | 15286145.884 |  |  | 15086145.884 |  | 830341.674 | 14255804.21
| Variation Order | 1123129.3772 | 0 | 0 | 0
| Total | 26953898.3772 | 26667132 | 260000 | 26927132 |  | 26766.3772 | 1 4,217,600.26 |  |  | 147900.07
Manpower | HVAC | 6180000 | 14217600.26 | 514800 | 14732400.26 | [5 empty] | 1236002.72
| Fire Fighting | [9 empty] | 1383902.79
Plumbing
Electrical
| Variation Order | 1306043.654
| Total | 7486043.654 | 14217600.26 | 514800 | 14732400.26 |  | -7246356.606 | 3 ,172,453.77 | 3172453.77
Prelims (Staff/Misc) |  | 6222000 | 3721391.28 | 150000 | 3871391.28 |  | 2350608.72 | 5 48,937.51 | 548937.51
Prelims - V. O. |  | 222829.5916 | 0 | 0 | 0 |  | 222829.5916 |  | 3721391.28
Sub-Contract |  | 2434887.28 | 3315978.16 | 150000 | 3465978.16
| Total | 2434887.28 | 3315978.16 | 150000 | 3465978.16 |  | -1031090.88 | 3 ,315,978.16
Other | Scope Deletion | 0 | 0 | 1000000 | 1000000
| Back Charges | 0 | 0 | 0 | 0
| Total | 0 | 0 | 1000000 | 1000000 |  | -1000000
G. Total: |  | 43319658.9028 | 47922101.7 | 2074800 | 49996901.7 |  | -6677242.7972
514800
| Contract Value Including Vos | Gross Profit (Budget) |  | Gross Profit (EAC)
|  | Percentage % | QR | Percentage % | QR
| 52051338.9626 | 16.78% | 8731680.0598 | 3.947% | 2054437.2626
Note:
01. | As of Our Record for the material recieved at site up to 31-Mar-16 |  |  | 26163189.28
| Actual Material Cost as per Finance Report up to 31-Mar-16 |  |  | 26667132
| Difference |  |  | -503942.72
02. | Material Cost (EAC) - Exceeded with last month expected |  |  | 3502161.91
| Sub Contract (EAC) - Exceeded with last month expected |  |  | 581736.05

## 10-Resources
| R67-M1-15 -Monthly Project Report RESOURCES | [10 empty] | Doc. No.: |  |  | REE/OPR/05.9
[12 empty] | Rev.: | 0 |  | 0
[12 empty] | Date: | 41922 |  | 2016-03-31
Resources
|  |  | Manpower |  |  |  |  | Man Hours | [5 empty] | Mob / DE Mob Plan
|  |  | Cum. Last Month | This Mionth |  |  |  | Cum. Last Month | This Mionth
|  |  |  | Plan | Actual | Variance |  |  | Plan | Actual | Variance |  |  | Mob |  | DE Mob
Staff |  |  | 347 | 15 | 10 | -5 |  | 72176 | 3900 | 2600 | -1300 |  |  |  |  | 4
Manpower |  | HVAC | 4297 | 16 | 48 | -32 |  | 11307824 | 4160 | 12480 | 8320 |  |  |  |  | 25
|  | FF |  | 0 | 3 | -3 |  |  | 0 | 780 | 780 |  |  |  |  | 0
|  | PL |  | 11 | 24 | -13 |  |  | 2860 | 6240 | 3380 |  |  |  |  | 10
|  | Elect. |  | 13 | 66 | -53 |  |  | 3380 | 17160 | 13780 |  |  |  |  | 30 | 72176
|  | Total |  | 40 | 141 | -101 |  |  | 10400 | 36660 | 26260 |  |  |  |  | 65
Sub-Con |  |  |  | 0 | 14 | -14 |  |  | 0 | 3640 | -3640 |  |  |  |  | 0
STB - Standard Tool Box
STB Type |  |  |  | No of Units @ Site |  | STB Issued to Worker |  |  |  | STB Available @ Store |  |  |  | Additional Requirement If any
Ducting |  |  |  | 5 |  | 0 |  |  |  | 10 |  |  |  | 0
Piping +A/C Tech. |  |  |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0
Plumbing |  |  |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0
Electrical + BMS |  |  |  | 5 |  | 0 |  |  |  | 15 |  |  |  | 0
Remarks
Monthly Unit Workshop
|  |  |  | Last Month |  |  | This Month |  |  |  |  | Next Month (Forecast)
Plan
Actual - Conducted
*-Approved Manpower plan and Histogram Attached

## 11-Account
| R67-M1-15 - Monthly Project Report ACCOUNTS |  |  | Doc. No.: |  |  | REE/OPR/05.10
|  |  |  | Rev.: |  | 0 | 0
|  |  |  | Date: |  | 41922 | 2016-03-31
Petty Cash Expenses Details
Petty Cash Expenses |  |  |  |  | Total Petty cash Expenses as of This Month
Upto Last Month |  | This Month | Next Month (Expected)
|  | 0 | 0

## 12-Store
| R67-M1-15 - Monthly Project Report STORE | [7 empty] | Doc. No.: | REE/OPR/05.11
[9 empty] | Rev.: | 1
[9 empty] | Date: | 2016-03-31
STOCK VALUE
Discipline |  | Stock Pervious Month (February - 2016) |  |  |  | Stock This Month (March - 2016)
|  | Permanent Material | Material which may not be used & need Transfer | Consumable /sundries | Total | Permanent Material | Material which may not be used & need Transfer | Consumable /sundries |  |  | Total
HVAC |  | 69746.02 | 0 | 8804.92 | 78550.94 | 73722.75 | 0 | 9138.55 |  |  | 82861.3 | 9138.5507 | 145667.36 |  | 6.045% | 9138.55
Plumbing |  | 368156.65 | 0 | 46477.03 | 414633.68 | 244238.61 | 0 | 48238.11 |  |  | 292476.72 | 48238.1097 |  |  | 31.91% | 48238.11
Fire Fighting |  | 106823.61 | 0 | 13485.68 | 120309.29 | 104909.66 | 0 | 13996.67 |  |  | 118906.33 | 13996.6713 | 9.757% | 14213.3637 | 9.258% | 13996.67
Electrical- MV/ LV |  | 609142.71 | 0 | 76899.73 | 686042.44 | 332685.41 | 0 | 79813.57 |  |  | 412498.98 | 79813.5683 | 32.33% | 47087.9369 | 52.79% | 79813.57
Electrical- ELV | [12 empty] | 13.89% | 20226.0382
Tools / Equipment's |  | 429448.31 | 0 | 0 | 429448.31 | 323526.01 | 0 | 0 |  |  | 323526.01 |  | 44.03% | 64140.0211
G. Total |  | 1583317.3 | 0 | 145667.36 | 1728984.66 | 1079082.44 | 0 | 151186.9 |  |  | 1230269.34 |  |  |  | 151186.9 | 151186.9

## 13-AOC
|  | R67-M1-15 -Monthly Project Report Areas Of Concern |  |  |  | Doc. No.: | REE/OPR/05.12
[6 empty] | Rev.: | 1
[6 empty] | Date: | 2016-03-31
Areas of Concern
S.# | Concern |  | Impact | Suggested Action
|  |  |  | Action | Action By |  |  | Date
1 | Delivery of Emergency lights for staircase in Palace, chalets & Ancillary buildings |  | Delay in Installation & Handing Over | Follow up with UCC | Mr. Mohannad Hanna |  |  | Weekly
2 | Delivery of wiring devices |  | Delaying the MEP Final Fixture Installation | Follow up with UCC | Mr. Mohannad Hanna |  |  | Daily
3 | Civil clearance for Bath Tub Installation in Chalets |  | Delay the installation in Chalet | Follow up with UCC | Mr. Mohannad Hanna |  |  | Daily
4 | Doors & Windows Installation are delaying |  | Delay the MEP Air Balancing Testing & Commissioning | Follow up with UCC | Mr. Mohannad Hanna |  |  | Daily
5
6
7
8
9
10

## 14-Close-out
| R67-M1-15 -Monthly Project Report CLOSE-OUT |  |  |  | Doc. No.: | REE/OPR/05.13
[5 empty] | Rev.: | 0
[5 empty] | Date: | 2016-03-31
Description |  | Total | HVAC | FF | PL |  | Electrical
Material Inspection | Total | 64 | 37 |  |  |  | 27
| Code - A | 25 | 13 |  |  |  | 12
| Total to be resubmitted for Code - A | 39 | 24 |  |  |  | 15
Exp. Date to Complete
Installation Inspection | Total | 1131 | 608 |  |  |  | 523
| Code - A | 672 | 344 |  |  |  | 328
| Total to be resubmitted for Code - A | 459 | 264 |  |  |  | 195
Exp. Date to Complete
Red Line Drw | Total
Submitted
Approved
Exp. Date to Complete
As-Built | Total | 457 | 202 |  |  |  | 255
| Submitted | 17 | 9 |  |  |  | 8
| Approved | 0 | 0 |  |  |  | 0
Handed Over
Exp. Date to Complete
T&C Procedure | Total | 15 | 1 | 4 | 2 |  | 8
| Submitted | 15 | 1 | 4 | 2 |  | 8
| Approved | 14 | 1 | 3 | 2 |  | 8
| Procedure Execution | 10 | 1 | 3 | 2 |  | 4
| T&C Accepted by The Engineer | 2 | 0 | 0 | 2 |  | 0
Exp. Date to Complete the T&C
Punch List | Total Received
Work Completed
Punch Item signed by the Engineer / Closed
Exp. Date to Complete
O&M Manual | Total | 21 | 4 | 4 | 6 |  | 7
| Submitted | 0 | 0 | 0 | 0 |  | 0
| Approved | 0 | 0 | 0 | 0 |  | 0
| Handed Over | 0 | 0 | 0 | 0 |  | 0
Exp. Date to Complete
Training | Total
Submitted
Approved
Conducted
Exp. Date to Complete
Warranties | Total
Submitted
Approved
Handed Over
Exp. Date to Complete
Spare Parts | Total
Submitted
Approved
Handed Over
Exp. Date to Complete

## Sub (hidden)
Project Report - Monthly
Project Name : xxxxxxx
TABLE OF CONTENTS
Project Overview
§ Project
§ Program
§ Progress
§ Progress S - Cuve
§ Loo Ahead Program
Engineering
Procurement
QA/QC Status
Resources
§ Man-hours
§ Tools & Plants
Sub-Con. Status
HSE - Report
Commercial
§ Contract Value Detail
§ Claim Detail & S- Curve
§ Budget - Cost Comparison
§ Completion Cost Forecast
§ Petty Cash Report
§ Correspondence Detail
§ Scope Management Matrix
Area of Concerns
Progress Photograph
Lesson Learned
Admin Report
Project Overview
Project Details
Project:
Client:
Designer:
MEP Designer:
Consultant:
Main Contractor:
MEP Contractor:
In House Sub-Con: | [11 empty] | 1
2
3
4
Program Detail
Program Detail | [9 empty] | Rev |  |  |  | Status | [6 empty] | Start Date | [9 empty] | Plan Completion Date | [12 empty] | Projected Completion Date
(A)- Approved, (F) - Followed, (S)-Submitted/under review
Progress Detail
Month | [9 empty] | Plan | [6 empty] | Actual | [6 empty] | Variance
[24 empty] | Total | [8 empty] | EL | [5 empty] | HVAC | [5 empty] | FF | [6 empty] | PL
Pervious
Current
Forecast
Progress- S Curve
3 Month Look Ahead Plan
(Major Activity only)
S.No | Activity Description | [29 empty] | Tentaivit Completion Date | [10 empty] | Remarks
Engineering - (As of Jan-14)
Procurement - (As of Jan-14)
QA/QC Status- (As of Jan-14)
Long Lead Material Track Sheet
S.No | Item Description | [10 empty] | Required at Site |  |  | Material Approval Status |  |  |  | MR Date |  |  |  | PO release Date |  |  |  |  | Delivery | [13 empty] | Material Inspection |  |  |  | Installation @ Site | [5 empty] | Remarks
[28 empty] | Deliver Period |  |  |  |  | Confirm by Sup |  |  |  |  | Actual
Resources- (As of Jan-14)
Tools & Plants
Tools | [25 empty] | Plants
S.# | Plants Description | [13 empty] | Required Period | [7 empty] | Qty |  |  | S.# |  |  | Plants Description | [15 empty] | Required Period | [8 empty] | Qty
Sub Contractor Status
Subcon Name |  |  |  | Scope
Contract Value | [12 empty] | Approved VO | [11 empty] | Total Scope Value | [15 empty] | Claim | [6 empty] | Certified as of
|  |  |  | Design | [8 empty] | Manpower |  |  |  |  | Material | [6 empty] | Long lead Items | [8 empty] | Progress | [6 empty] | Inspection | [6 empty] | Remarks :
Plan
Actual
Subcon Name |  |  |  | Scope
Contract Value | [12 empty] | Approved VO | [11 empty] | Total Scope Value | [15 empty] | Claim | [6 empty] | Certified as of
|  |  |  | Design | [8 empty] | Manpower |  |  |  |  | Material | [6 empty] | Long lead Items | [8 empty] | Progress | [6 empty] | Inspection | [6 empty] | Remarks :
Plan
Actual
HSE - Report
[13 empty] | last Month | [11 empty] | This Month | [15 empty] | Total
Total Number of Employees
Man-hours Worked
Man-hours Without LTI
Man-hours Without LTA
First Aid Case
Major Injuries
Medical Case
Occupational Illness
Incident Reports | [7 empty] | Near Miss | [9 empty] | Unsafe Act. | [11 empty] | Unsafe Condition | [10 empty] | Damage Report
This Month
Last Month / Cumulative
Induction / Training | [7 empty] | HSE Induction | [9 empty] | In house Training | [11 empty] | Tool Box Talks | [10 empty] | Tool Box Topics
This Month
Last Month / Cumulative
Commercial - (As of Jan-14)
Current Value Detail
Original Contract (a) |  |  |  |  | BOQ Adjustment (b) | [8 empty] | Scope Deletion (c) |  |  |  |  | Additional Qty (d) | [6 empty] | Variation Order | [23 empty] | Total Current Scope Value (a+b+d+f-c)
[26 empty] | Submitted | [8 empty] | Rejected (e) | [6 empty] | Approved (f)
1234556
Budget- Cost Comparison
Budget Details | [10 empty] | Total | [8 empty] | HVAC | [6 empty] | FF | [8 empty] | PL | [6 empty] | EL | [7 empty] | App. VO
Material Cost |  |  |  | Budget
Actual Cost
Variance
Resources |  |  |  | Budget
Actual Cost
Variance
Indirect Cost |  |  |  | Budget
Actual Cost
Variance
Committed Cost |  |  |  | Budget
Actual Cost
Variance
Total Project Cost |  |  |  | Budget
Actual Cost
Variance
Total |  |  |  | Budget
Actual Cost
Variance
Management Reserve |  |  |  | Budget
Actual Cost
Variance
O / H + Profit |  |  |  | Budget
Actual Cost
Variance
G. Total |  |  |  | Budget
Actual Cost
Variance
Completion Cost Forecast
As of January 2014 | [22 empty] | BAC - Budget at Completion | [9 empty] | EAC - Estimate at Completion | [7 empty] | ETC - Estimate to Complete | [8 empty] | TCPI - To Complete Performance Index
PV - Plan Vlaue {a} | [6 empty] | AC - Actual Cost {b} | [7 empty] | EV - Earn Value {C}
Petty Cash Expenses Details
Petty Cash Expenses | [41 empty] | Total Petty cash Expenses as of Jan-14
2013-11-01 | [8 empty] | 2013-12-01 | [9 empty] | 2014-01-01 | [11 empty] | Feb. 2014 (Expected)
Correspondence Details
[7 empty] | From Client / Eng. | [7 empty] | From Main Con. | [7 empty] | From Sub. Con | [9 empty] | From Client / Eng. | [7 empty] | From Main Con. | [8 empty] | From Sub. Con
Total Received
Response Req.
Responded
Open
Scope Management Matrix
VO # / Client Ref. |  | Description |  |  |  | Cost of VO | [9 empty] | VO Cost Breakdown (Approved) | [20 empty] | Current Status | [15 empty] | Remarks
[6 empty] | Submitted | [5 empty] | Approved |  |  |  | Material |  |  |  |  | Resources |  |  |  | Indirect Cost | [6 empty] | O/H, M-Res + Profit |  |  |  |  | Progress |  |  |  |  | Claim |  |  |  |  | Certification
Area of Concerns
Discipline |  |  |  | Concern | [17 empty] | Impact | [17 empty] | Recommendation
Progress Photograph
(Major Activity only)
Lesson Learned
S.# |  | Category | [6 empty] | Issue Name | [9 empty] | Problem / Success | [11 empty] | Impact | [10 empty] | Recommendation
Admin Report
|  |  |  | Last Month | [20 empty] | This Month | [23 empty] | Next Month
|  |  |  | Expire / Due | [8 empty] | Received |  |  |  |  | Still to Received | [6 empty] | Expire / Due | [8 empty] | Received | [6 empty] | Still to Received | [7 empty] | Look Ahead (Expire / Due)
Iqama
ATM
Insurance Card
Gate Pass
Exit / Pass / Leave Dues
* Detail monthly Report with name should be sent to Administration Department
January - 2014