## Weekly Detailed EVM Hrs
Project Name | [7 empty] | Data Date: |  | 2020-12-27
Location | [7 empty] | Current Week |  | 48
[8 empty] | Total Weeks |  | 114
1817-Zone | 1817-BOQ Summary | Activity ID | Activity Name | Budget hrs | Planned Hrs | Earned Hrs | Planned Hrs % Compl. | Planned Weightage % | Actual Weightage % | Actual Hrs % Complete | Hours Productivity
Z1 | Div 01 | PRL-MOB-1020 | Site Office Establishment | 162 | 162 | 124 | 100% | 0.0001868% | 0.0001429% | 76.54% | 76.54%
|  | PRL-MOB-1050 | Project Sign Boards and Hoarding | 162 | 162 | 124 | 100% | 0.0001868% | 0.0001429% | 76.54% | 76.54%
|  | PRL-MOB-1100 | Yards & Stores Establishment | 190 | 190 | 145 | 100% | 0.000219% | 0.0001672% | 76.32% | 76.32%
| Div 02 | C-EW-10370 | Excavation Stage 1 - Z1 | 2271 | 2271 | 1249 | 100% | 0.002618% | 0.00144% | 55% | 55%
|  | C-EW-10390 | Excavation Stage 2 - Z1 | 2272 | 2272 | 1250 | 100% | 0.002619% | 0.001441% | 55.02% | 55.02%
|  | C-EW-10450 | Waterproof Membrane on Gunite Wall - Z1-B1 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
|  | C-EW-2430 | Waterproof Membrane on Gunite Wall - Z1-B2 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
|  | C-SHRNG-DCE-C-2330 | Place Guide Wall - Z1 | 249 | 249 | 274 | 100% | 0.0002871% | 0.0003159% | 110% | 110%
|  | C-SHRNG-DCE-C-2350 | Install Capping Beam - Z1 | 2461 | 2461 | 1353 | 100% | 0.002837% | 0.00156% | 54.98% | 54.98%
|  | PRL-MOB-SCW-2330 | Clearing Existing Utilities | 495 | 495 | 272 | 100% | 0.0005706% | 0.0003136% | 54.95% | 54.95%
| Div 03 | C-EW-2420 | Gunite Wall - Z1 | 333 | 333 | 283 | 1 | 3.8389e-06 | 3.2625e-06 | 0.84985 | 84.98%
|  | Z1-C-CON-2400 | PCC Blind Concrete - Z1 - Lift Pit | 6 | 6 | 5 | 100% | 6.917e-06% | 5.764e-06% | 83.33% | 83.33%
|  | Z1-C-CON-2440 | Waterproof Membrane - Z1 - Lift Pit | 40 | 40 | 34 | 100% | 4.611e-05% | 3.92e-05% | 85% | 85%
|  | Z1-C-CON-2450 | Protection Screed - Z1 - Lift Pit | 24 | 24 | 20 | 100% | 2.767e-05% | 2.306e-05% | 83.33% | 83.33%
|  | Z1-C-CON-2460 | Fix Rebar - Z1 - Lift Pit | 497 | 497 | 422 | 100% | 0.000573% | 0.0004865% | 84.91% | 84.91%
|  | Z1-C-CON-2480 | Pour Concrete - Z1 - Lift Pit | 95 | 95 | 81 | 100% | 0.0001095% | 9.338e-05% | 85.26% | 85.26%
|  | Z1-C-CON-2500 | PCC Blind Concrete - Z1 - Raft | 196 | 196 | 167 | 100% | 0.000226% | 0.0001925% | 85.2% | 85.2%
|  | Z1-C-CON-2510 | Waterproof Membrane - Z1 - Raft | 1560 | 1560 | 1326 | 100% | 0.001798% | 0.001529% | 85% | 85%
|  | Z1-C-CON-2520 | Protection Screed - Z1 - Raft | 96 | 96 | 3 | 100% | 0.0001107% | 3.458e-06% | 3.125% | 3.125%
|  | Z1-C-CON-2530 | Fix Rebar - Z1 - Raft | 18159 | 18159 | 182 | 100% | 0.02093% | 0.0002098% | 1.002% | 1.002%
|  | Z1-C-CON-2550 | Fix Formwork - Z1 - Raft | 261 | 261 | 55 | 100% | 0.0003009% | 6.341e-05% | 21.07% | 21.07%
|  | Z1-C-CON-2560 | Pour Concrete - Z1 - Raft | 4422 | 4422 | 940 | 100% | 0.005098% | 0.001084% | 21.26% | 21.26%
|  | Z1-C-CON-2570 | Fix Rebar Core Walls - Z1 - B2 | 1609 | 1609 | 342 | 100% | 0.001855% | 0.0003943% | 21.26% | 21.26%
|  | Z1-C-CON-2580 | Fix Formwork Core Walls - Z1 - B2 | 1547 | 1547 | 1315 | 100% | 0.001783% | 0.001516% | 85% | 85%
|  | Z1-C-CON-2600 | Fix Rebar Retaining Walls - Z1 - B2 | 2863 | 2863 | 1216 | 100% | 0.003301% | 0.001402% | 42.47% | 42.47%
|  | Z1-C-CON-2610 | Fix Formwork Retaining Walls - Z1 - B2 | 2342 | 2342 | 498 | 100% | 0.0027% | 0.0005741% | 21.26% | 21.26%
|  | Z1-C-CON-2620 | Pour Concrete Retaining Walls - Z1 - B2 | 482 | 482 | 410 | 100% | 0.0005557% | 0.0004727% | 85.06% | 85.06%
|  | Z1-C-CON-2630 | Pour Concrete Core Walls - Z1 - B2 | 248 | 248 | 211 | 100% | 0.0002859% | 0.0002432% | 85.08% | 85.08%
|  | Z1-C-CON-2640 | Fix Rebar Columns - Z1 - B2 | 3020 | 3020 | 1284 | 100% | 0.003482% | 0.00148% | 42.52% | 42.52%
|  | Z1-C-CON-2650 | Fix Formwork Columns - Z1 - B2 | 889 | 889 | 189 | 100% | 0.001025% | 0.0002179% | 21.26% | 21.26%
|  | Z1-C-CON-2660 | Pour Concrete Columns - Z1 - B2 | 174 | 174 | 37 | 100% | 0.0002006% | 4.265e-05% | 21.26% | 21.26%
|  | Z1-C-CON-2670 | Fix Formwork Stairs - Z1 - B2 | 4 | 4 | 1 | 100% | 4.611e-06% | 1.153e-06% | 25% | 25%
|  | Z1-C-CON-2680 | Fix Rebar Stairs - Z1 - B2 | 43 | 43 | 1 | 100% | 4.957e-05% | 1.153e-06% | 2.326% | 2.326%
|  | Z1-C-CON-2690 | Pour Concrete Stairs - Z1 - B2 | 8 | 8 | 0 | 100% | 9.223e-06% |  | 0% | 0%
|  | Z1-C-CON-2700 | Pour Concrete Slabs - Z1 - B1 | 1426 | 1426 | 1212 | 100% | 0.001644% | 0.001397% | 84.99% | 84.99%
|  | Z1-C-CON-2710 | Fix Formwork Slabs - Z1 - B1 | 4167 | 4167 | 3542 | 100% | 0.004804% | 0.004083% | 85% | 85%
|  | Z1-C-CON-2720 | Fix Rebar Slabs - Z1 - B1 | 5965 | 5965 | 5070 | 100% | 0.006877% | 0.005845% | 85% | 85%
|  | Z1-C-CON-2730 | Fix Rebar Retaining Walls - Z1 - B1 | 2275 | 2275 | 23 | 100% | 0.002623% | 2.651e-05% | 1.011% | 1.011%
|  | Z1-C-CON-2740 | Fix Formwork Retaining Walls - Z1 - B1 | 2342 | 2342 | 70 | 100% | 0.0027% | 8.07e-05% | 2.989% | 2.989%
|  | Z1-C-CON-2750 | Pour Concrete Retaining Walls - Z1 - B1 | 484 | 484 | 20 | 100% | 0.000558% | 2.306e-05% | 4.132% | 4.132%
|  | Z1-C-CON-2760 | Fix Rebar Core Walls - Z1 - B1 | 1493 | 1493 | 15 | 100% | 0.001721% | 1.729e-05% | 1.005% | 1.005%
|  | Z1-C-CON-2770 | Fix Formwork Core Walls - Z1 - B1 | 1539 | 1539 | 240 | 100% | 0.001774% | 0.0002767% | 15.59% | 15.59%
|  | Z1-C-CON-2780 | Pour Concrete Core Walls - Z1 - B1 | 284 | 284 | 6 | 100% | 0.0003274% | 6.917e-06% | 2.113% | 2.113%
|  | Z1-C-CON-2790 | Fix Rebar Columns - Z1 - B1 | 2314 | 2314 | 315 | 100% | 0.002668% | 0.0003631% | 13.61% | 13.61%
|  | Z1-C-CON-2800 | Fix Formwork Columns - Z1 - B1 | 991 | 991 | 30 | 100% | 0.001142% | 3.458e-05% | 3.027% | 3.027%
|  | Z1-C-CON-2810 | Pour Concrete Columns - Z1 - B1 | 194 | 194 | 30 | 100% | 0.0002236% | 3.458e-05% | 15.46% | 15.46%
|  | Z1-C-CON-2820 | Fix Formwork Stairs - Z1 - B1 | 4 | 4 | 0 | 100% | 4.611e-06% |  | 0% | 0%
|  | Z1-C-CON-2830 | Fix Rebar Stairs - Z1 - B1 | 43 | 43 | 3 | 100% | 4.957e-05% | 3.458e-06% | 6.977% | 6.977%
|  | Z1-C-CON-2840 | Pour Concrete Stairs - Z1 - B1 | 8 | 8 | 0 | 100% | 9.223e-06% |  | 0% | 0%
|  | Z1-C-CON-3000 | Fix Formwork Slabs - Z1 - GF | 4684 | 4684 | 94 | 100% | 0.0054% | 0.0001084% | 2.007% | 2.007%
|  | Z1-C-CON-3010 | Fix Rebar Slabs - Z1 - GF | 11392 | 11392 | 9683 | 100% | 0.01313% | 0.01116% | 85% | 85%
|  | Z1-C-CON-3020 | Pour Concrete Slabs - Z1 - GF | 1908 | 1908 | 114 | 100% | 0.0022% | 0.0001314% | 5.975% | 5.975%
|  | Z1-C-CON-3030 | Fix Rebar Core Walls - Z1 - GF | 2275 | 2275 | 136 | 100% | 0.002623% | 0.0001568% | 5.978% | 5.978%
|  | Z1-C-CON-3040 | Fix Formwork Core Walls - Z1 - GF | 2295 | 1377 | 1211 | 60% | 0.001587% | 0.001396% | 52.77% | 87.94%
|  | Z1-C-CON-3060 | Fix Rebar Columns - Z1 - GF | 3008 | 3008 | 180 | 100% | 0.003468% | 0.0002075% | 5.984% | 5.984%
|  | Z1-C-CON-3070 | Fix Formwork Columns - Z1 - GF | 1515 | 1515 | 1416 | 100% | 0.001747% | 0.001632% | 93.47% | 93.47%
|  | Z1-C-CON-3080 | Pour Concrete Columns - Z1 - GF | 300 | 262 | 158 | 87.33% | 0.000302% | 0.0001821% | 52.67% | 60.31%
|  | Z1-C-CON-5840 | Fix Formwork Ramp - Z1 - B2 | 270 | 270 | 229 | 100% | 0.0003113% | 0.000264% | 84.81% | 84.81%
|  | Z1-C-CON-5850 | Fix Rebar Ramp - Z1 - B2 | 97 | 97 | 1 | 100% | 0.0001118% | 1.153e-06% | 1.031% | 1.031%
|  | Z1-C-CON-5860 | Pour Concrete Ramp - Z1 - B2 | 114 | 114 | 1 | 100% | 0.0001314% | 1.153e-06% | 0.8772% | 0.8772%
|  | Z1-C-CON-5870 | Fix Formwork Ramp - Z1 - B1 | 231 | 231 | 14 | 100% | 0.0002663% | 1.614e-05% | 6.061% | 6.061%
|  | Z1-C-CON-5880 | Fix Rebar Ramp - Z1 - B1 | 372 | 372 | 22 | 100% | 0.0004288% | 2.536e-05% | 5.914% | 5.914%
|  | Z1-C-CON-5890 | Pour Concrete Ramp - Z1 - B1 | 98 | 98 | 6 | 100% | 0.000113% | 6.917e-06% | 6.122% | 6.122%
|  | Z1-C-CON-5900 | Fix Rebar Core Walls Ramp - Z1 - B2 | 1055 | 1055 | 897 | 100% | 0.001216% | 0.001034% | 85.02% | 85.02%
|  | Z1-C-CON-5910 | Fix Formwork Walls Ramp - Z1 - B2 | 1040 | 1040 | 884 | 100% | 0.001199% | 0.001019% | 85% | 85%
|  | Z1-C-CON-5920 | Pour Concrete Core Walls Ramp - Z1 - B2 | 152 | 152 | 129 | 100% | 0.0001752% | 0.0001487% | 84.87% | 84.87%
|  | Z1-C-CON-5930 | Fix Rebar Core Walls Ramp - Z1 - B1 | 1015 | 1015 | 20 | 100% | 0.00117% | 2.306e-05% | 1.97% | 1.97%
|  | Z1-C-CON-5940 | Fix Formwork Walls Ramp - Z1 - B1 | 1050 | 1050 | 143 | 100% | 0.00121% | 0.0001649% | 13.62% | 13.62%
|  | Z1-C-CON-5950 | Pour Concrete Core Walls Ramp - Z1 - B1 | 152 | 152 | 129 | 100% | 0.0001752% | 0.0001487% | 84.87% | 84.87%
| Div 04 | Z1-C-FIN-5790 | Masonry Works - Z1 - B2 | 38 | 38 | 2 | 100% | 4.381e-05% | 2.306e-06% | 5.263% | 5.263%
| Div 10 | Z1-C-CON-2540 | Fix MEP Provisions - Z1 - Raft | 100 | 100 | 21 | 100% | 0.0001153% | 2.421e-05% | 21% | 21%
| Div 15 | Z1-C-MEP-5810 | Fix G.I Box and conduits - Z1 - B2 | 50 | 29 | 26 | 58% | 3.343e-05% | 2.997e-05% | 52% | 89.66%
Z2 | Div 02 | C-EW-10400 | Excavation Stage 2 - Z2&3 | 3408 | 3408 | 2207 | 100% | 0.003929% | 0.002544% | 64.76% | 64.76%
|  | C-EW-10440 | Excavation Stage 1 - Z2&3 | 3409 | 3409 | 2082 | 100% | 0.00393% | 0.0024% | 61.07% | 61.07%
|  | C-EW-10460 | Waterproof Membrane on Gunite Wall - Z2-B1 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
|  | C-EW-10480 | Gunite Wall - Z3 | 333 | 333 |  | 100% | 0.0003839% |  | 0% | 0%
|  | C-SHRNG-DCE-C-2360 | Place Guide Wall - Z2&3 | 249 | 249 | 274 | 100% | 0.0002871% | 0.0003159% | 110% | 110%
|  | C-SHRNG-DCE-C-2380 | Install Capping Beam - Z2&3 | 3692 | 3692 | 4062 | 100% | 0.004256% | 0.004683% | 110% | 110%
|  | Z2-C-EW-10420 | Waterproof Membrane on Gunite Wall - Z2-B2 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
| Div 03 | C-EW-10410 | Gunite Wall - Z2 | 333 | 333 | 3 | 100% | 0.0003839% | 3.458e-06% | 0.9009% | 0.9009%
|  | Z2-C-CON-5840 | PCC Blind Concrete - Z2 - Lift Pit | 4 | 4 | 0 | 100% | 4.611e-06% |  | 0% | 0%
|  | Z2-C-CON-5850 | Waterproof Membrane - Z2 - Lift Pit | 20 | 20 | 0 | 100% | 2.306e-05% |  | 0% | 0%
|  | Z2-C-CON-5860 | Protection Screed - Z2 - Lift Pit | 26 | 26 | 0 | 100% | 2.997e-05% |  | 0% | 0%
|  | Z2-C-CON-5870 | Fix Rebar - Z2 - Lift Pit | 249 | 249 | 5 | 100% | 0.0002871% | 5.764e-06% | 2.008% | 2.008%
|  | Z2-C-CON-5890 | Pour Concrete - Z2 - Lift Pit | 72 | 72 | 15 | 100% | 8.3e-05% | 1.729e-05% | 20.83% | 20.83%
|  | Z2-C-CON-5900 | PCC Blind Concrete - Z2 - Raft | 148 | 148 | 31 | 100% | 0.0001706% | 3.574e-05% | 20.95% | 20.95%
|  | Z2-C-CON-5910 | Waterproof Membrane - Z2 - Raft | 1180 | 1180 | 251 | 100% | 0.00136% | 0.0002894% | 21.27% | 21.27%
|  | Z2-C-CON-5920 | Protection Screed - Z2 - Raft | 72 | 72 | 15 | 100% | 8.3e-05% | 1.729e-05% | 20.83% | 20.83%
|  | Z2-C-CON-5930 | Fix Rebar - Z2 - Raft | 13737 | 13737 | 11676 | 100% | 0.01584% | 0.01346% | 85% | 85%
|  | Z2-C-CON-5950 | Fix Formwork - Z2 - Raft | 196 | 196 | 167 | 100% | 0.000226% | 0.0001925% | 85.2% | 85.2%
|  | Z2-C-CON-5960 | Pour Concrete - Z2 - Raft | 3317 | 3317 | 2819 | 100% | 0.003824% | 0.00325% | 84.99% | 84.99%
|  | Z2-C-CON-5970 | Fix Rebar Columns - Z2 - B2 | 2266 | 2266 | 1926 | 100% | 0.002612% | 0.00222% | 85% | 85%
|  | Z2-C-CON-5980 | Fix Formwork Columns - Z2 - B2 | 667 | 667 | 567 | 100% | 0.0007689% | 0.0006536% | 85.01% | 85.01%
|  | Z2-C-CON-5990 | Pour Concrete Columns - Z2 - B2 | 130 | 130 | 110 | 100% | 0.0001499% | 0.0001268% | 84.62% | 84.62%
|  | Z2-C-CON-6000 | Fix Rebar Retaining Walls - Z2 - B2 | 1432 | 1432 | 1217 | 100% | 0.001651% | 0.001403% | 84.99% | 84.99%
|  | Z2-C-CON-6010 | Fix Formwork Retaining Walls - Z2 - B2 | 1171 | 1171 | 995 | 100% | 0.00135% | 0.001147% | 84.97% | 84.97%
|  | Z2-C-CON-6020 | Pour Concrete Retaining Walls - Z2 - B2 | 240 | 240 | 204 | 100% | 0.0002767% | 0.0002352% | 85% | 85%
|  | Z2-C-CON-6030 | Pour Concrete Core Walls - Z2 - B2 | 136 | 136 | 116 | 100% | 0.0001568% | 0.0001337% | 85.29% | 85.29%
|  | Z2-C-CON-6040 | Fix Rebar Core Walls - Z2 - B2 | 950 | 950 | 807 | 100% | 0.001095% | 0.0009303% | 84.95% | 84.95%
|  | Z2-C-CON-6050 | Fix Formwork Core Walls - Z2 - B2 | 936 | 936 | 796 | 100% | 0.001079% | 0.0009176% | 85.04% | 85.04%
|  | Z2-C-CON-6060 | Fix Formwork Stairs - Z2 - B2 | 3 | 3 | 0 | 100% | 3.458e-06% |  | 0% | 0%
|  | Z2-C-CON-6070 | Fix Rebar Stairs - Z2 - B2 | 32 | 32 | 1 | 100% | 3.689e-05% | 1.153e-06% | 3.125% | 3.125%
|  | Z2-C-CON-6080 | Pour Concrete Stairs - Z2 - B2 | 8 | 8 | 1 | 100% | 9.223e-06% | 1.153e-06% | 12.5% | 12.5%
|  | Z2-C-CON-6090 | Fix Rebar Retaining Walls - Z2 - B1 | 1138 | 1138 | 155 | 100% | 0.001312% | 0.0001787% | 13.62% | 13.62%
|  | Z2-C-CON-6100 | Fix Formwork Retaining Walls - Z2 - B1 | 1171 | 1171 | 269 | 100% | 0.00135% | 0.0003101% | 22.97% | 22.97%
|  | Z2-C-CON-6110 | Pour Concrete Retaining Walls - Z2 - B1 | 240 | 240 | 14 | 100% | 0.0002767% | 1.614e-05% | 5.833% | 5.833%
|  | Z2-C-CON-6120 | Fix Formwork Core Walls - Z2 - B1 | 946 | 946 | 804 | 100% | 0.001091% | 0.0009269% | 84.99% | 84.99%
|  | Z2-C-CON-6130 | Fix Rebar Core Walls - Z2 - B1 | 913 | 913 | 18 | 100% | 0.001053% | 2.075e-05% | 1.972% | 1.972%
|  | Z2-C-CON-6140 | Pour Concrete Core Walls - Z2 - B1 | 138 | 138 | 7 | 100% | 0.0001591% | 8.07e-06% | 5.072% | 5.072%
|  | Z2-C-CON-6150 | Fix Rebar Columns - Z2 - B1 | 1735 | 1735 | 35 | 100% | 0.002% | 4.035e-05% | 2.017% | 2.017%
|  | Z2-C-CON-6160 | Fix Formwork Columns - Z2 - B1 | 743 | 743 | 101 | 100% | 0.0008565% | 0.0001164% | 13.59% | 13.59%
|  | Z2-C-CON-6170 | Pour Concrete Columns - Z2 - B1 | 146 | 146 | 20 | 100% | 0.0001683% | 2.306e-05% | 13.7% | 13.7%
|  | Z2-C-CON-6210 | Fix Formwork Slabs - Z2 - B1 | 3041 | 3041 | 2585 | 100% | 0.003506% | 0.00298% | 85% | 85%
|  | Z2-C-CON-6220 | Fix Rebar Slabs - Z2 - B1 | 4027 | 4027 | 121 | 100% | 0.004642% | 0.0001395% | 3.005% | 3.005%
|  | Z2-C-CON-6230 | Pour Concrete Slabs - Z2 - B1 | 1036 | 1036 | 21 | 100% | 0.001194% | 2.421e-05% | 2.027% | 2.027%
|  | Z2-C-CON-6340 | Fix Formwork Slabs - Z2 - GF | 2844 | 2844 | 171 | 100% | 0.003279% | 0.0001971% | 6.013% | 6.013%
|  | Z2-C-CON-6350 | Fix Rebar Slabs - Z2 - GF | 7049 | 4934 | 3718 | 70% | 0.005688% | 0.004286% | 52.75% | 75.35%
| Div 10 | Z2-C-CON-5940 | Fix MEP Provisions - Z2 - Raft | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
Z3 | Div 02 | C-EW-10490 | Waterproof Membrane on Gunite Wall - Z3-B2 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
|  | C-EW-10520 | Waterproof Membrane on Gunite Wall - Z3-B1 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
| Div 03 | Z3-C-CON-5840 | PCC Blind Concrete - Z3 - Lift Pit | 4 | 4 | 0 | 100% | 4.611e-06% |  | 0% | 0%
|  | Z3-C-CON-5860 | Protection Screed - Z3 - Lift Pit | 26 | 26 | 0 | 100% | 2.997e-05% |  | 0% | 0%
|  | Z3-C-CON-5870 | Fix Rebar - Z3 - Lift Pit | 248 | 248 | 2 | 100% | 0.0002859% | 2.306e-06% | 0.8065% | 0.8065%
|  | Z3-C-CON-5890 | Pour Concrete - Z3 - Lift Pit | 72 | 72 | 15 | 100% | 8.3e-05% | 1.729e-05% | 20.83% | 20.83%
|  | Z3-C-CON-5900 | PCC Blind Concrete - Z3 - Raft | 148 | 148 | 126 | 100% | 0.0001706% | 0.0001453% | 85.14% | 85.14%
|  | Z3-C-CON-5920 | Protection Screed - Z3 - Raft | 74 | 74 | 63 | 100% | 8.531e-05% | 7.263e-05% | 85.14% | 85.14%
|  | Z3-C-CON-5930 | Fix Rebar - Z3 - Raft | 13737 | 13737 | 11676 | 100% | 0.01584% | 0.01346% | 85% | 85%
|  | Z3-C-CON-5950 | Fix Formwork - Z3 - Raft | 196 | 196 | 167 | 100% | 0.000226% | 0.0001925% | 85.2% | 85.2%
|  | Z3-C-CON-5960 | Pour Concrete - Z3 - Raft | 3317 | 3317 | 2819 | 100% | 0.003824% | 0.00325% | 84.99% | 84.99%
|  | Z3-C-CON-5970 | Fix Rebar Columns - Z3 - B2 | 2265 | 2265 | 1925 | 100% | 0.002611% | 0.002219% | 84.99% | 84.99%
|  | Z3-C-CON-5980 | Fix Formwork Columns - Z3 - B2 | 668 | 668 | 91 | 100% | 0.0007701% | 0.0001049% | 13.62% | 13.62%
|  | Z3-C-CON-5990 | Pour Concrete Columns - Z3 - B2 | 132 | 132 | 18 | 100% | 0.0001522% | 2.075e-05% | 13.64% | 13.64%
|  | Z3-C-CON-6000 | Fix Rebar Retaining Walls - Z3 - B2 | 1433 | 1433 | 1218 | 100% | 0.001652% | 0.001404% | 85% | 85%
|  | Z3-C-CON-6010 | Fix Formwork Retaining Walls - Z3 - B2 | 1172 | 1172 | 159 | 100% | 0.001351% | 0.0001833% | 13.57% | 13.57%
|  | Z3-C-CON-6020 | Pour Concrete Retaining Walls - Z3 - B2 | 242 | 242 | 2 | 100% | 0.000279% | 2.306e-06% | 0.8264% | 0.8264%
|  | Z3-C-CON-6030 | Pour Concrete Core Walls - Z3 - B2 | 136 | 136 | 1 | 100% | 0.0001568% | 1.153e-06% | 0.7353% | 0.7353%
|  | Z3-C-CON-6040 | Fix Rebar Core Walls - Z3 - B2 | 949 | 949 | 9 | 100% | 0.001094% | 1.038e-05% | 0.9484% | 0.9484%
|  | Z3-C-CON-6050 | Fix Formwork Core Walls - Z3 - B2 | 936 | 936 | 9 | 100% | 0.001079% | 1.038e-05% | 0.9615% | 0.9615%
|  | Z3-C-CON-6060 | Fix Formwork Stairs - Z3 - B2 | 3 | 3 | 3 | 100% | 3.458e-06% | 3.458e-06% | 100% | 100%
|  | Z3-C-CON-6070 | Fix Rebar Stairs - Z3 - B2 | 32 | 32 | 4 | 100% | 3.689e-05% | 4.611e-06% | 12.5% | 12.5%
|  | Z3-C-CON-6080 | Pour Concrete Stairs - Z3 - B2 | 8 | 8 | 0 | 100% | 9.223e-06% |  | 0% | 0%
|  | Z3-C-CON-6090 | Fix Rebar Retaining Walls - Z3 - B1 | 1138 | 1138 | 68 | 100% | 0.001312% | 7.839e-05% | 5.975% | 5.975%
|  | Z3-C-CON-6100 | Fix Formwork Retaining Walls - Z3 - B1 | 1171 | 1171 | 70 | 100% | 0.00135% | 8.07e-05% | 5.978% | 5.978%
|  | Z3-C-CON-6110 | Pour Concrete Retaining Walls - Z3 - B1 | 240 | 240 | 112 | 100% | 0.0002767% | 0.0001291% | 46.67% | 46.67%
|  | Z3-C-CON-6120 | Fix Formwork Core Walls - Z3 - B1 | 945 | 945 | 57 | 100% | 0.001089% | 6.571e-05% | 6.032% | 6.032%
|  | Z3-C-CON-6130 | Fix Rebar Core Walls - Z3 - B1 | 914 | 914 | 629 | 100% | 0.001054% | 0.0007251% | 68.82% | 68.82%
|  | Z3-C-CON-6140 | Pour Concrete Core Walls - Z3 - B1 | 138 | 138 | 8 | 100% | 0.0001591% | 9.223e-06% | 5.797% | 5.797%
|  | Z3-C-CON-6150 | Fix Rebar Columns - Z3 - B1 | 1735 | 1735 | 1475 | 100% | 0.002% | 0.0017% | 85.01% | 85.01%
|  | Z3-C-CON-6160 | Fix Formwork Columns - Z3 - B1 | 743 | 743 | 45 | 100% | 0.0008565% | 5.188e-05% | 6.057% | 6.057%
|  | Z3-C-CON-6170 | Pour Concrete Columns - Z3 - B1 | 146 | 146 | 9 | 100% | 0.0001683% | 1.038e-05% | 6.164% | 6.164%
|  | Z3-C-CON-6210 | Fix Formwork Slabs - Z3 - B1 | 3040 | 3040 | 91 | 100% | 0.003505% | 0.0001049% | 2.993% | 2.993%
|  | Z3-C-CON-6220 | Fix Rebar Slabs - Z3 - B1 | 4028 | 4028 | 81 | 100% | 0.004644% | 9.338e-05% | 2.011% | 2.011%
|  | Z3-C-CON-6230 | Pour Concrete Slabs - Z3 - B1 | 1036 | 1036 | 881 | 100% | 0.001194% | 0.001016% | 85.04% | 85.04%
|  | Z3-C-CON-6340 | Fix Formwork Slabs - Z3 - GF | 2844 | 1422 | 1501 | 50% | 0.001639% | 0.00173% | 52.78% | 105.6%
| Div 10 | Z3-C-CON-5940 | Fix MEP Provisions - Z3 - Raft | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
Grand Total |  |  |  | 212819 | 208305 | 101795 | 97.88% | 0.2401% | 0.1174% | 47.83% | 48.87%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Weekly Hrs Summary
Project Name |  |  |  |  | Weekly Progress Hours Summary | [5 empty] | Data Date: | 2020-12-27
Location | [10 empty] | Current Week | 48
BOQ Item Wise Summary | [10 empty] | Total Weeks | 114
1817-BOQ Summary | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs % | Actual Hrs % | 1817-BOQ Summary | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs %
Div 01 | 514 | 514 | 393 | 100% | 76.46% | Div 01 | 514 | 514 | 393 | 100%
Div 02 | 20039 | 20039 | 13023 | 100% | 64.99% | Div 02 | 20039 | 20039 | 13023 | 100%
Div 03 | 377918 | 187385 | 118812 | 49.58% | 31.44% | Div 03 | 377918 | 187385 | 118812 | 49.58% |  |  | Row Labels | Sum of WeekID
Div 04 | 22530 | 38 | 1762 | 0.1687% | 7.821% | Div 04 | 22530 | 38 | 1762 | 0.1687% |  |  | 1 | 1
Div 05 | 6395 |  | 13 | 0% | 0.2033% | Div 05 | 6395 | 0 | 13 | 0% |  |  | 2 | 2
Div 06 | 1800 |  |  | 0% | 0% | Div 06 | 1800 | 0 | 0 | 0% |  |  | 3 | 3
Div 07 | 15326 |  |  | 0% | 0% | Div 07 | 15326 | 0 | 0 | 0% |  |  | 4 | 4
Div 08 | 12173 |  | 333 | 0% | 2.736% | Div 08 | 12173 | 0 | 333 | 0% |  |  | 5 | 5
Div 09 | 239501 |  | 21091 | 0% | 8.806% | Div 09 | 239501 | 0 | 21091 | 0% |  |  | 6 | 6
Div 10 | 16004 | 300 | 844 | 1.875% | 5.274% | Div 10 | 16004 | 300 | 844 | 1.875% |  |  | 7 | 7
Div 11 | 15404 |  | 1122 | 0% | 7.284% | Div 11 | 15404 | 0 | 1122 | 0% |  |  | 8 | 8
Div 12 | 27542 |  | 2269 | 0% | 8.238% | Div 12 | 27542 | 0 | 2269 | 0% |  |  | 9 | 9
Div 13 | 4682 |  |  | 0% | 0% | Div 13 | 4682 | 0 | 0 | 0% |  |  | 10 | 10
Div 14 | 2173 |  |  | 0% | 0% | Div 14 | 2173 | 0 | 0 | 0% |  |  | 11 | 11
Div 15 | 29297 | 29 | 2150 | 0.09899% | 7.339% | Div 15 | 29297 | 29 | 2150 | 0.09899% |  |  | 12 | 12
Grand Total | 791298 | 208305 | 161812 | 26.32% | 20.45% | Grand Total | 791298 | 208305 | 161812 | 26.32% |  |  | 13 | 13
[13 empty] | 14 | 14
Trade Item Wise Summary | [12 empty] | 15 | 15
1817-Trade | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs % | Actual Hrs % | 1817-Trade | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs % | Actual Hrs % |  | 16 | 16
Anti-Fungal & Carbonation | 12793 |  | 3224 | 0% | 25.2% | Anti-Fungal & Carbonation | 12793 | 0 | 3224 | 0% | 25.2% |  | 17 | 17
Ceramic | 12431 |  |  | 0% | 0% | Ceramic | 12431 | 0 | 0 | 0% | 0% |  | 18 | 18
Concrete | 377918 | 187385 | 118812 | 49.58% | 31.44% | Concrete | 377918 | 187385 | 118812 | 49.58% | 31.44% |  | 19 | 19
Conveying System | 4682 |  |  | 0% | 0% | Conveying System | 4682 | 0 | 0 | 0% | 0% |  | 20 | 20
Doors | 5692 |  | 333 | 0% | 5.85% | Doors | 5692 | 0 | 333 | 0% | 5.85% |  | 21 | 21
Electrical | 28801 | 29 | 2150 | 0.1007% | 7.465% | Electrical | 28801 | 29 | 2150 | 0.1007% | 7.465% |  | 22 | 22
Epoxy & Traffic Coating | 4452 |  | 24 | 0% | 0.5391% | Epoxy & Traffic Coating | 4452 | 0 | 24 | 0% | 0.5391% |  | 23 | 23
False Ceiling | 20728 |  | 7 | 0% | 0.03377% | False Ceiling | 20728 | 0 | 7 | 0% | 0.03377% |  | 24 | 24
Fire Fighting | 15404 |  | 1122 | 0% | 7.284% | Fire Fighting | 15404 | 0 | 1122 | 0% | 7.284% |  | 25 | 25
Glazing | 5473 |  |  | 0% | 0% | Glazing | 5473 | 0 | 0 | 0% | 0% |  | 26 | 26
HVAC | 27438 |  | 2269 | 0% | 8.27% | HVAC | 27438 | 0 | 2269 | 0% | 8.27% |  | 27 | 27
LPG System | 2173 |  |  | 0% | 0% | LPG System | 2173 | 0 | 0 | 0% | 0% |  | 28 | 28
Masonry | 22530 | 38 | 1762 | 0.1687% | 7.821% | Masonry | 22530 | 38 | 1762 | 0.1687% | 7.821% |  | 29 | 29
Natural Stone | 13058 |  |  | 0% | 0% | Natural Stone | 13058 | 0 | 0 | 0% | 0% |  | 30 | 30
Others Finishes | 36854 |  | 13 | 0% | 0.03527% | Others Finishes | 36854 | 0 | 13 | 0% | 0.03527% |  | 31 | 31
Paint | 18963 |  | 2067 | 0% | 10.9% | Paint | 18963 | 0 | 2067 | 0% | 10.9% |  | 32 | 32
Plaster | 112175 |  | 15634 | 0% | 13.94% | Plaster | 112175 | 0 | 15634 | 0% | 13.94% |  | 33 | 33
Plumbing | 16004 | 300 | 844 | 1.875% | 5.274% | Plumbing | 16004 | 300 | 844 | 1.875% | 5.274% |  | 34 | 34
Porcelain | 18774 |  | 135 | 0% | 0.7191% | Porcelain | 18774 | 0 | 135 | 0% | 0.7191% |  | 35 | 35
Prelims | 514 | 514 | 393 | 100% | 76.46% | Prelims | 514 | 514 | 393 | 26.32% | 20.45% |  | 36 | 36
Site Works | 20039 | 20039 | 13023 | 100% | 64.99% | [7 empty] | 37 | 37
Terrazo Tiles | 14402 |  |  | 0% | 0% | [7 empty] | 38 | 38
Grand Total | 791298 | 208305 | 161812 | 26.32% | 20.45% | [7 empty] | 39 | 39
[13 empty] | 40 | 40
[13 empty] | 41 | 41
[13 empty] | 42 | 42
[13 empty] | 43 | 43
[13 empty] | 44 | 44
[13 empty] | 45 | 45
[13 empty] | 46 | 46
[13 empty] | 47 | 47
[13 empty] | 48 | 48
[13 empty] | Grand Total | 1176
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Weekly Detailed EVM Cost
Project Name | [7 empty] | Data Date: |  | 2020-12-27
Location | [7 empty] | Current Week |  | 48
[8 empty] | Total Weeks |  | 114
1817-Zone | 1817-BOQ Summary | Activity ID | Activity Name | Budget Cost | Planned Cost | Earned Cost | Planned Cost % Compl. | Planned Weightage % | Actual Weightage % | Actual Cost % Complete | SPI
Z1 | Div 01 | PRL-MOB-1020 | Site Office Establishment | 767001 | 767001 | 586756 | 100% | 0.8842% | 0.6764% | 76.5% | 0.765
|  | PRL-MOB-1050 | Project Sign Boards and Hoarding | 60000 | 60000 | 45900 | 100% | 0.06917% | 0.05291% | 76.5% | 0.765
|  | PRL-MOB-1100 | Yards & Stores Establishment | 80000 | 80000 | 61200 | 100% | 0.09223% | 0.07055% | 76.5% | 0.765
| Div 02 | C-EW-10370 | Excavation Stage 1 - Z1 | 293640 | 293640 | 161502 | 100% | 0.3385% | 0.1862% | 55% | 0.55
|  | C-EW-10380 | Strut Pipe Bracing - Z1 | 162250 | 162250 | 178476 | 100% | 0.187% | 0.2058% | 110% | 1.1
|  | C-EW-10390 | Excavation Stage 2 - Z1 | 293641 | 293641 | 161503 | 100% | 0.3385% | 0.1862% | 55% | 0.55
|  | C-SHRNG-DCE-C-2330 | Place Guide Wall - Z1 | 162250 | 162250 | 178476 | 100% | 0.187% | 0.2058% | 110% | 1.1
|  | C-SHRNG-DCE-C-2340 | Install Shoring System - Z1 | 2016502 | 2016501 | 2218152 | 100% | 2.325% | 2.557% | 110% | 1.1
|  | C-SHRNG-DCE-C-2350 | Install Capping Beam - Z1 | 180856 | 180856 | 99471 | 100% | 0.2085% | 0.1147% | 55% | 0.55
|  | PRL-MOB-SCW-1600 | Soil Investigation & Report Submit | 55000 | 55000 | 42075 | 100% | 0.06341% | 0.0485% | 76.5% | 0.765
|  | PRL-MOB-SCW-2310 | Dewatering System Installation | 95000 | 95000 | 104500 | 100% | 0.1095% | 0.1205% | 110% | 1.1
|  | PRL-MOB-SCW-2320 | Demolition of Existing Structure | 140001 | 140001 | 77001 | 100% | 0.1614% | 0.08877% | 55% | 0.55
|  | PRL-MOB-SCW-2330 | Clearing Existing Utilities | 39000 | 39000 | 21450 | 100% | 0.04496% | 0.02473% | 55% | 0.55
| Div 03 | C-EW-2420 | Gunite Wall - Z1 | 152558 | 152558 | 129675 | 100% | 0.1759% | 0.1495% | 85% | 0.85
|  | Z1-C-CON-2400 | PCC Blind Concrete - Z1 - Lift Pit | 17220 | 17220 | 14637 | 100% | 0.01985% | 0.01687% | 85% | 0.85
|  | Z1-C-CON-2440 | Waterproof Membrane - Z1 - Lift Pit | 102280 | 102280 | 86938 | 100% | 0.1179% | 0.1002% | 85% | 0.85
|  | Z1-C-CON-2450 | Protection Screed - Z1 - Lift Pit | 10980 | 10980 | 9333 | 100% | 0.01266% | 0.01076% | 85% | 0.85
|  | Z1-C-CON-2460 | Fix Rebar - Z1 - Lift Pit | 20247 | 20247 | 17210 | 100% | 0.02334% | 0.01984% | 85% | 0.85
|  | Z1-C-CON-2480 | Pour Concrete - Z1 - Lift Pit | 20247 | 20247 | 17210 | 100% | 0.02334% | 0.01984% | 85% | 0.85
|  | Z1-C-CON-2500 | PCC Blind Concrete - Z1 - Raft | 51660 | 51660 | 43911 | 100% | 0.05955% | 0.05062% | 85% | 0.85
|  | Z1-C-CON-2510 | Waterproof Membrane - Z1 - Raft | 306840 | 306840 | 260814 | 100% | 0.3537% | 0.3007% | 85% | 0.85
|  | Z1-C-CON-2520 | Protection Screed - Z1 - Raft | 32940 | 32940 | 988 | 100% | 0.03797% | 0.001139% | 2.999% | 0.029994
|  | Z1-C-CON-2530 | Fix Rebar - Z1 - Raft | 687066 | 687066 | 6871 | 100% | 0.7921% | 0.007921% | 1% | 0.01
|  | Z1-C-CON-2550 | Fix Formwork - Z1 - Raft | 41321 | 41321 | 8781 | 100% | 0.04764% | 0.01012% | 21.25% | 0.21251
|  | Z1-C-CON-2560 | Pour Concrete - Z1 - Raft | 1004127 | 1004127 | 213377 | 100% | 1.158% | 0.246% | 21.25% | 0.2125
|  | Z1-C-CON-2570 | Fix Rebar Core Walls - Z1 - B2 | 49489 | 49489 | 10516 | 100% | 0.05705% | 0.01212% | 21.25% | 0.21249
|  | Z1-C-CON-2580 | Fix Formwork Core Walls - Z1 - B2 | 41489 | 41489 | 35266 | 100% | 0.04783% | 0.04066% | 85% | 0.85001
|  | Z1-C-CON-2600 | Fix Rebar Retaining Walls - Z1 - B2 | 87236 | 87236 | 37076 | 100% | 0.1006% | 0.04274% | 42.5% | 0.42501
|  | Z1-C-CON-2610 | Fix Formwork Retaining Walls - Z1 - B2 | 144300 | 144300 | 30664 | 100% | 0.1664% | 0.03535% | 21.25% | 0.2125
|  | Z1-C-CON-2620 | Pour Concrete Retaining Walls - Z1 - B2 | 288597 | 288597 | 245307 | 100% | 0.3327% | 0.2828% | 85% | 0.85
|  | Z1-C-CON-2630 | Pour Concrete Core Walls - Z1 - B2 | 161333 | 161333 | 137133 | 100% | 0.186% | 0.1581% | 85% | 0.85
|  | Z1-C-CON-2640 | Fix Rebar Columns - Z1 - B2 | 63240 | 63240 | 26878 | 100% | 0.0729% | 0.03099% | 42.5% | 0.42502
|  | Z1-C-CON-2650 | Fix Formwork Columns - Z1 - B2 | 132301 | 132301 | 28114 | 100% | 0.1525% | 0.03241% | 21.25% | 0.2125
|  | Z1-C-CON-2660 | Pour Concrete Columns - Z1 - B2 | 163921 | 163921 | 34833 | 100% | 0.189% | 0.04016% | 21.25% | 0.2125
|  | Z1-C-CON-2670 | Fix Formwork Stairs - Z1 - B2 | 2486 | 2486 | 338 | 100% | 0.002866% | 0.0003897% | 13.6% | 0.13596
|  | Z1-C-CON-2680 | Fix Rebar Stairs - Z1 - B2 | 4972 | 4972 | 99 | 100% | 0.005732% | 0.0001141% | 1.991% | 0.019912
|  | Z1-C-CON-2690 | Pour Concrete Stairs - Z1 - B2 | 4972 | 4972 | 99 | 100% | 0.005732% | 0.0001141% | 1.991% | 0.019912
|  | Z1-C-CON-2700 | Pour Concrete Slabs - Z1 - B1 | 315168 | 315168 | 267893 | 100% | 0.3633% | 0.3088% | 85% | 0.85
|  | Z1-C-CON-2710 | Fix Formwork Slabs - Z1 - B1 | 157584 | 157584 | 133946 | 100% | 0.1817% | 0.1544% | 85% | 0.85
|  | Z1-C-CON-2720 | Fix Rebar Slabs - Z1 - B1 | 315168 | 315168 | 267893 | 100% | 0.3633% | 0.3088% | 85% | 0.85
|  | Z1-C-CON-2730 | Fix Rebar Retaining Walls - Z1 - B1 | 87236 | 87236 | 872 | 100% | 0.1006% | 0.001005% | 0.9996% | 0.0099959
|  | Z1-C-CON-2740 | Fix Formwork Retaining Walls - Z1 - B1 | 43618 | 43618 | 1308 | 100% | 0.05028% | 0.001508% | 2.999% | 0.029988
|  | Z1-C-CON-2750 | Pour Concrete Retaining Walls - Z1 - B1 | 87236 | 87236 | 3490 | 100% | 0.1006% | 0.004023% | 4.001% | 0.040006
|  | Z1-C-CON-2760 | Fix Rebar Core Walls - Z1 - B1 | 49489 | 49489 | 495 | 100% | 0.05705% | 0.0005706% | 1% | 0.010002
|  | Z1-C-CON-2770 | Fix Formwork Core Walls - Z1 - B1 | 41489 | 41489 | 6473 | 100% | 0.04783% | 0.007462% | 15.6% | 0.15602
|  | Z1-C-CON-2780 | Pour Concrete Core Walls - Z1 - B1 | 60652 | 60652 | 1213 | 100% | 0.06992% | 0.001398% | 2% | 0.019999
|  | Z1-C-CON-2790 | Fix Rebar Columns - Z1 - B1 | 63240 | 63240 | 8601 | 100% | 0.0729% | 0.009915% | 13.6% | 0.13601
|  | Z1-C-CON-2800 | Fix Formwork Columns - Z1 - B1 | 31620 | 31620 | 948 | 100% | 0.03645% | 0.001093% | 2.998% | 0.029981
|  | Z1-C-CON-2810 | Pour Concrete Columns - Z1 - B1 | 63240 | 63240 | 9866 | 100% | 0.0729% | 0.01137% | 15.6% | 0.15601
|  | Z1-C-CON-2820 | Fix Formwork Stairs - Z1 - B1 | 2486 | 2486 | 149 | 100% | 0.002866% | 0.0001718% | 5.994% | 0.059936
|  | Z1-C-CON-2830 | Fix Rebar Stairs - Z1 - B1 | 4972 | 4972 | 298 | 100% | 0.005732% | 0.0003435% | 5.994% | 0.059936
|  | Z1-C-CON-2840 | Pour Concrete Stairs - Z1 - B1 | 4972 | 4972 | 298 | 100% | 0.005732% | 0.0003435% | 5.994% | 0.059936
|  | Z1-C-CON-3000 | Fix Formwork Slabs - Z1 - GF | 196850 | 196850 | 3937 | 100% | 0.2269% | 0.004539% | 2% | 0.02
|  | Z1-C-CON-3010 | Fix Rebar Slabs - Z1 - GF | 393700 | 393700 | 334644 | 100% | 0.4539% | 0.3858% | 85% | 0.85
|  | Z1-C-CON-3020 | Pour Concrete Slabs - Z1 - GF | 393699 | 393699 | 23622 | 100% | 0.4539% | 0.02723% | 6% | 0.06
|  | Z1-C-CON-3030 | Fix Rebar Core Walls - Z1 - GF | 72339 | 72339 | 4340 | 100% | 0.08339% | 0.005003% | 6% | 0.059995
|  | Z1-C-CON-3040 | Fix Formwork Core Walls - Z1 - GF | 37650 | 22590 | 19860 | 60% | 0.02604% | 0.0229% | 52.75% | 0.87915
|  | Z1-C-CON-3060 | Fix Rebar Columns - Z1 - GF | 96670 | 96670 | 5800 | 100% | 0.1114% | 0.006686% | 6% | 0.059998
|  | Z1-C-CON-3070 | Fix Formwork Columns - Z1 - GF | 50689 | 50689 | 47394 | 100% | 0.05844% | 0.05464% | 93.5% | 0.935
|  | Z1-C-CON-3080 | Pour Concrete Columns - Z1 - GF | 101503 | 88815 | 53543 | 87.5% | 0.1024% | 0.06173% | 52.75% | 0.60286
|  | Z1-C-CON-3120 | Fix MEP Containment & Provisions - Z1 - B1 | 10880 | 10880 | 9248 | 100% | 0.01254% | 0.01066% | 85% | 0.85
|  | Z1-C-CON-3140 | Fix MEP Containment & Provisions - Z1 - GF | 10880 | 10880 | 653 | 100% | 0.01254% | 0.0007528% | 6.002% | 0.060018
|  | Z1-C-CON-5840 | Fix Formwork Ramp - Z1 - B2 | 11760 | 11760 | 9996 | 100% | 0.01356% | 0.01152% | 85% | 0.85
|  | Z1-C-CON-5850 | Fix Rebar Ramp - Z1 - B2 | 23520 | 23520 | 235 | 100% | 0.02711% | 0.0002709% | 0.9991% | 0.0099915
|  | Z1-C-CON-5860 | Pour Concrete Ramp - Z1 - B2 | 23520 | 23520 | 235 | 100% | 0.02711% | 0.0002709% | 0.9991% | 0.0099915
|  | Z1-C-CON-5870 | Fix Formwork Ramp - Z1 - B1 | 11760 | 11760 | 706 | 100% | 0.01356% | 0.0008139% | 6.003% | 0.060034
|  | Z1-C-CON-5880 | Fix Rebar Ramp - Z1 - B1 | 23520 | 23520 | 1411 | 100% | 0.02711% | 0.001627% | 5.999% | 0.059991
|  | Z1-C-CON-5890 | Pour Concrete Ramp - Z1 - B1 | 23520 | 23520 | 1411 | 100% | 0.02711% | 0.001627% | 5.999% | 0.059991
|  | Z1-C-CON-5900 | Fix Rebar Core Walls Ramp - Z1 - B2 | 27909 | 27909 | 23722 | 100% | 0.03217% | 0.02735% | 85% | 0.84998
|  | Z1-C-CON-5910 | Fix Formwork Walls Ramp - Z1 - B2 | 27909 | 27909 | 23722 | 100% | 0.03217% | 0.02735% | 85% | 0.84998
|  | Z1-C-CON-5920 | Pour Concrete Core Walls Ramp - Z1 - B2 | 37210 | 37210 | 31628 | 100% | 0.0429% | 0.03646% | 85% | 0.84999
|  | Z1-C-CON-5930 | Fix Rebar Core Walls Ramp - Z1 - B1 | 27907 | 27907 | 558 | 100% | 0.03217% | 0.0006433% | 1.999% | 0.019995
|  | Z1-C-CON-5940 | Fix Formwork Walls Ramp - Z1 - B1 | 27908 | 27908 | 3795 | 100% | 0.03217% | 0.004375% | 13.6% | 0.13598
|  | Z1-C-CON-5950 | Pour Concrete Core Walls Ramp - Z1 - B1 | 37210 | 37210 | 31628 | 100% | 0.0429% | 0.03646% | 85% | 0.84999
| Div 04 | Z1-C-FIN-5790 | Masonry Works - Z1 - B2 | 3061 | 3061 | 184 | 100% | 0.003529% | 0.0002121% | 6.011% | 0.060111
| Div 10 | Z1-C-CON-2540 | Fix MEP Provisions - Z1 - Raft | 21000 | 21000 | 4463 | 100% | 0.02421% | 0.005145% | 21.25% | 0.21252
| Div 15 | Z1-C-MEP-5810 | Fix G.I Box and conduits - Z1 - B2 | 26755 | 15289 | 14113 | 57.14% | 0.01763% | 0.01627% | 52.75% | 0.92308
Z2 | Div 01 | PRL-RCR-6980 | Recurring Preliminaries through out the project | 4687620 | 1977131 | 15348714 | 42.18% | 2.279% | 17.69% | 327.4% | 7.7631
| Div 02 | C-EW-10400 | Excavation Stage 2 - Z2&3 | 440461 | 440461 | 285198 | 100% | 0.5078% | 0.3288% | 64.75% | 0.6475
|  | C-EW-10430 | Strut Pipe Bracing - Z2&3 | 254480 | 254480 | 216308 | 100% | 0.2934% | 0.2494% | 85% | 0.85
|  | C-EW-10440 | Excavation Stage 1 - Z2&3 | 348229 | 348229 | 212669 | 100% | 0.4014% | 0.2452% | 61.07% | 0.61072
|  | C-SHRNG-DCE-C-2360 | Place Guide Wall - Z2&3 | 162250 | 162250 | 178476 | 100% | 0.187% | 0.2058% | 110% | 1.1
|  | C-SHRNG-DCE-C-2370 | Install Shoring System - Z2&3 | 2987501 | 2987500 | 1643125 | 100% | 3.444% | 1.894% | 55% | 0.55
|  | C-SHRNG-DCE-C-2380 | Install Capping Beam - Z2&3 | 271284 | 271284 | 298412 | 100% | 0.3127% | 0.344% | 110% | 1.1
| Div 03 | C-EW-10410 | Gunite Wall - Z2 | 228837 | 228837 | 2288 | 100% | 0.2638% | 0.002638% | 0.9998% | 0.0099984
|  | Z2-C-CON-5840 | PCC Blind Concrete - Z2 - Lift Pit | 8610 | 8610 | 86 | 100% | 0.009926% | 9.914e-05% | 0.9988% | 0.0099884
|  | Z2-C-CON-5850 | Waterproof Membrane - Z2 - Lift Pit | 51140 | 51140 | 511 | 100% | 0.05896% | 0.0005891% | 0.9992% | 0.0099922
|  | Z2-C-CON-5860 | Protection Screed - Z2 - Lift Pit | 5490 | 5490 | 55 | 100% | 0.006329% | 6.341e-05% | 1.002% | 0.010018
|  | Z2-C-CON-5870 | Fix Rebar - Z2 - Lift Pit | 15186 | 15186 | 304 | 100% | 0.01751% | 0.0003505% | 2.002% | 0.020018
|  | Z2-C-CON-5890 | Pour Concrete - Z2 - Lift Pit | 15186 | 15186 | 3227 | 100% | 0.01751% | 0.00372% | 21.25% | 0.2125
|  | Z2-C-CON-5900 | PCC Blind Concrete - Z2 - Raft | 43050 | 43050 | 9148 | 100% | 0.04963% | 0.01055% | 21.25% | 0.2125
|  | Z2-C-CON-5910 | Waterproof Membrane - Z2 - Raft | 27450 | 27450 | 5833 | 100% | 0.03164% | 0.006724% | 21.25% | 0.2125
|  | Z2-C-CON-5920 | Protection Screed - Z2 - Raft | 255700 | 255700 | 54336 | 100% | 0.2948% | 0.06264% | 21.25% | 0.2125
|  | Z2-C-CON-5930 | Fix Rebar - Z2 - Raft | 746627 | 746627 | 634632 | 100% | 0.8607% | 0.7316% | 85% | 0.85
|  | Z2-C-CON-5950 | Fix Formwork - Z2 - Raft | 30991 | 30991 | 26342 | 100% | 0.03573% | 0.03037% | 85% | 0.84999
|  | Z2-C-CON-5960 | Pour Concrete - Z2 - Raft | 548054 | 548054 | 465846 | 100% | 0.6318% | 0.537% | 85% | 0.85
|  | Z2-C-CON-5970 | Fix Rebar Columns - Z2 - B2 | 47430 | 47430 | 40316 | 100% | 0.05468% | 0.04648% | 85% | 0.85001
|  | Z2-C-CON-5980 | Fix Formwork Columns - Z2 - B2 | 23715 | 23715 | 20158 | 100% | 0.02734% | 0.02324% | 85% | 0.85001
|  | Z2-C-CON-5990 | Pour Concrete Columns - Z2 - B2 | 47431 | 47431 | 40316 | 100% | 0.05468% | 0.04648% | 85% | 0.84999
|  | Z2-C-CON-6000 | Fix Rebar Retaining Walls - Z2 - B2 | 65426 | 65426 | 55613 | 100% | 0.07542% | 0.06411% | 85% | 0.85001
|  | Z2-C-CON-6010 | Fix Formwork Retaining Walls - Z2 - B2 | 32713 | 32713 | 27807 | 100% | 0.03771% | 0.03206% | 85% | 0.85003
|  | Z2-C-CON-6020 | Pour Concrete Retaining Walls - Z2 - B2 | 65427 | 65427 | 55613 | 100% | 0.07543% | 0.06411% | 85% | 0.85
|  | Z2-C-CON-6030 | Pour Concrete Core Walls - Z2 - B2 | 33489 | 33489 | 28466 | 100% | 0.03861% | 0.03282% | 85% | 0.85001
|  | Z2-C-CON-6040 | Fix Rebar Core Walls - Z2 - B2 | 25118 | 25118 | 21349 | 100% | 0.02896% | 0.02461% | 84.99% | 0.84995
|  | Z2-C-CON-6050 | Fix Formwork Core Walls - Z2 - B2 | 25117 | 25117 | 21349 | 100% | 0.02896% | 0.02461% | 85% | 0.84998
|  | Z2-C-CON-6060 | Fix Formwork Stairs - Z2 - B2 | 1864 | 1864 | 37 | 100% | 0.002149% | 4.265e-05% | 1.985% | 0.01985
|  | Z2-C-CON-6070 | Fix Rebar Stairs - Z2 - B2 | 3729 | 3729 | 75 | 100% | 0.004299% | 8.646e-05% | 2.011% | 0.020113
|  | Z2-C-CON-6080 | Pour Concrete Stairs - Z2 - B2 | 3729 | 3729 | 507 | 100% | 0.004299% | 0.0005845% | 13.6% | 0.13596
|  | Z2-C-CON-6090 | Fix Rebar Retaining Walls - Z2 - B1 | 65428 | 65428 | 8898 | 100% | 0.07543% | 0.01026% | 13.6% | 0.136
|  | Z2-C-CON-6100 | Fix Formwork Retaining Walls - Z2 - B1 | 32713 | 32713 | 7525 | 100% | 0.03771% | 0.008675% | 23% | 0.23003
|  | Z2-C-CON-6110 | Pour Concrete Retaining Walls - Z2 - B1 | 65427 | 65427 | 3926 | 100% | 0.07543% | 0.004526% | 6.001% | 0.060006
|  | Z2-C-CON-6120 | Fix Formwork Core Walls - Z2 - B1 | 25118 | 25118 | 21349 | 100% | 0.02896% | 0.02461% | 84.99% | 0.84995
|  | Z2-C-CON-6130 | Fix Rebar Core Walls - Z2 - B1 | 25117 | 25117 | 502 | 100% | 0.02896% | 0.0005787% | 1.999% | 0.019986
|  | Z2-C-CON-6140 | Pour Concrete Core Walls - Z2 - B1 | 33489 | 33489 | 1674 | 100% | 0.03861% | 0.00193% | 4.999% | 0.049987
|  | Z2-C-CON-6150 | Fix Rebar Columns - Z2 - B1 | 47430 | 47430 | 949 | 100% | 0.05468% | 0.001094% | 2.001% | 0.020008
|  | Z2-C-CON-6160 | Fix Formwork Columns - Z2 - B1 | 23714 | 23714 | 3225 | 100% | 0.02734% | 0.003718% | 13.6% | 0.136
|  | Z2-C-CON-6170 | Pour Concrete Columns - Z2 - B1 | 47431 | 47431 | 6451 | 100% | 0.05468% | 0.007437% | 13.6% | 0.13601
|  | Z2-C-CON-6210 | Fix Formwork Slabs - Z2 - B1 | 100188 | 100188 | 85160 | 100% | 0.1155% | 0.09817% | 85% | 0.85
|  | Z2-C-CON-6220 | Fix Rebar Slabs - Z2 - B1 | 200376 | 200376 | 6012 | 100% | 0.231% | 0.006931% | 3% | 0.030004
|  | Z2-C-CON-6230 | Pour Concrete Slabs - Z2 - B1 | 200376 | 200376 | 4008 | 100% | 0.231% | 0.004621% | 2% | 0.020002
|  | Z2-C-CON-6240 | Fix MEP Containment & Provisions - Z2 - B1 | 5440 | 5440 | 849 | 100% | 0.006271% | 0.0009787% | 15.61% | 0.15607
|  | Z2-C-CON-6340 | Fix Formwork Slabs - Z2 - GF | 129638 | 129638 | 7778 | 100% | 0.1494% | 0.008967% | 6% | 0.059998
|  | Z2-C-CON-6350 | Fix Rebar Slabs - Z2 - GF | 259274 | 181492 | 136767 | 70% | 0.2092% | 0.1577% | 52.75% | 0.75357
|  | Z2-C-CON-6370 | Fix MEP Containment & Provisions - Z2 - GF | 5440 | 1360 | 2543 | 25% | 0.001568% | 0.002932% | 46.75% | 1.8699
| Div 10 | Z2-C-CON-5940 | Fix MEP Provisions - Z2 - Raft | 10500 | 10500 | 8925 | 100% | 0.0121% | 0.01029% | 85% | 0.85
Z3 | Div 03 | Z3-C-CON-5840 | PCC Blind Concrete - Z3 - Lift Pit | 8610 | 8610 | 172 | 100% | 0.009926% | 0.0001983% | 1.998% | 0.019977
|  | Z3-C-CON-5850 | Waterproof Membrane - Z3 - Lift Pit | 51140 | 51140 | 1023 | 100% | 0.05896% | 0.001179% | 2% | 0.020004
|  | Z3-C-CON-5860 | Protection Screed - Z3 - Lift Pit | 5490 | 5490 | 55 | 100% | 0.006329% | 6.341e-05% | 1.002% | 0.010018
|  | Z3-C-CON-5870 | Fix Rebar - Z3 - Lift Pit | 15185 | 15185 | 152 | 100% | 0.01751% | 0.0001752% | 1.001% | 0.01001
|  | Z3-C-CON-5890 | Pour Concrete - Z3 - Lift Pit | 15186 | 15186 | 3227 | 100% | 0.01751% | 0.00372% | 21.25% | 0.2125
|  | Z3-C-CON-5900 | PCC Blind Concrete - Z3 - Raft | 345090 | 345090 | 293326 | 100% | 0.3978% | 0.3382% | 85% | 0.85
|  | Z3-C-CON-5910 | Waterproof Membrane - Z3 - Raft | 27450 | 27450 | 23332 | 100% | 0.03164% | 0.0269% | 85% | 0.84998
|  | Z3-C-CON-5920 | Protection Screed - Z3 - Raft | 255701 | 255701 | 217345 | 100% | 0.2948% | 0.2506% | 85% | 0.85
|  | Z3-C-CON-5930 | Fix Rebar - Z3 - Raft | 544585 | 544585 | 462897 | 100% | 0.6278% | 0.5336% | 85% | 0.85
|  | Z3-C-CON-5950 | Fix Formwork - Z3 - Raft | 30992 | 30992 | 26342 | 100% | 0.03573% | 0.03037% | 85% | 0.84996
|  | Z3-C-CON-5960 | Pour Concrete - Z3 - Raft | 548054 | 548054 | 465846 | 100% | 0.6318% | 0.537% | 85% | 0.85
|  | Z3-C-CON-5970 | Fix Rebar Columns - Z3 - B2 | 47431 | 47431 | 40316 | 100% | 0.05468% | 0.04648% | 85% | 0.84999
|  | Z3-C-CON-5980 | Fix Formwork Columns - Z3 - B2 | 23716 | 23716 | 3225 | 100% | 0.02734% | 0.003718% | 13.6% | 0.13598
|  | Z3-C-CON-5990 | Pour Concrete Columns - Z3 - B2 | 47430 | 47430 | 6450 | 100% | 0.05468% | 0.007436% | 13.6% | 0.13599
|  | Z3-C-CON-6000 | Fix Rebar Retaining Walls - Z3 - B2 | 65427 | 65427 | 55613 | 100% | 0.07543% | 0.06411% | 85% | 0.85
|  | Z3-C-CON-6010 | Fix Formwork Retaining Walls - Z3 - B2 | 32714 | 32714 | 4449 | 100% | 0.03771% | 0.005129% | 13.6% | 0.136
|  | Z3-C-CON-6020 | Pour Concrete Retaining Walls - Z3 - B2 | 65427 | 65427 | 654 | 100% | 0.07543% | 0.0007539% | 0.9996% | 0.0099959
|  | Z3-C-CON-6030 | Pour Concrete Core Walls - Z3 - B2 | 33489 | 33489 | 335 | 100% | 0.03861% | 0.0003862% | 1% | 0.010003
|  | Z3-C-CON-6040 | Fix Rebar Core Walls - Z3 - B2 | 25117 | 25117 | 251 | 100% | 0.02896% | 0.0002894% | 0.9993% | 0.0099932
|  | Z3-C-CON-6050 | Fix Formwork Core Walls - Z3 - B2 | 25118 | 25118 | 251 | 100% | 0.02896% | 0.0002894% | 0.9993% | 0.0099928
|  | Z3-C-CON-6060 | Fix Formwork Stairs - Z3 - B2 | 1865 | 1865 | 1585 | 100% | 0.00215% | 0.001827% | 84.99% | 0.84987
|  | Z3-C-CON-6070 | Fix Rebar Stairs - Z3 - B2 | 3729 | 3729 | 410 | 100% | 0.004299% | 0.0004727% | 10.99% | 0.10995
|  | Z3-C-CON-6080 | Pour Concrete Stairs - Z3 - B2 | 3729 | 3729 | 224 | 100% | 0.004299% | 0.0002582% | 6.007% | 0.06007
|  | Z3-C-CON-6090 | Fix Rebar Retaining Walls - Z3 - B1 | 65428 | 65428 | 3926 | 100% | 0.07543% | 0.004526% | 6% | 0.060005
|  | Z3-C-CON-6100 | Fix Formwork Retaining Walls - Z3 - B1 | 32714 | 32714 | 1963 | 100% | 0.03771% | 0.002263% | 6% | 0.060005
|  | Z3-C-CON-6110 | Pour Concrete Retaining Walls - Z3 - B1 | 65427 | 65427 | 30587 | 100% | 0.07543% | 0.03526% | 46.75% | 0.4675
|  | Z3-C-CON-6120 | Fix Formwork Core Walls - Z3 - B1 | 25117 | 25117 | 1507 | 100% | 0.02896% | 0.001737% | 6% | 0.059999
|  | Z3-C-CON-6130 | Fix Rebar Core Walls - Z3 - B1 | 25117 | 25117 | 17268 | 100% | 0.02896% | 0.01991% | 68.75% | 0.6875
|  | Z3-C-CON-6140 | Pour Concrete Core Walls - Z3 - B1 | 33489 | 33489 | 2009 | 100% | 0.03861% | 0.002316% | 5.999% | 0.05999
|  | Z3-C-CON-6150 | Fix Rebar Columns - Z3 - B1 | 47430 | 47430 | 40316 | 100% | 0.05468% | 0.04648% | 85% | 0.85001
|  | Z3-C-CON-6160 | Fix Formwork Columns - Z3 - B1 | 23715 | 23715 | 1423 | 100% | 0.02734% | 0.00164% | 6% | 0.060004
|  | Z3-C-CON-6170 | Pour Concrete Columns - Z3 - B1 | 47430 | 47430 | 2846 | 100% | 0.05468% | 0.003281% | 6% | 0.060004
|  | Z3-C-CON-6210 | Fix Formwork Slabs - Z3 - B1 | 100188 | 100188 | 3006 | 100% | 0.1155% | 0.003465% | 3% | 0.030004
|  | Z3-C-CON-6220 | Fix Rebar Slabs - Z3 - B1 | 200376 | 200376 | 4008 | 100% | 0.231% | 0.004621% | 2% | 0.020002
|  | Z3-C-CON-6230 | Pour Concrete Slabs - Z3 - B1 | 200376 | 200376 | 170320 | 100% | 0.231% | 0.1963% | 85% | 0.85
|  | Z3-C-CON-6240 | Fix MEP Containment & Provisions - Z3 - B1 | 5440 | 5440 | 740 | 100% | 0.006271% | 0.0008531% | 13.6% | 0.13603
|  | Z3-C-CON-6340 | Fix Formwork Slabs - Z3 - GF | 129638 | 64819 | 68384 | 50% | 0.07472% | 0.07883% | 52.75% | 1.055
| Div 10 | Z3-C-CON-5940 | Fix MEP Provisions - Z3 - Raft | 10500 | 10500 | 8925 | 100% | 0.0121% | 0.01029% | 85% | 0.85
Grand Total |  |  |  | 26999955 | 24103569 | 28655486 | 89.27% | 27.79% | 33.03% | 106.1% | 1.1888
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Weekly Cost Summary
Project Name |  |  |  |  | Weekly Progress Cost Summary | [5 empty] | Data Date: | 2020-12-27
Location | [10 empty] | Current Week | 48
BOQ Item Wise Summary | [10 empty] | Total Weeks | 114
1817-BOQ Summary | Budget Cost (AED) | Planned Cost (AED) | Earned Cost (AED) | Planned Cost % | Actual Cost % | 1817-BOQ Summary | Budget Cost (AED) | Planned Cost (AED) | Earned Cost (AED) | Planned Cost %
Div 01 | 5594621 | 2884132 | 16042570 | 51.55% | 286.7% | Div 01 | 5594621 | 2884132 | 16042570 | 51.55%
Div 02 | 8101845 | 7902343 | 6076794 | 97.54% | 75.01% | Div 02 | 8101845 | 7902343 | 6076794 | 97.54%
Div 03 | 26658801 | 13256744 | 8407576 | 49.73% | 31.54% | Div 03 | 26658801 | 13256744 | 8407576 | 49.73% |  |  | Row Labels | Sum of WeekID
Div 04 | 1709702 | 3061 | 142628 | 0.179% | 8.342% | Div 04 | 1709702 | 3061 | 142628 | 0.179% |  |  | 1 | 1
Div 05 | 432738 |  | 210 | 0% | 0.04853% | Div 05 | 432738 | 0 | 210 | 0% |  |  | 2 | 2
Div 06 | 358000 |  |  | 0% | 0% | Div 06 | 358000 | 0 | 0 | 0% |  |  | 3 | 3
Div 07 | 1024731 |  |  | 0% | 0% | Div 07 | 1024731 | 0 | 0 | 0% |  |  | 4 | 4
Div 08 | 2748699 |  | 66857 | 0% | 2.432% | Div 08 | 2748699 | 0 | 66857 | 0% |  |  | 5 | 5
Div 09 | 8267790 |  | 364084 | 0% | 4.404% | Div 09 | 8267790 | 0 | 364084 | 0% |  |  | 6 | 6
Div 10 | 2348697 | 42000 | 72343 | 1.788% | 3.08% | Div 10 | 2348697 | 42000 | 72343 | 1.788% |  |  | 7 | 7
Div 11 | 1781708 |  | 155177 | 0% | 8.709% | Div 11 | 1781708 | 0 | 155177 | 0% |  |  | 8 | 8
Div 12 | 10893557 |  | 704077 | 0% | 6.463% | Div 12 | 10893557 | 0 | 704077 | 0% |  |  | 9 | 9
Div 13 | 3801981 |  |  | 0% | 0% | Div 13 | 3801981 | 0 | 0 | 0% |  |  | 10 | 10
Div 14 | 148097 |  |  | 0% | 0% | Div 14 | 148097 | 0 | 0 | 0% |  |  | 11 | 11
Div 15 | 12872739 | 15289 | 397660 | 0.1188% | 3.089% | Div 15 | 12872739 | 15289 | 397660 | 0.1188% |  |  | 12 | 12
Grand Total | 86743706 | 24103569 | 32429976 | 27.79% | 37.39% | Grand Total | 86743706 | 24103569 | 32429976 | 27.79% |  |  | 13 | 13
[13 empty] | 14 | 14
Trade Item Wise Summary | [12 empty] | 15 | 15
1817-Trade | Budget Cost (AED) | Planned Cost (AED) | Earned Cost (AED) | Planned Cost % | Actual Cost % | 1817-Trade | Budget Cost (AED) | Planned Cost (AED) | Earned Cost (AED) | Planned Cost % | Actual Cost % |  | 16 | 16
Anti-Fungal & Carbonation | 572734 |  | 184292 | 0% | 32.18% | Anti-Fungal & Carbonation | 572734 | 0 | 184292 | 0% | 32.18% |  | 17 | 17
Ceramic | 355680 |  |  | 0% | 0% | Ceramic | 355680 | 0 | 0 | 0% | 0% |  | 18 | 18
Concrete | 26658801 | 13256744 | 8407576 | 49.73% | 31.54% | Concrete | 26658801 | 13256744 | 8407576 | 49.73% | 31.54% |  | 19 | 19
Conveying System | 3801981 |  |  | 0% | 0% | Conveying System | 3801981 | 0 | 0 | 0% | 0% |  | 20 | 20
Doors | 969680 |  | 66857 | 0% | 6.895% | Doors | 969680 | 0 | 66857 | 0% | 6.895% |  | 21 | 21
Electrical | 12872739 | 15289 | 397660 | 0.1188% | 3.089% | Electrical | 12872739 | 15289 | 397660 | 0.1188% | 3.089% |  | 22 | 22
Epoxy & Traffic Coating | 975846 |  | 6766 | 0% | 0.6933% | Epoxy & Traffic Coating | 975846 | 0 | 6766 | 0% | 0.6933% |  | 23 | 23
False Ceiling | 1052294 |  | 448 | 0% | 0.04257% | False Ceiling | 1052294 | 0 | 448 | 0% | 0.04257% |  | 24 | 24
Fire Fighting | 1781708 |  | 155177 | 0% | 8.709% | Fire Fighting | 1781708 | 0 | 155177 | 0% | 8.709% |  | 25 | 25
Glazing | 1644464 |  |  | 0% | 0% | Glazing | 1644464 | 0 | 0 | 0% | 0% |  | 26 | 26
HVAC | 10893557 |  | 704077 | 0% | 6.463% | HVAC | 10893557 | 0 | 704077 | 0% | 6.463% |  | 27 | 27
LPG System | 148097 |  |  | 0% | 0% | LPG System | 148097 | 0 | 0 | 0% | 0% |  | 28 | 28
Masonry | 1709702 | 3061 | 142628 | 0.179% | 8.342% | Masonry | 1709702 | 3061 | 142628 | 0.179% | 8.342% |  | 29 | 29
Natural Stone | 2149353 |  |  | 0% | 0% | Natural Stone | 2149353 | 0 | 0 | 0% | 0% |  | 30 | 30
Others Finishes | 2559272 |  | 210 | 0% | 0.008205% | Others Finishes | 2559272 | 0 | 210 | 0% | 0.008205% |  | 31 | 31
Paint | 354486 |  | 38876 | 0% | 10.97% | Paint | 354486 | 0 | 38876 | 0% | 10.97% |  | 32 | 32
Plaster | 908192 |  | 126439 | 0% | 13.92% | Plaster | 908192 | 0 | 126439 | 0% | 13.92% |  | 33 | 33
Plumbing | 2348697 | 42000 | 72343 | 1.788% | 3.08% | Plumbing | 2348697 | 42000 | 72343 | 1.788% | 3.08% |  | 34 | 34
Porcelain | 1017975 |  | 7263 | 0% | 0.7135% | Porcelain | 1017975 | 0 | 7263 | 0% | 0.7135% |  | 35 | 35
Prelims | 5594621 | 2884132 | 16042570 | 51.55% | 286.7% | Prelims | 5594621 | 2884132 | 16042570 | 27.79% | 37.39% |  | 36 | 36
Site Works | 8101845 | 7902343 | 6076794 | 97.54% | 75.01% | [7 empty] | 37 | 37
Terrazo Tiles | 271982 |  |  | 0% | 0% | [7 empty] | 38 | 38
Grand Total | 86743706 | 24103569 | 32429976 | 27.79% | 37.39% | [7 empty] | 39 | 39
[13 empty] | 40 | 40
[13 empty] | 41 | 41
[13 empty] | 42 | 42
[13 empty] | 43 | 43
[13 empty] | 44 | 44
[13 empty] | 45 | 45
[13 empty] | 46 | 46
[13 empty] | 47 | 47
[13 empty] | 48 | 48
[13 empty] | Grand Total | 1176
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## WeeklyPlanned (hidden)
Project Name | [5 empty] | Data Date: |  | 2020-12-27 | [6 empty] | Note: This report is not for printing, use it for only analysis purpose
Location | [5 empty] | Current Week |  | 48
[6 empty] | Total Weeks |  | 114
Sum of WeeklyPlannedCost | Week ID
Row Labels | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | Grand Total
Div 01 | 399657 | 343402 | 293013 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 41068 | 82136 | 5594620
Div 02 | 37445 | 83238 | 63596 | 65947 | 97350 | 48675 | 736404 | 801304 | 926172 | 855389 | 880926 | 907266 | 711928 | 284140 | 270956 | 252879 | 134040 | 195164 | 164121 | 110115 | 110115 | 110115 | 55058 | [75 empty] | 66500 | 83125 | 49875 | [12 empty] | 8101843
Div 03 | [16 empty] | 60808 | 160110 | 82367 | 102591 | 200574 | 227653 | 441360 | 402218 | 1189865 | 103749 | 241187 | 1015923 | 710463 | 499206 | 297029 | 870568 | 429304 | 520711 | 1095272 | 212253 | 254008 | 346374 | 302519 | 434363 | 278227 | 323802 | 520016 | 138241 | 365514 | 709434 | 313272 | 407763 | 634449 | 392444 | 617825 | 403528 | 623397 | 439392 | 553885 | 357886 | 499755 | 324699 | 306656 | 576046 | 310296 | 730982 | 348162 | 884597 | 329619 | 270932 | 265517 | 182736 | 254560 | 251168 | 558899 | 383608 | 742782 | 496689 | 615602 | 514046 | 39364 | 157083 | 91611 | 41318 | 64203 | 87538 | 50783 | [30 empty] | 26658801
Div 04 | [45 empty] | 612 | 1837 | 612 |  |  |  | 2756 | 7905 | 18203 | 6068 | 95758 | 95758 | 45571 | 27305 | 23171 | 111718 | 111718 | 103391 | 61758 | 61758 | 10293 | 14879 | 44637 | 44637 | 48418 | 72628 | 48418 |  | 108942 | 108942 | 54472 | 19455 | 58365 | 49286 | 77820 | 93384 | 46692 | 9296 | 23239 | [29 empty] | 1709702
Div 05 | [48 empty] | 600 | [7 empty] | 600 | [30 empty] | 30300 | 30300 | 10100 | 18877 | 47397 | 53961 | 29682 | 12721 | 22114 | 61371 | 64595 | 15286 | 9167 | 11000 | 11000 | 3667 | [10 empty] | 432738
Div 06 | [82 empty] | 12786 | 76714 | 63929 | 25571 |  |  | 25571 | 89500 | 63929 | [22 empty] | 358000
Div 07 | [62 empty] | 3898 | [5 empty] | 3898 |  |  |  |  | 1949 | 5847 |  |  | 84837 | 143927 | 186704 | 7240 | 18100 | 1950 | 14804 | 179698 | 300645 | 57590 | 9746 | 3898 | [24 empty] | 1024731
Div 08 | [51 empty] | 20822 | 41643 |  |  |  |  | 10411 | 52053 | 104105 |  |  |  | 83284 | 20821 | 62463 |  |  |  | 62463 | 20821 | 41643 | 20822 |  | 41642 | 83284 |  | 20821 | 31232 | 31232 |  | 31232 | 10410 | 22335 | 221174 | 216058 | 226558 | 219558 | 233498 | 197473 | 228361 | 234807 | 44148 | 21317 | 8923 | 5205 | 20822 | 28009 | 29249 | [14 empty] | 2748699
Div 09 | [48 empty] | 13950 | 27900 | 28182 | 87557 | 36569 | 6975 | 41851 | 56618 | 50177 | 59241 | 218166 | 61973 | 43024 | 57791 | 84183 | 67801 | 69819 | 53881 | 26710 | 33932 | 47395 | 91147 | 81583 | 62791 | 83743 | 82174 | 56506 | 97239 | 26295 | 110667 | 94726 | 211359 | 209279 | 248653 | 280559 | 374489 | 176017 | 309924 | 181437 | 540884 | 477470 | 376499 | 421889 | 403965 | 416636 | 336831 | 237068 | 64544 | 42597 | 64126 | 374400 | 117867 | 211990 | 98014 | 112234 | 12809 | 5684 | [8 empty] | 8267790
Div 10 | [23 empty] | 12600 | 8400 |  |  |  |  | 4375 | 5250 | 875 | 2625 | 5250 | 2625 | [16 empty] | 18956 | 58418 | 3105 | 3105 | 1035 |  | 2825 | 6442 | 5352 | 5352 | 5352 | 9202 | 10208 | 75476 | 229418 | 113611 | 223456 | 119121 | 11547 | 8094 | 8723 | 31300 | 58835 | 7876 | 13157 | 5105 | 14474 | 10417 | 9811 | 4874 | 76137 | 23096 | 51607 | 51882 | 70447 | 17594 | 15017 | 10730 | 162326 | 64429 | 43022 | 96839 | 78900 | 64778 | 43186 |  |  | 32389 | 141521 | 69428 | 32667 | 29667 | 22178 | 20526 | 13684 | [7 empty] | 2348697
Div 11 | [51 empty] | 3905 | 23431 | 23431 | 23431 | 7810 |  | 1518 | 26065 | 56950 | 44258 | 33912 | 42390 | 16956 | 12146 | 55450 | 25170 | 37648 | 42390 | 25434 | 26952 | 34543 | 39994 | 21860 | 37922 | 54286 | 21422 | 84527 | 79354 | 67075 | 85339 | 94255 | 88876 | 90465 | 44767 | 53755 | 36096 | 60864 | 47260 | 16210 | 22628 | 11588 | 33871 | 34560 | 18074 | 16416 | 20141 | 18416 | 6897 |  | 3143 | 3143 | 3143 | 1571 | [9 empty] | 1781708
Div 12 | [51 empty] | 14877 | 89261 | 89261 | 97526 | 40774 |  |  | 89260 | 193819 | 181071 | 192297 | 240948 | 164903 | 65390 | 141607 | 59926 | 94359 | 207927 | 118666 | 164180 | 223324 | 159583 | 143563 | 267970 | 189659 | 31675 | 278024 | 275103 | 143653 | 243505 | 299702 | 194123 | 220375 | 1855956 | 1348180 | 617931 | 701813 | 250951 | 98129 | 217477 | 80454 | 20473 | 86448 | 253446 | 96135 | 123341 | 88176 |  |  | 23715 | 23715 | 23715 | 23715 | 19761 | 11857 | 11857 | [5 empty] | 0 | 10893556
Div 13 | [80 empty] | 58338 | 58338 | 58338 | 68061 | 116676 | 204184 | 106953 | 190294 | 198397 | 158578 | 266225 | 327342 | 232426 | 215296 | 226871 | 166680 | 351188 | 235667 | 156263 | 118065 | 85722 | 85722 | 112549 | 1428 | 952 | 952 | 476 | [6 empty] | 3801981
Div 14 | [77 empty] | 13645 | 2880 | 2399 | 5965 | 12136 | 2880 | 12136 | 5965 | 1234 | 13576 | 1234 |  | 9256 | 3085 | 12341 | 15426 | 9256 | 3085 | 9256 | 6171 | 6171 | [15 empty] | 148097
Div 15 | [47 empty] | 15289 | 11466 |  |  | 14047 | 91928 | 109588 | 69436 | 70570 | 31093 | 13520 | 44657 | 452548 | 518902 | 118208 | 138345 | 98962 | 94854 | 282869 | 278729 | 492985 | 671417 | 251316 | 119433 | 135324 | 174710 | 347448 | 194014 | 330340 | 164639 | 224219 | 131214 | 173764 | 199901 | 209742 | 272626 | 954140 | 782131 | 789958 | 263202 | 249808 | 235546 | 355338 | 614327 | 207787 | 446153 | 440326 | 225141 | 230856 | 212481 | 253399 | 57855 | 1700 | 2040 | 1224 | 408 | 408 | 408 | [7 empty] | 0 | 12872739
Grand Total | 437102 | 426640 | 356609 | 107015 | 138418 | 89743 | 777472 | 842372 | 967240 | 896457 | 921994 | 948334 | 752996 | 325208 | 312024 | 293947 | 235916 | 396342 | 287556 | 253774 | 351757 | 378836 | 537486 | 455886 | 1239333 | 144817 | 282255 | 1056991 | 751531 | 544649 | 343347 | 912511 | 472997 | 567029 | 1138965 | 253321 | 295076 | 387442 | 343587 | 475431 | 319295 | 364870 | 561084 | 179309 | 406582 | 751114 | 356177 | 464732 | 701533 | 461412 | 687075 | 607516 | 1013620 | 731023 | 836370 | 671519 | 718451 | 498853 | 811672 | 1515032 | 1255689 | 1291328 | 1011587 | 1429537 | 770951 | 1147981 | 825610 | 1150821 | 1432413 | 901227 | 1093658 | 979442 | 1294002 | 1302528 | 1377389 | 1377551 | 349023 | 1087730 | 950818 | 986203 | 1013096 | 1223593 | 1046791 | 1949433 | 3539263 | 3361024 | 1562005 | 2060586 | 1554689 | 1514477 | 1962295 | 1409771 | 1401001 | 1293684 | 1091175 | 695460 | 879180 | 799627 | 779907 | 512513 | 497981 | 296553 | 326451 | 103177 | 88399 | 67561 | 53401 | 41068 | 41068 | 41068 | 41068 | 41068 | 82136 | 86743702
Sum of Earned Hrs | Column Labels
Row Labels | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | Grand Total
Div 01 | 393 | [78 empty] | 393
Div 02 | 272 | 411 | 4770 | 2031 | 3125 |  | 207 |  | 2173 | 34 | [69 empty] | 13023
Div 03 | [5 empty] | 126 | 162 | 54 | 1996 | 1 | 184 | 0 | 40 | 2276 | 1843 | 702 | 1888 | 9604 | 4155 | 15980 | 7270 | 6715 | 10618 | 325 | 76 | 58 | 428 | 222 | 2205 | 4450 | 7749 | 684 | 1065 | 7331 | 1952 | 820 | 1110 | 855 | 3374 | 9057 | 2148 | 1624 | 2653 | 670 | 1903 | 2429 | 1861 | 149 | 1125 | 2547 | 6829 | 18578 | 4858 | 5366 | 4686 | 1604 | 7088 | 7617 | 2756 | 12357 | 6235 | 2854 | 5040 | 1252 | 292 | 968 | 1049 | 489 | 64 | 148 | [9 empty] | 212614
Div 04 | [32 empty] | 2 |  |  | 20 |  | 8 |  | 212 | 690 | 690 |  |  | 140 | [5 empty] | 4146 | 4146 | 1300 |  | 217 |  | 2273 |  | 1782 |  | 764 | 1908 |  | 777 |  | 532 | 2292 |  |  | 342 | [9 empty] | 22241
Div 05 | [34 empty] | 2 | [7 empty] | 11 | [29 empty] | 519 |  | 1839 | 1282 | 1038 | 424 |  | 5115
Div 06 | [69 empty] | 382 | 382 |  |  | 764 | [5 empty] | 1528
Div 07 | [52 empty] | 29 |  |  |  |  | 29 |  |  |  |  | 56 |  | 496 | 2527 | 1695 | 114 | 58 |  | 5403 | 1931 | 343 | 58 | [5 empty] | 12739
Div 08 | [36 empty] | 32 |  | 58 | [6 empty] | 243 |  |  | 88 | 367 |  |  |  | 556 | 88 | 147 | 88 |  | 60 | 470 |  |  | 176 | 166 | 24 | 147 | 59 |  | 120 |  | 1756 | 162 | 1224 | 432 | 910 | 568 | 191 | 569 |  | 8701
Div 09 | [34 empty] | 805 | 108 | 290 | 328 |  | 6774 | 2130 |  | 2181 | 216 | 41 | 2209 | 1966 | 4043 | 83 |  | 12782 | 15151 | 2696 | 3160 | 5771 | 810 | 2374 | 765 | 4328 | 7200 | 3301 | 6465 | 1452 | 2235 | 3951 | 11615 | 10863 | 7388 | 10235 | 17040 | 6792 | 3679 | 9845 | 9224 | 7308 | 4683 | 1120 | 10032 | 42 | 203481
Div 10 | [12 empty] | 21 |  |  |  |  | 50 | 35 |  |  | 85 | [14 empty] | 19 | 37 | 261 | [5 empty] | 12 |  | 162 | 162 |  |  | 249 | 249 | 417 |  | 86 | 431 | 212 | 626 | 264 | 456 | 413 | 672 | 906 | 91 | 57 | 1189 | 42 | 537 | 866 | 485 | 623 | 154 | 106 | 636 |  | 1051 | 81 | 1104 | 85 | 12932
Div 11 | [37 empty] | 75 | 385 | [6 empty] | 12 | 325 | 325 | 396 |  | 500 | 1000 | 425 | 18 | 66 | 893 | 468 | 242 | 182 | 468 | 396 | 71 | 467 | 697 | 115 | 732 | 552 | 340 | 315 | 467 | 857 | 163 | 637 | 483 | 71 | 1021 | 469 | 553 |  | 14186
Div 12 | [37 empty] | 150 | 767 |  | 56 | [5 empty] | 648 | 648 | 243 |  | 998 | 1083 | 866 | 36 | 116 | 1090 | 242 | 432 | 418 | 1090 | 271 | 70 | 1312 | 473 | 481 | 1655 | 667 | 711 | 1003 | 1589 | 1046 | 1214 | 1587 | 837 | 425 | 1202 | 378 | 580 | 85 | 24469
Div 13 | [66 empty] | 85 |  | 42 | 127 | 248 | 68 | 297 | 340 | 431 | 1009 | 157 | 1192 |  | 3996
Div 14 | [64 empty] | 115 | 145 |  | 142 | 110 | 142 |  | 159 |  | 142 |  | 426 | 141 | 141 |  | 1663
Div 15 | [33 empty] | 26 |  |  | 38 | 265 | 394 | 47 | 282 | 112 |  |  | 12 |  | 487 | 487 | 549 |  | 1770 | 1202 | 366 | 248 | 200 | 737 | 1085 | 322 | 1485 | 691 | 378 | 275 | 1232 | 436 | 46 | 1161 | 340 | 361 | 766 | 1638 | 774 | 442 | 1285 | 1191 | 590 | 1138 | 482 | 1949 | 0 | 25289
Grand Total | 665 | 411 | 4770 | 2031 | 3125 | 126 | 369 | 54 | 4169 | 35 | 184 | 0 | 61 | 2276 | 1843 | 702 | 1888 | 9654 | 4190 | 15980 | 7270 | 6800 | 10618 | 325 | 76 | 58 | 428 | 222 | 2205 | 4450 | 7749 | 684 | 1067 | 7357 | 2759 | 948 | 1489 | 1718 | 5239 | 16090 | 5306 | 2426 | 4845 | 886 | 2108 | 4893 | 5449 | 5814 | 2484 | 2914 | 27274 | 41409 | 10957 | 9384 | 11230 | 5712 | 13830 | 10033 | 11275 | 22732 | 11758 | 12315 | 10641 | 6127 | 5577 | 20671 | 17644 | 10082 | 13579 | 22360 | 17881 | 7972 | 15843 | 14107 | 11574 | 12380 | 4057 | 16544 | 212 | 562370
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard Monthly
Project Name | [6 empty] | Data Date: |  | 2022-03-31
Location | Project Performance Dashboard | [5 empty] | Current Month |  | 26
[7 empty] | Total Months |  | 26
|  | EVM Cost & Hours Status as of Current Month | [10 empty] | PF Date | 2022-03-31
|  | Budget Cost (AED) | Planned Cost (AED) | Earned Cost (AED) | Planned % | Actual % | SPI | Variance Value (SV) | Variance % | Remaining Work |  |  | PS date | 2020-02-01
|  | 86743706 | 86743752 | 84700431 | 100% | 97.64% | 0.97644 | -2043321 | -2.356% | 2043275 | Row Labels |  | project Duration |  | 790
[11 empty] | 1 |  | Elapsed Duration | 100% | 790
[7 empty] | Work Done | Work Remaining |  |  | 2 |  | Remainiing Duration | 0% | 0
[7 empty] | 97.64% | 2.356% |  |  | 3 |  | Forcast Remaning Duration | 808.6087
4
5
6
7
8
|  | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs % | Actual Hrs % | Variance Hrs | Variance hrs % | Remaining Hrs | Remaining Hrs % | 9 |  |  | planned Productivity |  | 1
|  | 791298 | 791298 | 562370 | 100% | 71.07% | -228928 | -28.93% | 228928 | 28.93% | 10
11
12
13
14
15
16
17
|  | ESM Cost & Hours Status as of Current Month | [8 empty] | 18
|  | Schedule At Compl (SAC) | Actual Time (AT) | Planned Accomp. Rate (PAR) | Earned Schedule (ES) | Time Variance (TV) | Time Perform Index (TPI) | Forcaste Comp.Date | Target Accomp. Rate | Target Productivity | 19
|  | 790 | 790 | 109802.1595 | 771.3913 | -18.6087 | 0.97644 | 2022-04-18 14:37 |  |  | 20 |  | #DIV/0! | #DIV/0!
21
22
23
24
25
26
(blank)
Grand Total
[11 empty] | 76.61 | 76.61
[11 empty] | 1 | 76.61
[11 empty] | 122.39 | 76.61 | Speedometer
[13 empty] | 1 | white
[13 empty] | 0.45 | yellow
[13 empty] | 0.3 | yellow
[13 empty] | 0.25 | Yellow
Needle
[13 empty] | 0.8 | value
[13 empty] | 0.01 | pointer
[13 empty] | 1.19 | end
Formulas:
Forcaste Comp.Date = Z5-[Time Variance (TV)]
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Monthly Hrs Summary
Project Name |  |  |  | Monthly Progress Hours Summary | [10 empty] | Data Date: | 2022-03-31
Location | [14 empty] | Current Month | 26
BOQ Item Wise Summary | [14 empty] | Total Months | 26
1817-BOQ Summary | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs % | Actual Hrs % | Variance % | productivity | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs % | [5 empty] | Row Labels
Div 01 | 514 | 513 | 393 | 99.81% | 76.46% | -23.35% | 0.76608 | 514 | 513 | 393 | 99.81% | [5 empty] | 1
Div 02 | 20039 | 20037 | 13023 | 99.99% | 64.99% | -35% | 0.64995 | 20039 | 20037 | 13023 | 99.99% | [5 empty] | 2
Div 03 | 377918 | 377914 | 212614 | 100% | 56.26% | -43.74% | 0.5626 | 377918 | 377914 | 212614 | 100% | [5 empty] | 3
Div 04 | 22530 | 22522 | 22241 | 99.96% | 98.72% | -1.247% | 0.98752 | 22530 | 22522 | 22241 | 99.96% | [5 empty] | 4
Div 05 | 6395 | 6393 | 5115 | 99.97% | 79.98% | -19.98% | 0.80009 | 6395 | 6393 | 5115 | 99.97% | [5 empty] | 5
Div 06 | 1800 | 1800 | 1528 | 100% | 84.89% | -15.11% | 0.84889 | 1800 | 1800 | 1528 | 100% | [5 empty] | 6
Div 07 | 15326 | 15334 | 12739 | 100.1% | 83.12% | -16.93% | 0.83077 | 15326 | 15334 | 12739 | 100.1% | [5 empty] | 7
Div 08 | 12173 | 12163 | 8701 | 99.92% | 71.48% | -28.44% | 0.71537 | 12173 | 12163 | 8701 | 99.92% | [5 empty] | 8
Div 09 | 239501 | 239551 | 203481 | 100% | 84.96% | -15.06% | 0.84943 | 239501 | 239551 | 203481 | 100% | [5 empty] | 9
Div 10 | 16004 | 16013 | 12932 | 100.1% | 80.8% | -19.25% | 0.80759 | 16004 | 16013 | 12932 | 100.1% | [5 empty] | 10
Div 11 | 15404 | 15401 | 14186 | 99.98% | 92.09% | -7.888% | 0.92111 | 15404 | 15401 | 14186 | 99.98% | [5 empty] | 11
Div 12 | 27542 | 27560 | 24469 | 100.1% | 88.84% | -11.22% | 0.88784 | 27542 | 27560 | 24469 | 100.1% | [5 empty] | 12
Div 13 | 4682 | 4680 | 3996 | 99.96% | 85.35% | -14.61% | 0.85385 | 4682 | 4680 | 3996 | 99.96% | [5 empty] | 13
Div 14 | 2173 | 2170 | 1663 | 99.86% | 76.53% | -23.33% | 0.76636 | 2173 | 2170 | 1663 | 99.86% | [5 empty] | 14
Div 15 | 29297 | 29247 | 25289 | 99.83% | 86.32% | -13.51% | 0.86467 | 29297 | 29247 | 25289 | 99.83% | [5 empty] | 15
Grand Total | 791298 | 791298 | 562370 | 100% | 71.07% | -28.93% | 0.71069 | 791298 | 791298 | 562370 | 100% | [5 empty] | 16
17
Trade Item Wise Summary | [16 empty] | 18
1817-Trade | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs % | Actual Hrs % | Variance % | productivity |  |  | 1817-Trade | Budget Hrs | Planned Hrs | Earned Hrs | Planned Hrs % |  |  | 19
Anti-Fungal & Carbonation | 12793 | 12789 | 9700 | 99.97% | 75.82% | -24.15% | 0.75846 |  |  | Anti-Fungal & Carbonation | 12793 | 12789 | 9700 | 99.97% |  |  | 20
Ceramic | 12431 | 12432 | 10451 | 100% | 84.07% | -15.94% | 0.84065 |  |  | Ceramic | 12431 | 12432 | 10451 | 100% |  |  | 21
Concrete | 377918 | 377914 | 212614 | 100% | 56.26% | -43.74% | 0.5626 |  |  | Concrete | 377918 | 377914 | 212614 | 100% |  |  | 22
Conveying System | 4682 | 4680 | 3996 | 99.96% | 85.35% | -14.61% | 0.85385 |  |  | Conveying System | 4682 | 4680 | 3996 | 99.96% |  |  | 23
Doors | 5692 | 5678 | 4399 | 99.75% | 77.28% | -22.47% | 0.77474 |  |  | Doors | 5692 | 5678 | 4399 | 99.75% |  |  | 24
Electrical | 28801 | 28780 | 25289 | 99.93% | 87.81% | -12.12% | 0.8787 |  |  | Electrical | 28801 | 28780 | 25289 | 99.93% |  |  | 25
Epoxy & Traffic Coating | 4452 | 4453 | 3741 | 100% | 84.03% | -15.99% | 0.84011 |  |  | Epoxy & Traffic Coating | 4452 | 4453 | 3741 | 100% |  |  | 26
False Ceiling | 20728 | 20726 | 17639 | 99.99% | 85.1% | -14.89% | 0.85106 |  |  | False Ceiling | 20728 | 20726 | 17639 | 99.99% |  |  | (blank)
Fire Fighting | 15404 | 15401 | 14186 | 99.98% | 92.09% | -7.888% | 0.92111 |  |  | Fire Fighting | 15404 | 15401 | 14186 | 99.98% |  |  | Grand Total
Glazing | 5473 | 5475 | 3392 | 100% | 61.98% | -38.06% | 0.61954 |  |  | Glazing | 5473 | 5475 | 3392 | 100%
HVAC | 27438 | 27460 | 24469 | 100.1% | 89.18% | -10.9% | 0.89108 |  |  | HVAC | 27438 | 27460 | 24469 | 100.1%
LPG System | 2173 | 2170 | 1663 | 99.86% | 76.53% | -23.33% | 0.76636 |  |  | LPG System | 2173 | 2170 | 1663 | 99.86%
Masonry | 22530 | 22522 | 22241 | 99.96% | 98.72% | -1.247% | 0.98752 |  |  | Masonry | 22530 | 22522 | 22241 | 99.96%
Natural Stone | 13058 | 13058 | 11055 | 100% | 84.66% | -15.34% | 0.84661 |  |  | Natural Stone | 13058 | 13058 | 11055 | 100%
Others Finishes | 36854 | 36867 | 30104 | 100% | 81.68% | -18.35% | 0.81656 |  |  | Others Finishes | 36854 | 36867 | 30104 | 100%
Paint | 18963 | 18967 | 14408 | 100% | 75.98% | -24.04% | 0.75964
Plaster | 112175 | 112179 | 98858 | 100% | 88.13% | -11.88% | 0.88125
Plumbing | 16004 | 16013 | 12932 | 100.1% | 80.8% | -19.25% | 0.80759
Porcelain | 18774 | 18781 | 15716 | 100% | 83.71% | -16.33% | 0.8368
Prelims | 514 | 513 | 393 | 99.81% | 76.46% | -23.35% | 0.76608
Site Works | 20039 | 20037 | 13023 | 99.99% | 64.99% | -35% | 0.64995
Terrazo Tiles | 14402 | 14403 | 12101 | 100% | 84.02% | -15.98% | 0.84017
Grand Total | 791298 | 791298 | 562370 | 100% | 71.07% | -28.93% | 0.71069
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Monthly Cost Summary
Project Name |  |  |  | Monthly Progress Cost Summary | [10 empty] | Data Date: | 2022-03-31
Location | [14 empty] | Current Month | 26
BOQ Item Wise Summary | [14 empty] | Total Months | 26
1817-BOQ Summary | Budget Cost (AED) | Planned Cost (AED) | Earned Cost (AED) | Planned % | Actual % | Variance % | SPI | Budget Cost (AED) | Planned Cost (AED) | Earned Cost (AED) | Planned % | [5 empty] | Row Labels
Div 01 | 5594621 | 5573826 | 23321997 | 99.63% | 416.9% | 317.2% | 4.1842 | 5594621 | 5573826 | 23321997 | 99.63% | [5 empty] | 1
Div 02 | 8101845 | 8101840 | 6246369 | 100% | 77.1% | -22.9% | 0.77098 | 8101845 | 8101840 | 6246369 | 100% | [5 empty] | 2
Div 03 | 26658801 | 26615432 | 15438803 | 99.84% | 57.91% | -41.92% | 0.58007 | 26658801 | 26615432 | 15438803 | 99.84% | [5 empty] | 3
Div 04 | 1709702 | 1709700 | 1703030 | 100% | 99.61% | -0.3901% | 0.9961 | 1709702 | 1709700 | 1703030 | 100% | [5 empty] | 4
Div 05 | 432738 | 432738 | 367018 | 100% | 84.81% | -15.19% | 0.84813 | 432738 | 432738 | 367018 | 100% | [5 empty] | 5
Div 06 | 358000 | 358000 | 304300 | 100% | 85% | -15% | 0.85 | 358000 | 358000 | 304300 | 100% | [5 empty] | 6
Div 07 | 1024731 | 1024724 | 843510 | 100% | 82.32% | -17.68% | 0.82316 | 1024731 | 1024724 | 843510 | 100% | [5 empty] | 7
Div 08 | 2748699 | 2748699 | 1879885 | 100% | 68.39% | -31.61% | 0.68392 | 2748699 | 2748699 | 1879885 | 100% | [5 empty] | 8
Div 09 | 8267790 | 8270937 | 6891653 | 100% | 83.36% | -16.68% | 0.83324 | 8267790 | 8270937 | 6891653 | 100% | [5 empty] | 9
Div 10 | 2348697 | 2348702 | 1939800 | 100% | 82.59% | -17.41% | 0.8259 | 2348697 | 2348702 | 1939800 | 100% | [5 empty] | 10
Div 11 | 1781708 | 1781719 | 1622032 | 100% | 91.04% | -8.963% | 0.91037 | 1781708 | 1781719 | 1622032 | 100% | [5 empty] | 11
Div 12 | 10893557 | 10951726 | 9514255 | 100.5% | 87.34% | -13.2% | 0.86874 | 10893557 | 10951726 | 9514255 | 100.5% | [5 empty] | 12
Div 13 | 3801981 | 3802003 | 3249600 | 100% | 85.47% | -14.53% | 0.85471 | 3801981 | 3802003 | 3249600 | 100% | [5 empty] | 13
Div 14 | 148097 | 148103 | 122789 | 100% | 82.91% | -17.09% | 0.82908 | 148097 | 148103 | 122789 | 100% | [5 empty] | 14
Div 15 | 12872739 | 12875603 | 11255390 | 100% | 87.44% | -12.59% | 0.87416 | 12872739 | 12875603 | 11255390 | 100% | [5 empty] | 15
Grand Total | 86743706 | 86743752 | 84700431 | 100% | 97.64% | -0.023556 | 0.97644 | 86743706 | 86743752 | 84700431 | 100% | [5 empty] | 16
17
Trade Item Wise Summary | [16 empty] | 18
1817-Trade | Budget Cost | Planned Cost | Earned Value (AED) | Planned % | Actual % | Variance % | SPI |  |  | 1817-Trade | Budget Cost | Planned Cost | Earned Value (AED) | Planned % |  |  | 19
Anti-Fungal & Carbonation | 572734 | 572736 | 419459 | 100% | 73.24% | -26.76% | 0.73238 |  |  | Anti-Fungal & Carbonation | 572734 | 572736 | 419459 | 100% |  |  | 20
Ceramic | 355680 | 355680 | 297811 | 100% | 83.73% | -16.27% | 0.8373 |  |  | Ceramic | 355680 | 355680 | 297811 | 100% |  |  | 21
Concrete | 26658801 | 26615432 | 15438803 | 99.84% | 57.91% | -41.92% | 0.58007 |  |  | Concrete | 26658801 | 26615432 | 15438803 | 99.84% |  |  | 22
Conveying System | 3801981 | 3802003 | 3249600 | 100% | 85.47% | -14.53% | 0.85471 |  |  | Conveying System | 3801981 | 3802003 | 3249600 | 100% |  |  | 23
Doors | 969680 | 969676 | 744672 | 100% | 76.8% | -23.2% | 0.76796 |  |  | Doors | 969680 | 969676 | 744672 | 100% |  |  | 24
Electrical | 12872739 | 12872747 | 11255390 | 100% | 87.44% | -12.56% | 0.87436 |  |  | Electrical | 12872739 | 12872747 | 11255390 | 100% |  |  | 25
Epoxy & Traffic Coating | 975846 | 975845 | 818773 | 100% | 83.9% | -16.1% | 0.83904 |  |  | Epoxy & Traffic Coating | 975846 | 975845 | 818773 | 100% |  |  | 26
False Ceiling | 1052294 | 1052290 | 896463 | 100% | 85.19% | -14.81% | 0.85192 |  |  | False Ceiling | 1052294 | 1052290 | 896463 | 100% |  |  | (blank)
Fire Fighting | 1781708 | 1781719 | 1622032 | 100% | 91.04% | -8.963% | 0.91037 |  |  | Fire Fighting | 1781708 | 1781719 | 1622032 | 100% |  |  | Grand Total
Glazing | 1644464 | 1644468 | 1019226 | 100% | 61.98% | -38.02% | 0.61979 |  |  | Glazing | 1644464 | 1644468 | 1019226 | 100%
HVAC | 10893557 | 10893559 | 9514255 | 100% | 87.34% | -12.66% | 0.87338 |  |  | HVAC | 10893557 | 10893559 | 9514255 | 100%
LPG System | 148097 | 148103 | 122789 | 100% | 82.91% | -17.09% | 0.82908 |  |  | LPG System | 148097 | 148103 | 122789 | 100%
Masonry | 1709702 | 1709700 | 1703030 | 100% | 99.61% | -0.3901% | 0.9961 |  |  | Masonry | 1709702 | 1709700 | 1703030 | 100%
Natural Stone | 2149353 | 2152501 | 1806754 | 100.1% | 84.06% | -16.09% | 0.83937 |  |  | Natural Stone | 2149353 | 2152501 | 1806754 | 100.1%
Others Finishes | 2559272 | 2620288 | 2135674 | 102.4% | 83.45% | -18.94% | 0.81505 |  |  | Others Finishes | 2559272 | 2620288 | 2135674 | 102.4%
Paint | 354486 | 354488 | 266580 | 100% | 75.2% | -24.8% | 0.75201
Plaster | 908192 | 908194 | 800329 | 100% | 88.12% | -11.88% | 0.88123
Plumbing | 2348697 | 2348702 | 1939800 | 100% | 82.59% | -17.41% | 0.8259
Porcelain | 1017975 | 1017974 | 852100 | 100% | 83.71% | -16.29% | 0.83705
Prelims | 5594621 | 5573826 | 23321997 | 99.63% | 416.9% | 317.2% | 4.1842
Site Works | 8101845 | 8101840 | 6246369 | 100% | 77.1% | -22.9% | 0.77098
Terrazo Tiles | 271982 | 271981 | 228525 | 100% | 84.02% | -15.98% | 0.84022
Grand Total | 86743706 | 86743752 | 84700431 | 100% | 97.64% | -0.023556 | 0.97644
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Monthly Detailed EVM Hrs
Project Name | [7 empty] | Data Date: |  | 2022-03-31
Location | [7 empty] | Current Week |  | 26
[8 empty] | Total Weeks |  | 114
1817-Zone | 1817-BOQ Summary | Activity ID | Activity Name | Budget Hrs | Planned Hrs | Earned Hrs | Planned % Hrs | Planned Weightage % | Actual Weightage % | Actual % Complete | Productivity
Z1 | Div 01 | PRL-MOB-1020 | Site Office Establishment | 162 | 162 | 124 | 100% | 0.0001868% | 0.0001429% | 76.54% | 76.54%
|  | PRL-MOB-1050 | Project Sign Boards and Hoarding | 162 | 162 | 124 | 100% | 0.0001868% | 0.0001429% | 76.54% | 76.54%
|  | PRL-MOB-1100 | Yards & Stores Establishment | 190 | 189 | 145 | 99.47% | 0.0002179% | 0.0001672% | 76.32% | 76.72%
| Div 02 | C-EW-10370 | Excavation Stage 1 - Z1 | 2271 | 2272 | 1249 | 100% | 0.002619% | 0.00144% | 55% | 54.97%
|  | C-EW-10390 | Excavation Stage 2 - Z1 | 2272 | 2272 | 1250 | 100% | 0.002619% | 0.001441% | 55.02% | 55.02%
|  | C-EW-10450 | Waterproof Membrane on Gunite Wall - Z1-B1 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
|  | C-EW-2430 | Waterproof Membrane on Gunite Wall - Z1-B2 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
|  | C-SHRNG-DCE-C-2330 | Place Guide Wall - Z1 | 249 | 249 | 274 | 100% | 0.0002871% | 0.0003159% | 110% | 110%
|  | C-SHRNG-DCE-C-2350 | Install Capping Beam - Z1 | 2461 | 2460 | 1353 | 99.96% | 0.002836% | 0.00156% | 54.98% | 55%
|  | PRL-MOB-SCW-2330 | Clearing Existing Utilities | 495 | 494 | 272 | 99.8% | 0.0005695% | 0.0003136% | 54.95% | 55.06%
| Div 03 | C-EW-2420 | Gunite Wall - Z1 | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z1-11460 | Post Tensioning the Slab - Z1 - F1 | 8 | 8 | 4 | 100% | 9.223e-06% | 4.611e-06% | 50% | 50%
|  | Z1-11470 | Post Tensioning the Slab - Z1 - F2 | 8 | 8 | 7 | 100% | 9.223e-06% | 8.07e-06% | 87.5% | 87.5%
|  | Z1-11480 | Post Tensioning the Slab - Z1 - RF | 8 | 8 | 7 | 100% | 9.223e-06% | 8.07e-06% | 87.5% | 87.5%
|  | Z1-11490 | Post Tensioning the Slab - Z1 - SRVF | 8 | 8 | 7 | 100% | 9.223e-06% | 8.07e-06% | 87.5% | 87.5%
|  | Z1-C-CON-2400 | PCC Blind Concrete - Z1 - Lift Pit | 6 | 6 | 5 | 100% | 6.917e-06% | 5.764e-06% | 83.33% | 83.33%
|  | Z1-C-CON-2440 | Waterproof Membrane - Z1 - Lift Pit | 40 | 40 | 34 | 100% | 4.611e-05% | 3.92e-05% | 85% | 85%
|  | Z1-C-CON-2450 | Protection Screed - Z1 - Lift Pit | 24 | 24 | 20 | 100% | 2.767e-05% | 2.306e-05% | 83.33% | 83.33%
|  | Z1-C-CON-2460 | Fix Rebar - Z1 - Lift Pit | 497 | 497 | 422 | 100% | 0.000573% | 0.0004865% | 84.91% | 84.91%
|  | Z1-C-CON-2480 | Pour Concrete - Z1 - Lift Pit | 95 | 95 | 81 | 100% | 0.0001095% | 9.338e-05% | 85.26% | 85.26%
|  | Z1-C-CON-2500 | PCC Blind Concrete - Z1 - Raft | 196 | 196 | 167 | 100% | 0.000226% | 0.0001925% | 85.2% | 85.2%
|  | Z1-C-CON-2510 | Waterproof Membrane - Z1 - Raft | 1560 | 1560 | 1326 | 100% | 0.001798% | 0.001529% | 85% | 85%
|  | Z1-C-CON-2520 | Protection Screed - Z1 - Raft | 96 | 96 | 3 | 100% | 0.0001107% | 3.458e-06% | 3.125% | 3.125%
|  | Z1-C-CON-2530 | Fix Rebar - Z1 - Raft | 18159 | 18160 | 182 | 100% | 0.02094% | 0.0002098% | 1.002% | 1.002%
|  | Z1-C-CON-2550 | Fix Formwork - Z1 - Raft | 261 | 261 | 55 | 100% | 0.0003009% | 6.341e-05% | 21.07% | 21.07%
|  | Z1-C-CON-2560 | Pour Concrete - Z1 - Raft | 4422 | 4422 | 940 | 100% | 0.005098% | 0.001084% | 21.26% | 21.26%
|  | Z1-C-CON-2570 | Fix Rebar Core Walls - Z1 - B2 | 1609 | 1609 | 342 | 100% | 0.001855% | 0.0003943% | 21.26% | 21.26%
|  | Z1-C-CON-2580 | Fix Formwork Core Walls - Z1 - B2 | 1547 | 1548 | 1315 | 100.1% | 0.001785% | 0.001516% | 85% | 84.95%
|  | Z1-C-CON-2600 | Fix Rebar Retaining Walls - Z1 - B2 | 2863 | 2862 | 1216 | 99.97% | 0.003299% | 0.001402% | 42.47% | 42.49%
|  | Z1-C-CON-2610 | Fix Formwork Retaining Walls - Z1 - B2 | 2342 | 2342 | 498 | 100% | 0.0027% | 0.0005741% | 21.26% | 21.26%
|  | Z1-C-CON-2620 | Pour Concrete Retaining Walls - Z1 - B2 | 482 | 482 | 410 | 100% | 0.0005557% | 0.0004727% | 85.06% | 85.06%
|  | Z1-C-CON-2630 | Pour Concrete Core Walls - Z1 - B2 | 248 | 248 | 211 | 100% | 0.0002859% | 0.0002432% | 85.08% | 85.08%
|  | Z1-C-CON-2640 | Fix Rebar Columns - Z1 - B2 | 3020 | 3020 | 1284 | 100% | 0.003482% | 0.00148% | 42.52% | 42.52%
|  | Z1-C-CON-2650 | Fix Formwork Columns - Z1 - B2 | 889 | 889 | 189 | 100% | 0.001025% | 0.0002179% | 21.26% | 21.26%
|  | Z1-C-CON-2660 | Pour Concrete Columns - Z1 - B2 | 174 | 174 | 37 | 100% | 0.0002006% | 4.265e-05% | 21.26% | 21.26%
|  | Z1-C-CON-2670 | Fix Formwork Stairs - Z1 - B2 | 4 | 4 | 1 | 100% | 4.611e-06% | 1.153e-06% | 25% | 25%
|  | Z1-C-CON-2680 | Fix Rebar Stairs - Z1 - B2 | 43 | 43 | 1 | 100% | 4.957e-05% | 1.153e-06% | 2.326% | 2.326%
|  | Z1-C-CON-2690 | Pour Concrete Stairs - Z1 - B2 | 8 | 8 | 0 | 100% | 9.223e-06% |  | 0% | 0%
|  | Z1-C-CON-2700 | Pour Concrete Slabs - Z1 - B1 | 1426 | 1426 | 1212 | 100% | 0.001644% | 0.001397% | 84.99% | 84.99%
|  | Z1-C-CON-2710 | Fix Formwork Slabs - Z1 - B1 | 4167 | 4167 | 3542 | 100% | 0.004804% | 0.004083% | 85% | 85%
|  | Z1-C-CON-2720 | Fix Rebar Slabs - Z1 - B1 | 5965 | 5966 | 5070 | 100% | 0.006878% | 0.005845% | 85% | 84.98%
|  | Z1-C-CON-2730 | Fix Rebar Retaining Walls - Z1 - B1 | 2275 | 2275 | 23 | 100% | 0.002623% | 2.651e-05% | 1.011% | 1.011%
|  | Z1-C-CON-2740 | Fix Formwork Retaining Walls - Z1 - B1 | 2342 | 2342 | 70 | 100% | 0.0027% | 8.07e-05% | 2.989% | 2.989%
|  | Z1-C-CON-2750 | Pour Concrete Retaining Walls - Z1 - B1 | 484 | 484 | 20 | 100% | 0.000558% | 2.306e-05% | 4.132% | 4.132%
|  | Z1-C-CON-2760 | Fix Rebar Core Walls - Z1 - B1 | 1493 | 1493 | 15 | 100% | 0.001721% | 1.729e-05% | 1.005% | 1.005%
|  | Z1-C-CON-2770 | Fix Formwork Core Walls - Z1 - B1 | 1539 | 1539 | 240 | 100% | 0.001774% | 0.0002767% | 15.59% | 15.59%
|  | Z1-C-CON-2780 | Pour Concrete Core Walls - Z1 - B1 | 284 | 284 | 6 | 100% | 0.0003274% | 6.917e-06% | 2.113% | 2.113%
|  | Z1-C-CON-2790 | Fix Rebar Columns - Z1 - B1 | 2314 | 2313 | 315 | 99.96% | 0.002666% | 0.0003631% | 13.61% | 13.62%
|  | Z1-C-CON-2800 | Fix Formwork Columns - Z1 - B1 | 991 | 991 | 30 | 100% | 0.001142% | 3.458e-05% | 3.027% | 3.027%
|  | Z1-C-CON-2810 | Pour Concrete Columns - Z1 - B1 | 194 | 194 | 30 | 100% | 0.0002236% | 3.458e-05% | 15.46% | 15.46%
|  | Z1-C-CON-2820 | Fix Formwork Stairs - Z1 - B1 | 4 | 4 | 0 | 100% | 4.611e-06% |  | 0% | 0%
|  | Z1-C-CON-2830 | Fix Rebar Stairs - Z1 - B1 | 43 | 43 | 3 | 100% | 4.957e-05% | 3.458e-06% | 6.977% | 6.977%
|  | Z1-C-CON-2840 | Pour Concrete Stairs - Z1 - B1 | 8 | 8 | 0 | 100% | 9.223e-06% |  | 0% | 0%
|  | Z1-C-CON-3000 | Fix Formwork Slabs - Z1 - GF | 4684 | 4684 | 94 | 100% | 0.0054% | 0.0001084% | 2.007% | 2.007%
|  | Z1-C-CON-3010 | Fix Rebar Slabs - Z1 - GF | 11392 | 11393 | 9683 | 100% | 0.01313% | 0.01116% | 85% | 84.99%
|  | Z1-C-CON-3020 | Pour Concrete Slabs - Z1 - GF | 1908 | 1908 | 114 | 100% | 0.0022% | 0.0001314% | 5.975% | 5.975%
|  | Z1-C-CON-3030 | Fix Rebar Core Walls - Z1 - GF | 2275 | 2275 | 136 | 100% | 0.002623% | 0.0001568% | 5.978% | 5.978%
|  | Z1-C-CON-3040 | Fix Formwork Core Walls - Z1 - GF | 2295 | 2294 | 1211 | 99.96% | 0.002645% | 0.001396% | 52.77% | 52.79%
|  | Z1-C-CON-3050 | Pour Concrete Core Walls - Z1 - GF | 314 | 314 | 31 | 100% | 0.000362% | 3.574e-05% | 9.873% | 9.873%
|  | Z1-C-CON-3060 | Fix Rebar Columns - Z1 - GF | 3008 | 3007 | 180 | 99.97% | 0.003467% | 0.0002075% | 5.984% | 5.986%
|  | Z1-C-CON-3070 | Fix Formwork Columns - Z1 - GF | 1515 | 1514 | 1416 | 99.93% | 0.001745% | 0.001632% | 93.47% | 93.53%
|  | Z1-C-CON-3080 | Pour Concrete Columns - Z1 - GF | 300 | 298 | 158 | 99.33% | 0.0003435% | 0.0001821% | 52.67% | 53.02%
|  | Z1-C-CON-3090 | Fix Formwork Stairs - Z1 - GF | 7 | 7 | 4 | 100% | 8.07e-06% | 4.611e-06% | 57.14% | 57.14%
|  | Z1-C-CON-3100 | Fix Rebar Stairs - Z1 - GF | 21 | 21 | 12 | 100% | 2.421e-05% | 1.383e-05% | 57.14% | 57.14%
|  | Z1-C-CON-3110 | Pour Concrete Stairs - Z1 - GF | 12 | 12 | 7 | 100% | 1.383e-05% | 8.07e-06% | 58.33% | 58.33%
|  | Z1-C-CON-3160 | Fix Formwork Slabs - Z1 - F1 | 3790 | 3790 | 379 | 100% | 0.004369% | 0.0004369% | 10% | 10%
|  | Z1-C-CON-3170 | Pour Concrete Slabs - Z1 - F1 | 1316 | 1316 | 1119 | 100% | 0.001517% | 0.00129% | 85.03% | 85.03%
|  | Z1-C-CON-3180 | Fix Rebar Slabs - Z1 - F1 | 4939 | 4939 | 494 | 100% | 0.005694% | 0.0005695% | 10% | 10%
|  | Z1-C-CON-3190 | Fix Rebar Core Walls - Z1 - F1 | 2248 | 2248 | 1261 | 100% | 0.002592% | 0.001454% | 56.09% | 56.09%
|  | Z1-C-CON-3200 | Fix Formwork Core Walls - Z1 - F1 | 2298 | 2299 | 1289 | 100% | 0.00265% | 0.001486% | 56.09% | 56.07%
|  | Z1-C-CON-3210 | Pour Concrete Core Walls - Z1 - F1 | 318 | 318 | 80 | 100% | 0.0003666% | 9.223e-05% | 25.16% | 25.16%
|  | Z1-C-CON-3220 | Fix Rebar Columns - Z1 - F1 | 3046 | 3046 | 1709 | 100% | 0.003511% | 0.00197% | 56.11% | 56.11%
|  | Z1-C-CON-3230 | Fix Formwork Columns - Z1 - F1 | 1507 | 1507 | 845 | 100% | 0.001737% | 0.0009741% | 56.07% | 56.07%
|  | Z1-C-CON-3240 | Pour Concrete Columns - Z1 - F1 | 300 | 298 | 168 | 99.33% | 0.0003435% | 0.0001937% | 56% | 56.38%
|  | Z1-C-CON-3250 | Fix Formwork Stairs - Z1 - F1 | 7 | 7 | 6 | 100% | 8.07e-06% | 6.917e-06% | 85.71% | 85.71%
|  | Z1-C-CON-3260 | Fix Rebar Stairs - Z1 - F1 | 21 | 21 | 42 | 100% | 2.421e-05% | 4.842e-05% | 200% | 200%
|  | Z1-C-CON-3270 | Pour Concrete Stairs - Z1 - F1 | 12 | 12 | 10 | 100% | 1.383e-05% | 1.153e-05% | 83.33% | 83.33%
|  | Z1-C-CON-3280 | Fix Formwork Slabs - Z1 - F2 | 3776 | 3776 | 1888 | 100% | 0.004353% | 0.002177% | 50% | 50%
|  | Z1-C-CON-3290 | Fix Rebar Slabs - Z1 - F2 | 5071 | 5071 | 1268 | 100% | 0.005846% | 0.001462% | 25% | 25%
|  | Z1-C-CON-3300 | Pour Concrete Slabs - Z1 - F2 | 1324 | 1324 | 1125 | 100% | 0.001526% | 0.001297% | 84.97% | 84.97%
|  | Z1-C-CON-3320 | Fix Rebar Core Walls - Z1 - F2 | 1485 | 1485 | 2467 | 100% | 0.001712% | 0.002844% | 166.1% | 166.1%
|  | Z1-C-CON-3330 | Fix Formwork Core Walls - Z1 - F2 | 1357 | 1357 | 1154 | 100% | 0.001564% | 0.00133% | 85.04% | 85.04%
|  | Z1-C-CON-3340 | Pour Concrete Core Walls - Z1 - F2 | 192 | 192 | 163 | 100% | 0.0002213% | 0.0001879% | 84.9% | 84.9%
|  | Z1-C-CON-3350 | Fix Rebar Columns - Z1 - F2 | 2077 | 2077 | 3622 | 100% | 0.002394% | 0.004176% | 174.4% | 174.4%
|  | Z1-C-CON-3360 | Fix Formwork Columns - Z1 - F2 | 968 | 968 | 823 | 100% | 0.001116% | 0.0009488% | 85.02% | 85.02%
|  | Z1-C-CON-3370 | Pour Concrete Columns - Z1 - F2 | 190 | 188 | 161 | 98.95% | 0.0002167% | 0.0001856% | 84.74% | 85.64%
|  | Z1-C-CON-3380 | Fix Formwork Stairs - Z1 - F2 | 8 | 7 | 7 | 87.5% | 8.07e-06% | 8.07e-06% | 87.5% | 100%
|  | Z1-C-CON-3390 | Fix Rebar Stairs - Z1 - F2 | 16 | 16 | 14 | 100% | 1.845e-05% | 1.614e-05% | 87.5% | 87.5%
|  | Z1-C-CON-3400 | Pour Concrete Stairs - Z1 - F2 | 8 | 8 | 7 | 100% | 9.223e-06% | 8.07e-06% | 87.5% | 87.5%
|  | Z1-C-CON-3410 | Fix Formwork Slabs - Z1 - RF | 3775 | 3774 | 3209 | 99.97% | 0.004351% | 0.003699% | 85.01% | 85.03%
|  | Z1-C-CON-3420 | Fix Rebar Slabs - Z1 - RF | 5045 | 5046 | 4288 | 100% | 0.005817% | 0.004943% | 85% | 84.98%
|  | Z1-C-CON-3430 | Pour Concrete Slabs - Z1 - RF | 1320 | 1320 | 1122 | 100% | 0.001522% | 0.001293% | 85% | 85%
|  | Z1-C-CON-3450 | Fix Rebar Core Walls - Z1 - RF | 1460 | 1460 | 1241 | 100% | 0.001683% | 0.001431% | 85% | 85%
|  | Z1-C-CON-3460 | Fix Formwork Core Walls - Z1 - RF | 1352 | 1352 | 1150 | 100% | 0.001559% | 0.001326% | 85.06% | 85.06%
|  | Z1-C-CON-3470 | Pour Concrete Core Walls - Z1 - RF | 190 | 190 | 161 | 100% | 0.000219% | 0.0001856% | 84.74% | 84.74%
|  | Z1-C-CON-3480 | Fix Rebar Columns - Z1 - RF | 1700 | 1700 | 1445 | 100% | 0.00196% | 0.001666% | 85% | 85%
|  | Z1-C-CON-3490 | Fix Formwork Columns - Z1 - RF | 750 | 750 | 637 | 100% | 0.0008646% | 0.0007343% | 84.93% | 84.93%
|  | Z1-C-CON-3500 | Pour Concrete Columns - Z1 - RF | 150 | 152 | 128 | 101.3% | 0.0001752% | 0.0001476% | 85.33% | 84.21%
|  | Z1-C-CON-3510 | Fix Formwork Stairs - Z1 - RF | 8 | 7 | 7 | 87.5% | 8.07e-06% | 8.07e-06% | 87.5% | 100%
|  | Z1-C-CON-3520 | Fix Rebar Stairs - Z1 - RF | 16 | 16 | 14 | 100% | 1.845e-05% | 1.614e-05% | 87.5% | 87.5%
|  | Z1-C-CON-3530 | Pour Concrete Stairs - Z1 - RF | 8 | 8 | 7 | 100% | 9.223e-06% | 8.07e-06% | 87.5% | 87.5%
|  | Z1-C-CON-5620 | Fix Formwork Slabs - Z1 - SRVF | 3234 | 3234 | 2749 | 100% | 0.003728% | 0.003169% | 85% | 85%
|  | Z1-C-CON-5630 | Fix Rebar Slabs - Z1 - SRVF | 4156 | 4156 | 3533 | 100% | 0.004791% | 0.004073% | 85.01% | 85.01%
|  | Z1-C-CON-5640 | Pour Concrete Slabs - Z1 - SRVF | 1132 | 1132 | 962 | 100% | 0.001305% | 0.001109% | 84.98% | 84.98%
|  | Z1-C-CON-5660 | Fix Rebar Core Walls - Z1 - SRVF | 864 | 863 | 734 | 99.88% | 0.0009949% | 0.0008462% | 84.95% | 85.05%
|  | Z1-C-CON-5670 | Fix Formwork Core Walls - Z1 - SRVF | 769 | 769 | 654 | 100% | 0.0008865% | 0.0007539% | 85.05% | 85.05%
|  | Z1-C-CON-5680 | Pour Concrete Core Walls - Z1 - SRVF | 106 | 106 | 90 | 100% | 0.0001222% | 0.0001038% | 84.91% | 84.91%
|  | Z1-C-CON-5690 | Fix Rebar Columns - Z1 - SRVF | 153 | 154 | 130 | 100.7% | 0.0001775% | 0.0001499% | 84.97% | 84.42%
|  | Z1-C-CON-5700 | Fix Formwork Columns - Z1 - SRVF | 54 | 54 | 46 | 100% | 6.225e-05% | 5.303e-05% | 85.19% | 85.19%
|  | Z1-C-CON-5710 | Pour Concrete Columns - Z1 - SRVF | 10 | 10 | 8 | 100% | 1.153e-05% | 9.223e-06% | 80% | 80%
|  | Z1-C-CON-5720 | Fix Formwork Parapet - Z1 - SRVF | 151 | 150 | 129 | 99.34% | 0.0001729% | 0.0001487% | 85.43% | 86%
|  | Z1-C-CON-5730 | Fix Rebar Parapet - Z1 - SRVF | 314 | 314 | 267 | 100% | 0.000362% | 0.0003078% | 85.03% | 85.03%
|  | Z1-C-CON-5740 | Pour Concrete Parapet - Z1 - SRVF | 180 | 180 | 153 | 100% | 0.0002075% | 0.0001764% | 85% | 85%
|  | Z1-C-CON-5750 | Fix Formwork Slabs - Z1 - TRF | 397 | 397 | 337 | 100% | 0.0004577% | 0.0003885% | 84.89% | 84.89%
|  | Z1-C-CON-5760 | Fix Rebar Slabs - Z1 - TRF | 404 | 404 | 93 | 100% | 0.0004657% | 0.0001072% | 23.02% | 23.02%
|  | Z1-C-CON-5770 | Pour Concrete Slabs - Z1 - TRF | 120 | 120 | 28 | 100% | 0.0001383% | 3.228e-05% | 23.33% | 23.33%
|  | Z1-C-CON-5790 | Pour MEP RCC Pedastals - Z1 - SRVF | 2 | 2 | 2 | 100% | 2.306e-06% | 2.306e-06% | 100% | 100%
|  | Z1-C-CON-5810 | Fix Rebar Parapet - Z1 - TRF | 315 | 315 | 139 | 100% | 0.0003631% | 0.0001602% | 44.13% | 44.13%
|  | Z1-C-CON-5820 | Fix Formwork Parapet - Z1 - TRF | 151 | 151 | 128 | 100% | 0.0001741% | 0.0001476% | 84.77% | 84.77%
|  | Z1-C-CON-5830 | Pour Concrete Parapet - Z1 - TRF | 180 | 180 | 153 | 100% | 0.0002075% | 0.0001764% | 85% | 85%
|  | Z1-C-CON-5840 | Fix Formwork Ramp - Z1 - B2 | 270 | 270 | 229 | 100% | 0.0003113% | 0.000264% | 84.81% | 84.81%
|  | Z1-C-CON-5850 | Fix Rebar Ramp - Z1 - B2 | 97 | 96 | 1 | 98.97% | 0.0001107% | 1.153e-06% | 1.031% | 1.042%
|  | Z1-C-CON-5860 | Pour Concrete Ramp - Z1 - B2 | 114 | 114 | 1 | 100% | 0.0001314% | 1.153e-06% | 0.8772% | 0.8772%
|  | Z1-C-CON-5870 | Fix Formwork Ramp - Z1 - B1 | 231 | 232 | 14 | 100.4% | 0.0002675% | 1.614e-05% | 6.061% | 6.034%
|  | Z1-C-CON-5880 | Fix Rebar Ramp - Z1 - B1 | 372 | 372 | 22 | 100% | 0.0004288% | 2.536e-05% | 5.914% | 5.914%
|  | Z1-C-CON-5890 | Pour Concrete Ramp - Z1 - B1 | 98 | 98 | 6 | 100% | 0.000113% | 6.917e-06% | 6.122% | 6.122%
|  | Z1-C-CON-5900 | Fix Rebar Core Walls Ramp - Z1 - B2 | 1055 | 1055 | 897 | 100% | 0.001216% | 0.001034% | 85.02% | 85.02%
|  | Z1-C-CON-5910 | Fix Formwork Walls Ramp - Z1 - B2 | 1040 | 1040 | 884 | 100% | 0.001199% | 0.001019% | 85% | 85%
|  | Z1-C-CON-5920 | Pour Concrete Core Walls Ramp - Z1 - B2 | 152 | 152 | 129 | 100% | 0.0001752% | 0.0001487% | 84.87% | 84.87%
|  | Z1-C-CON-5930 | Fix Rebar Core Walls Ramp - Z1 - B1 | 1015 | 1015 | 20 | 100% | 0.00117% | 2.306e-05% | 1.97% | 1.97%
|  | Z1-C-CON-5940 | Fix Formwork Walls Ramp - Z1 - B1 | 1050 | 1050 | 143 | 100% | 0.00121% | 0.0001649% | 13.62% | 13.62%
|  | Z1-C-CON-5950 | Pour Concrete Core Walls Ramp - Z1 - B1 | 152 | 152 | 129 | 100% | 0.0001752% | 0.0001487% | 84.87% | 84.87%
|  | Z1-C-FIN-6140 | GRP Linning - Z1 - B2 | 100 | 100 | 47 | 100% | 0.0001153% | 5.418e-05% | 47% | 47%
|  | Z1-C-FIN-7390 | GRP Linning - Z1 - B1 | 100 | 100 | 50 | 100% | 0.0001153% | 5.764e-05% | 50% | 50%
| Div 04 | Z1-C-FIN-10120 | Masonry Works Wet Area - Z1 - F2 | 1048 | 1048 | 891 | 100% | 0.001208% | 0.001027% | 85.02% | 85.02%
|  | Z1-C-FIN-10460 | Masonry Works Dry Area - Z1 - F2 | 1048 | 1048 | 891 | 100% | 0.001208% | 0.001027% | 85.02% | 85.02%
|  | Z1-C-FIN-10760 | Masonry Works Wet Area - Z1 - RF | 896 | 898 | 777 | 100.2% | 0.001035% | 0.0008957% | 86.72% | 86.53%
|  | Z1-C-FIN-10940 | Masonry Works Dry Area - Z1 - RF | 896 | 898 | 532 | 100.2% | 0.001035% | 0.0006133% | 59.38% | 59.24%
|  | Z1-C-FIN-5790 | Masonry Works - Z1 - B2 | 38 | 38 | 2 | 100% | 4.381e-05% | 2.306e-06% | 5.263% | 5.263%
|  | Z1-C-FIN-7040 | Masonry Works - Z1 - B1 | 378 | 376 | 212 | 99.47% | 0.0004335% | 0.0002444% | 56.08% | 56.38%
|  | Z1-C-FIN-8330 | Masonry Works - Z1 - GF | 2762 | 2764 | 1380 | 100.1% | 0.003186% | 0.001591% | 49.96% | 49.93%
|  | Z1-C-FIN-9490 | Masonry Works Wet + Dry Area - Z1 - F1 | 1784 | 1782 | 1517 | 99.89% | 0.002054% | 0.001749% | 85.03% | 85.13%
| Div 05 | A7120 | Signages - F2 | 20 | 20 |  | 100% | 2.306e-05% |  | 0% | 0%
|  | A7200 | Signages - RF | 20 | 20 |  | 100% | 2.306e-05% |  | 0% | 0%
|  | A9750 | Install Steel Grating Drive Way - B2 | 50 | 50 |  | 100% | 5.764e-05% |  | 0% | 0%
|  | A9760 | Install Road Signages Drive Way - B2 | 50 | 50 |  | 100% | 5.764e-05% |  | 0% | 0%
|  | A9800 | Install Steel Grating Drive Way - B1 | 51 | 50 |  | 98.04% | 5.764e-05% |  | 0% | 0%
|  | A9830 | Install Road Signages Drive Way - B1 | 50 | 50 |  | 100% | 5.764e-05% |  | 0% | 0%
|  | C-FIN-ENVLP-9550 | Fix Steel Decore - GF to SRVF (Elev. 1 & 4) | 1508 | 1509 | 1282 | 100.1% | 0.00174% | 0.001478% | 85.01% | 84.96%
|  | C-FIN-ENVLP-9640 | Install Aluminum & Wood Roof Features | 611 | 611 | 519 | 100% | 0.0007044% | 0.0005983% | 84.94% | 84.94%
|  | Z1-C-FIN-6150 | Fix Galvonized Iron Cat Ladder - Z1 - B2 | 25 | 25 | 2 | 100% | 2.882e-05% | 2.306e-06% | 8% | 8%
|  | Z1-C-FIN-7400 | Fix Galvonized Iron Cat Ladder - Z1 - B1 | 45 | 45 | 11 | 100% | 5.188e-05% | 1.268e-05% | 24.44% | 24.44%
|  | Z1-C-FIN-SCASE-8810 | Install Haindrails Staircase - Z1 - B2 - SRVF | 610 | 610 | 518 | 100% | 0.0007032% | 0.0005972% | 84.92% | 84.92%
| Div 06 | Z1-C-FIN-10710 | Fix Furniture & Counter Works kitchen/Pantry - Z1 - F2 | 450 | 450 | 382 | 100% | 0.0005188% | 0.0004404% | 84.89% | 84.89%
|  | Z1-C-FIN-11180 | Fix Furniture & Counter Works kitchen/Pantry - Z1 - RF | 450 | 450 | 382 | 100% | 0.0005188% | 0.0004404% | 84.89% | 84.89%
| Div 07 | C-FIN-ENVLP-9540 | Osmotic Cement Waterproof - GF to SRVF (Elev. 1 & 4) | 1149 | 1148 | 1166 | 99.91% | 0.001323% | 0.001344% | 101.5% | 101.6%
|  | Z123-C-FIN-18510 | Foam Concrete - Z123 - TRF | 1960 | 1960 | 1666 | 100% | 0.00226% | 0.001921% | 85% | 85%
|  | Z123-C-FIN-18520 | 4mm Waterproof Membrane Wet Area - Z123 - TRF | 1960 | 1960 | 1666 | 100% | 0.00226% | 0.001921% | 85% | 85%
|  | Z123-C-FIN-18530 | Protection Screed Wet Area - Z123 - TRF | 1960 | 1960 | 1666 | 100% | 0.00226% | 0.001921% | 85% | 85%
|  | Z123-C-FIN-18550 | Polystyrene Thermal Insulation - Z123 - TRF | 32 | 34 | 27 | 106.2% | 3.92e-05% | 3.113e-05% | 84.38% | 79.41%
|  | Z123-C-FIN-18560 | Roof Floor Terrazo Tiles Wet Area - Z123 - TRF | 192 | 194 | 163 | 101% | 0.0002236% | 0.0001879% | 84.9% | 84.02%
|  | Z1-C-FIN-10490 | Waterproof Bath - Z1 - F2 | 34 | 34 | 8 | 100% | 3.92e-05% | 9.223e-06% | 23.53% | 23.53%
|  | Z1-C-FIN-10500 | Protection Screed Bath - Z1 - F2 | 32 | 32 | 21 | 100% | 3.689e-05% | 2.421e-05% | 65.62% | 65.62%
|  | Z1-C-FIN-10590 | Waterproof kitchen/Pantry - Z1 - F2 | 34 | 34 | 8 | 100% | 3.92e-05% | 9.223e-06% | 23.53% | 23.53%
|  | Z1-C-FIN-10600 | Protection Screed kitchen/Pantry - Z1 - F2 | 34 | 34 | 8 | 100% | 3.92e-05% | 9.223e-06% | 23.53% | 23.53%
|  | Z1-C-FIN-10670 | Waterproof Garbage Room - Z1 - F2 | 34 | 34 | 8 | 100% | 3.92e-05% | 9.223e-06% | 23.53% | 23.53%
|  | Z1-C-FIN-10680 | Protection Screed Garbage Room - Z1 - F2 | 32 | 32 | 21 | 100% | 3.689e-05% | 2.421e-05% | 65.62% | 65.62%
|  | Z1-C-FIN-11000 | Waterproof Bath - Z1 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z1-C-FIN-11010 | Protection Screed Bath - Z1 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z1-C-FIN-11080 | Waterproof kitchen/Pantry - Z1 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z1-C-FIN-11090 | Protection Screed kitchen/Pantry - Z1 - RF | 32 | 34 | 27 | 106.2% | 3.92e-05% | 3.113e-05% | 84.38% | 79.41%
|  | Z1-C-FIN-11150 | Waterproof Garbage Room - Z1 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z1-C-FIN-11160 | Protection Screed Garbage Room - Z1 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z1-C-FIN-8870 | Waterproof & Screed Garbage Room - Z1 - GF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
| Div 08 | A7100 | Fix Windows & Door Frame & Leaf - F2 | 222 | 222 | 189 | 100% | 0.0002559% | 0.0002179% | 85.14% | 85.14%
|  | A7110 | Fix Ironmongery - F2 | 222 | 222 | 189 | 100% | 0.0002559% | 0.0002179% | 85.14% | 85.14%
|  | A7180 | Fix Windows & Door Frame & Leaf - RF | 224 | 222 | 191 | 99.11% | 0.0002559% | 0.0002202% | 85.27% | 86.04%
|  | A7190 | Fix Ironmongery - RF | 222 | 222 | 189 | 100% | 0.0002559% | 0.0002179% | 85.14% | 85.14%
|  | C-FIN-ENVLP-9530 | Fix Aluminum Glazing Pannels - GF to SRVF (Elev. 1 & 4) | 2736 | 2738 | 1696 | 100.1% | 0.003156% | 0.001955% | 61.99% | 61.94%
|  | Z1-C-FIN-10370 | Fix Door Subframes Wet Area - Z1 - F2 | 70 | 70 | 59 | 100% | 8.07e-05% | 6.802e-05% | 84.29% | 84.29%
|  | Z1-C-FIN-10470 | Fix Door Subframes Dry Area - Z1 - F2 | 70 | 70 | 59 | 100% | 8.07e-05% | 6.802e-05% | 84.29% | 84.29%
|  | Z1-C-FIN-10900 | Fix Door Subframes Wet Area - Z1 - RF | 70 | 70 | 59 | 100% | 8.07e-05% | 6.802e-05% | 84.29% | 84.29%
|  | Z1-C-FIN-10960 | Fix Door Subframes Dry Area - Z1 - RF | 70 | 70 | 59 | 100% | 8.07e-05% | 6.802e-05% | 84.29% | 84.29%
|  | Z1-C-FIN-18600 | Fix Doors - Z1 - B1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-18640 | Fix Doors - Z1 - B1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-18690 | Fix Doors Loading Room - Z1 - GF | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-18730 | Fix Doors Serv. Rooms - Z1 - F1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-6220 | Fix Doors - Z1 - B2 | 104 | 103 | 16 | 99.04% | 0.0001187% | 1.845e-05% | 15.38% | 15.53%
|  | Z1-C-FIN-6230 | Fix Doors - Z1 - B2 | 104 | 103 | 16 | 99.04% | 0.0001187% | 1.845e-05% | 15.38% | 15.53%
|  | Z1-C-FIN-6240 | Fix Doors - Z1 - B2 | 103 | 103 | 58 | 100% | 0.0001187% | 6.686e-05% | 56.31% | 56.31%
|  | Z1-C-FIN-7470 | Fix Doors - Z1 - B1 | 103 | 103 | 103 | 100% | 0.0001187% | 0.0001187% | 100% | 100%
|  | Z1-C-FIN-7490 | Fix Doors - Z1 - B1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-8720 | Fix Doors Garbage & Service Room - Z1 - GF | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-8730 | Fix Doors Fire Pump & Cmd Room - Z1 - GF | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-8740 | Fix Doors Lift Lobby - Z1 - GF | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-8820 | Fix Steel Louver Frames & Doors Generator Room - Z1 - GF | 343 | 343 | 292 | 100% | 0.0003954% | 0.0003366% | 85.13% | 85.13%
|  | Z1-C-FIN-8860 | Fix Doors LV & Trnsf. Room - Z1 - B1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-9560 | Fix Door Subframes Wet + Dry Area - Z1 - F1 | 70 | 70 | 59 | 100% | 8.07e-05% | 6.802e-05% | 84.29% | 84.29%
|  | Z1-C-FIN-9630 | Fix Doors Lift Lobby & Passage - Z1 - F1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z1-C-FIN-9790 | Fix Doors Serv. Area - Z1 - F1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
| Div 09 | A9740 | Traffic Deck Coating Drive Way - B2 | 631 | 630 | 536 | 99.84% | 0.0007263% | 0.0006179% | 84.94% | 85.08%
|  | A9790 | Traffic Marking Drive Way - B2 | 630 | 630 | 535 | 100% | 0.0007263% | 0.0006168% | 84.92% | 84.92%
|  | A9810 | Traffic Deck Coating Drive Way - B1 | 631 | 630 | 536 | 99.84% | 0.0007263% | 0.0006179% | 84.94% | 85.08%
|  | A9840 | Traffic Marking Drive Way - B1 | 630 | 630 | 536 | 100% | 0.0007263% | 0.0006179% | 85.08% | 85.08%
|  | C-FIN-ENVLP-9490 | Fix Brackets for Natural Stone - GF to SRVF (Elev. 1 & 4) | 286 | 288 | 243 | 100.7% | 0.000332% | 0.0002801% | 84.97% | 84.38%
|  | C-FIN-ENVLP-9510 | Fix Natural Stone All types- GF to SRVF (Elev. 1 & 4) | 6241 | 6240 | 5305 | 99.98% | 0.007194% | 0.006116% | 85% | 85.02%
|  | C-FIN-ENVLP-9610 | Fix Wooden Decorarive Features (Elev. 1 & 4) | 598 | 598 | 509 | 100% | 0.0006894% | 0.0005868% | 85.12% | 85.12%
|  | C-FIN-ENVLP-9730 | External Plaster - GF to SRVF (Elev. 1 & 4) | 165 | 164 | 140 | 99.39% | 0.0001891% | 0.0001614% | 84.85% | 85.37%
|  | Z1-C-FIN-10050 | Anti Fungal Paint - Z1 - F1 | 302 | 302 | 257 | 100% | 0.0003482% | 0.0002963% | 85.1% | 85.1%
|  | Z1-C-FIN-10130 | Plaster Works Wet Area - Z1 - F2 | 4823 | 4824 | 4100 | 100% | 0.005561% | 0.004727% | 85.01% | 84.99%
|  | Z1-C-FIN-10180 | Fix False Ceiling Suspension Lift Lobby - Z1 - F2 | 390 | 391 | 381 | 100.3% | 0.0004508% | 0.0004392% | 97.69% | 97.44%
|  | Z1-C-FIN-10190 | Wall Paint (Emulsion) Lobby Passage & Offices - Z1 - F2 | 648 | 648 | 424 | 100% | 0.000747% | 0.0004888% | 65.43% | 65.43%
|  | Z1-C-FIN-10200 | Porcelain Floor Tiles Passage & Offices - Z1 - F2 | 3842 | 3843 | 3266 | 100% | 0.00443% | 0.003765% | 85.01% | 84.99%
|  | Z1-C-FIN-10230 | Floor Paint (Antifungal) Lift Shaft - Z1 - F2 | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z1-C-FIN-10240 | Wall Paint (Antifungal) Lift Shaft - Z1 - F2 | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z1-C-FIN-10250 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - F2 | 59 | 59 | 14 | 100% | 6.802e-05% | 1.614e-05% | 23.73% | 23.73%
|  | Z1-C-FIN-10260 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z1-C-FIN-10280 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z1-C-FIN-10300 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - F2 | 651 | 651 | 553 | 100% | 0.0007505% | 0.0006375% | 84.95% | 84.95%
|  | Z1-C-FIN-10310 | Wall Paint (Acrylic) Serv. Rooms - Z1 - F2 | 94 | 94 | 62 | 100% | 0.0001084% | 7.147e-05% | 65.96% | 65.96%
|  | Z1-C-FIN-10480 | Plaster Works Dry Area - Z1 - F2 | 4823 | 4824 | 4100 | 100% | 0.005561% | 0.004727% | 85.01% | 84.99%
|  | Z1-C-FIN-10510 | Wall Ceramic Tiles Bath - Z1 - F2 | 1090 | 1090 | 926 | 100% | 0.001257% | 0.001068% | 84.95% | 84.95%
|  | Z1-C-FIN-10520 | Floor Ceramic Tiles Bath - Z1 - F2 | 153 | 153 | 130 | 100% | 0.0001764% | 0.0001499% | 84.97% | 84.97%
|  | Z1-C-FIN-10540 | Fix False Ceiling Suspension Bath - Z1 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z1-C-FIN-10560 | Fix False Ceiling Gypsum Board Bath - Z1 - F2 | 651 | 651 | 553 | 100% | 0.0007505% | 0.0006375% | 84.95% | 84.95%
|  | Z1-C-FIN-10570 | Fix False Ceiling Aluminum Tiles Bath - Z1 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z1-C-FIN-10610 | Wall Ceramic Tiles kitchen/Pantry - Z1 - F2 | 1091 | 1091 | 912 | 100% | 0.001258% | 0.001051% | 83.59% | 83.59%
|  | Z1-C-FIN-10620 | Fix False Ceiling Suspension kitchen/Pantry - Z1 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z1-C-FIN-10640 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - F2 | 651 | 651 | 553 | 100% | 0.0007505% | 0.0006375% | 84.95% | 84.95%
|  | Z1-C-FIN-10650 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z1 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z1-C-FIN-10660 | Floor Ceramic Tiles kitchen/Pantry - Z1 - F2 | 153 | 153 | 130 | 100% | 0.0001764% | 0.0001499% | 84.97% | 84.97%
|  | Z1-C-FIN-10690 | Ceiling Paint (Emulsion) Garbage Room - Z1 - F2 | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z1-C-FIN-10700 | Wall Paint (Emulsion) Garbage Room - Z1 - F2 | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z1-C-FIN-10750 | Floor Epoxy Paint Garbage Room - Z1 - F2 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z1-C-FIN-10770 | Plaster Works Wet Area - Z1 - RF | 4043 | 4042 | 3437 | 99.98% | 0.00466% | 0.003962% | 85.01% | 85.03%
|  | Z1-C-FIN-10790 | Fix False Ceiling Suspension Lift Lobby - Z1 - RF | 299 | 299 | 254 | 100% | 0.0003447% | 0.0002928% | 84.95% | 84.95%
|  | Z1-C-FIN-10800 | Wall Paint (Emulsion) Lobby Passage & Offices - Z1 - RF | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z1-C-FIN-10810 | Porcelain Floor Tiles Passage & Offices - Z1 - RF | 2930 | 2930 | 2490 | 100% | 0.003378% | 0.002871% | 84.98% | 84.98%
|  | Z1-C-FIN-10820 | Floor Paint (Antifungal) Lift Shaft - Z1 - RF | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z1-C-FIN-10830 | Wall Paint (Antifungal) Lift Shaft - Z1 - RF | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z1-C-FIN-10840 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - RF | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z1-C-FIN-10850 | Wall Paint (Acrylic) Serv. Rooms - Z1 - RF | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z1-C-FIN-10860 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - RF | 299 | 299 | 254 | 100% | 0.0003447% | 0.0002928% | 84.95% | 84.95%
|  | Z1-C-FIN-10870 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - RF | 498 | 498 | 423 | 100% | 0.0005741% | 0.0004876% | 84.94% | 84.94%
|  | Z1-C-FIN-10880 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z1-C-FIN-10950 | Plaster Works Dry Area - Z1 - RF | 4043 | 4042 | 3437 | 99.98% | 0.00466% | 0.003962% | 85.01% | 85.03%
|  | Z1-C-FIN-10970 | Fix False Ceiling Suspension Bath - Z1 - RF | 299 | 299 | 254 | 100% | 0.0003447% | 0.0002928% | 84.95% | 84.95%
|  | Z1-C-FIN-10980 | Wall Ceramic Tiles Bath - Z1 - RF | 1090 | 1090 | 926 | 100% | 0.001257% | 0.001068% | 84.95% | 84.95%
|  | Z1-C-FIN-10990 | Floor Ceramic Tiles Bath - Z1 - RF | 153 | 153 | 130 | 100% | 0.0001764% | 0.0001499% | 84.97% | 84.97%
|  | Z1-C-FIN-11020 | Fix False Ceiling Gypsum Board Bath - Z1 - RF | 500 | 498 | 425 | 99.6% | 0.0005741% | 0.0004899% | 85% | 85.34%
|  | Z1-C-FIN-11030 | Fix False Ceiling Aluminum Tiles Bath - Z1 - RF | 300 | 299 | 255 | 99.67% | 0.0003447% | 0.000294% | 85% | 85.28%
|  | Z1-C-FIN-11050 | Fix False Ceiling Suspension kitchen/Pantry - Z1 - RF | 299 | 299 | 254 | 100% | 0.0003447% | 0.0002928% | 84.95% | 84.95%
|  | Z1-C-FIN-11060 | Wall Ceramic Tiles kitchen/Pantry - Z1 - RF | 1091 | 1090 | 927 | 99.91% | 0.001257% | 0.001069% | 84.97% | 85.05%
|  | Z1-C-FIN-11070 | Floor Ceramic Tiles kitchen/Pantry - Z1 - RF | 153 | 153 | 130 | 100% | 0.0001764% | 0.0001499% | 84.97% | 84.97%
|  | Z1-C-FIN-11100 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - RF | 498 | 498 | 423 | 100% | 0.0005741% | 0.0004876% | 84.94% | 84.94%
|  | Z1-C-FIN-11110 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z1 - RF | 299 | 299 | 254 | 100% | 0.0003447% | 0.0002928% | 84.95% | 84.95%
|  | Z1-C-FIN-11130 | Wall Paint (Emulsion) Garbage Room - Z1 - RF | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z1-C-FIN-11140 | Floor Epoxy Paint Garbage Room - Z1 - RF | 16 | 17 | 14 | 106.2% | 1.96e-05% | 1.614e-05% | 87.5% | 82.35%
|  | Z1-C-FIN-11170 | Ceiling Paint (Emulsion) Garbage Room - Z1 - RF | 25 | 26 | 21 | 104% | 2.997e-05% | 2.421e-05% | 84% | 80.77%
|  | Z1-C-FIN-18570 | Ceiling Paint (Emulsion/Acrylic) Secur. Ctrl & Eqpmt Room - Z1 - B1 | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z1-C-FIN-18580 | Wall Paint (Emulsion/Acrylic) Secur. Ctrl & Eqpmt Room - Z1 - B1 | 647 | 647 | 421 | 100% | 0.0007459% | 0.0004853% | 65.07% | 65.07%
|  | Z1-C-FIN-18590 | Floor Epoxy Paint (Secur. Ctrl & Eqpmt Room) - Z1 - B1 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z1-C-FIN-18610 | Ceiling Paint (Acrylic) Maint. & Serv. Provider Room) - Z1 - B1 | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z1-C-FIN-18620 | Wall Paint (Acrylic) Maint. & Serv. Provider Room) - Z1 - B1 | 94 | 94 | 61 | 100% | 0.0001084% | 7.032e-05% | 64.89% | 64.89%
|  | Z1-C-FIN-18630 | Floor Epoxy Paint (Maint. & Serv. Provider Room) - Z1 - B1 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z1-C-FIN-18650 | Ceiling Paint (Acrylic) Loading Room - Z1 - GF | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z1-C-FIN-18670 | Wall Paint (Acrylic) Loading Room - Z1 - GF | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z1-C-FIN-18680 | Floor Stamp Concrete Loading Room - Z1 - GF | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z1-C-FIN-18700 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - F1 | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z1-C-FIN-18710 | Floor Epoxy Paint Serv. Rooms - Z1 - F1 | 17 | 16 | 14 | 94.12% | 1.845e-05% | 1.614e-05% | 82.35% | 87.5%
|  | Z1-C-FIN-21360 | Wall Paint Outside Area (Acrylic) - Z1 - RF | 95 | 94 | 81 | 98.95% | 0.0001084% | 9.338e-05% | 85.26% | 86.17%
|  | Z1-C-FIN-21370 | Roof Floor Terrazo Tiles Outside Area - Z1 - RF | 720 | 720 | 612 | 100% | 0.00083% | 0.0007055% | 85% | 85%
|  | Z1-C-FIN-5800 | Plaster Works - Z1 - B2 | 8050 | 8050 | 805 | 100% | 0.00928% | 0.000928% | 10% | 10%
|  | Z1-C-FIN-6050 | Ceiling Paint (Acrylic) - Z1 - B2 | 58 | 59 | 21 | 101.7% | 6.802e-05% | 2.421e-05% | 36.21% | 35.59%
|  | Z1-C-FIN-6060 | Wall Paint (Acrylic) - Z1 - B2 | 94 | 94 | 34 | 100% | 0.0001084% | 3.92e-05% | 36.17% | 36.17%
|  | Z1-C-FIN-6070 | Floor Epoxy Paint Serv. Rooms - Z1 - B2 | 17 | 17 | 3 | 100% | 1.96e-05% | 3.458e-06% | 17.65% | 17.65%
|  | Z1-C-FIN-6080 | Ceiling Paint (Acrylic) - Z1 - B2 | 58 | 59 | 21 | 101.7% | 6.802e-05% | 2.421e-05% | 36.21% | 35.59%
|  | Z1-C-FIN-6090 | Wall Paint (Acrylic) - Z1 - B2 | 94 | 94 | 34 | 100% | 0.0001084% | 3.92e-05% | 36.17% | 36.17%
|  | Z1-C-FIN-6100 | Floor Epoxy Paint - Z1 - B2 | 17 | 17 | 3 | 100% | 1.96e-05% | 3.458e-06% | 17.65% | 17.65%
|  | Z1-C-FIN-6160 | Fix False Ceiling Suspension - Z1 - B2 | 28 | 29 | 7 | 103.6% | 3.343e-05% | 8.07e-06% | 25% | 24.14%
|  | Z1-C-FIN-6170 | Wall Paint (Emulsion) - Z1 - B2 | 647 | 647 | 32 | 100% | 0.0007459% | 3.689e-05% | 4.946% | 4.946%
|  | Z1-C-FIN-6180 | Porcelain Floor Tiles - Z1 - B2 | 119 | 119 | 18 | 100% | 0.0001372% | 2.075e-05% | 15.13% | 15.13%
|  | Z1-C-FIN-6270 | Wall Paint (Antifungal) Lift Shaft - Z1 - B2 | 272 | 271 | 177 | 99.63% | 0.0003124% | 0.000204% | 65.07% | 65.31%
|  | Z1-C-FIN-6280 | Floor Paint (Antifungal) Lift Shaft - Z1 - B2 | 271 | 271 | 176 | 100% | 0.0003124% | 0.0002029% | 64.94% | 64.94%
|  | Z1-C-FIN-6290 | Ceiling Paint (Anti-Carbonation) - Z1 - B2 | 770 | 770 | 116 | 100% | 0.0008877% | 0.0001337% | 15.06% | 15.06%
|  | Z1-C-FIN-6310 | Wall Paint (Anti-Carbonation) - Z1 - B2 | 771 | 770 | 444 | 99.87% | 0.0008877% | 0.0005119% | 57.59% | 57.66%
|  | Z1-C-FIN-6330 | Fix False Ceiling Gypsum Board & Tiles - Z1 - B2 | 48 | 48 | 41 | 100% | 5.534e-05% | 4.727e-05% | 85.42% | 85.42%
|  | Z1-C-FIN-7050 | Plaster Works - Z1 - B1 | 8522 | 8522 | 4260 | 100% | 0.009824% | 0.004911% | 49.99% | 49.99%
|  | Z1-C-FIN-7300 | Ceiling Paint (Emulsion/Acrylic) Store & Serv. Rooms - Z1 - B1 | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z1-C-FIN-7310 | Wall Paint (Emulsion/Acrylic) Store & Serv. Rooms - Z1 - B1 | 647 | 647 | 421 | 100% | 0.0007459% | 0.0004853% | 65.07% | 65.07%
|  | Z1-C-FIN-7320 | Raise Floor & Epoxy Paint Store & Serv. Rooms - Z1 - B1 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z1-C-FIN-7410 | Fix False Ceiling Gypsum Board & Tiles Lift Lobby - Z1 - B1 | 71 | 70 | 60 | 98.59% | 8.07e-05% | 6.917e-05% | 84.51% | 85.71%
|  | Z1-C-FIN-7420 | Wall Paint (Emulsion) Lift Lobby - Z1 - B1 | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z1-C-FIN-7430 | Porcelain Floor Tiles Lift Lobby - Z1 - B1 | 88 | 87 | 57 | 98.86% | 0.0001003% | 6.571e-05% | 64.77% | 65.52%
|  | Z1-C-FIN-7480 | Fix False Ceiling Suspension Lift Lobby - Z1 - B1 | 42 | 43 | 36 | 102.4% | 4.957e-05% | 4.15e-05% | 85.71% | 83.72%
|  | Z1-C-FIN-7540 | Ceiling Paint (Anti-Carbonation) - Z1 - B1 | 770 | 770 | 654 | 100% | 0.0008877% | 0.0007539% | 84.94% | 84.94%
|  | Z1-C-FIN-7560 | Wall Paint (Anti-Carbonation) - Z1 - B1 | 771 | 770 | 501 | 99.87% | 0.0008877% | 0.0005776% | 64.98% | 65.06%
|  | Z1-C-FIN-8340 | Plaster Works - Z1 - GF | 5838 | 5838 | 9633 | 100% | 0.00673% | 0.01111% | 165% | 165%
|  | Z1-C-FIN-8630 | Ceiling Paint Garbage & Service Room (Acrylic/Emulsion) - Z1 - GF | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z1-C-FIN-8640 | Wall Paint Garbage & Service Room (Acrylic/Emulsion) - Z1 - GF | 648 | 647 | 551 | 99.85% | 0.0007459% | 0.0006352% | 85.03% | 85.16%
|  | Z1-C-FIN-8650 | Floor Epoxy Paint Garbage & Service Room - Z1 - GF | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z1-C-FIN-8660 | Ceiling Paint (Acrylic/Emulsion) Fire Pump & Cmd Room - Z1 - GF | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z1-C-FIN-8670 | Wall Paint (Acrylic/Emulsion) Fire Pump & Cmd Room - Z1 - GF | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z1-C-FIN-8680 | Floor Epoxy Paint Fire Pump & Cmd Room - Z1 - GF | 16 | 17 | 14 | 106.2% | 1.96e-05% | 1.614e-05% | 87.5% | 82.35%
|  | Z1-C-FIN-8690 | Fix False Ceiling Suspension Lift Lobby - Z1 - GF | 111 | 110 | 94 | 99.1% | 0.0001268% | 0.0001084% | 84.68% | 85.45%
|  | Z1-C-FIN-8700 | Wall Paint (Emulsion) Lift Lobby - Z1 - GF | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z1-C-FIN-8710 | Porcelain Floor Tiles Lift Lobby - Z1 - GF | 510 | 511 | 433 | 100.2% | 0.0005891% | 0.0004992% | 84.9% | 84.74%
|  | Z1-C-FIN-8770 | Floor Paint (Antifungal) Lift Shaft - Z1 - GF | 272 | 271 | 231 | 99.63% | 0.0003124% | 0.0002663% | 84.93% | 85.24%
|  | Z1-C-FIN-8780 | Wall Paint (Antifungal) Lift Shaft - Z1 - GF | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z1-C-FIN-8790 | Ceiling Paint Generator Room (Acrylic) - Z1 - GF | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z1-C-FIN-8800 | Wall Paint Generator Room (Acrylic) - Z1 - GF | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z1-C-FIN-8810 | Floor Epoxy Paint Generator Room - Z1 - GF | 16 | 17 | 14 | 106.2% | 1.96e-05% | 1.614e-05% | 87.5% | 82.35%
|  | Z1-C-FIN-8830 | Ceiling Paint LV & Trnsf. Room (Acrylic) - Z1 - B1 | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z1-C-FIN-8840 | Wall Paint LV & Trnsf. Room (Acrylic) - Z1 - B1 | 94 | 94 | 61 | 100% | 0.0001084% | 7.032e-05% | 64.89% | 64.89%
|  | Z1-C-FIN-8850 | Floor Epoxy Paint LV & Trnsf. Room- Z1 - B1 | 16 | 17 | 14 | 106.2% | 1.96e-05% | 1.614e-05% | 87.5% | 82.35%
|  | Z1-C-FIN-8890 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - GF | 183 | 183 | 156 | 100% | 0.000211% | 0.0001798% | 85.25% | 85.25%
|  | Z1-C-FIN-8920 | Anti Fungal Paint all Shops - Z1 - GF | 301 | 302 | 256 | 100.3% | 0.0003482% | 0.0002951% | 85.05% | 84.77%
|  | Z1-C-FIN-9380 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z1-C-FIN-9500 | Plaster Works Wet + Dry Area - Z1 - F1 | 3910 | 3910 | 3324 | 100% | 0.004508% | 0.003832% | 85.01% | 85.01%
|  | Z1-C-FIN-9580 | Fix False Ceiling Suspension Lift Lobby & Passage - Z1 - F1 | 277 | 277 | 235 | 100% | 0.0003193% | 0.0002709% | 84.84% | 84.84%
|  | Z1-C-FIN-9590 | Wall Paint (Emulsion) Lift Lobby & Passage - Z1 - F1 | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z1-C-FIN-9600 | Porcelain Floor Tiles Lift Lobby & Passage- Z1 - F1 | 1482 | 1484 | 1260 | 100.1% | 0.001711% | 0.001453% | 85.02% | 84.91%
|  | Z1-C-FIN-9660 | Floor Paint (Antifungal) Lift Shaft - Z1 - F1 | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z1-C-FIN-9670 | Wall Paint (Antifungal) Lift Shaft - Z1 - F1 | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z1-C-FIN-9770 | Ceiling Paint (Acrylic) Serv. Area - Z1 - F1 | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z1-C-FIN-9780 | Epoxy Paint Serv. Area - Z1 - F1 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z1-C-FIN-9880 | Fix False Ceiling Aluminum Tiles Lift Lobby & Passage - Z1 - F1 | 277 | 277 | 235 | 100% | 0.0003193% | 0.0002709% | 84.84% | 84.84%
|  | Z1-C-FIN-9960 | Fix False Ceiling Gypsum Board Lift Lobby & Passage - Z1 - F1 | 461 | 461 | 392 | 100% | 0.0005315% | 0.0004519% | 85.03% | 85.03%
|  | Z1-C-FIN-SCASE-8790 | Staircase Acrylic Paint - Z1 - B2 - SRVF |  | 1 |  |  | 1.153e-06% |  |  | 0%
|  | Z1-C-FIN-SCASE-8800 | Staircase Floor Epoxy Paint - Z1 - B2 - SRVF | 16 | 17 | 14 | 106.2% | 1.96e-05% | 1.614e-05% | 87.5% | 82.35%
|  | Z1-C-GRBCH-9380 | Install Garbage Chute Cylinder - Z1 - GF to SRVF | 268 | 266 | 228 | 99.25% | 0.0003067% | 0.0002628% | 85.07% | 85.71%
|  | Z1-C-GRBCH-9390 | Install Garbage Chute Supporting Frame - Z1 - GF to SRVF | 268 | 266 | 228 | 99.25% | 0.0003067% | 0.0002628% | 85.07% | 85.71%
|  | Z1-C-GRBCH-9400 | Block & Plaster Garbage Room - Z1 - GF to SRVF | 172 | 172 | 146 | 100% | 0.0001983% | 0.0001683% | 84.88% | 84.88%
|  | Z1-C-GRBCH-9410 | Install Garbage Chute Openings & Doors - Z1 - GF to SRVF | 268 | 266 | 155 | 99.25% | 0.0003067% | 0.0001787% | 57.84% | 58.27%
|  | Z1-C-GRBCH-9460 | Install Garbage Chute Roof Top Unit with All Provisions | 266 | 266 | 226 | 100% | 0.0003067% | 0.0002605% | 84.96% | 84.96%
|  | Z1-C-GRBCH-9470 | Install Garbage Chute Bottom Unit with All Provisions | 266 | 266 | 226 | 100% | 0.0003067% | 0.0002605% | 84.96% | 84.96%
| Div 10 | A9670 | Casting Service Manholes | 166 | 166 | 141 | 100% | 0.0001914% | 0.0001625% | 84.94% | 84.94%
|  | Z123-C-FIN-18500 | Fix Rain Water Outlets - Z123 - TRF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-CON-2540 | Fix MEP Provisions - Z1 - Raft | 100 | 100 | 21 | 100% | 0.0001153% | 2.421e-05% | 21% | 21%
|  | Z1-C-FIN-6250 | Fix Pump - Z1 - B2 | 126 | 125 | 19 | 99.21% | 0.0001441% | 2.19e-05% | 15.08% | 15.2%
|  | Z1-C-FIN-6260 | Fix Final Connections of Pumps with Risers - Z1 - B2 | 125 | 125 | 70 | 100% | 0.0001441% | 8.07e-05% | 56% | 56%
|  | Z1-C-FIN-8750 | Fix Electric Pump Fire Pump Room - Z1 - GF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-FIN-8760 | Fix Final Connections with Risers Fire Pump Room - Z1 - GF | 125 | 125 | 106 | 100% | 0.0001441% | 0.0001222% | 84.8% | 84.8%
|  | Z1-C-FIN-9310 | Fix Diesel Pump Fire Pump Room- Z1 - GF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-FIN-9320 | Fix Jockey Pump Fire Pump Room- Z1 - GF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-FIN-9340 | Final Connections & Termination Fire Pump Room - Z1 - GF | 125 | 125 | 106 | 100% | 0.0001441% | 0.0001222% | 84.8% | 84.8%
|  | Z1-C-MEP-5820 | Fix Drainage Pipes - Z1 - B2 | 249 | 250 | 228 | 100.4% | 0.0002882% | 0.0002628% | 91.57% | 91.2%
|  | Z1-C-MEP-7070 | Fix Drainage Pipes - Z1 - B1 | 249 | 250 | 411 | 100.4% | 0.0002882% | 0.0004738% | 165.1% | 164.4%
|  | Z1-C-MEP-8360 | Fix Drainage Pipes - Z1 - GF | 250 | 250 | 213 | 100% | 0.0002882% | 0.0002456% | 85.2% | 85.2%
|  | Z1-C-MEP-8590 | Fix Water Supply Pipes - Z1 - GF | 250 | 250 | 213 | 100% | 0.0002882% | 0.0002456% | 85.2% | 85.2%
|  | Z1-C-MEP-8630 | Fix Water Heater & Sanitary Accessories - Z1 - GF | 333 | 334 | 283 | 100.3% | 0.000385% | 0.0003262% | 84.98% | 84.73%
|  | Z1-C-MEP-8640 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - GF | 50 | 50 | 12 | 100% | 5.764e-05% | 1.383e-05% | 24% | 24%
|  | Z1-C-MEP-8660 | Fix Drainage Pipes - Z1 - F1 | 249 | 250 | 212 | 100.4% | 0.0002882% | 0.0002444% | 85.14% | 84.8%
|  | Z1-C-MEP-8920 | Fix Water Supply Pipes - Z1 - F1 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-8930 | Fix Water Heater & Sanitary Accessories - Z1 - F1 | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z1-C-MEP-8940 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8960 | Fix Drainage Pipes - Z1 - F2 | 250 | 250 | 178 | 100% | 0.0002882% | 0.0002052% | 71.2% | 71.2%
|  | Z1-C-MEP-9220 | Fix Water Supply Pipes - Z1 - F2 | 250 | 250 | 209 | 100% | 0.0002882% | 0.0002409% | 83.6% | 83.6%
|  | Z1-C-MEP-9230 | Fix Water Heater & Sanitary Accessories - Z1 - F2 | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z1-C-MEP-9240 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9280 | Fix Drainage Pipes - Z1 - RF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-9540 | Fix Water Supply Pipes - Z1 - RF | 249 | 250 | 255 | 100.4% | 0.0002882% | 0.000294% | 102.4% | 102%
|  | Z1-C-MEP-9550 | Fix Water Heater & Sanitary Accessories - Z1 - RF | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z1-C-MEP-9560 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-RSRS-11020 | Install Drainage Pipe Risers | 999 | 1000 | 710 | 100.1% | 0.001153% | 0.0008185% | 71.07% | 71%
|  | Z1-C-RSRS-11030 | Install Water Supply Pipe Risers | 999 | 1000 | 710 | 100.1% | 0.001153% | 0.0008185% | 71.07% | 71%
| Div 11 | Z1-C-MEP-5830 | Fix Fire Fighting Pipes - Z1 - B2 | 501 | 500 | 460 | 99.8% | 0.0005764% | 0.0005303% | 91.82% | 92%
|  | Z1-C-MEP-5860 | Fix Fire Fighting Dropers - Z1 - B2 | 50 | 50 | 12 | 100% | 5.764e-05% | 1.383e-05% | 24% | 24%
|  | Z1-C-MEP-6020 | Fix Fire Hose Cabinets & Hose Reels - Z1 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-6030 | Fix Sprinklers - Z1 - B2 | 500 | 500 | 854 | 100% | 0.0005764% | 0.0009845% | 170.8% | 170.8%
|  | Z1-C-MEP-7080 | Fix Fire Fighting Pipes - Z1 - B1 | 500 | 500 | 825 | 100% | 0.0005764% | 0.0009511% | 165% | 165%
|  | Z1-C-MEP-7110 | Fix Fire Fighting Dropers - Z1 - B1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-7270 | Fix Fire Hose Cabinets & Hose Reels - Z1 - B1 | 51 | 50 | 43 | 98.04% | 5.764e-05% | 4.957e-05% | 84.31% | 86%
|  | Z1-C-MEP-7280 | Fix Sprinklers - Z1 - B1 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-8370 | Fix Fire Fighting Pipes - Z1 - GF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-8400 | Fix Fire Fighting Dropers - Z1 - GF | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z1-C-MEP-8560 | Fix Fire Hose Cabinets & Hose Reels - Z1 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8570 | Fix Sprinklers - Z1 - GF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-8670 | Fix Fire Fighting Pipes - Z1 - F1 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-8700 | Fix Fire Fighting Dropers - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8860 | Fix Fire Hose Cabinets & Hose Reels - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8870 | Fix Sprinklers - Z1 - F1 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-8970 | Fix Fire Fighting Pipes - Z1 - F2 | 499 | 500 | 357 | 100.2% | 0.0005764% | 0.0004116% | 71.54% | 71.4%
|  | Z1-C-MEP-9000 | Fix Fire Fighting Dropers - Z1 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9160 | Fix Fire Hose Cabinets & Hose Reels - Z1 - F2 | 51 | 50 | 43 | 98.04% | 5.764e-05% | 4.957e-05% | 84.31% | 86%
|  | Z1-C-MEP-9170 | Fix Sprinklers - Z1 - F2 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-9290 | Fix Fire Fighting Pipes - Z1 - RF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-9320 | Fix Fire Fighting Dropers - Z1 - RF | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z1-C-MEP-9480 | Fix Fire Hose Cabinets & Hose Reels - Z1 - RF | 51 | 51 | 44 | 100% | 5.879e-05% | 5.072e-05% | 86.27% | 86.27%
|  | Z1-C-MEP-9490 | Fix Sprinklers - Z1 - RF | 501 | 500 | 425 | 99.8% | 0.0005764% | 0.0004899% | 84.83% | 85%
| Div 12 | Z1-C-FIN-10000 | Fix MEP Droppers Lift Lobby & Passage - Z1 - F1 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z1-C-FIN-10320 | Fix MEP Droppers Lift Lobby - Z1 - F2 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z1-C-FIN-10550 | Fix MEP Droppers Bath - Z1 - F2 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z1-C-FIN-10630 | Fix MEP Droppers kitchen/Pantry - Z1 - F2 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z1-C-FIN-10890 | Fix MEP Droppers Lift Lobby - Z1 - RF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z1-C-FIN-11040 | Fix MEP Droppers Bath - Z1 - RF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z1-C-FIN-11120 | Fix MEP Droppers kitchen/Pantry - Z1 - RF | 200 | 200 | 127 | 100% | 0.0002306% | 0.0001464% | 63.5% | 63.5%
|  | Z1-C-FIN-8900 | Fix MEP Droppers Lift Lobby - Z1 - GF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z1-C-MEP-5840 | Fix Chill Water Pipes - Z1 - B2 | 333 | 334 | 306 | 100.3% | 0.000385% | 0.0003528% | 91.89% | 91.62%
|  | Z1-C-MEP-5850 | Fix HVAC Ducts & Insulation - Z1 - B2 | 665 | 666 | 611 | 100.2% | 0.0007678% | 0.0007044% | 91.88% | 91.74%
|  | Z1-C-MEP-5870 | Fix FCU - Z1 - B2 | 100 | 100 | 56 | 100% | 0.0001153% | 6.456e-05% | 56% | 56%
|  | Z1-C-MEP-6040 | Fix Grills & Diffusers - Z1 - B2 | 286 | 286 | 243 | 100% | 0.0003297% | 0.0002801% | 84.97% | 84.97%
|  | Z1-C-MEP-7090 | Fix Chill Water Pipes - Z1 - B1 | 333 | 333 | 549 | 100% | 0.0003839% | 0.0006329% | 164.9% | 164.9%
|  | Z1-C-MEP-7100 | Fix HVAC Ducts & Insulation - Z1 - B1 | 665 | 667 | 1097 | 100.3% | 0.0007689% | 0.001265% | 165% | 164.5%
|  | Z1-C-MEP-7120 | Fix FCU - Z1 - B1 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-7290 | Fix Grills & Diffusers - Z1 - B1 | 285 | 286 | 242 | 100.4% | 0.0003297% | 0.000279% | 84.91% | 84.62%
|  | Z1-C-MEP-8380 | Fix Chill Water Pipes - Z1 - GF | 332 | 333 | 282 | 100.3% | 0.0003839% | 0.0003251% | 84.94% | 84.68%
|  | Z1-C-MEP-8390 | Fix HVAC Ducts & Insulation - Z1 - GF | 666 | 667 | 566 | 100.2% | 0.0007689% | 0.0006525% | 84.98% | 84.86%
|  | Z1-C-MEP-8410 | Fix FCU - Z1 - GF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-8580 | Fix Grills & Diffusers - Z1 - GF | 286 | 286 | 243 | 100% | 0.0003297% | 0.0002801% | 84.97% | 84.97%
|  | Z1-C-MEP-8680 | Fix Chill Water Pipes - Z1 - F1 | 332 | 333 | 282 | 100.3% | 0.0003839% | 0.0003251% | 84.94% | 84.68%
|  | Z1-C-MEP-8690 | Fix HVAC Ducts & Insulation - Z1 - F1 | 666 | 667 | 566 | 100.2% | 0.0007689% | 0.0006525% | 84.98% | 84.86%
|  | Z1-C-MEP-8710 | Fix FCU - Z1 - F1 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-8880 | Fix Grills & Diffusers - Z1 - F1 | 285 | 286 | 242 | 100.4% | 0.0003297% | 0.000279% | 84.91% | 84.62%
|  | Z1-C-MEP-8980 | Fix Chill Water Pipes - Z1 - F2 | 332 | 333 | 278 | 100.3% | 0.0003839% | 0.0003205% | 83.73% | 83.48%
|  | Z1-C-MEP-8990 | Fix HVAC Ducts & Insulation - Z1 - F2 | 667 | 667 | 477 | 100% | 0.0007689% | 0.0005499% | 71.51% | 71.51%
|  | Z1-C-MEP-9010 | Fix FCU - Z1 - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-9180 | Fix Grills & Diffusers - Z1 - F2 | 285 | 286 | 242 | 100.4% | 0.0003297% | 0.000279% | 84.91% | 84.62%
|  | Z1-C-MEP-9300 | Fix Chill Water Pipes - Z1 - RF | 333 | 333 | 341 | 100% | 0.0003839% | 0.0003931% | 102.4% | 102.4%
|  | Z1-C-MEP-9310 | Fix HVAC Ducts & Insulation - Z1 - RF | 667 | 667 | 567 | 100% | 0.0007689% | 0.0006536% | 85.01% | 85.01%
|  | Z1-C-MEP-9330 | Fix FCU - Z1 - RF | 100 | 100 | 49 | 100% | 0.0001153% | 5.649e-05% | 49% | 49%
|  | Z1-C-MEP-9500 | Fix Grills & Diffusers - Z1 - RF | 286 | 285 | 243 | 99.65% | 0.0003286% | 0.0002801% | 84.97% | 85.26%
|  | Z1-C-RSRS-11050 | Install Fire Fighting Pipe Risers | 997 | 1000 | 606 | 100.3% | 0.001153% | 0.0006986% | 60.78% | 60.6%
| Div 13 | Z1-C-LIFT-9110 | Install Working Platm for PL-1 & 2 (B2 to SRVF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-LIFT-9120 | Install Steel Support Beams & Tracks PL-1 & 2 (B2 to SRVF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-LIFT-9190 | Repair Lift Shaft PL-1 & 2 (B2 to SRVF) | 100 | 100 | 84 | 100% | 0.0001153% | 9.684e-05% | 84% | 84%
|  | Z1-C-LIFT-9230 | Terminate Tracks & Cross Beams (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-LIFT-9240 | Install Lift Access Doors (B2 to GF) | 100 | 100 | 99 | 100% | 0.0001153% | 0.0001141% | 99% | 99%
|  | Z1-C-LIFT-9250 | Install Lift Cabin (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-LIFT-9260 | Install Lift Motors Cables, Counter Weight & Brakes (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-LIFT-9270 | Install Lift Control Unit (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-LIFT-9280 | Power Connection & Test Runs (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
| Div 14 | Z1-C-MEP-9250 | Fix LPG Pipes - Z1 - F2 | 167 | 167 | 38 | 100% | 0.0001925% | 4.381e-05% | 22.75% | 22.75%
|  | Z1-C-MEP-9260 | Fix Gas Detectors - Z1 - F2 | 167 | 167 | 142 | 100% | 0.0001925% | 0.0001637% | 85.03% | 85.03%
|  | Z1-C-MEP-9570 | Fix LPG Pipes - Z1 - RF | 167 | 167 | 142 | 100% | 0.0001925% | 0.0001637% | 85.03% | 85.03%
|  | Z1-C-MEP-9580 | Fix Gas Detectors - Z1 - RF | 167 | 167 | 141 | 100% | 0.0001925% | 0.0001625% | 84.43% | 84.43%
|  | Z1-C-RSRS-11070 | Install LPG Pipe Risers | 166 | 167 | 167 | 100.6% | 0.0001925% | 0.0001925% | 100.6% | 100%
| Div 15 | Z1-C-FIN-8880 | Final Connections & Termination Generator Room - Z1 - GF | 251 | 251 | 213 | 100% | 0.0002894% | 0.0002456% | 84.86% | 84.86%
|  | Z1-C-FIN-9300 | Fix Generator Generator Room - Z1 - GF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-FIN-9330 | Fix MCC Pannels LV & Trnsf. Room- Z1 - B1 | 270 | 271 | 540 | 100.4% | 0.0003124% | 0.0006225% | 200% | 199.3%
|  | Z1-C-FIN-9350 | Connections & Termonation LV & Trnsf. Room - Z1 - B1 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-FIN-SCASE-8910 | Install MEP Final Fixes Staircase - Z1 - B2 - SRVF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-5810 | Fix G.I Box and conduits - Z1 - B2 | 50 | 50 | 26 | 100% | 5.764e-05% | 2.997e-05% | 52% | 52%
|  | Z1-C-MEP-5880 | Fix ELV Trunkings - Z1 - B2 | 250 | 250 | 220 | 100% | 0.0002882% | 0.0002536% | 88% | 88%
|  | Z1-C-MEP-5890 | Pull ELV Cables - Z1 - B2 | 101 | 101 | 82 | 100% | 0.0001164% | 9.453e-05% | 81.19% | 81.19%
|  | Z1-C-MEP-5900 | Fix Power Cable Trays - Z1 - B2 | 500 | 500 | 439 | 100% | 0.0005764% | 0.0005061% | 87.8% | 87.8%
|  | Z1-C-MEP-5910 | Pull Electricl Wires (Ceiling & Walls) - Z1 - B2 | 101 | 101 | 82 | 100% | 0.0001164% | 9.453e-05% | 81.19% | 81.19%
|  | Z1-C-MEP-5920 | Pull Earthing & Power Cables - Z1 - B2 | 250 | 250 | 202 | 100% | 0.0002882% | 0.0002329% | 80.8% | 80.8%
|  | Z1-C-MEP-5930 | Fix DBs - Z1 - B2 | 50 | 50 | 38 | 100% | 5.764e-05% | 4.381e-05% | 76% | 76%
|  | Z1-C-MEP-5940 | Cable Terminations - Z1 - B2 | 33 | 33 | 19 | 100% | 3.804e-05% | 2.19e-05% | 57.58% | 57.58%
|  | Z1-C-MEP-5950 | Fix CCTV Devices - Z1 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-5960 | Fix Light Fixtures - Z1 - B2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-5970 | Fix Switches, Sockets & Isolators - Z1 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-5980 | Fix Fire Alarm Devices - Z1 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-5990 | Fix Telephone & Voice Evac. Devices - Z1 - B2 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-6000 | Fix LCS & ACS Devices - Z1 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-6010 | Fix Emergency & Exit Lights - Z1 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-7060 | Fix G.I Box and conduits - Z1 - B1 | 50 | 50 | 28 | 100% | 5.764e-05% | 3.228e-05% | 56% | 56%
|  | Z1-C-MEP-7130 | Fix ELV Trunkings - Z1 - B1 | 250 | 250 | 412 | 100% | 0.0002882% | 0.000475% | 164.8% | 164.8%
|  | Z1-C-MEP-7140 | Pull ELV Cables - Z1 - B1 | 100 | 101 | 85 | 101% | 0.0001164% | 9.799e-05% | 85% | 84.16%
|  | Z1-C-MEP-7150 | Fix Power Cable Trays - Z1 - B1 | 500 | 500 | 825 | 100% | 0.0005764% | 0.0009511% | 165% | 165%
|  | Z1-C-MEP-7160 | Pull Electricl Wires (Ceiling & Walls) - Z1 - B1 | 102 | 101 | 87 | 99.02% | 0.0001164% | 0.0001003% | 85.29% | 86.14%
|  | Z1-C-MEP-7170 | Pull Earthing & Power Cables - Z1 - B1 | 250 | 250 | 213 | 100% | 0.0002882% | 0.0002456% | 85.2% | 85.2%
|  | Z1-C-MEP-7180 | Fix DBs - Z1 - B1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-7190 | Cable Terminations - Z1 - B1 | 34 | 33 | 29 | 97.06% | 3.804e-05% | 3.343e-05% | 85.29% | 87.88%
|  | Z1-C-MEP-7200 | Fix CCTV Devices - Z1 - B1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-7210 | Fix Light Fixtures - Z1 - B1 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-7220 | Fix Switches, Sockets & Isolators - Z1 - B1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-7230 | Fix Fire Alarm Devices - Z1 - B1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-7240 | Fix Telephone & Voice Evac. Devices - Z1 - B1 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-7250 | Fix LCS & ACS Devices - Z1 - B1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-7260 | Fix Emergency & Exit Lights - Z1 - B1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8350 | Fix G.I Box and conduits - Z1 - GF | 50 | 50 | 12 | 100% | 5.764e-05% | 1.383e-05% | 24% | 24%
|  | Z1-C-MEP-8420 | Fix ELV Trunkings - Z1 - GF | 250 | 250 | 213 | 100% | 0.0002882% | 0.0002456% | 85.2% | 85.2%
|  | Z1-C-MEP-8430 | Pull ELV Cables - Z1 - GF | 101 | 101 | 86 | 100% | 0.0001164% | 9.914e-05% | 85.15% | 85.15%
|  | Z1-C-MEP-8440 | Fix Power Cable Trays - Z1 - GF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-8450 | Pull Electricl Wires (Ceiling & Walls) - Z1 - GF | 102 | 101 | 87 | 99.02% | 0.0001164% | 0.0001003% | 85.29% | 86.14%
|  | Z1-C-MEP-8460 | Pull Earthing & Power Cables - Z1 - GF | 252 | 250 | 214 | 99.21% | 0.0002882% | 0.0002467% | 84.92% | 85.6%
|  | Z1-C-MEP-8470 | Fix DBs - Z1 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8480 | Cable Terminations - Z1 - GF | 34 | 33 | 29 | 97.06% | 3.804e-05% | 3.343e-05% | 85.29% | 87.88%
|  | Z1-C-MEP-8490 | Fix CCTV Devices - Z1 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8500 | Fix Light Fixtures - Z1 - GF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-8510 | Fix Switches, Sockets & Isolators - Z1 - GF | 49 | 50 | 42 | 102% | 5.764e-05% | 4.842e-05% | 85.71% | 84%
|  | Z1-C-MEP-8520 | Fix Fire Alarm Devices - Z1 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8530 | Fix Telephone & Voice Evac. Devices - Z1 - GF | 250 | 250 | 213 | 100% | 0.0002882% | 0.0002456% | 85.2% | 85.2%
|  | Z1-C-MEP-8540 | Fix LCS & ACS Devices - Z1 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8550 | Fix Emergency & Exit Lights - Z1 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8650 | Fix G.I Box and conduits - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8720 | Fix ELV Trunkings - Z1 - F1 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-8730 | Pull ELV Cables - Z1 - F1 | 102 | 101 | 87 | 99.02% | 0.0001164% | 0.0001003% | 85.29% | 86.14%
|  | Z1-C-MEP-8740 | Fix Power Cable Trays - Z1 - F1 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z1-C-MEP-8750 | Pull Electricl Wires (Ceiling & Walls) - Z1 - F1 | 103 | 101 | 90 | 98.06% | 0.0001164% | 0.0001038% | 87.38% | 89.11%
|  | Z1-C-MEP-8760 | Pull Earthing & Power Cables - Z1 - F1 | 252 | 250 | 219 | 99.21% | 0.0002882% | 0.0002525% | 86.9% | 87.6%
|  | Z1-C-MEP-8770 | Fix DBs - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8780 | Cable Terminations - Z1 - F1 | 33 | 33 | 28 | 100% | 3.804e-05% | 3.228e-05% | 84.85% | 84.85%
|  | Z1-C-MEP-8790 | Fix CCTV Devices - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8800 | Fix Light Fixtures - Z1 - F1 | 101 | 100 | 86 | 99.01% | 0.0001153% | 9.914e-05% | 85.15% | 86%
|  | Z1-C-MEP-8810 | Fix Switches, Sockets & Isolators - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8820 | Fix Fire Alarm Devices - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8830 | Fix Telephone & Voice Evac. Devices - Z1 - F1 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-8840 | Fix LCS & ACS Devices - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8850 | Fix Emergency & Exit Lights - Z1 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-8950 | Fix G.I Box and conduits - Z1 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9020 | Fix ELV Trunkings - Z1 - F2 | 250 | 250 | 209 | 100% | 0.0002882% | 0.0002409% | 83.6% | 83.6%
|  | Z1-C-MEP-9030 | Pull ELV Cables - Z1 - F2 | 102 | 101 | 86 | 99.02% | 0.0001164% | 9.914e-05% | 84.31% | 85.15%
|  | Z1-C-MEP-9040 | Fix Power Cable Trays - Z1 - F2 | 500 | 500 | 419 | 100% | 0.0005764% | 0.000483% | 83.8% | 83.8%
|  | Z1-C-MEP-9050 | Pull Electricl Wires (Ceiling & Walls) - Z1 - F2 | 102 | 101 | 87 | 99.02% | 0.0001164% | 0.0001003% | 85.29% | 86.14%
|  | Z1-C-MEP-9060 | Pull Earthing & Power Cables - Z1 - F2 | 252 | 250 | 214 | 99.21% | 0.0002882% | 0.0002467% | 84.92% | 85.6%
|  | Z1-C-MEP-9070 | Fix DBs - Z1 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9080 | Cable Terminations - Z1 - F2 | 33 | 34 | 15 | 103% | 3.92e-05% | 1.729e-05% | 45.45% | 44.12%
|  | Z1-C-MEP-9090 | Fix CCTV Devices - Z1 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9100 | Fix Light Fixtures - Z1 - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-9110 | Fix Switches, Sockets & Isolators - Z1 - F2 | 50 | 50 | 17 | 100% | 5.764e-05% | 1.96e-05% | 34% | 34%
|  | Z1-C-MEP-9120 | Fix Fire Alarm Devices - Z1 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9130 | Fix Telephone & Voice Evac. Devices - Z1 - F2 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-9140 | Fix LCS & ACS Devices - Z1 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9150 | Fix Emergency & Exit Lights - Z1 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9270 | Fix G.I Box and conduits - Z1 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9340 | Fix ELV Trunkings - Z1 - RF | 249 | 250 | 212 | 100.4% | 0.0002882% | 0.0002444% | 85.14% | 84.8%
|  | Z1-C-MEP-9350 | Pull ELV Cables - Z1 - RF | 101 | 101 | 86 | 100% | 0.0001164% | 9.914e-05% | 85.15% | 85.15%
|  | Z1-C-MEP-9360 | Fix Power Cable Trays - Z1 - RF | 500 | 500 | 511 | 100% | 0.0005764% | 0.0005891% | 102.2% | 102.2%
|  | Z1-C-MEP-9370 | Pull Electricl Wires (Ceiling & Walls) - Z1 - RF | 102 | 101 | 86 | 99.02% | 0.0001164% | 9.914e-05% | 84.31% | 85.15%
|  | Z1-C-MEP-9380 | Pull Earthing & Power Cables - Z1 - RF | 252 | 250 | 215 | 99.21% | 0.0002882% | 0.0002479% | 85.32% | 86%
|  | Z1-C-MEP-9390 | Fix DBs - Z1 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9400 | Cable Terminations - Z1 - RF | 34 | 33 | 29 | 97.06% | 3.804e-05% | 3.343e-05% | 85.29% | 87.88%
|  | Z1-C-MEP-9410 | Fix CCTV Devices - Z1 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9420 | Fix Light Fixtures - Z1 - RF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z1-C-MEP-9430 | Fix Switches, Sockets & Isolators - Z1 - RF | 49 | 50 | 42 | 102% | 5.764e-05% | 4.842e-05% | 85.71% | 84%
|  | Z1-C-MEP-9440 | Fix Fire Alarm Devices - Z1 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9450 | Fix Telephone & Voice Evac. Devices - Z1 - RF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z1-C-MEP-9460 | Fix LCS & ACS Devices - Z1 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-MEP-9470 | Fix Emergency & Exit Lights - Z1 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z1-C-RSRS-11110 | Power Cable Pulling & Termination Risers | 97 | 101 | 83 | 104.1% | 0.0001164% | 9.568e-05% | 85.57% | 82.18%
Z2 | Div 02 | C-EW-10400 | Excavation Stage 2 - Z2&3 | 3408 | 3408 | 2207 | 100% | 0.003929% | 0.002544% | 64.76% | 64.76%
|  | C-EW-10440 | Excavation Stage 1 - Z2&3 | 3409 | 3408 | 2082 | 99.97% | 0.003929% | 0.0024% | 61.07% | 61.09%
|  | C-EW-10460 | Waterproof Membrane on Gunite Wall - Z2-B1 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
|  | C-EW-10480 | Gunite Wall - Z3 | 333 | 333 |  | 100% | 0.0003839% |  | 0% | 0%
|  | C-SHRNG-DCE-C-2360 | Place Guide Wall - Z2&3 | 249 | 249 | 274 | 100% | 0.0002871% | 0.0003159% | 110% | 110%
|  | C-SHRNG-DCE-C-2380 | Install Capping Beam - Z2&3 | 3692 | 3692 | 4062 | 100% | 0.004256% | 0.004683% | 110% | 110%
|  | Z2-C-EW-10420 | Waterproof Membrane on Gunite Wall - Z2-B2 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
| Div 03 | C-EW-10410 | Gunite Wall - Z2 | 333 | 333 | 3 | 100% | 0.0003839% | 3.458e-06% | 0.9009% | 0.9009%
|  | Z2-11520 | Post Tensioning the Slab - Z2 - F1 | 4 | 4 | 1 | 100% | 4.611e-06% | 1.153e-06% | 25% | 25%
|  | Z2-11530 | Post Tensioning the Slab - Z2 - F2 | 4 | 4 | 3 | 100% | 4.611e-06% | 3.458e-06% | 75% | 75%
|  | Z2-11540 | Post Tensioning the Slab - Z2 - RF | 4 | 4 | 3 | 100% | 4.611e-06% | 3.458e-06% | 75% | 75%
|  | Z2-11550 | Post Tensioning the Slab - Z2 - SRVF | 4 | 4 | 3 | 100% | 4.611e-06% | 3.458e-06% | 75% | 75%
|  | Z2-C-CON-5840 | PCC Blind Concrete - Z2 - Lift Pit | 4 | 4 | 0 | 100% | 4.611e-06% |  | 0% | 0%
|  | Z2-C-CON-5850 | Waterproof Membrane - Z2 - Lift Pit | 20 | 20 | 0 | 100% | 2.306e-05% |  | 0% | 0%
|  | Z2-C-CON-5860 | Protection Screed - Z2 - Lift Pit | 26 | 26 | 0 | 100% | 2.997e-05% |  | 0% | 0%
|  | Z2-C-CON-5870 | Fix Rebar - Z2 - Lift Pit | 249 | 249 | 5 | 100% | 0.0002871% | 5.764e-06% | 2.008% | 2.008%
|  | Z2-C-CON-5890 | Pour Concrete - Z2 - Lift Pit | 72 | 72 | 15 | 100% | 8.3e-05% | 1.729e-05% | 20.83% | 20.83%
|  | Z2-C-CON-5900 | PCC Blind Concrete - Z2 - Raft | 148 | 148 | 31 | 100% | 0.0001706% | 3.574e-05% | 20.95% | 20.95%
|  | Z2-C-CON-5910 | Waterproof Membrane - Z2 - Raft | 1180 | 1180 | 251 | 100% | 0.00136% | 0.0002894% | 21.27% | 21.27%
|  | Z2-C-CON-5920 | Protection Screed - Z2 - Raft | 72 | 74 | 15 | 102.8% | 8.531e-05% | 1.729e-05% | 20.83% | 20.27%
|  | Z2-C-CON-5930 | Fix Rebar - Z2 - Raft | 13737 | 13736 | 11676 | 99.99% | 0.01584% | 0.01346% | 85% | 85%
|  | Z2-C-CON-5950 | Fix Formwork - Z2 - Raft | 196 | 196 | 167 | 100% | 0.000226% | 0.0001925% | 85.2% | 85.2%
|  | Z2-C-CON-5960 | Pour Concrete - Z2 - Raft | 3317 | 3317 | 2819 | 100% | 0.003824% | 0.00325% | 84.99% | 84.99%
|  | Z2-C-CON-5970 | Fix Rebar Columns - Z2 - B2 | 2266 | 2265 | 1926 | 99.96% | 0.002611% | 0.00222% | 85% | 85.03%
|  | Z2-C-CON-5980 | Fix Formwork Columns - Z2 - B2 | 667 | 667 | 567 | 100% | 0.0007689% | 0.0006536% | 85.01% | 85.01%
|  | Z2-C-CON-5990 | Pour Concrete Columns - Z2 - B2 | 130 | 132 | 110 | 101.5% | 0.0001522% | 0.0001268% | 84.62% | 83.33%
|  | Z2-C-CON-6000 | Fix Rebar Retaining Walls - Z2 - B2 | 1432 | 1432 | 1217 | 100% | 0.001651% | 0.001403% | 84.99% | 84.99%
|  | Z2-C-CON-6010 | Fix Formwork Retaining Walls - Z2 - B2 | 1171 | 1171 | 995 | 100% | 0.00135% | 0.001147% | 84.97% | 84.97%
|  | Z2-C-CON-6020 | Pour Concrete Retaining Walls - Z2 - B2 | 240 | 242 | 204 | 100.8% | 0.000279% | 0.0002352% | 85% | 84.3%
|  | Z2-C-CON-6030 | Pour Concrete Core Walls - Z2 - B2 | 136 | 136 | 116 | 100% | 0.0001568% | 0.0001337% | 85.29% | 85.29%
|  | Z2-C-CON-6040 | Fix Rebar Core Walls - Z2 - B2 | 950 | 949 | 807 | 99.89% | 0.001094% | 0.0009303% | 84.95% | 85.04%
|  | Z2-C-CON-6050 | Fix Formwork Core Walls - Z2 - B2 | 936 | 936 | 796 | 100% | 0.001079% | 0.0009176% | 85.04% | 85.04%
|  | Z2-C-CON-6060 | Fix Formwork Stairs - Z2 - B2 | 3 | 3 | 0 | 100% | 3.458e-06% |  | 0% | 0%
|  | Z2-C-CON-6070 | Fix Rebar Stairs - Z2 - B2 | 32 | 32 | 1 | 100% | 3.689e-05% | 1.153e-06% | 3.125% | 3.125%
|  | Z2-C-CON-6080 | Pour Concrete Stairs - Z2 - B2 | 8 | 8 | 1 | 100% | 9.223e-06% | 1.153e-06% | 12.5% | 12.5%
|  | Z2-C-CON-6090 | Fix Rebar Retaining Walls - Z2 - B1 | 1138 | 1138 | 155 | 100% | 0.001312% | 0.0001787% | 13.62% | 13.62%
|  | Z2-C-CON-6100 | Fix Formwork Retaining Walls - Z2 - B1 | 1171 | 1171 | 269 | 100% | 0.00135% | 0.0003101% | 22.97% | 22.97%
|  | Z2-C-CON-6110 | Pour Concrete Retaining Walls - Z2 - B1 | 240 | 242 | 14 | 100.8% | 0.000279% | 1.614e-05% | 5.833% | 5.785%
|  | Z2-C-CON-6120 | Fix Formwork Core Walls - Z2 - B1 | 946 | 945 | 804 | 99.89% | 0.001089% | 0.0009269% | 84.99% | 85.08%
|  | Z2-C-CON-6130 | Fix Rebar Core Walls - Z2 - B1 | 913 | 914 | 18 | 100.1% | 0.001054% | 2.075e-05% | 1.972% | 1.969%
|  | Z2-C-CON-6140 | Pour Concrete Core Walls - Z2 - B1 | 138 | 138 | 7 | 100% | 0.0001591% | 8.07e-06% | 5.072% | 5.072%
|  | Z2-C-CON-6150 | Fix Rebar Columns - Z2 - B1 | 1735 | 1735 | 35 | 100% | 0.002% | 4.035e-05% | 2.017% | 2.017%
|  | Z2-C-CON-6160 | Fix Formwork Columns - Z2 - B1 | 743 | 743 | 101 | 100% | 0.0008565% | 0.0001164% | 13.59% | 13.59%
|  | Z2-C-CON-6170 | Pour Concrete Columns - Z2 - B1 | 146 | 146 | 20 | 100% | 0.0001683% | 2.306e-05% | 13.7% | 13.7%
|  | Z2-C-CON-6180 | Fix Formwork Stairs - Z2 - B1 | 4 | 3 | 0 | 75% | 3.458e-06% |  | 0% | 0%
|  | Z2-C-CON-6190 | Fix Rebar Stairs - Z2 - B1 | 32 | 32 | 3 | 100% | 3.689e-05% | 3.458e-06% | 9.375% | 9.375%
|  | Z2-C-CON-6200 | Pour Concrete Stairs - Z2 - B1 | 8 | 8 | 1 | 100% | 9.223e-06% | 1.153e-06% | 12.5% | 12.5%
|  | Z2-C-CON-6210 | Fix Formwork Slabs - Z2 - B1 | 3041 | 3041 | 2585 | 100% | 0.003506% | 0.00298% | 85% | 85%
|  | Z2-C-CON-6220 | Fix Rebar Slabs - Z2 - B1 | 4027 | 4027 | 121 | 100% | 0.004642% | 0.0001395% | 3.005% | 3.005%
|  | Z2-C-CON-6230 | Pour Concrete Slabs - Z2 - B1 | 1036 | 1036 | 21 | 100% | 0.001194% | 2.421e-05% | 2.027% | 2.027%
|  | Z2-C-CON-6250 | Fix Rebar Core Walls - Z2 - GF | 1707 | 1707 | 171 | 100% | 0.001968% | 0.0001971% | 10.02% | 10.02%
|  | Z2-C-CON-6260 | Fix Formwork Core Walls - Z2 - GF | 1721 | 1721 | 172 | 100% | 0.001984% | 0.0001983% | 9.994% | 9.994%
|  | Z2-C-CON-6270 | Pour Concrete Core Walls - Z2 - GF | 236 | 236 | 84 | 100% | 0.0002721% | 9.684e-05% | 35.59% | 35.59%
|  | Z2-C-CON-6280 | Fix Rebar Columns - Z2 - GF | 2256 | 2256 | 226 | 100% | 0.002601% | 0.0002605% | 10.02% | 10.02%
|  | Z2-C-CON-6290 | Fix Formwork Columns - Z2 - GF | 1136 | 1136 | 114 | 100% | 0.00131% | 0.0001314% | 10.04% | 10.04%
|  | Z2-C-CON-6300 | Pour Concrete Columns - Z2 - GF | 224 | 224 | 22 | 100% | 0.0002582% | 2.536e-05% | 9.821% | 9.821%
|  | Z2-C-CON-6310 | Fix Formwork Stairs - Z2 - GF | 4 | 4 | 1 | 100% | 4.611e-06% | 1.153e-06% | 25% | 25%
|  | Z2-C-CON-6320 | Fix Rebar Stairs - Z2 - GF | 16 | 16 | 8 | 100% | 1.845e-05% | 9.223e-06% | 50% | 50%
|  | Z2-C-CON-6330 | Pour Concrete Stairs - Z2 - GF | 10 | 10 | 2 | 100% | 1.153e-05% | 2.306e-06% | 20% | 20%
|  | Z2-C-CON-6340 | Fix Formwork Slabs - Z2 - GF | 2844 | 2843 | 171 | 99.96% | 0.003277% | 0.0001971% | 6.013% | 6.015%
|  | Z2-C-CON-6350 | Fix Rebar Slabs - Z2 - GF | 7049 | 7049 | 3718 | 100% | 0.008126% | 0.004286% | 52.75% | 52.75%
|  | Z2-C-CON-6360 | Pour Concrete Slabs - Z2 - GF | 1278 | 1278 | 128 | 100% | 0.001473% | 0.0001476% | 10.02% | 10.02%
|  | Z2-C-CON-6380 | Fix Formwork Slabs - Z2 - F1 | 2843 | 2843 | 1441 | 100% | 0.003277% | 0.001661% | 50.69% | 50.69%
|  | Z2-C-CON-6390 | Fix Rebar Slabs - Z2 - F1 | 3628 | 3627 | 2035 | 99.97% | 0.004181% | 0.002346% | 56.09% | 56.11%
|  | Z2-C-CON-6410 | Pour Concrete Slabs - Z2 - F1 | 988 | 988 | 247 | 100% | 0.001139% | 0.0002847% | 25% | 25%
|  | Z2-C-CON-6420 | Fix Rebar Core Walls - Z2 - F1 | 1686 | 1686 | 422 | 100% | 0.001944% | 0.0004865% | 25.03% | 25.03%
|  | Z2-C-CON-6430 | Fix Formwork Core Walls - Z2 - F1 | 1724 | 1724 | 431 | 100% | 0.001987% | 0.0004969% | 25% | 25%
|  | Z2-C-CON-6440 | Pour Concrete Core Walls - Z2 - F1 | 240 | 240 | 60 | 100% | 0.0002767% | 6.917e-05% | 25% | 25%
|  | Z2-C-CON-6450 | Fix Rebar Columns - Z2 - F1 | 2284 | 2285 | 1142 | 100% | 0.002634% | 0.001317% | 50% | 49.98%
|  | Z2-C-CON-6460 | Fix Formwork Columns - Z2 - F1 | 1130 | 1130 | 282 | 100% | 0.001303% | 0.0003251% | 24.96% | 24.96%
|  | Z2-C-CON-6470 | Pour Concrete Columns - Z2 - F1 | 224 | 224 | 56 | 100% | 0.0002582% | 6.456e-05% | 25% | 25%
|  | Z2-C-CON-6480 | Fix Formwork Stairs - Z2 - F1 | 4 | 4 | 1 | 100% | 4.611e-06% | 1.153e-06% | 25% | 25%
|  | Z2-C-CON-6490 | Fix Rebar Stairs - Z2 - F1 | 16 | 16 | 4 | 100% | 1.845e-05% | 4.611e-06% | 25% | 25%
|  | Z2-C-CON-6500 | Pour Concrete Stairs - Z2 - F1 | 10 | 10 | 8 | 100% | 1.153e-05% | 9.223e-06% | 80% | 80%
|  | Z2-C-CON-6510 | Fix Rebar Slabs - Z2 - F2 | 3726 | 3726 | 7452 | 100% | 0.004295% | 0.008591% | 200% | 200%
|  | Z2-C-CON-6520 | Fix Formwork Slabs - Z2 - F2 | 2832 | 2832 | 2407 | 100% | 0.003265% | 0.002775% | 84.99% | 84.99%
|  | Z2-C-CON-6530 | Pour Concrete Slabs - Z2 - F2 | 994 | 994 | 845 | 100% | 0.001146% | 0.0009741% | 85.01% | 85.01%
|  | Z2-C-CON-6550 | Fix Rebar Core Walls - Z2 - F2 | 1114 | 1114 | 947 | 100% | 0.001284% | 0.001092% | 85.01% | 85.01%
|  | Z2-C-CON-6560 | Fix Formwork Core Walls - Z2 - F2 | 1018 | 1018 | 865 | 100% | 0.001174% | 0.0009972% | 84.97% | 84.97%
|  | Z2-C-CON-6570 | Pour Concrete Core Walls - Z2 - F2 | 144 | 144 | 122 | 100% | 0.000166% | 0.0001406% | 84.72% | 84.72%
|  | Z2-C-CON-6580 | Fix Rebar Columns - Z2 - F2 | 1557 | 1558 | 1323 | 100.1% | 0.001796% | 0.001525% | 84.97% | 84.92%
|  | Z2-C-CON-6590 | Fix Formwork Columns - Z2 - F2 | 727 | 727 | 618 | 100% | 0.0008381% | 0.0007124% | 85.01% | 85.01%
|  | Z2-C-CON-6600 | Pour Concrete Columns - Z2 - F2 | 142 | 142 | 121 | 100% | 0.0001637% | 0.0001395% | 85.21% | 85.21%
|  | Z2-C-CON-6610 | Fix Formwork Stairs - Z2 - F2 | 4 | 4 | 3 | 100% | 4.611e-06% | 3.458e-06% | 75% | 75%
|  | Z2-C-CON-6620 | Fix Rebar Stairs - Z2 - F2 | 16 | 16 | 14 | 100% | 1.845e-05% | 1.614e-05% | 87.5% | 87.5%
|  | Z2-C-CON-6630 | Pour Concrete Stairs - Z2 - F2 | 10 | 10 | 8 | 100% | 1.153e-05% | 9.223e-06% | 80% | 80%
|  | Z2-C-CON-6640 | Fix Formwork Slabs - Z2 - RF | 2831 | 2831 | 2406 | 100% | 0.003264% | 0.002774% | 84.99% | 84.99%
|  | Z2-C-CON-6650 | Fix Rebar Slabs - Z2 - RF | 3707 | 3707 | 3151 | 100% | 0.004274% | 0.003633% | 85% | 85%
|  | Z2-C-CON-6660 | Pour Concrete Slabs - Z2 - RF | 990 | 990 | 841 | 100% | 0.001141% | 0.0009695% | 84.95% | 84.95%
|  | Z2-C-CON-6680 | Fix Rebar Core Walls - Z2 - RF | 1096 | 1095 | 932 | 99.91% | 0.001262% | 0.001074% | 85.04% | 85.11%
|  | Z2-C-CON-6690 | Fix Formwork Core Walls - Z2 - RF | 1015 | 1015 | 863 | 100% | 0.00117% | 0.0009949% | 85.02% | 85.02%
|  | Z2-C-CON-6700 | Pour Concrete Core Walls - Z2 - RF | 144 | 144 | 122 | 100% | 0.000166% | 0.0001406% | 84.72% | 84.72%
|  | Z2-C-CON-6710 | Fix Rebar Columns - Z2 - RF | 1275 | 1275 | 1084 | 100% | 0.00147% | 0.00125% | 85.02% | 85.02%
|  | Z2-C-CON-6720 | Fix Formwork Columns - Z2 - RF | 563 | 563 | 479 | 100% | 0.000649% | 0.0005522% | 85.08% | 85.08%
|  | Z2-C-CON-6730 | Pour Concrete Columns - Z2 - RF | 112 | 114 | 95 | 101.8% | 0.0001314% | 0.0001095% | 84.82% | 83.33%
|  | Z2-C-CON-6740 | Fix Formwork Stairs - Z2 - RF | 3 | 4 | 3 | 133.3% | 4.611e-06% | 3.458e-06% | 100% | 75%
|  | Z2-C-CON-6750 | Fix Rebar Stairs - Z2 - RF | 14 | 14 | 12 | 100% | 1.614e-05% | 1.383e-05% | 85.71% | 85.71%
|  | Z2-C-CON-6760 | Pour Concrete Stairs - Z2 - RF | 8 | 8 | 7 | 100% | 9.223e-06% | 8.07e-06% | 87.5% | 87.5%
|  | Z2-C-CON-6770 | Fix Formwork Slabs - Z2 - SRVF | 2426 | 2426 | 2062 | 100% | 0.002797% | 0.002377% | 85% | 85%
|  | Z2-C-CON-6780 | Fix Rebar Slabs - Z2 - SRVF | 3040 | 3040 | 2584 | 100% | 0.003505% | 0.002979% | 85% | 85%
|  | Z2-C-CON-6790 | Pour Concrete Slabs - Z2 - SRVF | 850 | 850 | 722 | 100% | 0.0009799% | 0.0008323% | 84.94% | 84.94%
|  | Z2-C-CON-6810 | Fix Rebar Core Walls - Z2 - SRVF | 648 | 648 | 551 | 100% | 0.000747% | 0.0006352% | 85.03% | 85.03%
|  | Z2-C-CON-6820 | Fix Formwork Core Walls - Z2 - SRVF | 576 | 577 | 132 | 100.2% | 0.0006652% | 0.0001522% | 22.92% | 22.88%
|  | Z2-C-CON-6830 | Pour Concrete Core Walls - Z2 - SRVF | 4 | 4 | 1 | 100% | 4.611e-06% | 1.153e-06% | 25% | 25%
|  | Z2-C-CON-6840 | Fix Rebar Columns - Z2 - SRVF | 116 | 116 | 99 | 100% | 0.0001337% | 0.0001141% | 85.34% | 85.34%
|  | Z2-C-CON-6850 | Fix Formwork Columns - Z2 - SRVF | 41 | 41 | 35 | 100% | 4.727e-05% | 4.035e-05% | 85.37% | 85.37%
|  | Z2-C-CON-6860 | Pour Concrete Columns - Z2 - SRVF | 8 | 8 | 2 | 100% | 9.223e-06% | 2.306e-06% | 25% | 25%
|  | Z2-C-CON-6870 | Pour MEP RCC Pedastals - Z2 - SRVF | 2 | 2 | 2 | 100% | 2.306e-06% | 2.306e-06% | 100% | 100%
|  | Z2-C-CON-6880 | Fix Formwork Parapet - Z2 - SRVF | 113 | 113 | 96 | 100% | 0.0001303% | 0.0001107% | 84.96% | 84.96%
|  | Z2-C-CON-6890 | Fix Rebar Parapet - Z2 - SRVF | 236 | 236 | 201 | 100% | 0.0002721% | 0.0002317% | 85.17% | 85.17%
|  | Z2-C-CON-6900 | Pour Concrete Parapet - Z2 - SRVF | 136 | 136 | 31 | 100% | 0.0001568% | 3.574e-05% | 22.79% | 22.79%
|  | Z2-C-CON-6910 | Fix Formwork Slabs - Z2 - TRF | 298 | 298 | 253 | 100% | 0.0003435% | 0.0002917% | 84.9% | 84.9%
|  | Z2-C-CON-6920 | Fix Rebar Slabs - Z2 - TRF | 304 | 303 | 258 | 99.67% | 0.0003493% | 0.0002974% | 84.87% | 85.15%
|  | Z2-C-CON-6930 | Pour Concrete Slabs - Z2 - TRF | 90 | 90 | 76 | 100% | 0.0001038% | 8.761e-05% | 84.44% | 84.44%
|  | Z2-C-CON-6950 | Fix Formwork Parapet - Z2 - TRF | 113 | 113 | 96 | 100% | 0.0001303% | 0.0001107% | 84.96% | 84.96%
|  | Z2-C-CON-6960 | Fix Rebar Parapet - Z2 - TRF | 236 | 236 | 201 | 100% | 0.0002721% | 0.0002317% | 85.17% | 85.17%
|  | Z2-C-CON-6970 | Pour Concrete Parapet - Z2 - TRF | 136 | 136 | 116 | 100% | 0.0001568% | 0.0001337% | 85.29% | 85.29%
| Div 04 | Z123-C-FIN-18110 | Masonry Works Dry Area - Z123 - SRVF | 402 | 402 | 342 | 100% | 0.0004634% | 0.0003943% | 85.07% | 85.07%
|  | Z2&3-C-FIN-18800 | Masonry Works - Z2&3 - B2 | 56 | 58 | 28 | 103.6% | 6.686e-05% | 3.228e-05% | 50% | 48.28%
|  | Z2&3-C-FIN-19050 | Masonry Works - Z2&3 - B1 | 562 | 562 | 140 | 100% | 0.0006479% | 0.0001614% | 24.91% | 24.91%
|  | Z2&3-C-FIN-19270 | Masonry Works Wet + Dry Area - Z2&3 - F1 | 2674 | 2672 | 2273 | 99.93% | 0.00308% | 0.00262% | 85% | 85.07%
|  | Z2&3-C-FIN-19540 | Masonry Works - Z2&3 - GF | 4146 | 4144 | 8292 | 99.95% | 0.004777% | 0.009559% | 200% | 200.1%
|  | Z2&3-C-FIN-20010 | Masonry Works Wet Area - Z2&3 - F2 | 1572 | 1570 | 1336 | 99.87% | 0.00181% | 0.00154% | 84.99% | 85.1%
|  | Z2&3-C-FIN-20040 | Masonry Works Dry Area - Z2&3 - F2 | 1572 | 1570 | 1336 | 99.87% | 0.00181% | 0.00154% | 84.99% | 85.1%
|  | Z2&3-C-FIN-20440 | Masonry Works Wet Area - Z2&3 - RF | 1348 | 1346 | 1146 | 99.85% | 0.001552% | 0.001321% | 85.01% | 85.14%
|  | Z2&3-C-FIN-20470 | Masonry Works Dry Area - Z2&3 - RF | 1348 | 1346 | 1146 | 99.85% | 0.001552% | 0.001321% | 85.01% | 85.14%
| Div 05 | A10910 | Install Road Signages Drive - Z2 - B1 | 20 | 20 |  | 100% | 2.306e-05% |  | 0% | 0%
|  | A10970 | Install Road Signages Drive - Z2 - B2 | 20 | 20 |  | 100% | 2.306e-05% |  | 0% | 0%
|  | A11230 | Signages - F2 | 20 | 20 |  | 100% | 2.306e-05% |  | 0% | 0%
|  | A11280 | Signages - RF | 20 | 20 |  | 100% | 2.306e-05% |  | 0% | 0%
|  | A11440 | Installation of BMU System | 499 | 500 | 424 | 100.2% | 0.0005764% | 0.0004888% | 84.97% | 84.8%
|  | C-FIN-ENVLP-9650 | Install Aluminum Wood Ground Features | 612 | 611 | 520 | 99.84% | 0.0007044% | 0.0005995% | 84.97% | 85.11%
|  | C-FIN-ENVLP-9710 | Fix Steel Decore - GF to SRVF (Elev. 2 & 3) | 1940 | 1940 | 1649 | 100% | 0.002236% | 0.001901% | 85% | 85%
|  | Z123-C-FIN-18370 | Install Aluminum Shades over GRP Water Tank - Z123 - SRVF | 224 | 222 | 190 | 99.11% | 0.0002559% | 0.000219% | 84.82% | 85.59%
| Div 06 | Z2&3-C-FIN-20150 | Fix Furniture & Counter Works kitchen/Pantry - Z2&3 - F2 | 450 | 450 | 382 | 100% | 0.0005188% | 0.0004404% | 84.89% | 84.89%
|  | Z2&3-C-FIN-20580 | Fix Furniture & Counter Works kitchen/Pantry - Z2&3 - RF | 450 | 450 | 382 | 100% | 0.0005188% | 0.0004404% | 84.89% | 84.89%
| Div 07 | C-FIN-ENVLP-9670 | Osmotic Cement Waterproof - GF to SRVF (Elev. 2 & 3) | 1149 | 1148 | 977 | 99.91% | 0.001323% | 0.001126% | 85.03% | 85.1%
|  | Z123-C-FIN-18170 | 4mm Waterproof Membrane Wet Area - Z123 - SRVF | 1960 | 1960 | 1666 | 100% | 0.00226% | 0.001921% | 85% | 85%
|  | Z123-C-FIN-18180 | Protection Screed Wet Area - Z123 - SRVF | 1960 | 1960 | 1666 | 100% | 0.00226% | 0.001921% | 85% | 85%
|  | Z123-C-FIN-18190 | Polystyrene Thermal Insulation - Z123 - SRVF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z123-C-FIN-18200 | Foam Concrete - Z123 - SRVF | 1960 | 1960 | 1283 | 100% | 0.00226% | 0.001479% | 65.46% | 65.46%
|  | Z123-C-FIN-18330 | Waterproof Filter & Pump Room - Z123 - SRVF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z123-C-FIN-18340 | Protection Screed Filter & Pump Room - Z123 - SRVF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-19330 | Protection Screed Wet Area - Z2&3 - F1 | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-19380 | Waterproof Wet Area - Z2&3 - F1 | 32 | 34 | 27 | 106.2% | 3.92e-05% | 3.113e-05% | 84.38% | 79.41%
|  | Z2&3-C-FIN-19580 | Waterproof & Screed Garbage Room - Z2&3 - GF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20100 | Waterproof kitchen/Pantry - Z2&3 - F2 | 32 | 34 | 27 | 106.2% | 3.92e-05% | 3.113e-05% | 84.38% | 79.41%
|  | Z2&3-C-FIN-20110 | Protection Screed kitchen/Pantry - Z2&3 - F2 | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20190 | Waterproof Bath - Z2&3 - F2 | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20200 | Protection Screed Bath - Z2&3 - F2 | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20260 | Waterproof Garbage Room - Z2&3 - F2 | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20270 | Protection Screed Garbage Room - Z2&3 - F2 | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20530 | Waterproof kitchen/Pantry - Z2&3 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20540 | Protection Screed kitchen/Pantry - Z2&3 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20620 | Waterproof Bath - Z2&3 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20630 | Protection Screed Bath - Z2&3 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20690 | Waterproof Garbage Room - Z2&3 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
|  | Z2&3-C-FIN-20700 | Protection Screed Garbage Room - Z2&3 - RF | 34 | 34 | 29 | 100% | 3.92e-05% | 3.343e-05% | 85.29% | 85.29%
| Div 08 | A11210 | Fix Windows & Door Frame & Leaf - F2 | 224 | 222 | 190 | 99.11% | 0.0002559% | 0.000219% | 84.82% | 85.59%
|  | A11220 | Fix Ironmongery - F2 | 222 | 222 | 189 | 100% | 0.0002559% | 0.0002179% | 85.14% | 85.14%
|  | A11260 | Fix Windows & Door Frame & Leaf - RF | 224 | 222 | 190 | 99.11% | 0.0002559% | 0.000219% | 84.82% | 85.59%
|  | A11270 | Fix Ironmongery - RF | 224 | 222 | 190 | 99.11% | 0.0002559% | 0.000219% | 84.82% | 85.59%
|  | C-FIN-ENVLP-9680 | Fix Aluminum Glazing Pannels - GF to SRVF (Elev. 2 & 3) | 2737 | 2737 | 1696 | 100% | 0.003155% | 0.001955% | 61.97% | 61.97%
|  | Z123-C-FIN-18130 | Fix Door Subframes Dry Area - Z123 - SRVF | 71 | 70 | 60 | 98.59% | 8.07e-05% | 6.917e-05% | 84.51% | 85.71%
|  | Z123-C-FIN-18220 | Install Aluminum Shades over FAHU - Z123 - SRVF | 286 | 286 | 243 | 100% | 0.0003297% | 0.0002801% | 84.97% | 84.97%
|  | Z123-C-FIN-18360 | Install Aluminum Shades over Chillers - Z123 - SRVF | 286 | 286 | 223 | 100% | 0.0003297% | 0.0002571% | 77.97% | 77.97%
|  | Z123-C-FIN-8540 | Fix Windows & Door Frame & Leaf - Z123 - SRVF | 222 | 224 | 188 | 100.9% | 0.0002582% | 0.0002167% | 84.68% | 83.93%
|  | Z123-C-FIN-8550 | Fix Ironmongery - Z123 - SRVF | 222 | 222 | 189 | 100% | 0.0002559% | 0.0002179% | 85.14% | 85.14%
|  | Z2&3-C-FIN-18910 | Fix Doors - Z2&3 - B2 | 104 | 103 | 88 | 99.04% | 0.0001187% | 0.0001014% | 84.62% | 85.44%
|  | Z2&3-C-FIN-18950 | Fix Doors - Z2&3 - B2 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z2&3-C-FIN-18990 | Fix Doors - Z2&3 - B2 | 103 | 103 | 67 | 100% | 0.0001187% | 7.724e-05% | 65.05% | 65.05%
|  | Z2&3-C-FIN-19100 | Fix Doors - Z2&3 - B1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z2&3-C-FIN-19190 | Fix Doors - Z2&3 - B1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z2&3-C-FIN-19290 | Fix Door Subframes Wet + Dry Area - Z2&3 - F1 | 70 | 70 | 60 | 100% | 8.07e-05% | 6.917e-05% | 85.71% | 85.71%
|  | Z2&3-C-FIN-19360 | Fix Doors Wet Area - Z2&3 - F1 | 103 | 103 | 24 | 100% | 0.0001187% | 2.767e-05% | 23.3% | 23.3%
|  | Z2&3-C-FIN-19420 | Fix Doors Lift Lobby - Z2&3 - F1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z2&3-C-FIN-19500 | Fix Doors IT Room - Z2&3 - F1 | 103 | 103 | 24 | 100% | 0.0001187% | 2.767e-05% | 23.3% | 23.3%
|  | Z2&3-C-FIN-19570 | Fix Doors Garbage & Service Room - Z2&3 - GF | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z2&3-C-FIN-19760 | Fix Doors Lift Lobby - Z2&3 - GF | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z2&3-C-FIN-20030 | Fix Door Subframes Wet Area - Z2&3 - F2 | 70 | 70 | 59 | 100% | 8.07e-05% | 6.802e-05% | 84.29% | 84.29%
|  | Z2&3-C-FIN-20060 | Fix Door Subframes Dry Area - Z2&3 - F2 | 70 | 70 | 59 | 100% | 8.07e-05% | 6.802e-05% | 84.29% | 84.29%
|  | Z2&3-C-FIN-20460 | Fix Door Subframes Wet Area - Z2&3 - RF | 71 | 70 | 60 | 98.59% | 8.07e-05% | 6.917e-05% | 84.51% | 85.71%
|  | Z2&3-C-FIN-20490 | Fix Door Subframes Dry Area - Z2&3 - RF | 71 | 70 | 60 | 98.59% | 8.07e-05% | 6.917e-05% | 84.51% | 85.71%
|  | Z2&3-C-FIN-20890 | Fix Doors - Z2&3 - B1 | 103 | 103 | 88 | 100% | 0.0001187% | 0.0001014% | 85.44% | 85.44%
|  | Z2&3-C-FIN-21010 | Fix Doors Serv. Rooms - Z2&3 - F1 | 103 | 103 | 24 | 100% | 0.0001187% | 2.767e-05% | 23.3% | 23.3%
| Div 09 | A10890 | Traffic Deck Coating Drive - Z2 - B1 | 630 | 630 | 535 | 100% | 0.0007263% | 0.0006168% | 84.92% | 84.92%
|  | A10950 | Traffic Deck Coating Drive - Z2 - B2 | 630 | 630 | 536 | 100% | 0.0007263% | 0.0006179% | 85.08% | 85.08%
|  | A11400 | Fix Flower Box | 212 | 214 | 180 | 100.9% | 0.0002467% | 0.0002075% | 84.91% | 84.11%
|  | A11410 | Fix Outdoor Green Area | 140 | 140 | 119 | 100% | 0.0001614% | 0.0001372% | 85% | 85%
|  | A9690 | Fix Pavement Tiles & Granite Colored Land Scaping | 6723 | 6773 | 5715 | 100.7% | 0.007808% | 0.006588% | 85.01% | 84.38%
|  | A9710 | Install Precast Wheel Stoper | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | A9720 | Trafic & Road Marking | 100 | 100 | 84 | 100% | 0.0001153% | 9.684e-05% | 84% | 84%
|  | C-FIN-ENVLP-9690 | Fix Brackets for Natural Stone - GF to SRVF (Elev. 2 & 3) | 290 | 288 | 185 | 99.31% | 0.000332% | 0.0002133% | 63.79% | 64.24%
|  | C-FIN-ENVLP-9700 | Fix Natural Stone All types- GF to SRVF (Elev. 2 & 3) | 6241 | 6242 | 5322 | 100% | 0.007196% | 0.006135% | 85.27% | 85.26%
|  | C-FIN-ENVLP-9720 | Fix Wooden Decorarive Features (Elev. 2 & 3) | 598 | 598 | 508 | 100% | 0.0006894% | 0.0005856% | 84.95% | 84.95%
|  | C-FIN-ENVLP-9740 | External Plaster - GF to SRVF (Elev. 2 & 3) | 165 | 164 | 140 | 99.39% | 0.0001891% | 0.0001614% | 84.85% | 85.37%
|  | Z123-C-FIN-18120 | Plaster Works Dry Area - Z123 - SRVF | 1375 | 1376 | 960 | 100.1% | 0.001586% | 0.001107% | 69.82% | 69.77%
|  | Z123-C-FIN-18160 | Roof Floor Terrazo Tiles Wet Area - Z123 - SRVF | 12242 | 12243 | 10406 | 100% | 0.01411% | 0.012% | 85% | 85%
|  | Z123-C-FIN-18310 | Wall Paint (Acrylic) Filter & Pump Room - Z123 - SRVF | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z123-C-FIN-18320 | Floor Epoxy Filter & Pump Room - Z123 - SRVF | 16 | 17 | 14 | 106.2% | 1.96e-05% | 1.614e-05% | 87.5% | 82.35%
|  | Z123-C-FIN-18350 | Ceiling Paint (Acrylic) Filter & Pump Room - Z123 - SRVF | 58 | 59 | 49 | 101.7% | 6.802e-05% | 5.649e-05% | 84.48% | 83.05%
|  | Z123-C-FIN-18390 | Fix False Ceiling Suspension Lift Lobby - Z123 - SRVF | 31 | 31 | 26 | 100% | 3.574e-05% | 2.997e-05% | 83.87% | 83.87%
|  | Z123-C-FIN-18400 | Porcelain Floor Tiles Lift Lobby - Z123 - SRVF | 115 | 115 | 98 | 100% | 0.0001326% | 0.000113% | 85.22% | 85.22%
|  | Z123-C-FIN-18410 | Wall Paint (Emulsion) Lift Lobby - Z123 - SRVF | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z123-C-FIN-18420 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z123 - SRVF | 31 | 31 | 26 | 100% | 3.574e-05% | 2.997e-05% | 83.87% | 83.87%
|  | Z123-C-FIN-18430 | Fix False Ceiling Gypsum Board Lift Lobby - Z123 - SRVF | 52 | 52 | 44 | 100% | 5.995e-05% | 5.072e-05% | 84.62% | 84.62%
|  | Z123-C-FIN-18450 | Ceiling Paint (Acrylic) GSM & MCC Rooms - Z123 - SRVF | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z123-C-FIN-18460 | Floor Epoxy GSM & MCC Rooms - Z123 - SRVF | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z123-C-FIN-18470 | Wall Paint (Acrylic) GSM & MCC Rooms - Z123 - SRVF | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z123-C-FIN-18480 | Floor Paint (Antifungal) Lift Shaft - Z123 - SRVF | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z123-C-FIN-18490 | Wall Paint (Antifungal) Lift Shaft - Z123 - SRVF | 271 | 272 | 230 | 100.4% | 0.0003136% | 0.0002651% | 84.87% | 84.56%
|  | Z2&3-C-FIN-18740 | Ceiling Paint (Anti-Carbonation) - Z2&3 - B2 | 771 | 770 | 655 | 99.87% | 0.0008877% | 0.0007551% | 84.95% | 85.06%
|  | Z2&3-C-FIN-18760 | Wall Paint (Anti-Carbonation) - Z2&3 - B2 | 771 | 770 | 501 | 99.87% | 0.0008877% | 0.0005776% | 64.98% | 65.06%
|  | Z2&3-C-FIN-18810 | Plaster Works - Z2&3 - B2 | 12074 | 12075 | 6774 | 100% | 0.01392% | 0.007809% | 56.1% | 56.1%
|  | Z2&3-C-FIN-18870 | Fix False Ceiling Suspension - Z2&3 - B2 | 29 | 28 | 24 | 96.55% | 3.228e-05% | 2.767e-05% | 82.76% | 85.71%
|  | Z2&3-C-FIN-18880 | Wall Paint (Emulsion) - Z2&3 - B2 | 119 | 119 | 30 | 100% | 0.0001372% | 3.458e-05% | 25.21% | 25.21%
|  | Z2&3-C-FIN-18890 | Porcelain Floor Tiles - Z2&3 - B2 | 119 | 119 | 30 | 100% | 0.0001372% | 3.458e-05% | 25.21% | 25.21%
|  | Z2&3-C-FIN-18900 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B2 | 47 | 48 | 40 | 102.1% | 5.534e-05% | 4.611e-05% | 85.11% | 83.33%
|  | Z2&3-C-FIN-18920 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - B2 | 59 | 59 | 15 | 100% | 6.802e-05% | 1.729e-05% | 25.42% | 25.42%
|  | Z2&3-C-FIN-18930 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - B2 | 95 | 94 | 24 | 98.95% | 0.0001084% | 2.767e-05% | 25.26% | 25.53%
|  | Z2&3-C-FIN-18940 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B2 | 17 | 17 | 4 | 100% | 1.96e-05% | 4.611e-06% | 23.53% | 23.53%
|  | Z2&3-C-FIN-18960 | Ceiling Paint (Emulsion) Travelator - Z2&3 - B2 | 26 | 26 | 6 | 100% | 2.997e-05% | 6.917e-06% | 23.08% | 23.08%
|  | Z2&3-C-FIN-18970 | Wall Paint (Emulsion) Travelator - Z2&3 - B2 | 647 | 647 | 162 | 100% | 0.0007459% | 0.0001868% | 25.04% | 25.04%
|  | Z2&3-C-FIN-18980 | Porcelain Floor Tiles Travelator - Z2&3 - B2 | 118 | 119 | 30 | 100.8% | 0.0001372% | 3.458e-05% | 25.42% | 25.21%
|  | Z2&3-C-FIN-19060 | Plaster Works - Z2&3 - B1 | 12782 | 12782 | 22095 | 100% | 0.01474% | 0.02547% | 172.9% | 172.9%
|  | Z2&3-C-FIN-19070 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - B1 | 58 | 59 | 49 | 101.7% | 6.802e-05% | 5.649e-05% | 84.48% | 83.05%
|  | Z2&3-C-FIN-19080 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - B1 | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z2&3-C-FIN-19090 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B1 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z2&3-C-FIN-19160 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B1 | 71 | 70 | 60 | 98.59% | 8.07e-05% | 6.917e-05% | 84.51% | 85.71%
|  | Z2&3-C-FIN-19170 | Wall Paint (Emulsion) - Z2&3 - B1 | 88 | 87 | 75 | 98.86% | 0.0001003% | 8.646e-05% | 85.23% | 86.21%
|  | Z2&3-C-FIN-19180 | Porcelain Floor Tiles - Z2&3 - B1 | 87 | 87 | 74 | 100% | 0.0001003% | 8.531e-05% | 85.06% | 85.06%
|  | Z2&3-C-FIN-19200 | Fix False Ceiling Suspension - Z2&3 - B1 | 42 | 42 | 36 | 100% | 4.842e-05% | 4.15e-05% | 85.71% | 85.71%
|  | Z2&3-C-FIN-19230 | Ceiling Paint (Anti-Carbonation) - Z2&3 - B1 | 770 | 770 | 654 | 100% | 0.0008877% | 0.0007539% | 84.94% | 84.94%
|  | Z2&3-C-FIN-19250 | Wall Paint (Anti-Carbonation) - Z2&3 - B1 | 770 | 770 | 654 | 100% | 0.0008877% | 0.0007539% | 84.94% | 84.94%
|  | Z2&3-C-FIN-19280 | Plaster Works Wet + Dry Area - Z2&3 - F1 | 5866 | 5866 | 4986 | 100% | 0.006762% | 0.005748% | 85% | 85%
|  | Z2&3-C-FIN-19300 | Fix False Ceiling Suspension - Z2&3 - F1 | 277 | 276 | 236 | 99.64% | 0.0003182% | 0.0002721% | 85.2% | 85.51%
|  | Z2&3-C-FIN-19310 | Wall Ceramic Tiles Wet Area - Z2&3 - F1 | 1090 | 1090 | 926 | 100% | 0.001257% | 0.001068% | 84.95% | 84.95%
|  | Z2&3-C-FIN-19320 | Floor Ceramic Tiles Wet Area - Z2&3 - F1 | 153 | 153 | 35 | 100% | 0.0001764% | 4.035e-05% | 22.88% | 22.88%
|  | Z2&3-C-FIN-19340 | Fix False Ceiling Gypsum Board - Z2&3 - F1 | 461 | 461 | 392 | 100% | 0.0005315% | 0.0004519% | 85.03% | 85.03%
|  | Z2&3-C-FIN-19350 | Fix False Ceiling Aluminum Tiles - Z2&3 - F1 | 277 | 277 | 235 | 100% | 0.0003193% | 0.0002709% | 84.84% | 84.84%
|  | Z2&3-C-FIN-19390 | Fix False Ceiling Suspension Lift Lobby - Z2&3 - F1 | 277 | 277 | 235 | 100% | 0.0003193% | 0.0002709% | 84.84% | 84.84%
|  | Z2&3-C-FIN-19400 | Wall Paint (Emulsion) Lift Lobby - Z2&3 - F1 | 646 | 647 | 549 | 100.2% | 0.0007459% | 0.0006329% | 84.98% | 84.85%
|  | Z2&3-C-FIN-19410 | Porcelain Floor Tiles Lift Lobby - Z2&3 - F1 | 1482 | 1484 | 1260 | 100.1% | 0.001711% | 0.001453% | 85.02% | 84.91%
|  | Z2&3-C-FIN-19430 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z2&3 - F1 | 276 | 277 | 235 | 100.4% | 0.0003193% | 0.0002709% | 85.14% | 84.84%
|  | Z2&3-C-FIN-19440 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - F1 | 460 | 461 | 391 | 100.2% | 0.0005315% | 0.0004508% | 85% | 84.82%
|  | Z2&3-C-FIN-19460 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - F1 | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z2&3-C-FIN-19470 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - F1 | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z2&3-C-FIN-19480 | Wall Paint (Acrylic) IT Room - Z2&3 - F1 | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z2&3-C-FIN-19490 | Anti Static Raised Floor IT Room - Z2&3 - F1 | 240 | 240 | 204 | 100% | 0.0002767% | 0.0002352% | 85% | 85%
|  | Z2&3-C-FIN-19510 | Ceiling Paint (Acrylic) IT Room - Z2&3 - F1 | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z2&3-C-FIN-19520 | Anti Fungal Paint - Z2&3 - F1 | 301 | 302 | 256 | 100.3% | 0.0003482% | 0.0002951% | 85.05% | 84.77%
|  | Z2&3-C-FIN-19550 | Plaster Works - Z2&3 - GF | 8758 | 8758 | 7444 | 100% | 0.0101% | 0.008582% | 85% | 85%
|  | Z2&3-C-FIN-19560 | Floor Epoxy Paint Garbage & Service Room - Z2&3 - GF | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z2&3-C-FIN-19590 | Ceiling Paint Garbage & Service Room (Acrylic/Emulsion)- Z2&3 - GF | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z2&3-C-FIN-19600 | Wall Paint Garbage & Service Room (Acrylic/Emulsion) - Z2&3 - GF | 648 | 647 | 551 | 99.85% | 0.0007459% | 0.0006352% | 85.03% | 85.16%
|  | Z2&3-C-FIN-19770 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - GF | 182 | 183 | 155 | 100.5% | 0.000211% | 0.0001787% | 85.16% | 84.7%
|  | Z2&3-C-FIN-19790 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z2&3 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z2&3-C-FIN-19800 | Fix False Ceiling Suspension Lift Lobby - Z2&3 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z2&3-C-FIN-19810 | Wall Paint (Emulsion) Lift Lobby - Z2&3 - GF | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z2&3-C-FIN-19820 | Porcelain Floor Tiles Lift Lobby - Z2&3 - GF | 511 | 511 | 434 | 100% | 0.0005891% | 0.0005003% | 84.93% | 84.93%
|  | Z2&3-C-FIN-19830 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - GF | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z2&3-C-FIN-19840 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - GF | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z2&3-C-FIN-19940 | Anti Fungal Paint all Shops - Z2&3 - GF | 302 | 302 | 257 | 100% | 0.0003482% | 0.0002963% | 85.1% | 85.1%
|  | Z2&3-C-FIN-20020 | Plaster Works Wet Area - Z2&3 - F2 | 7234 | 7235 | 6345 | 100% | 0.008341% | 0.007315% | 87.71% | 87.7%
|  | Z2&3-C-FIN-20050 | Plaster Works Dry Area - Z2&3 - F2 | 7234 | 7235 | 6345 | 100% | 0.008341% | 0.007315% | 87.71% | 87.7%
|  | Z2&3-C-FIN-20070 | Fix False Ceiling Suspension kitchen/Pantry - Z2&3 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z2&3-C-FIN-20080 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 1090 | 1090 | 926 | 100% | 0.001257% | 0.001068% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20090 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 152 | 153 | 129 | 100.7% | 0.0001764% | 0.0001487% | 84.87% | 84.31%
|  | Z2&3-C-FIN-20120 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - F2 | 651 | 651 | 553 | 100% | 0.0007505% | 0.0006375% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20130 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z2&3 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z2&3-C-FIN-20160 | Fix False Ceiling Suspension Bath - Z2&3 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z2&3-C-FIN-20170 | Wall Ceramic Tiles Bath - Z2&3 - F2 | 1091 | 1091 | 927 | 100% | 0.001258% | 0.001069% | 84.97% | 84.97%
|  | Z2&3-C-FIN-20180 | Floor Ceramic Tiles Bath - Z2&3 - F2 | 153 | 153 | 130 | 100% | 0.0001764% | 0.0001499% | 84.97% | 84.97%
|  | Z2&3-C-FIN-20210 | Fix False Ceiling Gypsum Board Bath - Z2&3 - F2 | 651 | 651 | 553 | 100% | 0.0007505% | 0.0006375% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20220 | Fix False Ceiling Aluminum Tiles Bath - Z2&3 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z2&3-C-FIN-20240 | Wall Paint (Emulsion) Garbage Room - Z2&3 - F2 | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z2&3-C-FIN-20250 | Floor Epoxy Paint Garbage Room - Z2&3 - F2 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z2&3-C-FIN-20280 | Ceiling Paint (Emulsion) Garbage Room - Z2&3 - F2 | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z2&3-C-FIN-20290 | Fix False Ceiling Suspension Lobby Passage & Offices- Z2&3 - F2 | 391 | 391 | 332 | 100% | 0.0004508% | 0.0003827% | 84.91% | 84.91%
|  | Z2&3-C-FIN-20300 | Wall Paint (Emulsion) Lobby Passage & Offices - Z2&3 - F2 | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z2&3-C-FIN-20310 | Porcelain Floor Tiles Passage & Offices - Z2&3 - F2 | 3843 | 3843 | 3267 | 100% | 0.00443% | 0.003766% | 85.01% | 85.01%
|  | Z2&3-C-FIN-20320 | Fix False Ceiling Aluminum Tiles Lobby Passage & Offices - Z2&3 - F2 | 391 | 391 | 333 | 100% | 0.0004508% | 0.0003839% | 85.17% | 85.17%
|  | Z2&3-C-FIN-20330 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - F2 | 651 | 651 | 553 | 100% | 0.0007505% | 0.0006375% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20350 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - F2 | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z2&3-C-FIN-20360 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - F2 | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z2&3-C-FIN-20400 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - F2 | 58 | 59 | 49 | 101.7% | 6.802e-05% | 5.649e-05% | 84.48% | 83.05%
|  | Z2&3-C-FIN-20410 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - F2 | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z2&3-C-FIN-20420 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F2 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z2&3-C-FIN-20450 | Plaster Works Wet Area - Z2&3 - RF | 6063 | 6064 | 5154 | 100% | 0.006991% | 0.005942% | 85.01% | 84.99%
|  | Z2&3-C-FIN-20480 | Plaster Works Dry Area - Z2&3 - RF | 6063 | 6064 | 5154 | 100% | 0.006991% | 0.005942% | 85.01% | 84.99%
|  | Z2&3-C-FIN-20500 | Fix False Ceiling Suspension kitchen/Pantry - Z2&3 - RF | 299 | 299 | 254 | 100% | 0.0003447% | 0.0002928% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20510 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 1090 | 1090 | 926 | 100% | 0.001257% | 0.001068% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20520 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 153 | 153 | 130 | 100% | 0.0001764% | 0.0001499% | 84.97% | 84.97%
|  | Z2&3-C-FIN-20550 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - RF | 499 | 498 | 424 | 99.8% | 0.0005741% | 0.0004888% | 84.97% | 85.14%
|  | Z2&3-C-FIN-20560 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z2&3 - RF | 300 | 299 | 255 | 99.67% | 0.0003447% | 0.000294% | 85% | 85.28%
|  | Z2&3-C-FIN-20590 | Fix False Ceiling Suspension Bath - Z2&3 - RF | 300 | 299 | 255 | 99.67% | 0.0003447% | 0.000294% | 85% | 85.28%
|  | Z2&3-C-FIN-20600 | Wall Ceramic Tiles Bath - Z2&3 - RF | 1090 | 1090 | 926 | 100% | 0.001257% | 0.001068% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20610 | Floor Ceramic Tiles Bath - Z2&3 - RF | 152 | 153 | 129 | 100.7% | 0.0001764% | 0.0001487% | 84.87% | 84.31%
|  | Z2&3-C-FIN-20640 | Fix False Ceiling Gypsum Board Bath - Z2&3 - RF | 498 | 498 | 423 | 100% | 0.0005741% | 0.0004876% | 84.94% | 84.94%
|  | Z2&3-C-FIN-20650 | Fix False Ceiling Aluminum Tiles Bath - Z2&3 - RF | 300 | 300 | 255 | 100% | 0.0003458% | 0.000294% | 85% | 85%
|  | Z2&3-C-FIN-20670 | Wall Paint (Emulsion) Garbage Room - Z2&3 - RF | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z2&3-C-FIN-20680 | Floor Epoxy Paint Garbage Room - Z2&3 - RF | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z2&3-C-FIN-20710 | Ceiling Paint (Emulsion) Garbage Room - Z2&3 - RF | 25 | 26 | 21 | 104% | 2.997e-05% | 2.421e-05% | 84% | 80.77%
|  | Z2&3-C-FIN-20750 | Fix False Ceiling Suspension Lobby Passage & Offices - Z2&3 - RF | 299 | 299 | 254 | 100% | 0.0003447% | 0.0002928% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20760 | Wall Paint (Emulsion) Lobby Passage & Offices - Z2&3 - RF | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z2&3-C-FIN-20770 | Porcelain Floor Tiles Passage & Offices - Z2&3 - RF | 2929 | 2930 | 2490 | 100% | 0.003378% | 0.002871% | 85.01% | 84.98%
|  | Z2&3-C-FIN-20780 | Fix False Ceiling Aluminum Tiles Lobby Passage & Offices - Z2&3 - RF | 299 | 299 | 254 | 100% | 0.0003447% | 0.0002928% | 84.95% | 84.95%
|  | Z2&3-C-FIN-20790 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - RF | 498 | 498 | 423 | 100% | 0.0005741% | 0.0004876% | 84.94% | 84.94%
|  | Z2&3-C-FIN-20810 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - RF | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z2&3-C-FIN-20820 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - RF | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z2&3-C-FIN-20830 | Floor Epoxy Paint Serv. Rooms - Z2&3 - RF | 18 | 16 | 12 | 88.89% | 1.845e-05% | 1.383e-05% | 66.67% | 75%
|  | Z2&3-C-FIN-20840 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - RF | 272 | 271 | 231 | 99.63% | 0.0003124% | 0.0002663% | 84.93% | 85.24%
|  | Z2&3-C-FIN-20850 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - RF | 271 | 271 | 230 | 100% | 0.0003124% | 0.0002651% | 84.87% | 84.87%
|  | Z2&3-C-FIN-20860 | Ceiling Paint (Emulsion) Travelator - Z2&3 - B1 | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z2&3-C-FIN-20870 | Wall Paint (Emulsion) Travelator - Z2&3 - B1 | 647 | 647 | 550 | 100% | 0.0007459% | 0.0006341% | 85.01% | 85.01%
|  | Z2&3-C-FIN-20880 | Porcelain Floor Tiles Travelator - Z2&3 - B1 | 88 | 88 | 75 | 100% | 0.0001014% | 8.646e-05% | 85.23% | 85.23%
|  | Z2&3-C-FIN-20990 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - F1 | 59 | 59 | 50 | 100% | 6.802e-05% | 5.764e-05% | 84.75% | 84.75%
|  | Z2&3-C-FIN-21000 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F1 | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z2&3-C-FIN-21020 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - F1 | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z2&3-C-FIN-21040 | Fix False Ceiling Gypsum Board Passage & Entrance - Z2&3 - GF | 182 | 183 | 155 | 100.5% | 0.000211% | 0.0001787% | 85.16% | 84.7%
|  | Z2&3-C-FIN-21060 | Fix False Ceiling Aluminum Tiles Passage & Entrance - Z2&3 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z2&3-C-FIN-21070 | Fix False Ceiling Suspension Passage & Entrance - Z2&3 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z2&3-C-FIN-21080 | Wall Paint (Emulsion) Passage & Entrance - Z2&3 - GF | 646 | 647 | 549 | 100.2% | 0.0007459% | 0.0006329% | 84.98% | 84.85%
|  | Z2&3-C-FIN-21090 | Porcelain Floor Tiles Passage & Entrance - Z2&3 - GF | 511 | 511 | 434 | 100% | 0.0005891% | 0.0005003% | 84.93% | 84.93%
|  | Z2&3-C-FIN-21100 | Fix False Ceiling Suspension Wet + Nursing Area - Z2&3 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z2&3-C-FIN-21110 | Wall Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 1090 | 1090 | 926 | 100% | 0.001257% | 0.001068% | 84.95% | 84.95%
|  | Z2&3-C-FIN-21120 | Floor Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 153 | 153 | 130 | 100% | 0.0001764% | 0.0001499% | 84.97% | 84.97%
|  | Z2&3-C-FIN-21140 | Fix False Ceiling Gypsum Board Wet + Nursing Area - Z2&3 - GF | 183 | 183 | 156 | 100% | 0.000211% | 0.0001798% | 85.25% | 85.25%
|  | Z2&3-C-FIN-21150 | Fix False Ceiling Aluminum Tiles Wet + Nursing Area - Z2&3 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z2&3-C-FIN-21200 | Fix False Ceiling Gypsum Board Passage H.Market - Z2&3 - GF | 182 | 183 | 155 | 100.5% | 0.000211% | 0.0001787% | 85.16% | 84.7%
|  | Z2&3-C-FIN-21220 | Fix False Ceiling Aluminum Tiles Passage H.Market - Z2&3 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z2&3-C-FIN-21230 | Fix False Ceiling Suspension Passage H.Market - Z2&3 - GF | 110 | 110 | 93 | 100% | 0.0001268% | 0.0001072% | 84.55% | 84.55%
|  | Z2&3-C-FIN-21250 | Floor Stamp Concrete Passage H.Market- Z2&3 - GF | 314 | 312 | 267 | 99.36% | 0.0003597% | 0.0003078% | 85.03% | 85.58%
|  | Z2&3-C-FIN-21260 | Floor Epoxy Paint IT & Maintanance Room - Z2&3 - GF | 17 | 17 | 14 | 100% | 1.96e-05% | 1.614e-05% | 82.35% | 82.35%
|  | Z2&3-C-FIN-21290 | Ceiling Paint IT & Maintanance Room (Acrylic/Emulsion)- Z2&3 - GF | 26 | 26 | 22 | 100% | 2.997e-05% | 2.536e-05% | 84.62% | 84.62%
|  | Z2&3-C-FIN-21300 | Wall Paint IT & Maintanance Room (Acrylic/Emulsion) - Z2&3 - GF | 648 | 647 | 551 | 99.85% | 0.0007459% | 0.0006352% | 85.03% | 85.16%
|  | Z2&3-C-FIN-21310 | Wall Paint Outside Area (Acrylic) - Z2&3 - F1 | 94 | 94 | 80 | 100% | 0.0001084% | 9.223e-05% | 85.11% | 85.11%
|  | Z2&3-C-FIN-21320 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - F1 | 720 | 720 | 471 | 100% | 0.00083% | 0.000543% | 65.42% | 65.42%
|  | Z2&3-C-FIN-21340 | Wall Paint Outside Area (Acrylic) - Z2&3 - RF | 95 | 94 | 81 | 98.95% | 0.0001084% | 9.338e-05% | 85.26% | 86.17%
|  | Z2&3-C-FIN-21350 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - RF | 720 | 720 | 612 | 100% | 0.00083% | 0.0007055% | 85% | 85%
|  | Z2&3-C-FIN-21360 | Floor Carpet Prayer Room - Z2&3 - F1 | 134 | 134 | 31 | 100% | 0.0001545% | 3.574e-05% | 23.13% | 23.13%
|  | Z2&3-C-FIN-SCASE-100 | on Staircase Acrylic Paint - Z2&3 - B2 - SRVF |  | 1 |  |  | 1.153e-06% |  |  | 0%
|  | Z2&3-C-FIN-SCASE-101 | on Staircase Floor Epoxy Paint - Z2&3 - B2 - SRVF | 16 | 16 | 14 | 100% | 1.845e-05% | 1.614e-05% | 87.5% | 87.5%
|  | Z2-C-GRBCH-11370 | Install Garbage Chute Cylinder - Z2 - GF to SRVF | 268 | 266 | 228 | 99.25% | 0.0003067% | 0.0002628% | 85.07% | 85.71%
|  | Z2-C-GRBCH-11380 | Install Garbage Chute Supporting Frame - Z2 - GF to SRVF | 268 | 266 | 228 | 99.25% | 0.0003067% | 0.0002628% | 85.07% | 85.71%
|  | Z2-C-GRBCH-11390 | Block & Plaster Garbage Room - Z2 - GF to SRVF | 172 | 172 | 79 | 100% | 0.0001983% | 9.107e-05% | 45.93% | 45.93%
|  | Z2-C-GRBCH-11400 | Install Garbage Chute Openings & Doors - Z2 - GF to SRVF | 268 | 266 | 228 | 99.25% | 0.0003067% | 0.0002628% | 85.07% | 85.71%
|  | Z2-C-GRBCH-11410 | Install Garbage Chute Roof Top Unit with All Provisions | 266 | 266 | 226 | 100% | 0.0003067% | 0.0002605% | 84.96% | 84.96%
|  | Z2-C-GRBCH-11420 | Install Garbage Chute Bottom Unit with All Provisions | 266 | 266 | 226 | 100% | 0.0003067% | 0.0002605% | 84.96% | 84.96%
| Div 10 | A11450 | External Drainage Pipes & Connections | 99 | 100 | 84 | 101% | 0.0001153% | 9.684e-05% | 84.85% | 84%
|  | A9700 | Install Man Holes Covers | 167 | 167 | 142 | 100% | 0.0001925% | 0.0001637% | 85.03% | 85.03%
|  | ADCE-MALL-WS-2200 | Installation of Water Meter & AADC Approval | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | T&C-10000 | Water Supply System Testing & Commissioning | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | T&C-10010 | Water Drainage System Testing & Commissioning | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z123-C-FIN-18210 | Fix Rain Water Outlets - Z123 - SRVF | 100 | 100 | 23 | 100% | 0.0001153% | 2.651e-05% | 23% | 23%
|  | Z123-C-MEP-14740 | Fix Drainage & Water Supply Pipes Block Wall - Z123 - SRVF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z123-C-MEP-14880 | Fix Water Supply Pipes - Z123 - SRVF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z123-C-MEP-14900 | Fix Drainage Pipes - Z123 - SRVF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z123-C-MEP-15010 | Fix Water Heater & Sanitary Accessories - Z123 - SRVF | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z123-C-MEP-15060 | Install GRP Water Tank & Accessories - Z123 - SRVF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z123-C-MEP-15070 | Install Filteration Plant System - Z123 - SRVF | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z2&3-C-MEP-15240 | Fix Drainage Pipes - Z2&3 - B2 | 249 | 250 | 411 | 100.4% | 0.0002882% | 0.0004738% | 165.1% | 164.4%
|  | Z2&3-C-MEP-15510 | Fix Drainage Pipes - Z2&3 - B1 | 249 | 250 | 212 | 100.4% | 0.0002882% | 0.0002444% | 85.14% | 84.8%
|  | Z2&3-C-MEP-15710 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15790 | Fix Drainage Pipes - Z2&3 - F1 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-15850 | Fix Water Supply Pipes - Z2&3 - F1 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-15940 | Fix Water Heater & Sanitary Accessories - Z2&3 - F1 | 334 | 333 | 284 | 99.7% | 0.0003839% | 0.0003274% | 85.03% | 85.29%
|  | Z2&3-C-MEP-16010 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16090 | Fix Drainage Pipes - Z2&3 - GF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-16150 | Fix Water Supply Pipes - Z2&3 - GF | 249 | 250 | 212 | 100.4% | 0.0002882% | 0.0002444% | 85.14% | 84.8%
|  | Z2&3-C-MEP-16260 | Fix Water Heater & Sanitary Accessories - Z2&3 - GF | 334 | 333 | 284 | 99.7% | 0.0003839% | 0.0003274% | 85.03% | 85.29%
|  | Z2&3-C-MEP-16310 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - F2 | 50 | 50 | 11 | 100% | 5.764e-05% | 1.268e-05% | 22% | 22%
|  | Z2&3-C-MEP-16390 | Fix Drainage Pipes - Z2&3 - F2 | 250 | 250 | 213 | 100% | 0.0002882% | 0.0002456% | 85.2% | 85.2%
|  | Z2&3-C-MEP-16450 | Fix Water Supply Pipes - Z2&3 - F2 | 249 | 250 | 212 | 100.4% | 0.0002882% | 0.0002444% | 85.14% | 84.8%
|  | Z2&3-C-MEP-16560 | Fix Water Heater & Sanitary Accessories - Z2&3 - F2 | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z2&3-C-MEP-16630 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16720 | Fix Drainage Pipes - Z2&3 - RF | 250 | 250 | 114 | 100% | 0.0002882% | 0.0001314% | 45.6% | 45.6%
|  | Z2&3-C-MEP-16780 | Fix Water Supply Pipes - Z2&3 - RF | 250 | 250 | 93 | 100% | 0.0002882% | 0.0001072% | 37.2% | 37.2%
|  | Z2&3-C-MEP-16900 | Fix Water Heater & Sanitary Accessories - Z2&3 - RF | 334 | 334 | 284 | 100% | 0.000385% | 0.0003274% | 85.03% | 85.03%
|  | Z2-C-CON-5940 | Fix MEP Provisions - Z2 - Raft | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-RSRS-11120 | Install Drainage Pipe Risers | 999 | 999 | 711 | 100% | 0.001152% | 0.0008197% | 71.17% | 71.17%
|  | Z2-C-RSRS-11130 | Install Water Supply Pipe Risers | 999 | 999 | 711 | 100% | 0.001152% | 0.0008197% | 71.17% | 71.17%
| Div 11 | T&C-9980 | Fire Fighting System Testing & Commissioning | 101 | 100 | 86 | 99.01% | 0.0001153% | 9.914e-05% | 85.15% | 86%
|  | Z123-C-MEP-14830 | Fix Fire Fighting Pipes - Z123 - SRVF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z123-C-MEP-14860 | Fix Fire Fighting Dropers - Z123 - SRVF | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z123-C-MEP-14980 | Fix Fire Hose Cabinets & Hose Reels - Z123 - SRVF | 51 | 50 | 43 | 98.04% | 5.764e-05% | 4.957e-05% | 84.31% | 86%
|  | Z123-C-MEP-14990 | Fix Sprinklers - Z123 - SRVF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-15250 | Fix Fire Fighting Pipes - Z2&3 - B2 | 500 | 500 | 825 | 100% | 0.0005764% | 0.0009511% | 165% | 165%
|  | Z2&3-C-MEP-15280 | Fix Fire Fighting Dropers - Z2&3 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15370 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - B2 | 51 | 50 | 43 | 98.04% | 5.764e-05% | 4.957e-05% | 84.31% | 86%
|  | Z2&3-C-MEP-15380 | Fix Sprinklers - Z2&3 - B2 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-15520 | Fix Fire Fighting Pipes - Z2&3 - B1 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-15550 | Fix Fire Fighting Dropers - Z2&3 - B1 | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z2&3-C-MEP-15640 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - B1 | 51 | 50 | 43 | 98.04% | 5.764e-05% | 4.957e-05% | 84.31% | 86%
|  | Z2&3-C-MEP-15650 | Fix Sprinklers - Z2&3 - B1 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-15800 | Fix Fire Fighting Pipes - Z2&3 - F1 | 499 | 500 | 424 | 100.2% | 0.0005764% | 0.0004888% | 84.97% | 84.8%
|  | Z2&3-C-MEP-15830 | Fix Fire Fighting Dropers - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15950 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15960 | Fix Sprinklers - Z2&3 - F1 | 500 | 500 | 496 | 100% | 0.0005764% | 0.0005718% | 99.2% | 99.2%
|  | Z2&3-C-MEP-16100 | Fix Fire Fighting Pipes - Z2&3 - GF | 499 | 500 | 424 | 100.2% | 0.0005764% | 0.0004888% | 84.97% | 84.8%
|  | Z2&3-C-MEP-16130 | Fix Fire Fighting Dropers - Z2&3 - GF | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z2&3-C-MEP-16230 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16240 | Fix Sprinklers - Z2&3 - GF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-16400 | Fix Fire Fighting Pipes - Z2&3 - F2 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-16430 | Fix Fire Fighting Dropers - Z2&3 - F2 | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z2&3-C-MEP-16540 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - F2 | 51 | 50 | 43 | 98.04% | 5.764e-05% | 4.957e-05% | 84.31% | 86%
|  | Z2&3-C-MEP-16550 | Fix Sprinklers - Z2&3 - F2 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-16730 | Fix Fire Fighting Pipes - Z2&3 - RF | 500 | 500 | 227 | 100% | 0.0005764% | 0.0002617% | 45.4% | 45.4%
|  | Z2&3-C-MEP-16760 | Fix Fire Fighting Dropers - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16870 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16880 | Fix Sprinklers - Z2&3 - RF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2-C-RSRS-11150 | Install Fire Fighting Pipe Risers | 997 | 1000 | 907 | 100.3% | 0.001153% | 0.001046% | 90.97% | 90.7%
| Div 12 | T&C-9920 | Chilled Water Pump Testing | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | T&C-9930 | Chilled Water System Flushing & Cleaning | 101 | 100 | 86 | 99.01% | 0.0001153% | 9.914e-05% | 85.15% | 86%
|  | T&C-9940 | HVAC Equipment Testing & Commissioning | 98 | 100 | 83 | 102% | 0.0001153% | 9.568e-05% | 84.69% | 83%
|  | T&C-9950 | Air Balancing FCU & FAHU | 98 | 100 | 83 | 102% | 0.0001153% | 9.568e-05% | 84.69% | 83%
|  | T&C-9960 | Chilled Water Balancing | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z123-C-FIN-18440 | Fix MEP Droppers Lift Lobby - Z123 - SRVF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z123-C-MEP-14840 | Fix Chill Water Pipes - Z123 - SRVF | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z123-C-MEP-14850 | Fix HVAC Ducts & Insulation - Z123 - SRVF | 667 | 667 | 567 | 100% | 0.0007689% | 0.0006536% | 85.01% | 85.01%
|  | Z123-C-MEP-14870 | Fix FCU - Z123 - SRVF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z123-C-MEP-15000 | Fix Grills & Diffusers - Z123 - SRVF | 286 | 286 | 243 | 100% | 0.0003297% | 0.0002801% | 84.97% | 84.97%
|  | Z123-C-MEP-15030 | Fix FAHU - Z123 - SRVF | 400 | 400 | 340 | 100% | 0.0004611% | 0.000392% | 85% | 85%
|  | Z123-C-MEP-15040 | Fix Chillers - Z123 - SRVF | 845 | 844 | 718 | 99.88% | 0.000973% | 0.0008277% | 84.97% | 85.07%
|  | Z123-C-MEP-15050 | Fix Extract Fans - Z123 - SRVF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z123-C-MEP-15090 | Install Chilled Water Pump - Z123 - SRVF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z123-C-MEP-15120 | Termination of MEP Equipment With Risers - Z123 - SRVF | 101 | 100 | 86 | 99.01% | 0.0001153% | 9.914e-05% | 85.15% | 86%
|  | Z123-C-MEP-15130 | Fix Pressurization Guages & Units Lift & Stair - Z123 - SRVF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z123-C-MEP-15140 | Fix Chemical Dosing Pot - Z123 - SRVF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-FIN-19370 | Fix MEP Droppers - Z2&3 - F1 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-FIN-19450 | Fix MEP Droppers Lift Lobby - Z2&3 - F1 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-FIN-19780 | Fix MEP Droppers Lift Lobby - Z2&3 - GF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-FIN-20140 | Fix MEP Droppers kitchen/Pantry - Z2&3 - F2 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-FIN-20230 | Fix MEP Droppers Bath - Z2&3 - F2 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-FIN-20340 | Fix MEP Droppers Lobby Passage & Offices- Z2&3 - F2 | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-FIN-20570 | Fix MEP Droppers kitchen/Pantry - Z2&3 - RF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-FIN-20660 | Fix MEP Droppers Bath - Z2&3 - RF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-FIN-20800 | Fix MEP Droppers Lobby Passage & Offices - Z2&3 - RF | 200 | 200 | 170 | 100% | 0.0002306% | 0.000196% | 85% | 85%
|  | Z2&3-C-MEP-15260 | Fix Chill Water Pipes - Z2&3 - B2 | 333 | 333 | 549 | 100% | 0.0003839% | 0.0006329% | 164.9% | 164.9%
|  | Z2&3-C-MEP-15270 | Fix HVAC Ducts & Insulation - Z2&3 - B2 | 665 | 667 | 1097 | 100.3% | 0.0007689% | 0.001265% | 165% | 164.5%
|  | Z2&3-C-MEP-15290 | Fix FCU - Z2&3 - B2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-15390 | Fix Grills & Diffusers - Z2&3 - B2 | 285 | 286 | 242 | 100.4% | 0.0003297% | 0.000279% | 84.91% | 84.62%
|  | Z2&3-C-MEP-15530 | Fix Chill Water Pipes - Z2&3 - B1 | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z2&3-C-MEP-15540 | Fix HVAC Ducts & Insulation - Z2&3 - B1 | 665 | 667 | 565 | 100.3% | 0.0007689% | 0.0006513% | 84.96% | 84.71%
|  | Z2&3-C-MEP-15560 | Fix FCU - Z2&3 - B1 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-15660 | Fix Grills & Diffusers - Z2&3 - B1 | 286 | 286 | 243 | 100% | 0.0003297% | 0.0002801% | 84.97% | 84.97%
|  | Z2&3-C-MEP-15810 | Fix Chill Water Pipes - Z2&3 - F1 | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z2&3-C-MEP-15820 | Fix HVAC Ducts & Insulation - Z2&3 - F1 | 667 | 667 | 567 | 100% | 0.0007689% | 0.0006536% | 85.01% | 85.01%
|  | Z2&3-C-MEP-15840 | Fix FCU - Z2&3 - F1 | 100 | 100 | 65 | 100% | 0.0001153% | 7.493e-05% | 65% | 65%
|  | Z2&3-C-MEP-15930 | Fix Grills & Diffusers - Z2&3 - F1 | 286 | 286 | 243 | 100% | 0.0003297% | 0.0002801% | 84.97% | 84.97%
|  | Z2&3-C-MEP-16110 | Fix Chill Water Pipes - Z2&3 - GF | 333 | 333 | 283 | 100% | 0.0003839% | 0.0003262% | 84.98% | 84.98%
|  | Z2&3-C-MEP-16120 | Fix HVAC Ducts & Insulation - Z2&3 - GF | 667 | 667 | 567 | 100% | 0.0007689% | 0.0006536% | 85.01% | 85.01%
|  | Z2&3-C-MEP-16140 | Fix FCU - Z2&3 - GF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-16250 | Fix Grills & Diffusers - Z2&3 - GF | 285 | 286 | 242 | 100.4% | 0.0003297% | 0.000279% | 84.91% | 84.62%
|  | Z2&3-C-MEP-16410 | Fix Chill Water Pipes - Z2&3 - F2 | 333 | 334 | 283 | 100.3% | 0.000385% | 0.0003262% | 84.98% | 84.73%
|  | Z2&3-C-MEP-16420 | Fix HVAC Ducts & Insulation - Z2&3 - F2 | 668 | 666 | 568 | 99.7% | 0.0007678% | 0.0006548% | 85.03% | 85.29%
|  | Z2&3-C-MEP-16440 | Fix FCU - Z2&3 - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-16580 | Fix Grills & Diffusers - Z2&3 - F2 | 286 | 286 | 243 | 100% | 0.0003297% | 0.0002801% | 84.97% | 84.97%
|  | Z2&3-C-MEP-16740 | Fix Chill Water Pipes - Z2&3 - RF | 332 | 333 | 125 | 100.3% | 0.0003839% | 0.0001441% | 37.65% | 37.54%
|  | Z2&3-C-MEP-16750 | Fix HVAC Ducts & Insulation - Z2&3 - RF | 667 | 666 | 304 | 99.85% | 0.0007678% | 0.0003505% | 45.58% | 45.65%
|  | Z2&3-C-MEP-16770 | Fix FCU - Z2&3 - RF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-16890 | Fix Grills & Diffusers - Z2&3 - RF | 286 | 286 | 243 | 100% | 0.0003297% | 0.0002801% | 84.97% | 84.97%
|  | Z2-C-RSRS-11140 | Install CHW Pipe Risers | 1000 | 1000 | 952 | 100% | 0.001153% | 0.001097% | 95.2% | 95.2%
|  | Z2-C-RSRS-11160 | Install Duct Risers | 998 | 1000 | 1058 | 100.2% | 0.001153% | 0.00122% | 106% | 105.8%
| Div 13 | T&C-10080 | Passenger Lift Testing & Commissioning | 101 | 100 | 86 | 99.01% | 0.0001153% | 9.914e-05% | 85.15% | 86%
|  | T&C-10090 | Travelators Testing & Commissioning | 101 | 100 | 86 | 99.01% | 0.0001153% | 9.914e-05% | 85.15% | 86%
|  | T&C-10110 | Escalator Testing & Commissioning | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10520 | Install Working Platform for PL-3 & 4 (B2 to SRVF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10530 | Install Steel Support Beams & Tracks PL-3 & 4 (B2 to SRVF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10540 | Repair Lift Shaft PL-3 & 4 (B2 to SRVF) | 100 | 100 | 89 | 100% | 0.0001153% | 0.0001026% | 89% | 89%
|  | Z2-C-LIFT-10550 | Install Working Platform for CL B2 to - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10560 | Install Steel Support Beams & Tracks CL B2 to - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10580 | Terminate Tracks & Cross Beams CL B2 to - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10610 | Install Lift Motors & Hydraulics CL B2 to - F2) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10620 | Install Lift Control Unit CL B2 to - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10630 | Power Connection & Test Runs CL B2 to - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10640 | Terminate Tracks & Cross Beams (B2 to GF) | 100 | 100 | 84 | 100% | 0.0001153% | 9.684e-05% | 84% | 84%
|  | Z2-C-LIFT-10650 | Install Lift Access Doors (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10660 | Install Lift Cabin (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10670 | Install Lift Motors, Cables, Counter Weight & Brakes (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10680 | Install Lift Control Unit (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10690 | Power Connection & Test Runs (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10700 | Install Working Platform for PL-5 (B2 to SRVF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10710 | Install Steel Support Beams & Tracks PL-5 (B2 to SRVF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10720 | Repair Lift Shaft PL-5 (B2 to SRVF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10730 | Terminate Tracks & Cross Beams (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10740 | Install Lift Access Doors (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10750 | Install Lift Cabin (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10760 | Install Lift Motors, Cables, Counter Weight & Brakes (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10770 | Install Lift Control Unit (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10780 | Power Connection & Test Runs (B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10790 | Install Working Platform for CL B2 to GF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10800 | Install Steel Support Beams & Tracks CL B2 to GF | 580 | 580 | 493 | 100% | 0.0006686% | 0.0005683% | 85% | 85%
|  | Z2-C-LIFT-10820 | Terminate Tracks & Cross Beams CL B2 to GF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10850 | Install Lift Motors & Hydraulics CL B2 to GF) | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10860 | Install Lift Control Unit CL B2 to GF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2-C-LIFT-10870 | Power Connection & Test Runs CL B2 to GF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
| Div 14 | Z123-C-MEP-15020 | Fix Gas Detectors - Z123 - SRVF | 167 | 167 | 142 | 100% | 0.0001925% | 0.0001637% | 85.03% | 85.03%
|  | Z123-C-MEP-15110 | Install LPG Tank - Z123 - SRVF | 167 | 167 | 142 | 100% | 0.0001925% | 0.0001637% | 85.03% | 85.03%
|  | Z2&3-C-MEP-16460 | Fix LPG Pipes - Z2&3 - F2 | 167 | 167 | 142 | 100% | 0.0001925% | 0.0001637% | 85.03% | 85.03%
|  | Z2&3-C-MEP-16570 | Fix Gas Detectors - Z2&3 - F2 | 167 | 167 | 142 | 100% | 0.0001925% | 0.0001637% | 85.03% | 85.03%
|  | Z2&3-C-MEP-16710 | Fix LPG Pipes - Z2&3 - RF | 167 | 167 | 142 | 100% | 0.0001925% | 0.0001637% | 85.03% | 85.03%
|  | Z2&3-C-MEP-16860 | Fix Gas Detectors - Z2&3 - RF | 166 | 167 | 141 | 100.6% | 0.0001925% | 0.0001625% | 84.94% | 84.43%
|  | Z2-C-RSRS-11170 | Install LPG Pipe Risers | 170 | 166 | 182 | 97.65% | 0.0001914% | 0.0002098% | 107.1% | 109.6%
| Div 15 | T&C-10040 | Telephone & Voice Evac. System Testing & Commissioning | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | T&C-10050 | Emergency Lighting System Testing & Commissioning | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | T&C-10060 | Access Control System Testing & Commissioning | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | T&C-10070 | Fire Alarm System Testing & Commissioning | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | T&C-10120 | BMS Testing & Commissioning | 249 | 250 | 211 | 100.4% | 0.0002882% | 0.0002432% | 84.74% | 84.4%
|  | T&C-10130 | Security System Testing & Commissioning | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z123-C-MEP-14750 | Fix G.I Box and conduits - Z123 - SRVF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z123-C-MEP-14760 | Fix ELV Trunkings - Z123 - SRVF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z123-C-MEP-14770 | Pull ELV Cables - Z123 - SRVF | 101 | 101 | 86 | 100% | 0.0001164% | 9.914e-05% | 85.15% | 85.15%
|  | Z123-C-MEP-14780 | Fix Power Cable Trays - Z123 - SRVF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z123-C-MEP-14790 | Pull Electricl Wires (Ceiling & Walls) - Z123 - SRVF | 101 | 101 | 86 | 100% | 0.0001164% | 9.914e-05% | 85.15% | 85.15%
|  | Z123-C-MEP-14800 | Pull Earthing & Power Cables - Z123 - SRVF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z123-C-MEP-14810 | Fix DBs - Z123 - SRVF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z123-C-MEP-14820 | Cable Terminations - Z123 - SRVF | 34 | 34 | 28 | 100% | 3.92e-05% | 3.228e-05% | 82.35% | 82.35%
|  | Z123-C-MEP-14910 | Fix CCTV Devices - Z123 - SRVF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z123-C-MEP-14920 | Fix Light Fixtures - Z123 - SRVF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z123-C-MEP-14930 | Fix Switches, Sockets & Isolators - Z123 - SRVF | 49 | 50 | 42 | 102% | 5.764e-05% | 4.842e-05% | 85.71% | 84%
|  | Z123-C-MEP-14940 | Fix Fire Alarm Devices - Z123 - SRVF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z123-C-MEP-14950 | Fix Telephone & Voice Evac. Devices - Z123 - SRVF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z123-C-MEP-14960 | Fix LCS & ACS Devices - Z123 - SRVF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z123-C-MEP-14970 | Fix Emergency & Exit Lights - Z123 - SRVF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z123-C-MEP-15100 | Install MCC Pannels - Z123 - SRVF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-15160 | Fix G.I Box and conduits - Z2&3 - B2 | 50 | 50 | 28 | 100% | 5.764e-05% | 3.228e-05% | 56% | 56%
|  | Z2&3-C-MEP-15170 | Fix ELV Trunkings - Z2&3 - B2 | 250 | 250 | 412 | 100% | 0.0002882% | 0.000475% | 164.8% | 164.8%
|  | Z2&3-C-MEP-15180 | Pull ELV Cables - Z2&3 - B2 | 100 | 101 | 85 | 101% | 0.0001164% | 9.799e-05% | 85% | 84.16%
|  | Z2&3-C-MEP-15190 | Fix Power Cable Trays - Z2&3 - B2 | 500 | 500 | 825 | 100% | 0.0005764% | 0.0009511% | 165% | 165%
|  | Z2&3-C-MEP-15200 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - B2 | 102 | 101 | 87 | 99.02% | 0.0001164% | 0.0001003% | 85.29% | 86.14%
|  | Z2&3-C-MEP-15210 | Pull Earthing & Power Cables - Z2&3 - B2 | 250 | 250 | 213 | 100% | 0.0002882% | 0.0002456% | 85.2% | 85.2%
|  | Z2&3-C-MEP-15220 | Fix DBs - Z2&3 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15230 | Cable Terminations - Z2&3 - B2 | 34 | 33 | 29 | 97.06% | 3.804e-05% | 3.343e-05% | 85.29% | 87.88%
|  | Z2&3-C-MEP-15300 | Fix CCTV Devices - Z2&3 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15310 | Fix Light Fixtures - Z2&3 - B2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-15320 | Fix Switches, Sockets & Isolators - Z2&3 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15330 | Fix Fire Alarm Devices - Z2&3 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15340 | Fix Telephone & Voice Evac. Devices - Z2&3 - B2 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-15350 | Fix LCS & ACS Devices - Z2&3 - B2 | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z2&3-C-MEP-15360 | Fix Emergency & Exit Lights - Z2&3 - B2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15430 | Fix G.I Box and conduits - Z2&3 - B1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15440 | Fix ELV Trunkings - Z2&3 - B1 | 249 | 250 | 212 | 100.4% | 0.0002882% | 0.0002444% | 85.14% | 84.8%
|  | Z2&3-C-MEP-15450 | Pull ELV Cables - Z2&3 - B1 | 101 | 101 | 86 | 100% | 0.0001164% | 9.914e-05% | 85.15% | 85.15%
|  | Z2&3-C-MEP-15460 | Fix Power Cable Trays - Z2&3 - B1 | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-15470 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - B1 | 102 | 101 | 87 | 99.02% | 0.0001164% | 0.0001003% | 85.29% | 86.14%
|  | Z2&3-C-MEP-15480 | Pull Earthing & Power Cables - Z2&3 - B1 | 252 | 250 | 214 | 99.21% | 0.0002882% | 0.0002467% | 84.92% | 85.6%
|  | Z2&3-C-MEP-15490 | Fix DBs - Z2&3 - B1 | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z2&3-C-MEP-15500 | Cable Terminations - Z2&3 - B1 | 34 | 33 | 29 | 97.06% | 3.804e-05% | 3.343e-05% | 85.29% | 87.88%
|  | Z2&3-C-MEP-15570 | Fix CCTV Devices - Z2&3 - B1 | 50 | 50 | 11 | 100% | 5.764e-05% | 1.268e-05% | 22% | 22%
|  | Z2&3-C-MEP-15580 | Fix Light Fixtures - Z2&3 - B1 | 100 | 100 | 23 | 100% | 0.0001153% | 2.651e-05% | 23% | 23%
|  | Z2&3-C-MEP-15590 | Fix Switches, Sockets & Isolators - Z2&3 - B1 | 50 | 50 | 11 | 100% | 5.764e-05% | 1.268e-05% | 22% | 22%
|  | Z2&3-C-MEP-15600 | Fix Fire Alarm Devices - Z2&3 - B1 | 50 | 50 | 11 | 100% | 5.764e-05% | 1.268e-05% | 22% | 22%
|  | Z2&3-C-MEP-15610 | Fix Telephone & Voice Evac. Devices - Z2&3 - B1 | 250 | 250 | 57 | 100% | 0.0002882% | 6.571e-05% | 22.8% | 22.8%
|  | Z2&3-C-MEP-15620 | Fix LCS & ACS Devices - Z2&3 - B1 | 50 | 50 | 11 | 100% | 5.764e-05% | 1.268e-05% | 22% | 22%
|  | Z2&3-C-MEP-15630 | Fix Emergency & Exit Lights - Z2&3 - B1 | 50 | 50 | 11 | 100% | 5.764e-05% | 1.268e-05% | 22% | 22%
|  | Z2&3-C-MEP-15700 | Fix G.I Box and conduits - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15720 | Fix ELV Trunkings - Z2&3 - F1 | 250 | 250 | 213 | 100% | 0.0002882% | 0.0002456% | 85.2% | 85.2%
|  | Z2&3-C-MEP-15730 | Pull ELV Cables - Z2&3 - F1 | 101 | 101 | 105 | 100% | 0.0001164% | 0.000121% | 104% | 104%
|  | Z2&3-C-MEP-15740 | Fix Power Cable Trays - Z2&3 - F1 | 501 | 500 | 426 | 99.8% | 0.0005764% | 0.0004911% | 85.03% | 85.2%
|  | Z2&3-C-MEP-15750 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - F1 | 101 | 101 | 105 | 100% | 0.0001164% | 0.000121% | 104% | 104%
|  | Z2&3-C-MEP-15760 | Pull Earthing & Power Cables - Z2&3 - F1 | 250 | 250 | 259 | 100% | 0.0002882% | 0.0002986% | 103.6% | 103.6%
|  | Z2&3-C-MEP-15770 | Fix DBs - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15780 | Cable Terminations - Z2&3 - F1 | 34 | 33 | 29 | 97.06% | 3.804e-05% | 3.343e-05% | 85.29% | 87.88%
|  | Z2&3-C-MEP-15860 | Fix CCTV Devices - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15870 | Fix Light Fixtures - Z2&3 - F1 | 101 | 100 | 76 | 99.01% | 0.0001153% | 8.761e-05% | 75.25% | 76%
|  | Z2&3-C-MEP-15880 | Fix Switches, Sockets & Isolators - Z2&3 - F1 | 50 | 50 | 47 | 100% | 5.764e-05% | 5.418e-05% | 94% | 94%
|  | Z2&3-C-MEP-15890 | Fix Fire Alarm Devices - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15900 | Fix Telephone & Voice Evac. Devices - Z2&3 - F1 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-15910 | Fix LCS & ACS Devices - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-15920 | Fix Emergency & Exit Lights - Z2&3 - F1 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16000 | Fix G.I Box and conduits - Z2&3 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16020 | Fix ELV Trunkings - Z2&3 - GF | 249 | 250 | 211 | 100.4% | 0.0002882% | 0.0002432% | 84.74% | 84.4%
|  | Z2&3-C-MEP-16030 | Pull ELV Cables - Z2&3 - GF | 101 | 101 | 86 | 100% | 0.0001164% | 9.914e-05% | 85.15% | 85.15%
|  | Z2&3-C-MEP-16040 | Fix Power Cable Trays - Z2&3 - GF | 500 | 500 | 425 | 100% | 0.0005764% | 0.0004899% | 85% | 85%
|  | Z2&3-C-MEP-16050 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - GF | 102 | 101 | 91 | 99.02% | 0.0001164% | 0.0001049% | 89.22% | 90.1%
|  | Z2&3-C-MEP-16060 | Pull Earthing & Power Cables - Z2&3 - GF | 252 | 250 | 226 | 99.21% | 0.0002882% | 0.0002605% | 89.68% | 90.4%
|  | Z2&3-C-MEP-16070 | Fix DBs - Z2&3 - GF | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z2&3-C-MEP-16080 | Cable Terminations - Z2&3 - GF | 33 | 33 | 28 | 100% | 3.804e-05% | 3.228e-05% | 84.85% | 84.85%
|  | Z2&3-C-MEP-16160 | Fix CCTV Devices - Z2&3 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16170 | Fix Light Fixtures - Z2&3 - GF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-16180 | Fix Switches, Sockets & Isolators - Z2&3 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16190 | Fix Fire Alarm Devices - Z2&3 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16200 | Fix Telephone & Voice Evac. Devices - Z2&3 - GF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-16210 | Fix LCS & ACS Devices - Z2&3 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16220 | Fix Emergency & Exit Lights - Z2&3 - GF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16300 | Fix G.I Box and conduits - Z2&3 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16320 | Fix ELV Trunkings - Z2&3 - F2 | 249 | 250 | 212 | 100.4% | 0.0002882% | 0.0002444% | 85.14% | 84.8%
|  | Z2&3-C-MEP-16330 | Pull ELV Cables - Z2&3 - F2 | 101 | 101 | 82 | 100% | 0.0001164% | 9.453e-05% | 81.19% | 81.19%
|  | Z2&3-C-MEP-16340 | Fix Power Cable Trays - Z2&3 - F2 | 501 | 500 | 426 | 99.8% | 0.0005764% | 0.0004911% | 85.03% | 85.2%
|  | Z2&3-C-MEP-16350 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - F2 | 101 | 101 | 82 | 100% | 0.0001164% | 9.453e-05% | 81.19% | 81.19%
|  | Z2&3-C-MEP-16360 | Pull Earthing & Power Cables - Z2&3 - F2 | 250 | 250 | 205 | 100% | 0.0002882% | 0.0002363% | 82% | 82%
|  | Z2&3-C-MEP-16370 | Fix DBs - Z2&3 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16380 | Cable Terminations - Z2&3 - F2 | 34 | 33 | 29 | 97.06% | 3.804e-05% | 3.343e-05% | 85.29% | 87.88%
|  | Z2&3-C-MEP-16470 | Fix CCTV Devices - Z2&3 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16480 | Fix Light Fixtures - Z2&3 - F2 | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-16490 | Fix Switches, Sockets & Isolators - Z2&3 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16500 | Fix Fire Alarm Devices - Z2&3 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16510 | Fix Telephone & Voice Evac. Devices - Z2&3 - F2 | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-16520 | Fix LCS & ACS Devices - Z2&3 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16530 | Fix Emergency & Exit Lights - Z2&3 - F2 | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16620 | Fix G.I Box and conduits - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16640 | Fix ELV Trunkings - Z2&3 - RF | 250 | 250 | 93 | 100% | 0.0002882% | 0.0001072% | 37.2% | 37.2%
|  | Z2&3-C-MEP-16650 | Pull ELV Cables - Z2&3 - RF | 102 | 101 | 87 | 99.02% | 0.0001164% | 0.0001003% | 85.29% | 86.14%
|  | Z2&3-C-MEP-16660 | Fix Power Cable Trays - Z2&3 - RF | 500 | 500 | 187 | 100% | 0.0005764% | 0.0002156% | 37.4% | 37.4%
|  | Z2&3-C-MEP-16670 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - RF | 102 | 101 | 87 | 99.02% | 0.0001164% | 0.0001003% | 85.29% | 86.14%
|  | Z2&3-C-MEP-16680 | Pull Earthing & Power Cables - Z2&3 - RF | 249 | 250 | 212 | 100.4% | 0.0002882% | 0.0002444% | 85.14% | 84.8%
|  | Z2&3-C-MEP-16690 | Fix DBs - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16700 | Cable Terminations - Z2&3 - RF | 33 | 34 | 28 | 103% | 3.92e-05% | 3.228e-05% | 84.85% | 82.35%
|  | Z2&3-C-MEP-16790 | Fix CCTV Devices - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16800 | Fix Light Fixtures - Z2&3 - RF | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 85%
|  | Z2&3-C-MEP-16810 | Fix Switches, Sockets & Isolators - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16820 | Fix Fire Alarm Devices - Z2&3 - RF | 50 | 50 | 43 | 100% | 5.764e-05% | 4.957e-05% | 86% | 86%
|  | Z2&3-C-MEP-16830 | Fix Telephone & Voice Evac. Devices - Z2&3 - RF | 250 | 250 | 212 | 100% | 0.0002882% | 0.0002444% | 84.8% | 84.8%
|  | Z2&3-C-MEP-16840 | Fix LCS & ACS Devices - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2&3-C-MEP-16850 | Fix Emergency & Exit Lights - Z2&3 - RF | 50 | 50 | 42 | 100% | 5.764e-05% | 4.842e-05% | 84% | 84%
|  | Z2-C-RSRS-11180 | Install Cable treys & Trunking Risers | 251 | 249 | 245 | 99.2% | 0.0002871% | 0.0002824% | 97.61% | 98.39%
|  | Z2-C-RSRS-11190 | Install Busbar Risers | 251 | 250 | 213 | 99.6% | 0.0002882% | 0.0002456% | 84.86% | 85.2%
Z3 | Div 02 | C-EW-10490 | Waterproof Membrane on Gunite Wall - Z3-B2 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
|  | C-EW-10520 | Waterproof Membrane on Gunite Wall - Z3-B1 | 200 | 200 |  | 100% | 0.0002306% |  | 0% | 0%
| Div 03 | Z3-C-CON-5840 | PCC Blind Concrete - Z3 - Lift Pit | 4 | 4 | 0 | 100% | 4.611e-06% |  | 0% | 0%
|  | Z3-C-CON-5860 | Protection Screed - Z3 - Lift Pit | 26 | 26 | 0 | 100% | 2.997e-05% |  | 0% | 0%
|  | Z3-C-CON-5870 | Fix Rebar - Z3 - Lift Pit | 248 | 249 | 2 | 100.4% | 0.0002871% | 2.306e-06% | 0.8065% | 0.8032%
|  | Z3-C-CON-5890 | Pour Concrete - Z3 - Lift Pit | 72 | 72 | 15 | 100% | 8.3e-05% | 1.729e-05% | 20.83% | 20.83%
|  | Z3-C-CON-5900 | PCC Blind Concrete - Z3 - Raft | 148 | 148 | 126 | 100% | 0.0001706% | 0.0001453% | 85.14% | 85.14%
|  | Z3-C-CON-5920 | Protection Screed - Z3 - Raft | 74 | 74 | 63 | 100% | 8.531e-05% | 7.263e-05% | 85.14% | 85.14%
|  | Z3-C-CON-5930 | Fix Rebar - Z3 - Raft | 13737 | 13736 | 11676 | 99.99% | 0.01584% | 0.01346% | 85% | 85%
|  | Z3-C-CON-5950 | Fix Formwork - Z3 - Raft | 196 | 196 | 167 | 100% | 0.000226% | 0.0001925% | 85.2% | 85.2%
|  | Z3-C-CON-5960 | Pour Concrete - Z3 - Raft | 3317 | 3317 | 2819 | 100% | 0.003824% | 0.00325% | 84.99% | 84.99%
|  | Z3-C-CON-5970 | Fix Rebar Columns - Z3 - B2 | 2265 | 2265 | 1925 | 100% | 0.002611% | 0.002219% | 84.99% | 84.99%
|  | Z3-C-CON-5980 | Fix Formwork Columns - Z3 - B2 | 668 | 667 | 91 | 99.85% | 0.0007689% | 0.0001049% | 13.62% | 13.64%
|  | Z3-C-CON-5990 | Pour Concrete Columns - Z3 - B2 | 132 | 132 | 18 | 100% | 0.0001522% | 2.075e-05% | 13.64% | 13.64%
|  | Z3-C-CON-6000 | Fix Rebar Retaining Walls - Z3 - B2 | 1433 | 1432 | 1218 | 99.93% | 0.001651% | 0.001404% | 85% | 85.06%
|  | Z3-C-CON-6010 | Fix Formwork Retaining Walls - Z3 - B2 | 1172 | 1171 | 159 | 99.91% | 0.00135% | 0.0001833% | 13.57% | 13.58%
|  | Z3-C-CON-6020 | Pour Concrete Retaining Walls - Z3 - B2 | 242 | 242 | 2 | 100% | 0.000279% | 2.306e-06% | 0.8264% | 0.8264%
|  | Z3-C-CON-6030 | Pour Concrete Core Walls - Z3 - B2 | 136 | 136 | 1 | 100% | 0.0001568% | 1.153e-06% | 0.7353% | 0.7353%
|  | Z3-C-CON-6040 | Fix Rebar Core Walls - Z3 - B2 | 949 | 949 | 9 | 100% | 0.001094% | 1.038e-05% | 0.9484% | 0.9484%
|  | Z3-C-CON-6050 | Fix Formwork Core Walls - Z3 - B2 | 936 | 936 | 9 | 100% | 0.001079% | 1.038e-05% | 0.9615% | 0.9615%
|  | Z3-C-CON-6060 | Fix Formwork Stairs - Z3 - B2 | 3 | 3 | 3 | 100% | 3.458e-06% | 3.458e-06% | 100% | 100%
|  | Z3-C-CON-6070 | Fix Rebar Stairs - Z3 - B2 | 32 | 32 | 4 | 100% | 3.689e-05% | 4.611e-06% | 12.5% | 12.5%
|  | Z3-C-CON-6080 | Pour Concrete Stairs - Z3 - B2 | 8 | 8 | 0 | 100% | 9.223e-06% |  | 0% | 0%
|  | Z3-C-CON-6090 | Fix Rebar Retaining Walls - Z3 - B1 | 1138 | 1138 | 68 | 100% | 0.001312% | 7.839e-05% | 5.975% | 5.975%
|  | Z3-C-CON-6100 | Fix Formwork Retaining Walls - Z3 - B1 | 1171 | 1171 | 70 | 100% | 0.00135% | 8.07e-05% | 5.978% | 5.978%
|  | Z3-C-CON-6110 | Pour Concrete Retaining Walls - Z3 - B1 | 240 | 242 | 112 | 100.8% | 0.000279% | 0.0001291% | 46.67% | 46.28%
|  | Z3-C-CON-6120 | Fix Formwork Core Walls - Z3 - B1 | 945 | 945 | 57 | 100% | 0.001089% | 6.571e-05% | 6.032% | 6.032%
|  | Z3-C-CON-6130 | Fix Rebar Core Walls - Z3 - B1 | 914 | 913 | 629 | 99.89% | 0.001053% | 0.0007251% | 68.82% | 68.89%
|  | Z3-C-CON-6140 | Pour Concrete Core Walls - Z3 - B1 | 138 | 138 | 8 | 100% | 0.0001591% | 9.223e-06% | 5.797% | 5.797%
|  | Z3-C-CON-6150 | Fix Rebar Columns - Z3 - B1 | 1735 | 1735 | 1475 | 100% | 0.002% | 0.0017% | 85.01% | 85.01%
|  | Z3-C-CON-6160 | Fix Formwork Columns - Z3 - B1 | 743 | 743 | 45 | 100% | 0.0008565% | 5.188e-05% | 6.057% | 6.057%
|  | Z3-C-CON-6170 | Pour Concrete Columns - Z3 - B1 | 146 | 146 | 9 | 100% | 0.0001683% | 1.038e-05% | 6.164% | 6.164%
|  | Z3-C-CON-6180 | Fix Formwork Stairs - Z3 - B1 | 4 | 3 | 0 | 75% | 3.458e-06% |  | 0% | 0%
|  | Z3-C-CON-6190 | Fix Rebar Stairs - Z3 - B1 | 32 | 32 | 11 | 100% | 3.689e-05% | 1.268e-05% | 34.38% | 34.38%
|  | Z3-C-CON-6200 | Pour Concrete Stairs - Z3 - B1 | 8 | 8 | 1 | 100% | 9.223e-06% | 1.153e-06% | 12.5% | 12.5%
|  | Z3-C-CON-6210 | Fix Formwork Slabs - Z3 - B1 | 3040 | 3041 | 91 | 100% | 0.003506% | 0.0001049% | 2.993% | 2.992%
|  | Z3-C-CON-6220 | Fix Rebar Slabs - Z3 - B1 | 4028 | 4028 | 81 | 100% | 0.004644% | 9.338e-05% | 2.011% | 2.011%
|  | Z3-C-CON-6230 | Pour Concrete Slabs - Z3 - B1 | 1036 | 1036 | 881 | 100% | 0.001194% | 0.001016% | 85.04% | 85.04%
|  | Z3-C-CON-6250 | Fix Rebar Core Walls - Z3 - GF | 1707 | 1707 | 85 | 100% | 0.001968% | 9.799e-05% | 4.979% | 4.979%
|  | Z3-C-CON-6260 | Fix Formwork Core Walls - Z3 - GF | 1721 | 1721 | 1538 | 100% | 0.001984% | 0.001773% | 89.37% | 89.37%
|  | Z3-C-CON-6270 | Pour Concrete Core Walls - Z3 - GF | 236 | 236 | 132 | 100% | 0.0002721% | 0.0001522% | 55.93% | 55.93%
|  | Z3-C-CON-6280 | Fix Rebar Columns - Z3 - GF | 2256 | 2256 | 113 | 100% | 0.002601% | 0.0001303% | 5.009% | 5.009%
|  | Z3-C-CON-6290 | Fix Formwork Columns - Z3 - GF | 1136 | 1136 | 1015 | 100% | 0.00131% | 0.00117% | 89.35% | 89.35%
|  | Z3-C-CON-6300 | Pour Concrete Columns - Z3 - GF | 224 | 224 | 126 | 100% | 0.0002582% | 0.0001453% | 56.25% | 56.25%
|  | Z3-C-CON-6310 | Fix Formwork Stairs - Z3 - GF | 4 | 4 | 1 | 100% | 4.611e-06% | 1.153e-06% | 25% | 25%
|  | Z3-C-CON-6320 | Fix Rebar Stairs - Z3 - GF | 16 | 16 | 14 | 100% | 1.845e-05% | 1.614e-05% | 87.5% | 87.5%
|  | Z3-C-CON-6330 | Pour Concrete Stairs - Z3 - GF | 10 | 10 | 6 | 100% | 1.153e-05% | 6.917e-06% | 60% | 60%
|  | Z3-C-CON-6340 | Fix Formwork Slabs - Z3 - GF | 2844 | 2843 | 1501 | 99.96% | 0.003277% | 0.00173% | 52.78% | 52.8%
|  | Z3-C-CON-6350 | Fix Rebar Slabs - Z3 - GF | 7049 | 7049 | 705 | 100% | 0.008126% | 0.0008127% | 10% | 10%
|  | Z3-C-CON-6360 | Pour Concrete Slabs - Z3 - GF | 1278 | 1278 | 128 | 100% | 0.001473% | 0.0001476% | 10.02% | 10.02%
|  | Z3-C-CON-6380 | Fix Formwork Slabs - Z3 - F1 | 2843 | 2843 | 1595 | 100% | 0.003277% | 0.001839% | 56.1% | 56.1%
|  | Z3-C-CON-6390 | Fix Rebar Slabs - Z3 - F1 | 3628 | 3627 | 1814 | 99.97% | 0.004181% | 0.002091% | 50% | 50.01%
|  | Z3-C-CON-6410 | Pour Concrete Slabs - Z3 - F1 | 988 | 988 | 247 | 100% | 0.001139% | 0.0002847% | 25% | 25%
|  | Z3-C-CON-6420 | Fix Rebar Core Walls - Z3 - F1 | 1686 | 1686 | 422 | 100% | 0.001944% | 0.0004865% | 25.03% | 25.03%
|  | Z3-C-CON-6430 | Fix Formwork Core Walls - Z3 - F1 | 1725 | 1724 | 1121 | 99.94% | 0.001987% | 0.001292% | 64.99% | 65.02%
|  | Z3-C-CON-6440 | Pour Concrete Core Walls - Z3 - F1 | 240 | 240 | 240 | 100% | 0.0002767% | 0.0002767% | 100% | 100%
|  | Z3-C-CON-6450 | Fix Rebar Columns - Z3 - F1 | 2285 | 2285 | 571 | 100% | 0.002634% | 0.0006583% | 24.99% | 24.99%
|  | Z3-C-CON-6460 | Fix Formwork Columns - Z3 - F1 | 1130 | 1130 | 734 | 100% | 0.001303% | 0.0008462% | 64.96% | 64.96%
|  | Z3-C-CON-6470 | Pour Concrete Columns - Z3 - F1 | 224 | 224 | 146 | 100% | 0.0002582% | 0.0001683% | 65.18% | 65.18%
|  | Z3-C-CON-6480 | Fix Formwork Stairs - Z3 - F1 | 4 | 4 | 3 | 100% | 4.611e-06% | 3.458e-06% | 75% | 75%
|  | Z3-C-CON-6490 | Fix Rebar Stairs - Z3 - F1 | 16 | 16 | 14 | 100% | 1.845e-05% | 1.614e-05% | 87.5% | 87.5%
|  | Z3-C-CON-6500 | Pour Concrete Stairs - Z3 - F1 | 10 | 10 | 10 | 100% | 1.153e-05% | 1.153e-05% | 100% | 100%
|  | Z3-C-CON-6510 | Fix Rebar Slabs - Z3 - F2 | 3726 | 3726 | 3167 | 100% | 0.004295% | 0.003651% | 85% | 85%
|  | Z3-C-CON-6520 | Fix Formwork Slabs - Z3 - F2 | 2832 | 2832 | 5664 | 100% | 0.003265% | 0.00653% | 200% | 200%
|  | Z3-C-CON-6530 | Pour Concrete Slabs - Z3 - F2 | 994 | 994 | 845 | 100% | 0.001146% | 0.0009741% | 85.01% | 85.01%
|  | Z3-C-CON-6550 | Fix Rebar Core Walls - Z3 - F2 | 1114 | 1114 | 947 | 100% | 0.001284% | 0.001092% | 85.01% | 85.01%
|  | Z3-C-CON-6560 | Fix Formwork Core Walls - Z3 - F2 | 1018 | 1018 | 865 | 100% | 0.001174% | 0.0009972% | 84.97% | 84.97%
|  | Z3-C-CON-6570 | Pour Concrete Core Walls - Z3 - F2 | 144 | 144 | 122 | 100% | 0.000166% | 0.0001406% | 84.72% | 84.72%
|  | Z3-C-CON-6580 | Fix Rebar Columns - Z3 - F2 | 1557 | 1558 | 1323 | 100.1% | 0.001796% | 0.001525% | 84.97% | 84.92%
|  | Z3-C-CON-6590 | Fix Formwork Columns - Z3 - F2 | 727 | 727 | 618 | 100% | 0.0008381% | 0.0007124% | 85.01% | 85.01%
|  | Z3-C-CON-6600 | Pour Concrete Columns - Z3 - F2 | 142 | 142 | 121 | 100% | 0.0001637% | 0.0001395% | 85.21% | 85.21%
|  | Z3-C-CON-6610 | Fix Formwork Stairs - Z3 - F2 | 4 | 4 | 3 | 100% | 4.611e-06% | 3.458e-06% | 75% | 75%
|  | Z3-C-CON-6620 | Fix Rebar Stairs - Z3 - F2 | 16 | 16 | 14 | 100% | 1.845e-05% | 1.614e-05% | 87.5% | 87.5%
|  | Z3-C-CON-6630 | Pour Concrete Stairs - Z3 - F2 | 10 | 10 | 8 | 100% | 1.153e-05% | 9.223e-06% | 80% | 80%
|  | Z3-C-CON-6640 | Fix Formwork Slabs - Z3 - RF | 2831 | 2831 | 2406 | 100% | 0.003264% | 0.002774% | 84.99% | 84.99%
|  | Z3-C-CON-6650 | Fix Rebar Slabs - Z3 - RF | 3707 | 3706 | 3150 | 99.97% | 0.004272% | 0.003631% | 84.97% | 85%
|  | Z3-C-CON-6660 | Pour Concrete Slabs - Z3 - RF | 990 | 990 | 841 | 100% | 0.001141% | 0.0009695% | 84.95% | 84.95%
|  | Z3-C-CON-6680 | Fix Rebar Core Walls - Z3 - RF | 1096 | 1095 | 932 | 99.91% | 0.001262% | 0.001074% | 85.04% | 85.11%
|  | Z3-C-CON-6690 | Fix Formwork Core Walls - Z3 - RF | 1015 | 1015 | 863 | 100% | 0.00117% | 0.0009949% | 85.02% | 85.02%
|  | Z3-C-CON-6700 | Pour Concrete Core Walls - Z3 - RF | 144 | 144 | 122 | 100% | 0.000166% | 0.0001406% | 84.72% | 84.72%
|  | Z3-C-CON-6710 | Fix Rebar Columns - Z3 - RF | 1275 | 1275 | 1084 | 100% | 0.00147% | 0.00125% | 85.02% | 85.02%
|  | Z3-C-CON-6720 | Fix Formwork Columns - Z3 - RF | 563 | 563 | 479 | 100% | 0.000649% | 0.0005522% | 85.08% | 85.08%
|  | Z3-C-CON-6730 | Pour Concrete Columns - Z3 - RF | 112 | 114 | 95 | 101.8% | 0.0001314% | 0.0001095% | 84.82% | 83.33%
|  | Z3-C-CON-6740 | Fix Formwork Stairs - Z3 - RF | 3 | 4 | 3 | 133.3% | 4.611e-06% | 3.458e-06% | 100% | 75%
|  | Z3-C-CON-6750 | Fix Rebar Stairs - Z3 - RF | 14 | 14 | 12 | 100% | 1.614e-05% | 1.383e-05% | 85.71% | 85.71%
|  | Z3-C-CON-6760 | Pour Concrete Stairs - Z3 - RF | 8 | 8 | 7 | 100% | 9.223e-06% | 8.07e-06% | 87.5% | 87.5%
|  | Z3-C-CON-6770 | Fix Formwork Slabs - Z3 - SRVF | 2426 | 2426 | 2062 | 100% | 0.002797% | 0.002377% | 85% | 85%
|  | Z3-C-CON-6780 | Fix Rebar Slabs - Z3 - SRVF | 3040 | 3040 | 2584 | 100% | 0.003505% | 0.002979% | 85% | 85%
|  | Z3-C-CON-6790 | Pour Concrete Slabs - Z3 - SRVF | 850 | 850 | 195 | 100% | 0.0009799% | 0.0002248% | 22.94% | 22.94%
|  | Z3-C-CON-6810 | Fix Rebar Core Walls - Z3 - SRVF | 648 | 648 | 149 | 100% | 0.000747% | 0.0001718% | 22.99% | 22.99%
|  | Z3-C-CON-6820 | Fix Formwork Core Walls - Z3 - SRVF | 576 | 576 | 499 | 100% | 0.000664% | 0.0005753% | 86.63% | 0.86632
|  | Z3-C-CON-6830 | Pour Concrete Core Walls - Z3 - SRVF | 4 | 4 | 3 | 100% | 4.611e-06% | 3.458e-06% | 75% | 0.75
|  | Z3-C-CON-6840 | Fix Rebar Columns - Z3 - SRVF | 116 | 116 | 27 | 100% | 0.0001337% | 3.113e-05% | 23.28% | 0.23276
|  | Z3-C-CON-6850 | Fix Formwork Columns - Z3 - SRVF | 41 | 41 | 9 | 100% | 4.727e-05% | 1.038e-05% | 21.95% | 0.21951
|  | Z3-C-CON-6860 | Pour Concrete Columns - Z3 - SRVF | 8 | 8 | 2 | 100% | 9.223e-06% | 2.306e-06% | 25% | 0.25
|  | Z3-C-CON-6870 | Pour MEP RCC Pedastals - Z3 - SRVF | 2 | 2 | 0 | 100% | 2.306e-06% |  | 0% | 0
|  | Z3-C-CON-6880 | Fix Formwork Parapet - Z3 - SRVF | 113 | 113 | 26 | 100% | 0.0001303% | 2.997e-05% | 23.01% | 0.23009
|  | Z3-C-CON-6890 | Fix Rebar Parapet - Z3 - SRVF | 236 | 236 | 54 | 100% | 0.0002721% | 6.225e-05% | 22.88% | 0.22881
|  | Z3-C-CON-6900 | Pour Concrete Parapet - Z3 - SRVF | 136 | 136 | 31 | 100% | 0.0001568% | 3.574e-05% | 22.79% | 0.22794
|  | Z3-C-CON-6910 | Fix Formwork Slabs - Z3 - TRF | 298 | 298 | 253 | 100% | 0.0003435% | 0.0002917% | 84.9% | 0.84899
|  | Z3-C-CON-6920 | Fix Rebar Slabs - Z3 - TRF | 303 | 303 | 258 | 100% | 0.0003493% | 0.0002974% | 85.15% | 0.85149
|  | Z3-C-CON-6930 | Pour Concrete Slabs - Z3 - TRF | 90 | 90 | 76 | 100% | 0.0001038% | 8.761e-05% | 84.44% | 0.84444
|  | Z3-C-CON-6950 | Fix Formwork Parapet - Z3 - TRF | 113 | 113 | 96 | 100% | 0.0001303% | 0.0001107% | 84.96% | 0.84956
|  | Z3-C-CON-6960 | Fix Rebar Parapet - Z3 - TRF | 236 | 236 | 201 | 100% | 0.0002721% | 0.0002317% | 85.17% | 0.85169
|  | Z3-C-CON-6970 | Pour Concrete Parapet - Z3 - TRF | 136 | 136 | 116 | 100% | 0.0001568% | 0.0001337% | 85.29% | 0.85294
| Div 10 | Z3-C-CON-5940 | Fix MEP Provisions - Z3 - Raft | 100 | 100 | 85 | 100% | 0.0001153% | 9.799e-05% | 85% | 0.85
Grand Total |  |  |  | 790530 | 790564 | 562370 | 100% | 0.9114% | 0.6483% | 71.14% | 0.71135
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Monthly Detailed EVM Cost
Project Name | [7 empty] | Data Date: |  | 2022-03-31
Location | [7 empty] | Current Week |  | 26
[8 empty] | Total Weeks |  | 114
1817-Zone | 1817-BOQ Summary | Activity ID | Activity Name | Budget Cost | Planned Value | Earned Value | Activity Planned % | Planned Weightage % | Actual Weightage % | Actual % Complete | SPI
Z1 | Div 01 | PRL-MOB-1020 | Site Office Establishment | 767001 | 767000 | 586756 | 100% | 0.8842% | 0.6764% | 76.5% | 0.765
|  | PRL-MOB-1050 | Project Sign Boards and Hoarding | 60000 | 60000 | 45900 | 100% | 0.06917% | 0.05291% | 76.5% | 0.765
|  | PRL-MOB-1100 | Yards & Stores Establishment | 80000 | 80000 | 61200 | 100% | 0.09223% | 0.07055% | 76.5% | 0.765
| Div 02 | C-EW-10370 | Excavation Stage 1 - Z1 | 293640 | 293640 | 161502 | 100% | 0.3385% | 0.1862% | 55% | 0.55
|  | C-EW-10380 | Strut Pipe Bracing - Z1 | 162250 | 162250 | 178476 | 100% | 0.187% | 0.2058% | 110% | 1.1
|  | C-EW-10390 | Excavation Stage 2 - Z1 | 293641 | 293640 | 161503 | 100% | 0.3385% | 0.1862% | 55% | 0.55
|  | C-SHRNG-DCE-C-2330 | Place Guide Wall - Z1 | 162250 | 162250 | 178476 | 100% | 0.187% | 0.2058% | 110% | 1.1
|  | C-SHRNG-DCE-C-2340 | Install Shoring System - Z1 | 2016502 | 2016500 | 2218152 | 100% | 2.325% | 2.557% | 110% | 1.1
|  | C-SHRNG-DCE-C-2350 | Install Capping Beam - Z1 | 180856 | 180856 | 99471 | 100% | 0.2085% | 0.1147% | 55% | 0.55
|  | PRL-MOB-SCW-1600 | Soil Investigation & Report Submit | 55000 | 55000 | 42075 | 100% | 0.06341% | 0.0485% | 76.5% | 0.765
|  | PRL-MOB-SCW-2310 | Dewatering System Installation | 95000 | 95000 | 104500 | 100% | 0.1095% | 0.1205% | 110% | 1.1
|  | PRL-MOB-SCW-2320 | Demolition of Existing Structure | 140001 | 140000 | 77001 | 100% | 0.1614% | 0.08877% | 55% | 0.55001
|  | PRL-MOB-SCW-2330 | Clearing Existing Utilities | 39000 | 39000 | 21450 | 100% | 0.04496% | 0.02473% | 55% | 0.55
| Div 03 | C-EW-2420 | Gunite Wall - Z1 | 152558 | 152558 | 129675 | 100% | 0.1759% | 0.1495% | 85% | 0.85
|  | Z1-11460 | Post Tensioning the Slab - Z1 - F1 | 25092 | 25092 | 14077 | 100% | 0.02893% | 0.01623% | 56.1% | 0.56102
|  | Z1-11470 | Post Tensioning the Slab - Z1 - F2 | 25471 | 25471 | 21650 | 100% | 0.02936% | 0.02496% | 85% | 0.84999
|  | Z1-11480 | Post Tensioning the Slab - Z1 - RF | 25392 | 25392 | 21583 | 100% | 0.02927% | 0.02488% | 85% | 0.84999
|  | Z1-11490 | Post Tensioning the Slab - Z1 - SRVF | 21331 | 21331 | 18131 | 100% | 0.02459% | 0.0209% | 85% | 0.84998
|  | Z1-C-CON-2400 | PCC Blind Concrete - Z1 - Lift Pit | 17220 | 17220 | 14637 | 100% | 0.01985% | 0.01687% | 85% | 0.85
|  | Z1-C-CON-2440 | Waterproof Membrane - Z1 - Lift Pit | 102280 | 102280 | 86938 | 100% | 0.1179% | 0.1002% | 85% | 0.85
|  | Z1-C-CON-2450 | Protection Screed - Z1 - Lift Pit | 10980 | 10980 | 9333 | 100% | 0.01266% | 0.01076% | 85% | 0.85
|  | Z1-C-CON-2460 | Fix Rebar - Z1 - Lift Pit | 20247 | 20247 | 17210 | 100% | 0.02334% | 0.01984% | 85% | 0.85
|  | Z1-C-CON-2480 | Pour Concrete - Z1 - Lift Pit | 20247 | 20247 | 17210 | 100% | 0.02334% | 0.01984% | 85% | 0.85
|  | Z1-C-CON-2500 | PCC Blind Concrete - Z1 - Raft | 51660 | 51660 | 43911 | 100% | 0.05955% | 0.05062% | 85% | 0.85
|  | Z1-C-CON-2510 | Waterproof Membrane - Z1 - Raft | 306840 | 306840 | 260814 | 100% | 0.3537% | 0.3007% | 85% | 0.85
|  | Z1-C-CON-2520 | Protection Screed - Z1 - Raft | 32940 | 32941 | 988 | 100% | 0.03798% | 0.001139% | 2.999% | 0.029993
|  | Z1-C-CON-2530 | Fix Rebar - Z1 - Raft | 687066 | 687066 | 6871 | 100% | 0.7921% | 0.007921% | 1% | 0.01
|  | Z1-C-CON-2550 | Fix Formwork - Z1 - Raft | 41321 | 41321 | 8781 | 100% | 0.04764% | 0.01012% | 21.25% | 0.21251
|  | Z1-C-CON-2560 | Pour Concrete - Z1 - Raft | 1004127 | 1004127 | 213377 | 100% | 1.158% | 0.246% | 21.25% | 0.2125
|  | Z1-C-CON-2570 | Fix Rebar Core Walls - Z1 - B2 | 49489 | 49489 | 10516 | 100% | 0.05705% | 0.01212% | 21.25% | 0.21249
|  | Z1-C-CON-2580 | Fix Formwork Core Walls - Z1 - B2 | 41489 | 41489 | 35266 | 100% | 0.04783% | 0.04066% | 85% | 0.85001
|  | Z1-C-CON-2600 | Fix Rebar Retaining Walls - Z1 - B2 | 87236 | 87236 | 37076 | 100% | 0.1006% | 0.04274% | 42.5% | 0.42501
|  | Z1-C-CON-2610 | Fix Formwork Retaining Walls - Z1 - B2 | 144300 | 144299 | 30664 | 100% | 0.1664% | 0.03535% | 21.25% | 0.2125
|  | Z1-C-CON-2620 | Pour Concrete Retaining Walls - Z1 - B2 | 288597 | 288597 | 245307 | 100% | 0.3327% | 0.2828% | 85% | 0.85
|  | Z1-C-CON-2630 | Pour Concrete Core Walls - Z1 - B2 | 161333 | 161333 | 137133 | 100% | 0.186% | 0.1581% | 85% | 0.85
|  | Z1-C-CON-2640 | Fix Rebar Columns - Z1 - B2 | 63240 | 63240 | 26878 | 100% | 0.0729% | 0.03099% | 42.5% | 0.42502
|  | Z1-C-CON-2650 | Fix Formwork Columns - Z1 - B2 | 132301 | 132301 | 28114 | 100% | 0.1525% | 0.03241% | 21.25% | 0.2125
|  | Z1-C-CON-2660 | Pour Concrete Columns - Z1 - B2 | 163921 | 163921 | 34833 | 100% | 0.189% | 0.04016% | 21.25% | 0.2125
|  | Z1-C-CON-2670 | Fix Formwork Stairs - Z1 - B2 | 2486 | 2486 | 338 | 100% | 0.002866% | 0.0003897% | 13.6% | 0.13596
|  | Z1-C-CON-2680 | Fix Rebar Stairs - Z1 - B2 | 4972 | 4972 | 99 | 100% | 0.005732% | 0.0001141% | 1.991% | 0.019912
|  | Z1-C-CON-2690 | Pour Concrete Stairs - Z1 - B2 | 4972 | 4972 | 99 | 100% | 0.005732% | 0.0001141% | 1.991% | 0.019912
|  | Z1-C-CON-2700 | Pour Concrete Slabs - Z1 - B1 | 315168 | 315168 | 267893 | 100% | 0.3633% | 0.3088% | 85% | 0.85
|  | Z1-C-CON-2710 | Fix Formwork Slabs - Z1 - B1 | 157584 | 157584 | 133946 | 100% | 0.1817% | 0.1544% | 85% | 0.85
|  | Z1-C-CON-2720 | Fix Rebar Slabs - Z1 - B1 | 315168 | 315168 | 267893 | 100% | 0.3633% | 0.3088% | 85% | 0.85
|  | Z1-C-CON-2730 | Fix Rebar Retaining Walls - Z1 - B1 | 87236 | 87236 | 872 | 100% | 0.1006% | 0.001005% | 0.9996% | 0.0099959
|  | Z1-C-CON-2740 | Fix Formwork Retaining Walls - Z1 - B1 | 43618 | 43618 | 1308 | 100% | 0.05028% | 0.001508% | 2.999% | 0.029988
|  | Z1-C-CON-2750 | Pour Concrete Retaining Walls - Z1 - B1 | 87236 | 87236 | 3490 | 100% | 0.1006% | 0.004023% | 4.001% | 0.040006
|  | Z1-C-CON-2760 | Fix Rebar Core Walls - Z1 - B1 | 49489 | 49489 | 495 | 100% | 0.05705% | 0.0005706% | 1% | 0.010002
|  | Z1-C-CON-2770 | Fix Formwork Core Walls - Z1 - B1 | 41489 | 41489 | 6473 | 100% | 0.04783% | 0.007462% | 15.6% | 0.15602
|  | Z1-C-CON-2780 | Pour Concrete Core Walls - Z1 - B1 | 60652 | 60652 | 1213 | 100% | 0.06992% | 0.001398% | 2% | 0.019999
|  | Z1-C-CON-2790 | Fix Rebar Columns - Z1 - B1 | 63240 | 63240 | 8601 | 100% | 0.0729% | 0.009915% | 13.6% | 0.13601
|  | Z1-C-CON-2800 | Fix Formwork Columns - Z1 - B1 | 31620 | 31620 | 948 | 100% | 0.03645% | 0.001093% | 2.998% | 0.029981
|  | Z1-C-CON-2810 | Pour Concrete Columns - Z1 - B1 | 63240 | 63240 | 9866 | 100% | 0.0729% | 0.01137% | 15.6% | 0.15601
|  | Z1-C-CON-2820 | Fix Formwork Stairs - Z1 - B1 | 2486 | 2486 | 149 | 100% | 0.002866% | 0.0001718% | 5.994% | 0.059936
|  | Z1-C-CON-2830 | Fix Rebar Stairs - Z1 - B1 | 4972 | 4972 | 298 | 100% | 0.005732% | 0.0003435% | 5.994% | 0.059936
|  | Z1-C-CON-2840 | Pour Concrete Stairs - Z1 - B1 | 4972 | 4972 | 298 | 100% | 0.005732% | 0.0003435% | 5.994% | 0.059936
|  | Z1-C-CON-3000 | Fix Formwork Slabs - Z1 - GF | 196850 | 196850 | 3937 | 100% | 0.2269% | 0.004539% | 2% | 0.02
|  | Z1-C-CON-3010 | Fix Rebar Slabs - Z1 - GF | 393700 | 393699 | 334644 | 100% | 0.4539% | 0.3858% | 85% | 0.85
|  | Z1-C-CON-3020 | Pour Concrete Slabs - Z1 - GF | 393699 | 393699 | 23622 | 100% | 0.4539% | 0.02723% | 6% | 0.06
|  | Z1-C-CON-3030 | Fix Rebar Core Walls - Z1 - GF | 72339 | 72339 | 4340 | 100% | 0.08339% | 0.005003% | 6% | 0.059995
|  | Z1-C-CON-3040 | Fix Formwork Core Walls - Z1 - GF | 37650 | 37650 | 19860 | 100% | 0.0434% | 0.0229% | 52.75% | 0.52749
|  | Z1-C-CON-3050 | Pour Concrete Core Walls - Z1 - GF | 74214 | 74214 | 7421 | 100% | 0.08556% | 0.008555% | 9.999% | 0.099995
|  | Z1-C-CON-3060 | Fix Rebar Columns - Z1 - GF | 96670 | 96671 | 5800 | 100% | 0.1114% | 0.006686% | 6% | 0.059997
|  | Z1-C-CON-3070 | Fix Formwork Columns - Z1 - GF | 50689 | 50689 | 47394 | 100% | 0.05844% | 0.05464% | 93.5% | 0.935
|  | Z1-C-CON-3080 | Pour Concrete Columns - Z1 - GF | 101503 | 101503 | 53543 | 100% | 0.117% | 0.06173% | 52.75% | 0.5275
|  | Z1-C-CON-3090 | Fix Formwork Stairs - Z1 - GF | 4838 | 4838 | 2714 | 100% | 0.005577% | 0.003129% | 56.1% | 0.56098
|  | Z1-C-CON-3100 | Fix Rebar Stairs - Z1 - GF | 6451 | 6451 | 3619 | 100% | 0.007437% | 0.004172% | 56.1% | 0.561
|  | Z1-C-CON-3110 | Pour Concrete Stairs - Z1 - GF | 49823 | 6451 | 27951 | 12.95% | 0.007437% | 0.03222% | 56.1% | 4.3328
|  | Z1-C-CON-3120 | Fix MEP Containment & Provisions - Z1 - B1 | 10880 | 10880 | 9248 | 100% | 0.01254% | 0.01066% | 85% | 0.85
|  | Z1-C-CON-3140 | Fix MEP Containment & Provisions - Z1 - GF | 10880 | 10880 | 653 | 100% | 0.01254% | 0.0007528% | 6.002% | 0.060018
|  | Z1-C-CON-3150 | Fix MEP Containment & Provisions - Z1 - F1 | 10880 | 10880 | 3884 | 100% | 0.01254% | 0.004478% | 35.7% | 0.35699
|  | Z1-C-CON-3160 | Fix Formwork Slabs - Z1 - F1 | 226317 | 226317 | 22632 | 100% | 0.2609% | 0.02609% | 10% | 0.1
|  | Z1-C-CON-3170 | Pour Concrete Slabs - Z1 - F1 | 326686 | 326686 | 277683 | 100% | 0.3766% | 0.3201% | 85% | 0.85
|  | Z1-C-CON-3180 | Fix Rebar Slabs - Z1 - F1 | 250571 | 250572 | 25057 | 100% | 0.2889% | 0.02889% | 10% | 0.099999
|  | Z1-C-CON-3190 | Fix Rebar Core Walls - Z1 - F1 | 71458 | 71458 | 40088 | 100% | 0.08238% | 0.04621% | 56.1% | 0.561
|  | Z1-C-CON-3200 | Fix Formwork Core Walls - Z1 - F1 | 37716 | 37716 | 21159 | 100% | 0.04348% | 0.02439% | 56.1% | 0.56101
|  | Z1-C-CON-3210 | Pour Concrete Core Walls - Z1 - F1 | 75216 | 75216 | 18804 | 100% | 0.08671% | 0.02168% | 25% | 0.25
|  | Z1-C-CON-3220 | Fix Rebar Columns - Z1 - F1 | 97930 | 97930 | 54939 | 100% | 0.1129% | 0.06333% | 56.1% | 0.561
|  | Z1-C-CON-3230 | Fix Formwork Columns - Z1 - F1 | 50440 | 50440 | 28297 | 100% | 0.05815% | 0.03262% | 56.1% | 0.561
|  | Z1-C-CON-3240 | Pour Concrete Columns - Z1 - F1 | 101184 | 101185 | 56764 | 100% | 0.1166% | 0.06544% | 56.1% | 0.56099
|  | Z1-C-CON-3250 | Fix Formwork Stairs - Z1 - F1 | 4839 | 4838 | 4112 | 99.98% | 0.005577% | 0.00474% | 84.98% | 0.84994
|  | Z1-C-CON-3260 | Fix Rebar Stairs - Z1 - F1 | 6451 | 6451 | 12902 | 100% | 0.007437% | 0.01487% | 200% | 2
|  | Z1-C-CON-3270 | Pour Concrete Stairs - Z1 - F1 | 6451 | 6451 | 5483 | 100% | 0.007437% | 0.006321% | 84.99% | 0.84995
|  | Z1-C-CON-3280 | Fix Formwork Slabs - Z1 - F2 | 228211 | 228211 | 114106 | 100% | 0.2631% | 0.1315% | 50% | 0.5
|  | Z1-C-CON-3290 | Fix Rebar Slabs - Z1 - F2 | 157731 | 157731 | 39433 | 100% | 0.1818% | 0.04546% | 25% | 0.25
|  | Z1-C-CON-3300 | Pour Concrete Slabs - Z1 - F2 | 230096 | 230096 | 195582 | 100% | 0.2653% | 0.2255% | 85% | 0.85
|  | Z1-C-CON-3310 | Fix MEP Containment & Provisions - Z1 - F2 | 10881 | 10880 | 9248 | 99.99% | 0.01254% | 0.01066% | 84.99% | 0.85
|  | Z1-C-CON-3320 | Fix Rebar Core Walls - Z1 - F2 | 47223 | 47223 | 78443 | 100% | 0.05444% | 0.09043% | 166.1% | 1.6611
|  | Z1-C-CON-3330 | Fix Formwork Core Walls - Z1 - F2 | 22272 | 22273 | 18932 | 100% | 0.02568% | 0.02183% | 85% | 0.85
|  | Z1-C-CON-3340 | Pour Concrete Core Walls - Z1 - F2 | 45198 | 45198 | 38418 | 100% | 0.05211% | 0.04429% | 85% | 0.84999
|  | Z1-C-CON-3350 | Fix Rebar Columns - Z1 - F2 | 66757 | 66757 | 116407 | 100% | 0.07696% | 0.1342% | 174.4% | 1.7437
|  | Z1-C-CON-3360 | Fix Formwork Columns - Z1 - F2 | 32421 | 32420 | 27557 | 100% | 0.03737% | 0.03177% | 85% | 0.85
|  | Z1-C-CON-3370 | Pour Concrete Columns - Z1 - F2 | 64003 | 64002 | 54402 | 100% | 0.07378% | 0.06272% | 85% | 0.85
|  | Z1-C-CON-3380 | Fix Formwork Stairs - Z1 - F2 | 4838 | 4838 | 4112 | 100% | 0.005577% | 0.00474% | 84.99% | 0.84994
|  | Z1-C-CON-3390 | Fix Rebar Stairs - Z1 - F2 | 4838 | 4838 | 4112 | 100% | 0.005577% | 0.00474% | 84.99% | 0.84994
|  | Z1-C-CON-3400 | Pour Concrete Stairs - Z1 - F2 | 4838 | 4838 | 4112 | 100% | 0.005577% | 0.00474% | 84.99% | 0.84994
|  | Z1-C-CON-3410 | Fix Formwork Slabs - Z1 - RF | 461149 | 461148 | 391976 | 100% | 0.5316% | 0.4519% | 85% | 0.85
|  | Z1-C-CON-3420 | Fix Rebar Slabs - Z1 - RF | 156343 | 156343 | 132892 | 100% | 0.1802% | 0.1532% | 85% | 0.85
|  | Z1-C-CON-3430 | Pour Concrete Slabs - Z1 - RF | 149383 | 149383 | 126976 | 100% | 0.1722% | 0.1464% | 85% | 0.85
|  | Z1-C-CON-3440 | Fix MEP Containment & Provisions - Z1 - RF | 10880 | 10880 | 9248 | 100% | 0.01254% | 0.01066% | 85% | 0.85
|  | Z1-C-CON-3450 | Fix Rebar Core Walls - Z1 - RF | 46414 | 46413 | 39451 | 100% | 0.05351% | 0.04548% | 85% | 0.85
|  | Z1-C-CON-3460 | Fix Formwork Core Walls - Z1 - RF | 22188 | 22188 | 18860 | 100% | 0.02558% | 0.02174% | 85% | 0.85001
|  | Z1-C-CON-3470 | Pour Concrete Core Walls - Z1 - RF | 45050 | 45050 | 38292 | 100% | 0.05193% | 0.04414% | 85% | 0.84999
|  | Z1-C-CON-3480 | Fix Rebar Columns - Z1 - RF | 54661 | 54662 | 46463 | 100% | 0.06302% | 0.05356% | 85% | 0.85001
|  | Z1-C-CON-3490 | Fix Formwork Columns - Z1 - RF | 25132 | 25132 | 21362 | 100% | 0.02897% | 0.02463% | 85% | 0.84999
|  | Z1-C-CON-3500 | Pour Concrete Columns - Z1 - RF | 51065 | 51064 | 43404 | 100% | 0.05887% | 0.05004% | 85% | 0.84999
|  | Z1-C-CON-3510 | Fix Formwork Stairs - Z1 - RF | 4838 | 4838 | 4112 | 100% | 0.005577% | 0.00474% | 84.99% | 0.84994
|  | Z1-C-CON-3520 | Fix Rebar Stairs - Z1 - RF | 4838 | 4838 | 4112 | 100% | 0.005577% | 0.00474% | 84.99% | 0.84994
|  | Z1-C-CON-3530 | Pour Concrete Stairs - Z1 - RF | 4838 | 4838 | 4112 | 100% | 0.005577% | 0.00474% | 84.99% | 0.84994
|  | Z1-C-CON-5620 | Fix Formwork Slabs - Z1 - SRVF | 207509 | 207509 | 176383 | 100% | 0.2392% | 0.2033% | 85% | 0.85
|  | Z1-C-CON-5630 | Fix Rebar Slabs - Z1 - SRVF | 308219 | 308219 | 261986 | 100% | 0.3553% | 0.302% | 85% | 0.85
|  | Z1-C-CON-5640 | Pour Concrete Slabs - Z1 - SRVF | 392832 | 392832 | 333907 | 100% | 0.4529% | 0.3849% | 85% | 0.85
|  | Z1-C-CON-5650 | Fix MEP Containment & Provisions - Z1 - SRVF | 10880 | 10880 | 9248 | 100% | 0.01254% | 0.01066% | 85% | 0.85
|  | Z1-C-CON-5660 | Fix Rebar Core Walls - Z1 - SRVF | 27454 | 27453 | 23335 | 100% | 0.03165% | 0.0269% | 85% | 0.85
|  | Z1-C-CON-5670 | Fix Formwork Core Walls - Z1 - SRVF | 12615 | 12615 | 10723 | 100% | 0.01454% | 0.01236% | 85% | 0.85002
|  | Z1-C-CON-5680 | Pour Concrete Core Walls - Z1 - SRVF | 25208 | 25208 | 21427 | 100% | 0.02906% | 0.0247% | 85% | 0.85001
|  | Z1-C-CON-5690 | Fix Rebar Columns - Z1 - SRVF | 4941 | 4941 | 4200 | 100% | 0.005696% | 0.004842% | 85% | 0.85003
|  | Z1-C-CON-5700 | Fix Formwork Columns - Z1 - SRVF | 1799 | 1799 | 1529 | 100% | 0.002074% | 0.001763% | 84.99% | 0.84992
|  | Z1-C-CON-5710 | Pour Concrete Columns - Z1 - SRVF | 3206 | 3206 | 2725 | 100% | 0.003696% | 0.003141% | 85% | 0.84997
|  | Z1-C-CON-5720 | Fix Formwork Parapet - Z1 - SRVF | 19346 | 19346 | 16444 | 100% | 0.0223% | 0.01896% | 85% | 0.84999
|  | Z1-C-CON-5730 | Fix Rebar Parapet - Z1 - SRVF | 38692 | 38691 | 32887 | 100% | 0.0446% | 0.03791% | 85% | 0.84999
|  | Z1-C-CON-5740 | Pour Concrete Parapet - Z1 - SRVF | 38691 | 38691 | 32887 | 100% | 0.0446% | 0.03791% | 85% | 0.84999
|  | Z1-C-CON-5750 | Fix Formwork Slabs - Z1 - TRF | 10217 | 10217 | 8684 | 100% | 0.01178% | 0.01001% | 85% | 0.84996
|  | Z1-C-CON-5760 | Fix Rebar Slabs - Z1 - TRF | 20434 | 20434 | 4690 | 100% | 0.02356% | 0.005407% | 22.95% | 0.22952
|  | Z1-C-CON-5770 | Pour Concrete Slabs - Z1 - TRF | 20434 | 20434 | 4690 | 100% | 0.02356% | 0.005407% | 22.95% | 0.22952
|  | Z1-C-CON-5780 | Fix MEP Containment & Provisions - Z1 - TRF | 10880 | 10880 | 2497 | 100% | 0.01254% | 0.002879% | 22.95% | 0.2295
|  | Z1-C-CON-5790 | Pour MEP RCC Pedastals - Z1 - SRVF | 1613 | 1613 | 1371 | 100% | 0.00186% | 0.001581% | 85% | 0.84997
|  | Z1-C-CON-5810 | Fix Rebar Parapet - Z1 - TRF | 38691 | 38691 | 17102 | 100% | 0.0446% | 0.01972% | 44.2% | 0.44201
|  | Z1-C-CON-5820 | Fix Formwork Parapet - Z1 - TRF | 19346 | 19346 | 16444 | 100% | 0.0223% | 0.01896% | 85% | 0.84999
|  | Z1-C-CON-5830 | Pour Concrete Parapet - Z1 - TRF | 38691 | 38691 | 32887 | 100% | 0.0446% | 0.03791% | 85% | 0.84999
|  | Z1-C-CON-5840 | Fix Formwork Ramp - Z1 - B2 | 11760 | 11760 | 9996 | 100% | 0.01356% | 0.01152% | 85% | 0.85
|  | Z1-C-CON-5850 | Fix Rebar Ramp - Z1 - B2 | 23520 | 23520 | 235 | 100% | 0.02711% | 0.0002709% | 0.9991% | 0.0099915
|  | Z1-C-CON-5860 | Pour Concrete Ramp - Z1 - B2 | 23520 | 23520 | 235 | 100% | 0.02711% | 0.0002709% | 0.9991% | 0.0099915
|  | Z1-C-CON-5870 | Fix Formwork Ramp - Z1 - B1 | 11760 | 11760 | 706 | 100% | 0.01356% | 0.0008139% | 6.003% | 0.060034
|  | Z1-C-CON-5880 | Fix Rebar Ramp - Z1 - B1 | 23520 | 23520 | 1411 | 100% | 0.02711% | 0.001627% | 5.999% | 0.059991
|  | Z1-C-CON-5890 | Pour Concrete Ramp - Z1 - B1 | 23520 | 23520 | 1411 | 100% | 0.02711% | 0.001627% | 5.999% | 0.059991
|  | Z1-C-CON-5900 | Fix Rebar Core Walls Ramp - Z1 - B2 | 27909 | 27908 | 23722 | 100% | 0.03217% | 0.02735% | 85% | 0.85001
|  | Z1-C-CON-5910 | Fix Formwork Walls Ramp - Z1 - B2 | 27909 | 27908 | 23722 | 100% | 0.03217% | 0.02735% | 85% | 0.85001
|  | Z1-C-CON-5920 | Pour Concrete Core Walls Ramp - Z1 - B2 | 37210 | 37210 | 31628 | 100% | 0.0429% | 0.03646% | 85% | 0.84999
|  | Z1-C-CON-5930 | Fix Rebar Core Walls Ramp - Z1 - B1 | 27907 | 27908 | 558 | 100% | 0.03217% | 0.0006433% | 1.999% | 0.019994
|  | Z1-C-CON-5940 | Fix Formwork Walls Ramp - Z1 - B1 | 27908 | 27908 | 3795 | 100% | 0.03217% | 0.004375% | 13.6% | 0.13598
|  | Z1-C-CON-5950 | Pour Concrete Core Walls Ramp - Z1 - B1 | 37210 | 37210 | 31628 | 100% | 0.0429% | 0.03646% | 85% | 0.84999
|  | Z1-C-FIN-6140 | GRP Linning - Z1 - B2 | 45350 | 45350 | 21201 | 100% | 0.05228% | 0.02444% | 46.75% | 0.4675
|  | Z1-C-FIN-7390 | GRP Linning - Z1 - B1 | 45350 | 45350 | 22676 | 100% | 0.05228% | 0.02614% | 50% | 0.50002
| Div 04 | Z1-C-FIN-10120 | Masonry Works Wet Area - Z1 - F2 | 84732 | 84733 | 72023 | 100% | 0.09768% | 0.08303% | 85% | 0.85
|  | Z1-C-FIN-10460 | Masonry Works Dry Area - Z1 - F2 | 84732 | 84733 | 72023 | 100% | 0.09768% | 0.08303% | 85% | 0.85
|  | Z1-C-FIN-10760 | Masonry Works Wet Area - Z1 - RF | 72632 | 72631 | 62971 | 100% | 0.08373% | 0.07259% | 86.7% | 0.867
|  | Z1-C-FIN-10940 | Masonry Works Dry Area - Z1 - RF | 72632 | 72632 | 43128 | 100% | 0.08373% | 0.04972% | 59.38% | 0.59379
|  | Z1-C-FIN-5790 | Masonry Works - Z1 - B2 | 3061 | 3062 | 184 | 100% | 0.00353% | 0.0002121% | 6.011% | 0.060091
|  | Z1-C-FIN-7040 | Masonry Works - Z1 - B1 | 30339 | 30338 | 17020 | 100% | 0.03497% | 0.01962% | 56.1% | 0.56101
|  | Z1-C-FIN-8330 | Masonry Works - Z1 - GF | 223435 | 223436 | 111718 | 100% | 0.2576% | 0.1288% | 50% | 0.5
|  | Z1-C-FIN-9490 | Masonry Works Wet + Dry Area - Z1 - F1 | 144102 | 144102 | 122487 | 100% | 0.1661% | 0.1412% | 85% | 0.85
| Div 05 | C-FIN-ENVLP-9550 | Fix Steel Decore - GF to SRVF (Elev. 1 & 4) | 59364 | 59364 | 50459 | 100% | 0.06844% | 0.05817% | 85% | 0.84999
|  | C-FIN-ENVLP-9640 | Install Aluminum & Wood Roof Features | 70700 | 70700 | 60095 | 100% | 0.0815% | 0.06928% | 85% | 0.85
|  | Z1-C-FIN-6150 | Fix Galvonized Iron Cat Ladder - Z1 - B2 | 600 | 600 | 60 | 100% | 0.0006917% | 6.917e-05% | 10% | 0.1
|  | Z1-C-FIN-7400 | Fix Galvonized Iron Cat Ladder - Z1 - B1 | 600 | 600 | 150 | 100% | 0.0006917% | 0.0001729% | 25% | 0.25
|  | Z1-C-FIN-SCASE-8810 | Install Haindrails Staircase - Z1 - B2 - SRVF | 83199 | 83200 | 70720 | 100% | 0.09591% | 0.08153% | 85% | 0.85
| Div 06 | Z1-C-FIN-10710 | Fix Furniture & Counter Works kitchen/Pantry - Z1 - F2 | 89500 | 89500 | 76075 | 100% | 0.1032% | 0.0877% | 85% | 0.85
|  | Z1-C-FIN-11180 | Fix Furniture & Counter Works kitchen/Pantry - Z1 - RF | 89500 | 89500 | 76075 | 100% | 0.1032% | 0.0877% | 85% | 0.85
| Div 07 | C-FIN-ENVLP-9540 | Osmotic Cement Waterproof - GF to SRVF (Elev. 1 & 4) | 55965 | 55965 | 56821 | 100% | 0.06452% | 0.0655% | 101.5% | 1.0153
|  | Z123-C-FIN-18510 | Foam Concrete - Z123 - TRF | 130693 | 130693 | 111089 | 100% | 0.1507% | 0.1281% | 85% | 0.85
|  | Z123-C-FIN-18520 | 4mm Waterproof Membrane Wet Area - Z123 - TRF | 130693 | 130693 | 111089 | 100% | 0.1507% | 0.1281% | 85% | 0.85
|  | Z123-C-FIN-18530 | Protection Screed Wet Area - Z123 - TRF | 130693 | 130693 | 111089 | 100% | 0.1507% | 0.1281% | 85% | 0.85
|  | Z123-C-FIN-18550 | Polystyrene Thermal Insulation - Z123 - TRF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z123-C-FIN-18560 | Roof Floor Terrazo Tiles Wet Area - Z123 - TRF | 3898 | 3899 | 3313 | 100% | 0.004495% | 0.003819% | 84.99% | 0.84971
|  | Z1-C-FIN-10490 | Waterproof Bath - Z1 - F2 | 3898 | 3898 | 895 | 100% | 0.004494% | 0.001032% | 22.96% | 0.2296
|  | Z1-C-FIN-10500 | Protection Screed Bath - Z1 - F2 | 3898 | 3898 | 2552 | 100% | 0.004494% | 0.002942% | 65.47% | 0.65469
|  | Z1-C-FIN-10590 | Waterproof kitchen/Pantry - Z1 - F2 | 3898 | 3898 | 895 | 100% | 0.004494% | 0.001032% | 22.96% | 0.2296
|  | Z1-C-FIN-10600 | Protection Screed kitchen/Pantry - Z1 - F2 | 3898 | 3898 | 895 | 100% | 0.004494% | 0.001032% | 22.96% | 0.2296
|  | Z1-C-FIN-10670 | Waterproof Garbage Room - Z1 - F2 | 3898 | 3898 | 895 | 100% | 0.004494% | 0.001032% | 22.96% | 0.2296
|  | Z1-C-FIN-10680 | Protection Screed Garbage Room - Z1 - F2 | 3898 | 3898 | 2552 | 100% | 0.004494% | 0.002942% | 65.47% | 0.65469
|  | Z1-C-FIN-11000 | Waterproof Bath - Z1 - RF | 3899 | 3898 | 3313 | 99.97% | 0.004494% | 0.003819% | 84.97% | 0.84992
|  | Z1-C-FIN-11010 | Protection Screed Bath - Z1 - RF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z1-C-FIN-11080 | Waterproof kitchen/Pantry - Z1 - RF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z1-C-FIN-11090 | Protection Screed kitchen/Pantry - Z1 - RF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z1-C-FIN-11150 | Waterproof Garbage Room - Z1 - RF | 3899 | 3898 | 3313 | 99.97% | 0.004494% | 0.003819% | 84.97% | 0.84992
|  | Z1-C-FIN-11160 | Protection Screed Garbage Room - Z1 - RF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z1-C-FIN-8870 | Waterproof & Screed Garbage Room - Z1 - GF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
| Div 08 | A7100 | Fix Windows & Door Frame & Leaf - F2 | 20820 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | A7110 | Fix Ironmongery - F2 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | A7180 | Fix Windows & Door Frame & Leaf - RF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | A7190 | Fix Ironmongery - RF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | C-FIN-ENVLP-9530 | Fix Aluminum Glazing Pannels - GF to SRVF (Elev. 1 & 4) | 822232 | 822234 | 509613 | 100% | 0.9479% | 0.5875% | 61.98% | 0.61979
|  | Z1-C-FIN-10370 | Fix Door Subframes Wet Area - Z1 - F2 | 20822 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-10470 | Fix Door Subframes Dry Area - Z1 - F2 | 20822 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-10900 | Fix Door Subframes Wet Area - Z1 - RF | 20822 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-10960 | Fix Door Subframes Dry Area - Z1 - RF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-18600 | Fix Doors - Z1 - B1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-18640 | Fix Doors - Z1 - B1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-18690 | Fix Doors Loading Room - Z1 - GF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-18730 | Fix Doors Serv. Rooms - Z1 - F1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-6220 | Fix Doors - Z1 - B2 | 20822 | 20821 | 3123 | 100% | 0.024% | 0.0036% | 15% | 0.14999
|  | Z1-C-FIN-6230 | Fix Doors - Z1 - B2 | 20822 | 20821 | 3123 | 100% | 0.024% | 0.0036% | 15% | 0.14999
|  | Z1-C-FIN-6240 | Fix Doors - Z1 - B2 | 20821 | 20821 | 11681 | 100% | 0.024% | 0.01347% | 56.1% | 0.56102
|  | Z1-C-FIN-7470 | Fix Doors - Z1 - B1 | 20821 | 20821 | 20821 | 100% | 0.024% | 0.024% | 100% | 1
|  | Z1-C-FIN-7490 | Fix Doors - Z1 - B1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-8720 | Fix Doors Garbage & Service Room - Z1 - GF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-8730 | Fix Doors Fire Pump & Cmd Room - Z1 - GF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-8740 | Fix Doors Lift Lobby - Z1 - GF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-8820 | Fix Steel Louver Frames & Doors Generator Room - Z1 - GF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-8860 | Fix Doors LV & Trnsf. Room - Z1 - B1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-9560 | Fix Door Subframes Wet + Dry Area - Z1 - F1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-9630 | Fix Doors Lift Lobby & Passage - Z1 - F1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z1-C-FIN-9790 | Fix Doors Serv. Area - Z1 - F1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
| Div 09 | A9740 | Traffic Deck Coating Drive Way - B2 | 138667 | 138667 | 117867 | 100% | 0.1599% | 0.1359% | 85% | 0.85
|  | A9790 | Traffic Marking Drive Way - B2 | 138667 | 138667 | 117867 | 100% | 0.1599% | 0.1359% | 85% | 0.85
|  | A9810 | Traffic Deck Coating Drive Way - B1 | 138667 | 138667 | 117867 | 100% | 0.1599% | 0.1359% | 85% | 0.85
|  | A9840 | Traffic Marking Drive Way - B1 | 138666 | 138667 | 117867 | 100% | 0.1599% | 0.1359% | 85% | 0.85
|  | C-FIN-ENVLP-9490 | Fix Brackets for Natural Stone - GF to SRVF (Elev. 1 & 4) | 107625 | 107625 | 91481 | 100% | 0.1241% | 0.1055% | 85% | 0.85
|  | C-FIN-ENVLP-9510 | Fix Natural Stone All types- GF to SRVF (Elev. 1 & 4) | 968627 | 968625 | 823331 | 100% | 1.117% | 0.9492% | 85% | 0.85
|  | C-FIN-ENVLP-9610 | Fix Wooden Decorarive Features (Elev. 1 & 4) | 104055 | 104055 | 88447 | 100% | 0.12% | 0.102% | 85% | 0.85
|  | C-FIN-ENVLP-9730 | External Plaster - GF to SRVF (Elev. 1 & 4) | 1822 | 1823 | 1550 | 100.1% | 0.002102% | 0.001787% | 85.07% | 0.85025
|  | Z1-C-FIN-10050 | Anti Fungal Paint - Z1 - F1 | 8946 | 8946 | 7604 | 100% | 0.01031% | 0.008766% | 85% | 0.84999
|  | Z1-C-FIN-10130 | Plaster Works Wet Area - Z1 - F2 | 39011 | 39011 | 33160 | 100% | 0.04497% | 0.03823% | 85% | 0.85002
|  | Z1-C-FIN-10180 | Fix False Ceiling Suspension Lift Lobby - Z1 - F2 | 24288 | 24288 | 23741 | 100% | 0.028% | 0.02737% | 97.75% | 0.97748
|  | Z1-C-FIN-10190 | Wall Paint (Emulsion) Lobby Passage & Offices - Z1 - F2 | 10000 | 10000 | 6545 | 100% | 0.01153% | 0.007545% | 65.45% | 0.6545
|  | Z1-C-FIN-10200 | Porcelain Floor Tiles Passage & Offices - Z1 - F2 | 208302 | 208302 | 177057 | 100% | 0.2401% | 0.2041% | 85% | 0.85
|  | Z1-C-FIN-10230 | Floor Paint (Antifungal) Lift Shaft - Z1 - F2 | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z1-C-FIN-10240 | Wall Paint (Antifungal) Lift Shaft - Z1 - F2 | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z1-C-FIN-10250 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - F2 | 2432 | 2432 | 558 | 100% | 0.002804% | 0.0006433% | 22.94% | 0.22944
|  | Z1-C-FIN-10260 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z1-C-FIN-10280 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - F2 | 24287 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z1-C-FIN-10300 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - F2 | 24287 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z1-C-FIN-10310 | Wall Paint (Acrylic) Serv. Rooms - Z1 - F2 | 2432 | 2432 | 1592 | 100% | 0.002804% | 0.001835% | 65.46% | 0.65461
|  | Z1-C-FIN-10480 | Plaster Works Dry Area - Z1 - F2 | 39011 | 39011 | 33160 | 100% | 0.04497% | 0.03823% | 85% | 0.85002
|  | Z1-C-FIN-10510 | Wall Ceramic Tiles Bath - Z1 - F2 | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z1-C-FIN-10520 | Floor Ceramic Tiles Bath - Z1 - F2 | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z1-C-FIN-10540 | Fix False Ceiling Suspension Bath - Z1 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z1-C-FIN-10560 | Fix False Ceiling Gypsum Board Bath - Z1 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z1-C-FIN-10570 | Fix False Ceiling Aluminum Tiles Bath - Z1 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z1-C-FIN-10610 | Wall Ceramic Tiles kitchen/Pantry - Z1 - F2 | 28908 | 28908 | 24186 | 100% | 0.03333% | 0.02788% | 83.67% | 0.83665
|  | Z1-C-FIN-10620 | Fix False Ceiling Suspension kitchen/Pantry - Z1 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z1-C-FIN-10640 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z1-C-FIN-10650 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z1 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z1-C-FIN-10660 | Floor Ceramic Tiles kitchen/Pantry - Z1 - F2 | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z1-C-FIN-10690 | Ceiling Paint (Emulsion) Garbage Room - Z1 - F2 | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z1-C-FIN-10700 | Wall Paint (Emulsion) Garbage Room - Z1 - F2 | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z1-C-FIN-10750 | Floor Epoxy Paint Garbage Room - Z1 - F2 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z1-C-FIN-10770 | Plaster Works Wet Area - Z1 - RF | 32690 | 32691 | 27787 | 100% | 0.03769% | 0.03203% | 85% | 0.84999
|  | Z1-C-FIN-10790 | Fix False Ceiling Suspension Lift Lobby - Z1 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z1-C-FIN-10800 | Wall Paint (Emulsion) Lobby Passage & Offices - Z1 - RF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z1-C-FIN-10810 | Porcelain Floor Tiles Passage & Offices - Z1 - RF | 158821 | 158821 | 134998 | 100% | 0.1831% | 0.1556% | 85% | 0.85
|  | Z1-C-FIN-10820 | Floor Paint (Antifungal) Lift Shaft - Z1 - RF | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z1-C-FIN-10830 | Wall Paint (Antifungal) Lift Shaft - Z1 - RF | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z1-C-FIN-10840 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - RF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-10850 | Wall Paint (Acrylic) Serv. Rooms - Z1 - RF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-10860 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z1-C-FIN-10870 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z1-C-FIN-10880 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z1-C-FIN-10950 | Plaster Works Dry Area - Z1 - RF | 32690 | 32691 | 27787 | 100% | 0.03769% | 0.03203% | 85% | 0.84999
|  | Z1-C-FIN-10970 | Fix False Ceiling Suspension Bath - Z1 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z1-C-FIN-10980 | Wall Ceramic Tiles Bath - Z1 - RF | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z1-C-FIN-10990 | Floor Ceramic Tiles Bath - Z1 - RF | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z1-C-FIN-11020 | Fix False Ceiling Gypsum Board Bath - Z1 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z1-C-FIN-11030 | Fix False Ceiling Aluminum Tiles Bath - Z1 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z1-C-FIN-11050 | Fix False Ceiling Suspension kitchen/Pantry - Z1 - RF | 18599 | 18598 | 15808 | 99.99% | 0.02144% | 0.01822% | 84.99% | 0.84998
|  | Z1-C-FIN-11060 | Wall Ceramic Tiles kitchen/Pantry - Z1 - RF | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z1-C-FIN-11070 | Floor Ceramic Tiles kitchen/Pantry - Z1 - RF | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z1-C-FIN-11100 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z1-C-FIN-11110 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z1 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z1-C-FIN-11130 | Wall Paint (Emulsion) Garbage Room - Z1 - RF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z1-C-FIN-11140 | Floor Epoxy Paint Garbage Room - Z1 - RF | 4834 | 4833 | 4108 | 99.98% | 0.005572% | 0.004736% | 84.98% | 0.84999
|  | Z1-C-FIN-11170 | Ceiling Paint (Emulsion) Garbage Room - Z1 - RF | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z1-C-FIN-18570 | Ceiling Paint (Emulsion/Acrylic) Secur. Ctrl & Eqpmt Room - Z1 - B1 | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z1-C-FIN-18580 | Wall Paint (Emulsion/Acrylic) Secur. Ctrl & Eqpmt Room - Z1 - B1 | 10000 | 10000 | 6500 | 100% | 0.01153% | 0.007493% | 65% | 0.65
|  | Z1-C-FIN-18590 | Floor Epoxy Paint (Secur. Ctrl & Eqpmt Room) - Z1 - B1 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z1-C-FIN-18610 | Ceiling Paint (Acrylic) Maint. & Serv. Provider Room) - Z1 - B1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-18620 | Wall Paint (Acrylic) Maint. & Serv. Provider Room) - Z1 - B1 | 2432 | 2432 | 1581 | 100% | 0.002804% | 0.001823% | 65.01% | 0.65008
|  | Z1-C-FIN-18630 | Floor Epoxy Paint (Maint. & Serv. Provider Room) - Z1 - B1 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z1-C-FIN-18650 | Ceiling Paint (Acrylic) Loading Room - Z1 - GF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-18670 | Wall Paint (Acrylic) Loading Room - Z1 - GF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-18680 | Floor Stamp Concrete Loading Room - Z1 - GF | 21250 | 21250 | 18062 | 100% | 0.0245% | 0.02082% | 85% | 0.84998
|  | Z1-C-FIN-18700 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - F1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-18710 | Floor Epoxy Paint Serv. Rooms - Z1 - F1 | 4833 | 4834 | 4108 | 100% | 0.005573% | 0.004736% | 85% | 0.84981
|  | Z1-C-FIN-21360 | Wall Paint Outside Area (Acrylic) - Z1 - RF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-21370 | Roof Floor Terrazo Tiles Outside Area - Z1 - RF | 13599 | 13599 | 11559 | 100% | 0.01568% | 0.01333% | 85% | 0.84999
|  | Z1-C-FIN-5800 | Plaster Works - Z1 - B2 | 65100 | 65101 | 6510 | 100% | 0.07505% | 0.007505% | 10% | 0.099998
|  | Z1-C-FIN-6050 | Ceiling Paint (Acrylic) - Z1 - B2 | 2432 | 2432 | 868 | 100% | 0.002804% | 0.001001% | 35.69% | 0.35691
|  | Z1-C-FIN-6060 | Wall Paint (Acrylic) - Z1 - B2 | 2432 | 2432 | 868 | 100% | 0.002804% | 0.001001% | 35.69% | 0.35691
|  | Z1-C-FIN-6070 | Floor Epoxy Paint Serv. Rooms - Z1 - B2 | 4833 | 4833 | 725 | 100% | 0.005572% | 0.0008358% | 15% | 0.15001
|  | Z1-C-FIN-6080 | Ceiling Paint (Acrylic) - Z1 - B2 | 2432 | 2432 | 868 | 100% | 0.002804% | 0.001001% | 35.69% | 0.35691
|  | Z1-C-FIN-6090 | Wall Paint (Acrylic) - Z1 - B2 | 2432 | 2432 | 868 | 100% | 0.002804% | 0.001001% | 35.69% | 0.35691
|  | Z1-C-FIN-6100 | Floor Epoxy Paint - Z1 - B2 | 4833 | 4833 | 725 | 100% | 0.005572% | 0.0008358% | 15% | 0.15001
|  | Z1-C-FIN-6160 | Fix False Ceiling Suspension - Z1 - B2 | 1793 | 1794 | 448 | 100.1% | 0.002068% | 0.0005165% | 24.99% | 0.24972
|  | Z1-C-FIN-6170 | Wall Paint (Emulsion) - Z1 - B2 | 10000 | 10000 | 500 | 100% | 0.01153% | 0.0005764% | 5% | 0.05
|  | Z1-C-FIN-6180 | Porcelain Floor Tiles - Z1 - B2 | 6439 | 6439 | 966 | 100% | 0.007423% | 0.001114% | 15% | 0.15002
|  | Z1-C-FIN-6270 | Wall Paint (Antifungal) Lift Shaft - Z1 - B2 | 8200 | 8200 | 5330 | 100% | 0.009453% | 0.006145% | 65% | 0.65
|  | Z1-C-FIN-6280 | Floor Paint (Antifungal) Lift Shaft - Z1 - B2 | 8200 | 8200 | 5330 | 100% | 0.009453% | 0.006145% | 65% | 0.65
|  | Z1-C-FIN-6290 | Ceiling Paint (Anti-Carbonation) - Z1 - B2 | 46613 | 46613 | 6992 | 100% | 0.05374% | 0.008061% | 15% | 0.15
|  | Z1-C-FIN-6310 | Wall Paint (Anti-Carbonation) - Z1 - B2 | 46612 | 46612 | 26802 | 100% | 0.05374% | 0.0309% | 57.5% | 0.575
|  | Z1-C-FIN-6330 | Fix False Ceiling Gypsum Board & Tiles - Z1 - B2 | 1794 | 1794 | 1525 | 100% | 0.002068% | 0.001758% | 85.01% | 0.85006
|  | Z1-C-FIN-7050 | Plaster Works - Z1 - B1 | 68913 | 68912 | 34456 | 100% | 0.07944% | 0.03972% | 50% | 0.5
|  | Z1-C-FIN-7300 | Ceiling Paint (Emulsion/Acrylic) Store & Serv. Rooms - Z1 - B1 | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z1-C-FIN-7310 | Wall Paint (Emulsion/Acrylic) Store & Serv. Rooms - Z1 - B1 | 10000 | 10000 | 6500 | 100% | 0.01153% | 0.007493% | 65% | 0.65
|  | Z1-C-FIN-7320 | Raise Floor & Epoxy Paint Store & Serv. Rooms - Z1 - B1 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z1-C-FIN-7410 | Fix False Ceiling Gypsum Board & Tiles Lift Lobby - Z1 - B1 | 2621 | 2622 | 2229 | 100% | 0.003023% | 0.00257% | 85.04% | 0.85011
|  | Z1-C-FIN-7420 | Wall Paint (Emulsion) Lift Lobby - Z1 - B1 | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z1-C-FIN-7430 | Porcelain Floor Tiles Lift Lobby - Z1 - B1 | 4734 | 4734 | 3077 | 100% | 0.005457% | 0.003547% | 65% | 0.64998
|  | Z1-C-FIN-7480 | Fix False Ceiling Suspension Lift Lobby - Z1 - B1 | 2622 | 2621 | 2228 | 99.96% | 0.003022% | 0.002568% | 84.97% | 0.85006
|  | Z1-C-FIN-7540 | Ceiling Paint (Anti-Carbonation) - Z1 - B1 | 46613 | 46613 | 39621 | 100% | 0.05374% | 0.04568% | 85% | 0.85
|  | Z1-C-FIN-7560 | Wall Paint (Anti-Carbonation) - Z1 - B1 | 46612 | 46613 | 30298 | 100% | 0.05374% | 0.03493% | 65% | 0.64999
|  | Z1-C-FIN-8340 | Plaster Works - Z1 - GF | 47215 | 47215 | 77905 | 100% | 0.05443% | 0.08981% | 165% | 1.65
|  | Z1-C-FIN-8630 | Ceiling Paint Garbage & Service Room (Acrylic/Emulsion) - Z1 - GF | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z1-C-FIN-8640 | Wall Paint Garbage & Service Room (Acrylic/Emulsion) - Z1 - GF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z1-C-FIN-8650 | Floor Epoxy Paint Garbage & Service Room - Z1 - GF | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z1-C-FIN-8660 | Ceiling Paint (Acrylic/Emulsion) Fire Pump & Cmd Room - Z1 - GF | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z1-C-FIN-8670 | Wall Paint (Acrylic/Emulsion) Fire Pump & Cmd Room - Z1 - GF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z1-C-FIN-8680 | Floor Epoxy Paint Fire Pump & Cmd Room - Z1 - GF | 4834 | 4833 | 4108 | 99.98% | 0.005572% | 0.004736% | 84.98% | 0.84999
|  | Z1-C-FIN-8690 | Fix False Ceiling Suspension Lift Lobby - Z1 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z1-C-FIN-8700 | Wall Paint (Emulsion) Lift Lobby - Z1 - GF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z1-C-FIN-8710 | Porcelain Floor Tiles Lift Lobby - Z1 - GF | 27711 | 27710 | 23553 | 100% | 0.03194% | 0.02715% | 85% | 0.84998
|  | Z1-C-FIN-8770 | Floor Paint (Antifungal) Lift Shaft - Z1 - GF | 8200 | 8200 | 6970 | 100% | 0.009453% | 0.008035% | 85% | 0.85
|  | Z1-C-FIN-8780 | Wall Paint (Antifungal) Lift Shaft - Z1 - GF | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z1-C-FIN-8790 | Ceiling Paint Generator Room (Acrylic) - Z1 - GF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-8800 | Wall Paint Generator Room (Acrylic) - Z1 - GF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-8810 | Floor Epoxy Paint Generator Room - Z1 - GF | 4834 | 4833 | 4108 | 99.98% | 0.005572% | 0.004736% | 84.98% | 0.84999
|  | Z1-C-FIN-8830 | Ceiling Paint LV & Trnsf. Room (Acrylic) - Z1 - B1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-8840 | Wall Paint LV & Trnsf. Room (Acrylic) - Z1 - B1 | 2432 | 2432 | 1581 | 100% | 0.002804% | 0.001823% | 65.01% | 0.65008
|  | Z1-C-FIN-8850 | Floor Epoxy Paint LV & Trnsf. Room- Z1 - B1 | 4834 | 4833 | 4108 | 99.98% | 0.005572% | 0.004736% | 84.98% | 0.84999
|  | Z1-C-FIN-8890 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z1-C-FIN-8920 | Anti Fungal Paint all Shops - Z1 - GF | 8946 | 8946 | 7604 | 100% | 0.01031% | 0.008766% | 85% | 0.84999
|  | Z1-C-FIN-9380 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z1-C-FIN-9500 | Plaster Works Wet + Dry Area - Z1 - F1 | 31626 | 31626 | 26883 | 100% | 0.03646% | 0.03099% | 85% | 0.85003
|  | Z1-C-FIN-9580 | Fix False Ceiling Suspension Lift Lobby & Passage - Z1 - F1 | 17190 | 17189 | 14611 | 99.99% | 0.01982% | 0.01684% | 85% | 0.85002
|  | Z1-C-FIN-9590 | Wall Paint (Emulsion) Lift Lobby & Passage - Z1 - F1 | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z1-C-FIN-9600 | Porcelain Floor Tiles Lift Lobby & Passage- Z1 - F1 | 80416 | 80417 | 68355 | 100% | 0.09271% | 0.0788% | 85% | 0.85001
|  | Z1-C-FIN-9660 | Floor Paint (Antifungal) Lift Shaft - Z1 - F1 | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z1-C-FIN-9670 | Wall Paint (Antifungal) Lift Shaft - Z1 - F1 | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z1-C-FIN-9770 | Ceiling Paint (Acrylic) Serv. Area - Z1 - F1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z1-C-FIN-9780 | Epoxy Paint Serv. Area - Z1 - F1 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z1-C-FIN-9880 | Fix False Ceiling Aluminum Tiles Lift Lobby & Passage - Z1 - F1 | 17189 | 17189 | 14610 | 100% | 0.01982% | 0.01684% | 85% | 0.84996
|  | Z1-C-FIN-9960 | Fix False Ceiling Gypsum Board Lift Lobby & Passage - Z1 - F1 | 17189 | 17189 | 14610 | 100% | 0.01982% | 0.01684% | 85% | 0.84996
|  | Z1-C-FIN-SCASE-8790 | Staircase Acrylic Paint - Z1 - B2 - SRVF | 4259 | 4259 | 3620 | 100% | 0.00491% | 0.004173% | 85% | 0.84996
|  | Z1-C-FIN-SCASE-8800 | Staircase Floor Epoxy Paint - Z1 - B2 - SRVF | 4832 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85.02% | 0.84999
|  | Z1-C-GRBCH-9380 | Install Garbage Chute Cylinder - Z1 - GF to SRVF | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
|  | Z1-C-GRBCH-9390 | Install Garbage Chute Supporting Frame - Z1 - GF to SRVF | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
|  | Z1-C-GRBCH-9400 | Block & Plaster Garbage Room - Z1 - GF to SRVF | 1391 | 1390 | 1182 | 99.93% | 0.001602% | 0.001363% | 84.97% | 0.85036
|  | Z1-C-GRBCH-9410 | Install Garbage Chute Openings & Doors - Z1 - GF to SRVF | 16800 | 16800 | 9690 | 100% | 0.01937% | 0.01117% | 57.68% | 0.57679
|  | Z1-C-GRBCH-9460 | Install Garbage Chute Roof Top Unit with All Provisions | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
|  | Z1-C-GRBCH-9470 | Install Garbage Chute Bottom Unit with All Provisions | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
| Div 10 | A9670 | Casting Service Manholes | 78300 | 78300 | 66555 | 100% | 0.09027% | 0.07673% | 85% | 0.85
|  | Z123-C-FIN-18500 | Fix Rain Water Outlets - Z123 - TRF | 6000 | 6000 | 5100 | 100% | 0.006917% | 0.005879% | 85% | 0.85
|  | Z1-C-CON-2540 | Fix MEP Provisions - Z1 - Raft | 21000 | 21000 | 4463 | 100% | 0.02421% | 0.005145% | 21.25% | 0.21252
|  | Z1-C-FIN-6250 | Fix Pump - Z1 - B2 | 36876 | 36875 | 5531 | 100% | 0.04251% | 0.006376% | 15% | 0.14999
|  | Z1-C-FIN-6260 | Fix Final Connections of Pumps with Risers - Z1 - B2 | 36875 | 36875 | 20687 | 100% | 0.04251% | 0.02385% | 56.1% | 0.561
|  | Z1-C-FIN-8750 | Fix Electric Pump Fire Pump Room - Z1 - GF | 220779 | 220780 | 187663 | 100% | 0.2545% | 0.2163% | 85% | 0.85
|  | Z1-C-FIN-8760 | Fix Final Connections with Risers Fire Pump Room - Z1 - GF | 36875 | 36875 | 31344 | 100% | 0.04251% | 0.03613% | 85% | 0.85001
|  | Z1-C-FIN-9310 | Fix Diesel Pump Fire Pump Room- Z1 - GF | 220780 | 220779 | 187662 | 100% | 0.2545% | 0.2163% | 85% | 0.85
|  | Z1-C-FIN-9320 | Fix Jockey Pump Fire Pump Room- Z1 - GF | 220780 | 220779 | 187662 | 100% | 0.2545% | 0.2163% | 85% | 0.85
|  | Z1-C-FIN-9340 | Final Connections & Termination Fire Pump Room - Z1 - GF | 36875 | 36875 | 31344 | 100% | 0.04251% | 0.03613% | 85% | 0.85001
|  | Z1-C-MEP-5820 | Fix Drainage Pipes - Z1 - B2 | 10868 | 10868 | 9988 | 100% | 0.01253% | 0.01151% | 91.9% | 0.91903
|  | Z1-C-MEP-7070 | Fix Drainage Pipes - Z1 - B1 | 9366 | 9368 | 15454 | 100% | 0.0108% | 0.01782% | 165% | 1.6497
|  | Z1-C-MEP-8360 | Fix Drainage Pipes - Z1 - GF | 9367 | 9368 | 7963 | 100% | 0.0108% | 0.00918% | 85.01% | 0.85002
|  | Z1-C-MEP-8590 | Fix Water Supply Pipes - Z1 - GF | 6590 | 6591 | 5603 | 100% | 0.007598% | 0.006459% | 85.02% | 0.8501
|  | Z1-C-MEP-8630 | Fix Water Heater & Sanitary Accessories - Z1 - GF | 75575 | 75574 | 64238 | 100% | 0.08712% | 0.07405% | 85% | 0.85
|  | Z1-C-MEP-8640 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - GF | 6591 | 6591 | 1648 | 100% | 0.007598% | 0.0019% | 25% | 0.25004
|  | Z1-C-MEP-8660 | Fix Drainage Pipes - Z1 - F1 | 9367 | 9368 | 7963 | 100% | 0.0108% | 0.00918% | 85.01% | 0.85002
|  | Z1-C-MEP-8920 | Fix Water Supply Pipes - Z1 - F1 | 6590 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 85.01% | 0.84995
|  | Z1-C-MEP-8930 | Fix Water Heater & Sanitary Accessories - Z1 - F1 | 75575 | 75575 | 64239 | 100% | 0.08712% | 0.07406% | 85% | 0.85
|  | Z1-C-MEP-8940 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - F1 | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z1-C-MEP-8960 | Fix Drainage Pipes - Z1 - F2 | 9368 | 9368 | 6700 | 100% | 0.0108% | 0.007724% | 71.52% | 0.7152
|  | Z1-C-MEP-9220 | Fix Water Supply Pipes - Z1 - F2 | 6590 | 6591 | 5514 | 100% | 0.007598% | 0.006357% | 83.67% | 0.8366
|  | Z1-C-MEP-9230 | Fix Water Heater & Sanitary Accessories - Z1 - F2 | 75575 | 75575 | 64239 | 100% | 0.08712% | 0.07406% | 85% | 0.85
|  | Z1-C-MEP-9240 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - F2 | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z1-C-MEP-9280 | Fix Drainage Pipes - Z1 - RF | 9368 | 9368 | 7963 | 100% | 0.0108% | 0.00918% | 85% | 0.85002
|  | Z1-C-MEP-9540 | Fix Water Supply Pipes - Z1 - RF | 6591 | 6591 | 6736 | 100% | 0.007598% | 0.007765% | 102.2% | 1.022
|  | Z1-C-MEP-9550 | Fix Water Heater & Sanitary Accessories - Z1 - RF | 75575 | 75575 | 64239 | 100% | 0.08712% | 0.07406% | 85% | 0.85
|  | Z1-C-MEP-9560 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - RF | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z1-C-RSRS-11020 | Install Drainage Pipe Risers | 6591 | 6591 | 4687 | 100% | 0.007598% | 0.005403% | 71.11% | 0.71112
|  | Z1-C-RSRS-11030 | Install Water Supply Pipe Risers | 6591 | 6591 | 4687 | 100% | 0.007598% | 0.005403% | 71.11% | 0.71112
| Div 11 | Z1-C-MEP-5830 | Fix Fire Fighting Pipes - Z1 - B2 | 82008 | 82009 | 75370 | 100% | 0.09454% | 0.08689% | 91.91% | 0.91905
|  | Z1-C-MEP-5860 | Fix Fire Fighting Dropers - Z1 - B2 | 10627 | 10628 | 2657 | 100% | 0.01225% | 0.003063% | 25% | 0.25
|  | Z1-C-MEP-6020 | Fix Fire Hose Cabinets & Hose Reels - Z1 - B2 | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z1-C-MEP-6030 | Fix Sprinklers - Z1 - B2 | 20692 | 20693 | 35349 | 100% | 0.02386% | 0.04075% | 170.8% | 1.7083
|  | Z1-C-MEP-7080 | Fix Fire Fighting Pipes - Z1 - B1 | 59346 | 59346 | 97921 | 100% | 0.06842% | 0.1129% | 165% | 1.65
|  | Z1-C-MEP-7110 | Fix Fire Fighting Dropers - Z1 - B1 | 10628 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85% | 0.85002
|  | Z1-C-MEP-7270 | Fix Fire Hose Cabinets & Hose Reels - Z1 - B1 | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z1-C-MEP-7280 | Fix Sprinklers - Z1 - B1 | 20692 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
|  | Z1-C-MEP-8370 | Fix Fire Fighting Pipes - Z1 - GF | 59346 | 59346 | 50444 | 100% | 0.06842% | 0.05815% | 85% | 0.85
|  | Z1-C-MEP-8400 | Fix Fire Fighting Dropers - Z1 - GF | 10627 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85.01% | 0.85002
|  | Z1-C-MEP-8560 | Fix Fire Hose Cabinets & Hose Reels - Z1 - GF | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z1-C-MEP-8570 | Fix Sprinklers - Z1 - GF | 20692 | 20693 | 17589 | 100% | 0.02386% | 0.02028% | 85% | 0.85
|  | Z1-C-MEP-8670 | Fix Fire Fighting Pipes - Z1 - F1 | 59346 | 59346 | 50444 | 100% | 0.06842% | 0.05815% | 85% | 0.85
|  | Z1-C-MEP-8700 | Fix Fire Fighting Dropers - Z1 - F1 | 10628 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85% | 0.85002
|  | Z1-C-MEP-8860 | Fix Fire Hose Cabinets & Hose Reels - Z1 - F1 | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z1-C-MEP-8870 | Fix Sprinklers - Z1 - F1 | 20692 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
|  | Z1-C-MEP-8970 | Fix Fire Fighting Pipes - Z1 - F2 | 59346 | 59346 | 42445 | 100% | 0.06842% | 0.04893% | 71.52% | 0.71521
|  | Z1-C-MEP-9000 | Fix Fire Fighting Dropers - Z1 - F2 | 10628 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85% | 0.85002
|  | Z1-C-MEP-9160 | Fix Fire Hose Cabinets & Hose Reels - Z1 - F2 | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z1-C-MEP-9170 | Fix Sprinklers - Z1 - F2 | 20692 | 20693 | 17589 | 100% | 0.02386% | 0.02028% | 85% | 0.85
|  | Z1-C-MEP-9290 | Fix Fire Fighting Pipes - Z1 - RF | 59346 | 59346 | 50444 | 100% | 0.06842% | 0.05815% | 85% | 0.85
|  | Z1-C-MEP-9320 | Fix Fire Fighting Dropers - Z1 - RF | 10627 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85.01% | 0.85002
|  | Z1-C-MEP-9480 | Fix Fire Hose Cabinets & Hose Reels - Z1 - RF | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z1-C-MEP-9490 | Fix Sprinklers - Z1 - RF | 20691 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
| Div 12 | Z1-C-FIN-10000 | Fix MEP Droppers Lift Lobby & Passage - Z1 - F1 | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z1-C-FIN-10320 | Fix MEP Droppers Lift Lobby - Z1 - F2 | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z1-C-FIN-10550 | Fix MEP Droppers Bath - Z1 - F2 | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z1-C-FIN-10630 | Fix MEP Droppers kitchen/Pantry - Z1 - F2 | 10750 | 10750 | 9138 | 100% | 0.01239% | 0.01053% | 85% | 0.85005
|  | Z1-C-FIN-10890 | Fix MEP Droppers Lift Lobby - Z1 - RF | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z1-C-FIN-11040 | Fix MEP Droppers Bath - Z1 - RF | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z1-C-FIN-11120 | Fix MEP Droppers kitchen/Pantry - Z1 - RF | 10751 | 10750 | 6854 | 99.99% | 0.01239% | 0.007901% | 63.75% | 0.63758
|  | Z1-C-FIN-8900 | Fix MEP Droppers Lift Lobby - Z1 - GF | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z1-C-MEP-5840 | Fix Chill Water Pipes - Z1 - B2 | 106572 | 106572 | 97945 | 100% | 0.1229% | 0.1129% | 91.91% | 0.91905
|  | Z1-C-MEP-5850 | Fix HVAC Ducts & Insulation - Z1 - B2 | 205842 | 205841 | 189177 | 100% | 0.2373% | 0.2181% | 91.9% | 0.91904
|  | Z1-C-MEP-5870 | Fix FCU - Z1 - B2 | 19285 | 19285 | 10819 | 100% | 0.02223% | 0.01247% | 56.1% | 0.56101
|  | Z1-C-MEP-6040 | Fix Grills & Diffusers - Z1 - B2 | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z1-C-MEP-7090 | Fix Chill Water Pipes - Z1 - B1 | 106571 | 106572 | 175842 | 100% | 0.1229% | 0.2027% | 165% | 1.65
|  | Z1-C-MEP-7100 | Fix HVAC Ducts & Insulation - Z1 - B1 | 205842 | 205840 | 339639 | 100% | 0.2373% | 0.3915% | 165% | 1.65
|  | Z1-C-MEP-7120 | Fix FCU - Z1 - B1 | 39085 | 39085 | 33222 | 100% | 0.04506% | 0.0383% | 85% | 0.84999
|  | Z1-C-MEP-7290 | Fix Grills & Diffusers - Z1 - B1 | 17845 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z1-C-MEP-8380 | Fix Chill Water Pipes - Z1 - GF | 106571 | 106571 | 90585 | 100% | 0.1229% | 0.1044% | 85% | 0.85
|  | Z1-C-MEP-8390 | Fix HVAC Ducts & Insulation - Z1 - GF | 205841 | 205841 | 174965 | 100% | 0.2373% | 0.2017% | 85% | 0.85
|  | Z1-C-MEP-8410 | Fix FCU - Z1 - GF | 151284 | 151285 | 128592 | 100% | 0.1744% | 0.1482% | 85% | 0.85
|  | Z1-C-MEP-8580 | Fix Grills & Diffusers - Z1 - GF | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z1-C-MEP-8680 | Fix Chill Water Pipes - Z1 - F1 | 106571 | 106572 | 90586 | 100% | 0.1229% | 0.1044% | 85% | 0.85
|  | Z1-C-MEP-8690 | Fix HVAC Ducts & Insulation - Z1 - F1 | 205841 | 205841 | 174965 | 100% | 0.2373% | 0.2017% | 85% | 0.85
|  | Z1-C-MEP-8710 | Fix FCU - Z1 - F1 | 129834 | 129834 | 110359 | 100% | 0.1497% | 0.1272% | 85% | 0.85
|  | Z1-C-MEP-8880 | Fix Grills & Diffusers - Z1 - F1 | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z1-C-MEP-8980 | Fix Chill Water Pipes - Z1 - F2 | 106571 | 106571 | 89162 | 100% | 0.1229% | 0.1028% | 83.66% | 0.83664
|  | Z1-C-MEP-8990 | Fix HVAC Ducts & Insulation - Z1 - F2 | 205840 | 205840 | 147220 | 100% | 0.2373% | 0.1697% | 71.52% | 0.71522
|  | Z1-C-MEP-9010 | Fix FCU - Z1 - F2 | 151284 | 151285 | 128592 | 100% | 0.1744% | 0.1482% | 85% | 0.85
|  | Z1-C-MEP-9180 | Fix Grills & Diffusers - Z1 - F2 | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z1-C-MEP-9300 | Fix Chill Water Pipes - Z1 - RF | 106571 | 106572 | 108918 | 100% | 0.1229% | 0.1256% | 102.2% | 1.022
|  | Z1-C-MEP-9310 | Fix HVAC Ducts & Insulation - Z1 - RF | 205841 | 205841 | 174965 | 100% | 0.2373% | 0.2017% | 85% | 0.85
|  | Z1-C-MEP-9330 | Fix FCU - Z1 - RF | 129835 | 129834 | 64376 | 100% | 0.1497% | 0.07421% | 49.58% | 0.49583
|  | Z1-C-MEP-9500 | Fix Grills & Diffusers - Z1 - RF | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z1-C-RSRS-11050 | Install Fire Fighting Pipe Risers | 404399 | 404400 | 245583 | 100% | 0.4662% | 0.2831% | 60.73% | 0.60728
| Div 13 | Z1-C-LIFT-9110 | Install Working Platm for PL-1 & 2 (B2 to SRVF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z1-C-LIFT-9120 | Install Steel Support Beams & Tracks PL-1 & 2 (B2 to SRVF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z1-C-LIFT-9190 | Repair Lift Shaft PL-1 & 2 (B2 to SRVF) | 97230 | 97230 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85001
|  | Z1-C-LIFT-9230 | Terminate Tracks & Cross Beams (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z1-C-LIFT-9240 | Install Lift Access Doors (B2 to GF) | 97230 | 97231 | 96420 | 100% | 0.1121% | 0.1112% | 99.17% | 0.99166
|  | Z1-C-LIFT-9250 | Install Lift Cabin (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z1-C-LIFT-9260 | Install Lift Motors Cables, Counter Weight & Brakes (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z1-C-LIFT-9270 | Install Lift Control Unit (B2 to GF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z1-C-LIFT-9280 | Power Connection & Test Runs (B2 to GF) | 97230 | 97230 | 82645 | 100% | 0.1121% | 0.09527% | 85% | 0.84999
| Div 14 | Z1-C-MEP-9250 | Fix LPG Pipes - Z1 - F2 | 12342 | 12342 | 2832 | 100% | 0.01423% | 0.003265% | 22.95% | 0.22946
|  | Z1-C-MEP-9260 | Fix Gas Detectors - Z1 - F2 | 12341 | 12342 | 10491 | 100% | 0.01423% | 0.01209% | 85.01% | 0.85002
|  | Z1-C-MEP-9570 | Fix LPG Pipes - Z1 - RF | 12341 | 12342 | 10491 | 100% | 0.01423% | 0.01209% | 85.01% | 0.85002
|  | Z1-C-MEP-9580 | Fix Gas Detectors - Z1 - RF | 12341 | 12341 | 10490 | 100% | 0.01423% | 0.01209% | 85% | 0.85001
|  | Z1-C-RSRS-11070 | Install LPG Pipe Risers | 12344 | 12342 | 12391 | 99.98% | 0.01423% | 0.01428% | 100.4% | 1.004
| Div 15 | ADCE-MALL-EL-2280 | Installation of HV Panels, Transformers & etc by AADC | 1210608 | 1210609 | 1029018 | 100% | 1.396% | 1.186% | 85% | 0.85
|  | Z1-C-FIN-8880 | Final Connections & Termination Generator Room - Z1 - GF | 61109 | 61109 | 51942 | 100% | 0.07045% | 0.05988% | 85% | 0.84999
|  | Z1-C-FIN-9300 | Fix Generator Generator Room - Z1 - GF | 703940 | 703939 | 598348 | 100% | 0.8115% | 0.6898% | 85% | 0.85
|  | Z1-C-FIN-9330 | Fix MCC Pannels LV & Trnsf. Room- Z1 - B1 | 442610 | 442609 | 885220 | 100% | 0.5102% | 1.021% | 200% | 2
|  | Z1-C-FIN-9350 | Connections & Termonation LV & Trnsf. Room - Z1 - B1 | 31615 | 31615 | 26873 | 100% | 0.03645% | 0.03098% | 85% | 0.85001
|  | Z1-C-FIN-SCASE-8910 | Install MEP Final Fixes Staircase - Z1 - B2 - SRVF | 7203 | 7203 | 6123 | 100% | 0.008304% | 0.007059% | 85.01% | 0.85006
|  | Z1-C-MEP-5810 | Fix G.I Box and conduits - Z1 - B2 | 26755 | 26755 | 14113 | 100% | 0.03084% | 0.01627% | 52.75% | 0.52749
|  | Z1-C-MEP-5880 | Fix ELV Trunkings - Z1 - B2 | 35620 | 35621 | 31295 | 100% | 0.04106% | 0.03608% | 87.86% | 0.87855
|  | Z1-C-MEP-5890 | Pull ELV Cables - Z1 - B2 | 46004 | 46003 | 37309 | 100% | 0.05303% | 0.04301% | 81.1% | 0.81101
|  | Z1-C-MEP-5900 | Fix Power Cable Trays - Z1 - B2 | 32904 | 32905 | 28909 | 100% | 0.03793% | 0.03333% | 87.86% | 0.87856
|  | Z1-C-MEP-5910 | Pull Electricl Wires (Ceiling & Walls) - Z1 - B2 | 10783 | 10782 | 8745 | 99.99% | 0.01243% | 0.01008% | 81.1% | 0.81107
|  | Z1-C-MEP-5920 | Pull Earthing & Power Cables - Z1 - B2 | 84717 | 84717 | 68705 | 100% | 0.09766% | 0.0792% | 81.1% | 0.81099
|  | Z1-C-MEP-5930 | Fix DBs - Z1 - B2 | 64069 | 64068 | 48509 | 100% | 0.07386% | 0.05592% | 75.71% | 0.75715
|  | Z1-C-MEP-5940 | Cable Terminations - Z1 - B2 | 61109 | 61109 | 34282 | 100% | 0.07045% | 0.03952% | 56.1% | 0.561
|  | Z1-C-MEP-5950 | Fix CCTV Devices - Z1 - B2 | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z1-C-MEP-5960 | Fix Light Fixtures - Z1 - B2 | 115829 | 115829 | 98455 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z1-C-MEP-5970 | Fix Switches, Sockets & Isolators - Z1 - B2 | 11418 | 11418 | 9705 | 100% | 0.01316% | 0.01119% | 85% | 0.84997
|  | Z1-C-MEP-5980 | Fix Fire Alarm Devices - Z1 - B2 | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z1-C-MEP-5990 | Fix Telephone & Voice Evac. Devices - Z1 - B2 | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z1-C-MEP-6000 | Fix LCS & ACS Devices - Z1 - B2 | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z1-C-MEP-6010 | Fix Emergency & Exit Lights - Z1 - B2 | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z1-C-MEP-7060 | Fix G.I Box and conduits - Z1 - B1 | 26755 | 26755 | 15010 | 100% | 0.03084% | 0.0173% | 56.1% | 0.56102
|  | Z1-C-MEP-7130 | Fix ELV Trunkings - Z1 - B1 | 35621 | 35620 | 58775 | 100% | 0.04106% | 0.06776% | 165% | 1.6501
|  | Z1-C-MEP-7140 | Pull ELV Cables - Z1 - B1 | 46004 | 46003 | 39103 | 100% | 0.05303% | 0.04508% | 85% | 0.85001
|  | Z1-C-MEP-7150 | Fix Power Cable Trays - Z1 - B1 | 32905 | 32904 | 54293 | 100% | 0.03793% | 0.06259% | 165% | 1.65
|  | Z1-C-MEP-7160 | Pull Electricl Wires (Ceiling & Walls) - Z1 - B1 | 10783 | 10782 | 9165 | 99.99% | 0.01243% | 0.01057% | 84.99% | 0.85003
|  | Z1-C-MEP-7170 | Pull Earthing & Power Cables - Z1 - B1 | 84716 | 84717 | 72009 | 100% | 0.09766% | 0.08301% | 85% | 0.84999
|  | Z1-C-MEP-7180 | Fix DBs - Z1 - B1 | 64069 | 64069 | 54458 | 100% | 0.07386% | 0.06278% | 85% | 0.84999
|  | Z1-C-MEP-7190 | Cable Terminations - Z1 - B1 | 61108 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z1-C-MEP-7200 | Fix CCTV Devices - Z1 - B1 | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z1-C-MEP-7210 | Fix Light Fixtures - Z1 - B1 | 115829 | 115829 | 98455 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z1-C-MEP-7220 | Fix Switches, Sockets & Isolators - Z1 - B1 | 11418 | 11418 | 9705 | 100% | 0.01316% | 0.01119% | 85% | 0.84997
|  | Z1-C-MEP-7230 | Fix Fire Alarm Devices - Z1 - B1 | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z1-C-MEP-7240 | Fix Telephone & Voice Evac. Devices - Z1 - B1 | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z1-C-MEP-7250 | Fix LCS & ACS Devices - Z1 - B1 | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z1-C-MEP-7260 | Fix Emergency & Exit Lights - Z1 - B1 | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z1-C-MEP-8350 | Fix G.I Box and conduits - Z1 - GF | 26755 | 26755 | 6689 | 100% | 0.03084% | 0.007711% | 25% | 0.25001
|  | Z1-C-MEP-8420 | Fix ELV Trunkings - Z1 - GF | 35620 | 35620 | 30277 | 100% | 0.04106% | 0.0349% | 85% | 0.85
|  | Z1-C-MEP-8430 | Pull ELV Cables - Z1 - GF | 46003 | 46003 | 39103 | 100% | 0.05303% | 0.04508% | 85% | 0.85001
|  | Z1-C-MEP-8440 | Fix Power Cable Trays - Z1 - GF | 32904 | 32904 | 27969 | 100% | 0.03793% | 0.03224% | 85% | 0.85002
|  | Z1-C-MEP-8450 | Pull Electricl Wires (Ceiling & Walls) - Z1 - GF | 10780 | 10782 | 9165 | 100% | 0.01243% | 0.01057% | 85.02% | 0.85003
|  | Z1-C-MEP-8460 | Pull Earthing & Power Cables - Z1 - GF | 84718 | 84718 | 72010 | 100% | 0.09766% | 0.08301% | 85% | 0.85
|  | Z1-C-MEP-8470 | Fix DBs - Z1 - GF | 64069 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z1-C-MEP-8480 | Cable Terminations - Z1 - GF | 61109 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z1-C-MEP-8490 | Fix CCTV Devices - Z1 - GF | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z1-C-MEP-8500 | Fix Light Fixtures - Z1 - GF | 115828 | 115828 | 98454 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z1-C-MEP-8510 | Fix Switches, Sockets & Isolators - Z1 - GF | 11417 | 11418 | 9706 | 100% | 0.01316% | 0.01119% | 85.01% | 0.85006
|  | Z1-C-MEP-8520 | Fix Fire Alarm Devices - Z1 - GF | 51070 | 51069 | 43408 | 100% | 0.05887% | 0.05004% | 85% | 0.84999
|  | Z1-C-MEP-8530 | Fix Telephone & Voice Evac. Devices - Z1 - GF | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z1-C-MEP-8540 | Fix LCS & ACS Devices - Z1 - GF | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z1-C-MEP-8550 | Fix Emergency & Exit Lights - Z1 - GF | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z1-C-MEP-8650 | Fix G.I Box and conduits - Z1 - F1 | 26755 | 26755 | 22742 | 100% | 0.03084% | 0.02622% | 85% | 0.85001
|  | Z1-C-MEP-8720 | Fix ELV Trunkings - Z1 - F1 | 35620 | 35620 | 30277 | 100% | 0.04106% | 0.0349% | 85% | 0.85
|  | Z1-C-MEP-8730 | Pull ELV Cables - Z1 - F1 | 46004 | 46003 | 39103 | 100% | 0.05303% | 0.04508% | 85% | 0.85001
|  | Z1-C-MEP-8740 | Fix Power Cable Trays - Z1 - F1 | 32904 | 32905 | 27969 | 100% | 0.03793% | 0.03224% | 85% | 0.84999
|  | Z1-C-MEP-8750 | Pull Electricl Wires (Ceiling & Walls) - Z1 - F1 | 10780 | 10781 | 9347 | 100% | 0.01243% | 0.01078% | 86.71% | 0.86699
|  | Z1-C-MEP-8760 | Pull Earthing & Power Cables - Z1 - F1 | 84719 | 84717 | 73450 | 100% | 0.09766% | 0.08467% | 86.7% | 0.867
|  | Z1-C-MEP-8770 | Fix DBs - Z1 - F1 | 64069 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z1-C-MEP-8780 | Cable Terminations - Z1 - F1 | 61109 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z1-C-MEP-8790 | Fix CCTV Devices - Z1 - F1 | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z1-C-MEP-8800 | Fix Light Fixtures - Z1 - F1 | 115829 | 115829 | 98455 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z1-C-MEP-8810 | Fix Switches, Sockets & Isolators - Z1 - F1 | 11418 | 11418 | 9705 | 100% | 0.01316% | 0.01119% | 85% | 0.84997
|  | Z1-C-MEP-8820 | Fix Fire Alarm Devices - Z1 - F1 | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z1-C-MEP-8830 | Fix Telephone & Voice Evac. Devices - Z1 - F1 | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z1-C-MEP-8840 | Fix LCS & ACS Devices - Z1 - F1 | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z1-C-MEP-8850 | Fix Emergency & Exit Lights - Z1 - F1 | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z1-C-MEP-8950 | Fix G.I Box and conduits - Z1 - F2 | 26755 | 26755 | 22742 | 100% | 0.03084% | 0.02622% | 85% | 0.85001
|  | Z1-C-MEP-9020 | Fix ELV Trunkings - Z1 - F2 | 35620 | 35620 | 29802 | 100% | 0.04106% | 0.03436% | 83.67% | 0.83666
|  | Z1-C-MEP-9030 | Pull ELV Cables - Z1 - F2 | 46004 | 46003 | 39102 | 100% | 0.05303% | 0.04508% | 85% | 0.84999
|  | Z1-C-MEP-9040 | Fix Power Cable Trays - Z1 - F2 | 32904 | 32904 | 27529 | 100% | 0.03793% | 0.03174% | 83.66% | 0.83665
|  | Z1-C-MEP-9050 | Pull Electricl Wires (Ceiling & Walls) - Z1 - F2 | 10780 | 10782 | 9165 | 100% | 0.01243% | 0.01057% | 85.02% | 0.85003
|  | Z1-C-MEP-9060 | Pull Earthing & Power Cables - Z1 - F2 | 84718 | 84718 | 72011 | 100% | 0.09766% | 0.08302% | 85% | 0.85001
|  | Z1-C-MEP-9070 | Fix DBs - Z1 - F2 | 64069 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z1-C-MEP-9080 | Cable Terminations - Z1 - F2 | 61109 | 61109 | 27827 | 100% | 0.07045% | 0.03208% | 45.54% | 0.45537
|  | Z1-C-MEP-9090 | Fix CCTV Devices - Z1 - F2 | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z1-C-MEP-9100 | Fix Light Fixtures - Z1 - F2 | 115829 | 115828 | 98454 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z1-C-MEP-9110 | Fix Switches, Sockets & Isolators - Z1 - F2 | 11418 | 11418 | 3812 | 100% | 0.01316% | 0.004395% | 33.39% | 0.33386
|  | Z1-C-MEP-9120 | Fix Fire Alarm Devices - Z1 - F2 | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z1-C-MEP-9130 | Fix Telephone & Voice Evac. Devices - Z1 - F2 | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z1-C-MEP-9140 | Fix LCS & ACS Devices - Z1 - F2 | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z1-C-MEP-9150 | Fix Emergency & Exit Lights - Z1 - F2 | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z1-C-MEP-9270 | Fix G.I Box and conduits - Z1 - RF | 26755 | 26755 | 22742 | 100% | 0.03084% | 0.02622% | 85% | 0.85001
|  | Z1-C-MEP-9340 | Fix ELV Trunkings - Z1 - RF | 35620 | 35620 | 30277 | 100% | 0.04106% | 0.0349% | 85% | 0.85
|  | Z1-C-MEP-9350 | Pull ELV Cables - Z1 - RF | 46003 | 46003 | 39103 | 100% | 0.05303% | 0.04508% | 85% | 0.85001
|  | Z1-C-MEP-9360 | Fix Power Cable Trays - Z1 - RF | 32904 | 32905 | 33629 | 100% | 0.03793% | 0.03877% | 102.2% | 1.022
|  | Z1-C-MEP-9370 | Pull Electricl Wires (Ceiling & Walls) - Z1 - RF | 10780 | 10782 | 9165 | 100% | 0.01243% | 0.01057% | 85.02% | 0.85003
|  | Z1-C-MEP-9380 | Pull Earthing & Power Cables - Z1 - RF | 84718 | 84717 | 72010 | 100% | 0.09766% | 0.08301% | 85% | 0.85001
|  | Z1-C-MEP-9390 | Fix DBs - Z1 - RF | 64069 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z1-C-MEP-9400 | Cable Terminations - Z1 - RF | 61109 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z1-C-MEP-9410 | Fix CCTV Devices - Z1 - RF | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z1-C-MEP-9420 | Fix Light Fixtures - Z1 - RF | 115828 | 115828 | 98454 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z1-C-MEP-9430 | Fix Switches, Sockets & Isolators - Z1 - RF | 11417 | 11418 | 9705 | 100% | 0.01316% | 0.01119% | 85% | 0.84997
|  | Z1-C-MEP-9440 | Fix Fire Alarm Devices - Z1 - RF | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z1-C-MEP-9450 | Fix Telephone & Voice Evac. Devices - Z1 - RF | 43578 | 43578 | 37042 | 100% | 0.05024% | 0.0427% | 85% | 0.85002
|  | Z1-C-MEP-9460 | Fix LCS & ACS Devices - Z1 - RF | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z1-C-MEP-9470 | Fix Emergency & Exit Lights - Z1 - RF | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z1-C-RSRS-11110 | Power Cable Pulling & Termination Risers | 61105 | 61108 | 51941 | 100% | 0.07045% | 0.05988% | 85% | 0.84999
Z2 | Div 01 | PRL-RCR-6980 | Recurring Preliminaries through out the project | 4687620 | 4634826 | 22628141 | 98.87% | 5.343% | 26.09% | 482.7% | 4.8822
| Div 02 | A9860 | Install Stamped Concrete | 199500 | 199500 | 169575 | 100% | 0.23% | 0.1955% | 85% | 0.85
|  | C-EW-10400 | Excavation Stage 2 - Z2&3 | 440461 | 440460 | 285198 | 100% | 0.5078% | 0.3288% | 64.75% | 0.6475
|  | C-EW-10430 | Strut Pipe Bracing - Z2&3 | 254480 | 254480 | 216308 | 100% | 0.2934% | 0.2494% | 85% | 0.85
|  | C-EW-10440 | Excavation Stage 1 - Z2&3 | 348229 | 348230 | 212669 | 100% | 0.4014% | 0.2452% | 61.07% | 0.61071
|  | C-SHRNG-DCE-C-2360 | Place Guide Wall - Z2&3 | 162250 | 162250 | 178476 | 100% | 0.187% | 0.2058% | 110% | 1.1
|  | C-SHRNG-DCE-C-2370 | Install Shoring System - Z2&3 | 2987501 | 2987500 | 1643125 | 100% | 3.444% | 1.894% | 55% | 0.55
|  | C-SHRNG-DCE-C-2380 | Install Capping Beam - Z2&3 | 271284 | 271284 | 298412 | 100% | 0.3127% | 0.344% | 110% | 1.1
| Div 03 | C-EW-10410 | Gunite Wall - Z2 | 228837 | 228838 | 2288 | 100% | 0.2638% | 0.002638% | 0.9998% | 0.0099983
|  | Z2-11520 | Post Tensioning the Slab - Z2 - F1 | 18819 | 18819 | 4705 | 100% | 0.02169% | 0.005424% | 25% | 0.25001
|  | Z2-11530 | Post Tensioning the Slab - Z2 - F2 | 19103 | 19104 | 16238 | 100% | 0.02202% | 0.01872% | 85% | 0.84998
|  | Z2-11540 | Post Tensioning the Slab - Z2 - RF | 19044 | 19044 | 16187 | 100% | 0.02195% | 0.01866% | 85% | 0.84998
|  | Z2-11550 | Post Tensioning the Slab - Z2 - SRVF | 15998 | 15998 | 13598 | 100% | 0.01844% | 0.01568% | 85% | 0.84998
|  | Z2-C-CON-5840 | PCC Blind Concrete - Z2 - Lift Pit | 8610 | 8610 | 86 | 100% | 0.009926% | 9.914e-05% | 0.9988% | 0.0099884
|  | Z2-C-CON-5850 | Waterproof Membrane - Z2 - Lift Pit | 51140 | 51140 | 511 | 100% | 0.05896% | 0.0005891% | 0.9992% | 0.0099922
|  | Z2-C-CON-5860 | Protection Screed - Z2 - Lift Pit | 5490 | 5490 | 55 | 100% | 0.006329% | 6.341e-05% | 1.002% | 0.010018
|  | Z2-C-CON-5870 | Fix Rebar - Z2 - Lift Pit | 15186 | 15186 | 304 | 100% | 0.01751% | 0.0003505% | 2.002% | 0.020018
|  | Z2-C-CON-5890 | Pour Concrete - Z2 - Lift Pit | 15186 | 15186 | 3227 | 100% | 0.01751% | 0.00372% | 21.25% | 0.2125
|  | Z2-C-CON-5900 | PCC Blind Concrete - Z2 - Raft | 43050 | 43050 | 9148 | 100% | 0.04963% | 0.01055% | 21.25% | 0.2125
|  | Z2-C-CON-5910 | Waterproof Membrane - Z2 - Raft | 27450 | 27450 | 5833 | 100% | 0.03164% | 0.006724% | 21.25% | 0.2125
|  | Z2-C-CON-5920 | Protection Screed - Z2 - Raft | 255700 | 255700 | 54336 | 100% | 0.2948% | 0.06264% | 21.25% | 0.2125
|  | Z2-C-CON-5930 | Fix Rebar - Z2 - Raft | 746627 | 746626 | 634632 | 100% | 0.8607% | 0.7316% | 85% | 0.85
|  | Z2-C-CON-5950 | Fix Formwork - Z2 - Raft | 30991 | 30991 | 26342 | 100% | 0.03573% | 0.03037% | 85% | 0.84999
|  | Z2-C-CON-5960 | Pour Concrete - Z2 - Raft | 548054 | 548054 | 465846 | 100% | 0.6318% | 0.537% | 85% | 0.85
|  | Z2-C-CON-5970 | Fix Rebar Columns - Z2 - B2 | 47430 | 47430 | 40316 | 100% | 0.05468% | 0.04648% | 85% | 0.85001
|  | Z2-C-CON-5980 | Fix Formwork Columns - Z2 - B2 | 23715 | 23715 | 20158 | 100% | 0.02734% | 0.02324% | 85% | 0.85001
|  | Z2-C-CON-5990 | Pour Concrete Columns - Z2 - B2 | 47431 | 47430 | 40316 | 100% | 0.05468% | 0.04648% | 85% | 0.85001
|  | Z2-C-CON-6000 | Fix Rebar Retaining Walls - Z2 - B2 | 65426 | 65427 | 55613 | 100% | 0.07543% | 0.06411% | 85% | 0.85
|  | Z2-C-CON-6010 | Fix Formwork Retaining Walls - Z2 - B2 | 32713 | 32714 | 27807 | 100% | 0.03771% | 0.03206% | 85% | 0.85
|  | Z2-C-CON-6020 | Pour Concrete Retaining Walls - Z2 - B2 | 65427 | 65427 | 55613 | 100% | 0.07543% | 0.06411% | 85% | 0.85
|  | Z2-C-CON-6030 | Pour Concrete Core Walls - Z2 - B2 | 33489 | 33489 | 28466 | 100% | 0.03861% | 0.03282% | 85% | 0.85001
|  | Z2-C-CON-6040 | Fix Rebar Core Walls - Z2 - B2 | 25118 | 25117 | 21349 | 100% | 0.02896% | 0.02461% | 84.99% | 0.84998
|  | Z2-C-CON-6050 | Fix Formwork Core Walls - Z2 - B2 | 25117 | 25117 | 21349 | 100% | 0.02896% | 0.02461% | 85% | 0.84998
|  | Z2-C-CON-6060 | Fix Formwork Stairs - Z2 - B2 | 1864 | 1865 | 37 | 100.1% | 0.00215% | 4.265e-05% | 1.985% | 0.019839
|  | Z2-C-CON-6070 | Fix Rebar Stairs - Z2 - B2 | 3729 | 3729 | 75 | 100% | 0.004299% | 8.646e-05% | 2.011% | 0.020113
|  | Z2-C-CON-6080 | Pour Concrete Stairs - Z2 - B2 | 3729 | 3729 | 507 | 100% | 0.004299% | 0.0005845% | 13.6% | 0.13596
|  | Z2-C-CON-6090 | Fix Rebar Retaining Walls - Z2 - B1 | 65428 | 65427 | 8898 | 100% | 0.07543% | 0.01026% | 13.6% | 0.136
|  | Z2-C-CON-6100 | Fix Formwork Retaining Walls - Z2 - B1 | 32713 | 32714 | 7525 | 100% | 0.03771% | 0.008675% | 23% | 0.23002
|  | Z2-C-CON-6110 | Pour Concrete Retaining Walls - Z2 - B1 | 65427 | 65427 | 3926 | 100% | 0.07543% | 0.004526% | 6.001% | 0.060006
|  | Z2-C-CON-6120 | Fix Formwork Core Walls - Z2 - B1 | 25118 | 25117 | 21349 | 100% | 0.02896% | 0.02461% | 84.99% | 0.84998
|  | Z2-C-CON-6130 | Fix Rebar Core Walls - Z2 - B1 | 25117 | 25117 | 502 | 100% | 0.02896% | 0.0005787% | 1.999% | 0.019986
|  | Z2-C-CON-6140 | Pour Concrete Core Walls - Z2 - B1 | 33489 | 33489 | 1674 | 100% | 0.03861% | 0.00193% | 4.999% | 0.049987
|  | Z2-C-CON-6150 | Fix Rebar Columns - Z2 - B1 | 47430 | 47430 | 949 | 100% | 0.05468% | 0.001094% | 2.001% | 0.020008
|  | Z2-C-CON-6160 | Fix Formwork Columns - Z2 - B1 | 23714 | 23715 | 3225 | 100% | 0.02734% | 0.003718% | 13.6% | 0.13599
|  | Z2-C-CON-6170 | Pour Concrete Columns - Z2 - B1 | 47431 | 47430 | 6451 | 100% | 0.05468% | 0.007437% | 13.6% | 0.13601
|  | Z2-C-CON-6180 | Fix Formwork Stairs - Z2 - B1 | 1864 | 1865 | 186 | 100.1% | 0.00215% | 0.0002144% | 9.979% | 0.099732
|  | Z2-C-CON-6190 | Fix Rebar Stairs - Z2 - B1 | 3729 | 3729 | 373 | 100% | 0.004299% | 0.00043% | 10% | 0.10003
|  | Z2-C-CON-6200 | Pour Concrete Stairs - Z2 - B1 | 3729 | 3729 | 373 | 100% | 0.004299% | 0.00043% | 10% | 0.10003
|  | Z2-C-CON-6210 | Fix Formwork Slabs - Z2 - B1 | 100188 | 100188 | 85160 | 100% | 0.1155% | 0.09817% | 85% | 0.85
|  | Z2-C-CON-6220 | Fix Rebar Slabs - Z2 - B1 | 200376 | 200376 | 6012 | 100% | 0.231% | 0.006931% | 3% | 0.030004
|  | Z2-C-CON-6230 | Pour Concrete Slabs - Z2 - B1 | 200376 | 200376 | 4008 | 100% | 0.231% | 0.004621% | 2% | 0.020002
|  | Z2-C-CON-6240 | Fix MEP Containment & Provisions - Z2 - B1 | 5440 | 5440 | 849 | 100% | 0.006271% | 0.0009787% | 15.61% | 0.15607
|  | Z2-C-CON-6250 | Fix Rebar Core Walls - Z2 - GF | 54255 | 54254 | 5426 | 100% | 0.06255% | 0.006255% | 10% | 0.10001
|  | Z2-C-CON-6260 | Fix Formwork Core Walls - Z2 - GF | 28239 | 28238 | 2824 | 100% | 0.03255% | 0.003256% | 10% | 0.10001
|  | Z2-C-CON-6270 | Pour Concrete Core Walls - Z2 - GF | 55661 | 55661 | 19871 | 100% | 0.06417% | 0.02291% | 35.7% | 0.357
|  | Z2-C-CON-6280 | Fix Rebar Columns - Z2 - GF | 72503 | 72503 | 7250 | 100% | 0.08358% | 0.008358% | 10% | 0.099996
|  | Z2-C-CON-6290 | Fix Formwork Columns - Z2 - GF | 38017 | 38017 | 3802 | 100% | 0.04383% | 0.004383% | 10% | 0.10001
|  | Z2-C-CON-6300 | Pour Concrete Columns - Z2 - GF | 76127 | 76127 | 7613 | 100% | 0.08776% | 0.008776% | 10% | 0.1
|  | Z2-C-CON-6310 | Fix Formwork Stairs - Z2 - GF | 2419 | 2419 | 605 | 100% | 0.002789% | 0.0006975% | 25.01% | 0.2501
|  | Z2-C-CON-6320 | Fix Rebar Stairs - Z2 - GF | 4838 | 4839 | 2420 | 100% | 0.005579% | 0.00279% | 50.02% | 0.5001
|  | Z2-C-CON-6330 | Pour Concrete Stairs - Z2 - GF | 4839 | 4839 | 1210 | 100% | 0.005579% | 0.001395% | 25.01% | 0.25005
|  | Z2-C-CON-6340 | Fix Formwork Slabs - Z2 - GF | 129638 | 129637 | 7778 | 100% | 0.1494% | 0.008967% | 6% | 0.059998
|  | Z2-C-CON-6350 | Fix Rebar Slabs - Z2 - GF | 259274 | 259275 | 136767 | 100% | 0.2989% | 0.1577% | 52.75% | 0.5275
|  | Z2-C-CON-6360 | Pour Concrete Slabs - Z2 - GF | 259275 | 259275 | 25928 | 100% | 0.2989% | 0.02989% | 10% | 0.1
|  | Z2-C-CON-6370 | Fix MEP Containment & Provisions - Z2 - GF | 5440 | 5440 | 2543 | 100% | 0.006271% | 0.002932% | 46.75% | 0.46746
|  | Z2-C-CON-6380 | Fix Formwork Slabs - Z2 - F1 | 144523 | 144523 | 73273 | 100% | 0.1666% | 0.08447% | 50.7% | 0.507
|  | Z2-C-CON-6390 | Fix Rebar Slabs - Z2 - F1 | 187928 | 187929 | 105428 | 100% | 0.2166% | 0.1215% | 56.1% | 0.561
|  | Z2-C-CON-6400 | Fix MEP Containment & Provisions - Z2 - F1 | 5440 | 5440 | 3052 | 100% | 0.006271% | 0.003518% | 56.1% | 0.56103
|  | Z2-C-CON-6410 | Pour Concrete Slabs - Z2 - F1 | 219801 | 219801 | 54950 | 100% | 0.2534% | 0.06335% | 25% | 0.25
|  | Z2-C-CON-6420 | Fix Rebar Core Walls - Z2 - F1 | 53594 | 53594 | 13399 | 100% | 0.06178% | 0.01545% | 25% | 0.25001
|  | Z2-C-CON-6430 | Fix Formwork Core Walls - Z2 - F1 | 28287 | 28287 | 7072 | 100% | 0.03261% | 0.008153% | 25% | 0.25001
|  | Z2-C-CON-6440 | Pour Concrete Core Walls - Z2 - F1 | 56412 | 56412 | 14103 | 100% | 0.06503% | 0.01626% | 25% | 0.25
|  | Z2-C-CON-6450 | Fix Rebar Columns - Z2 - F1 | 73448 | 73448 | 36724 | 100% | 0.08467% | 0.04234% | 50% | 0.5
|  | Z2-C-CON-6460 | Fix Formwork Columns - Z2 - F1 | 37830 | 37831 | 9458 | 100% | 0.04361% | 0.0109% | 25% | 0.25001
|  | Z2-C-CON-6470 | Pour Concrete Columns - Z2 - F1 | 75888 | 75889 | 18972 | 100% | 0.08749% | 0.02187% | 25% | 0.25
|  | Z2-C-CON-6480 | Fix Formwork Stairs - Z2 - F1 | 2419 | 2419 | 605 | 100% | 0.002789% | 0.0006975% | 25.01% | 0.2501
|  | Z2-C-CON-6490 | Fix Rebar Stairs - Z2 - F1 | 4839 | 4839 | 1210 | 100% | 0.005579% | 0.001395% | 25.01% | 0.25005
|  | Z2-C-CON-6500 | Pour Concrete Stairs - Z2 - F1 | 4839 | 4839 | 4113 | 100% | 0.005579% | 0.004742% | 85% | 0.84997
|  | Z2-C-CON-6510 | Fix Rebar Slabs - Z2 - F2 | 193299 | 193298 | 386598 | 100% | 0.2228% | 0.4457% | 200% | 2
|  | Z2-C-CON-6520 | Fix Formwork Slabs - Z2 - F2 | 145945 | 145945 | 124053 | 100% | 0.1682% | 0.143% | 85% | 0.85
|  | Z2-C-CON-6530 | Pour Concrete Slabs - Z2 - F2 | 455692 | 455692 | 387338 | 100% | 0.5253% | 0.4465% | 85% | 0.85
|  | Z2-C-CON-6540 | Fix MEP Containment & Provisions - Z2 - F2 | 5440 | 5440 | 10880 | 100% | 0.006271% | 0.01254% | 200% | 2
|  | Z2-C-CON-6550 | Fix Rebar Core Walls - Z2 - F2 | 35418 | 35418 | 30105 | 100% | 0.04083% | 0.03471% | 85% | 0.84999
|  | Z2-C-CON-6560 | Fix Formwork Core Walls - Z2 - F2 | 16704 | 16705 | 14199 | 100% | 0.01926% | 0.01637% | 85% | 0.84999
|  | Z2-C-CON-6570 | Pour Concrete Core Walls - Z2 - F2 | 33899 | 33899 | 28814 | 100% | 0.03908% | 0.03322% | 85% | 0.85
|  | Z2-C-CON-6580 | Fix Rebar Columns - Z2 - F2 | 50067 | 50067 | 42557 | 100% | 0.05772% | 0.04906% | 85% | 0.85
|  | Z2-C-CON-6590 | Fix Formwork Columns - Z2 - F2 | 24315 | 24316 | 20669 | 100% | 0.02803% | 0.02383% | 85.01% | 0.85002
|  | Z2-C-CON-6600 | Pour Concrete Columns - Z2 - F2 | 48001 | 48002 | 40802 | 100% | 0.05534% | 0.04704% | 85% | 0.85001
|  | Z2-C-CON-6610 | Fix Formwork Stairs - Z2 - F2 | 2419 | 2419 | 2056 | 100% | 0.002789% | 0.00237% | 84.99% | 0.84994
|  | Z2-C-CON-6620 | Fix Rebar Stairs - Z2 - F2 | 4839 | 4838 | 4112 | 99.98% | 0.005577% | 0.00474% | 84.98% | 0.84994
|  | Z2-C-CON-6630 | Pour Concrete Stairs - Z2 - F2 | 4839 | 4839 | 4113 | 100% | 0.005579% | 0.004742% | 85% | 0.84997
|  | Z2-C-CON-6640 | Fix Formwork Slabs - Z2 - RF | 145648 | 145647 | 123800 | 100% | 0.1679% | 0.1427% | 85% | 0.85
|  | Z2-C-CON-6650 | Fix Rebar Slabs - Z2 - RF | 114257 | 114257 | 97118 | 100% | 0.1317% | 0.112% | 85% | 0.85
|  | Z2-C-CON-6660 | Pour Concrete Slabs - Z2 - RF | 41824 | 41824 | 35550 | 100% | 0.04822% | 0.04098% | 85% | 0.84999
|  | Z2-C-CON-6670 | Fix MEP Containment & Provisions - Z2 - RF | 5440 | 5440 | 4624 | 100% | 0.006271% | 0.005331% | 85% | 0.85
|  | Z2-C-CON-6680 | Fix Rebar Core Walls - Z2 - RF | 34810 | 34809 | 29588 | 100% | 0.04013% | 0.03411% | 85% | 0.85001
|  | Z2-C-CON-6690 | Fix Formwork Core Walls - Z2 - RF | 16641 | 16642 | 14146 | 100% | 0.01919% | 0.01631% | 85.01% | 0.85002
|  | Z2-C-CON-6700 | Pour Concrete Core Walls - Z2 - RF | 33788 | 33788 | 28720 | 100% | 0.03895% | 0.03311% | 85% | 0.85001
|  | Z2-C-CON-6710 | Fix Rebar Columns - Z2 - RF | 40997 | 40997 | 34847 | 100% | 0.04726% | 0.04017% | 85% | 0.84999
|  | Z2-C-CON-6720 | Fix Formwork Columns - Z2 - RF | 18849 | 18849 | 16022 | 100% | 0.02173% | 0.01847% | 85% | 0.85002
|  | Z2-C-CON-6730 | Pour Concrete Columns - Z2 - RF | 38299 | 38299 | 32554 | 100% | 0.04415% | 0.03753% | 85% | 0.85
|  | Z2-C-CON-6740 | Fix Formwork Stairs - Z2 - RF | 2419 | 2419 | 2056 | 100% | 0.002789% | 0.00237% | 84.99% | 0.84994
|  | Z2-C-CON-6750 | Fix Rebar Stairs - Z2 - RF | 4032 | 4032 | 3427 | 100% | 0.004648% | 0.003951% | 85% | 0.84995
|  | Z2-C-CON-6760 | Pour Concrete Stairs - Z2 - RF | 4032 | 4032 | 3427 | 100% | 0.004648% | 0.003951% | 85% | 0.84995
|  | Z2-C-CON-6770 | Fix Formwork Slabs - Z2 - SRVF | 130418 | 130418 | 110855 | 100% | 0.1503% | 0.1278% | 85% | 0.85
|  | Z2-C-CON-6780 | Fix Rebar Slabs - Z2 - SRVF | 236165 | 236165 | 200740 | 100% | 0.2723% | 0.2314% | 85% | 0.85
|  | Z2-C-CON-6790 | Pour Concrete Slabs - Z2 - SRVF | 274411 | 274411 | 233249 | 100% | 0.3163% | 0.2689% | 85% | 0.85
|  | Z2-C-CON-6800 | Fix MEP Containment & Provisions - Z2 - SRVF | 5440 | 5440 | 4624 | 100% | 0.006271% | 0.005331% | 85% | 0.85
|  | Z2-C-CON-6810 | Fix Rebar Core Walls - Z2 - SRVF | 20590 | 20590 | 17502 | 100% | 0.02374% | 0.02018% | 85% | 0.85002
|  | Z2-C-CON-6820 | Fix Formwork Core Walls - Z2 - SRVF | 9461 | 9462 | 2171 | 100% | 0.01091% | 0.002503% | 22.95% | 0.22944
|  | Z2-C-CON-6830 | Pour Concrete Core Walls - Z2 - SRVF | 18906 | 18906 | 4339 | 100% | 0.0218% | 0.005002% | 22.95% | 0.2295
|  | Z2-C-CON-6840 | Fix Rebar Columns - Z2 - SRVF | 3706 | 3706 | 3150 | 100% | 0.004272% | 0.003631% | 85% | 0.84997
|  | Z2-C-CON-6850 | Fix Formwork Columns - Z2 - SRVF | 1349 | 1349 | 1147 | 100% | 0.001555% | 0.001322% | 85.03% | 0.85026
|  | Z2-C-CON-6860 | Pour Concrete Columns - Z2 - SRVF | 2405 | 2405 | 552 | 100% | 0.002773% | 0.0006364% | 22.95% | 0.22952
|  | Z2-C-CON-6870 | Pour MEP RCC Pedastals - Z2 - SRVF | 807 | 807 | 686 | 100% | 0.0009303% | 0.0007908% | 85.01% | 0.85006
|  | Z2-C-CON-6880 | Fix Formwork Parapet - Z2 - SRVF | 14509 | 14509 | 12333 | 100% | 0.01673% | 0.01422% | 85% | 0.85002
|  | Z2-C-CON-6890 | Fix Rebar Parapet - Z2 - SRVF | 29019 | 29019 | 24666 | 100% | 0.03345% | 0.02844% | 85% | 0.84999
|  | Z2-C-CON-6900 | Pour Concrete Parapet - Z2 - SRVF | 29019 | 29019 | 6660 | 100% | 0.03345% | 0.007678% | 22.95% | 0.2295
|  | Z2-C-CON-6910 | Fix Formwork Slabs - Z2 - TRF | 7663 | 7663 | 6514 | 100% | 0.008834% | 0.007509% | 85.01% | 0.85006
|  | Z2-C-CON-6920 | Fix Rebar Slabs - Z2 - TRF | 15325 | 15325 | 13026 | 100% | 0.01767% | 0.01502% | 85% | 0.84998
|  | Z2-C-CON-6930 | Pour Concrete Slabs - Z2 - TRF | 15325 | 15325 | 13026 | 100% | 0.01767% | 0.01502% | 85% | 0.84998
|  | Z2-C-CON-6940 | Fix MEP Containment & Provisions - Z2 - TRF | 5440 | 5440 | 4624 | 100% | 0.006271% | 0.005331% | 85% | 0.85
|  | Z2-C-CON-6950 | Fix Formwork Parapet - Z2 - TRF | 14509 | 14509 | 12333 | 100% | 0.01673% | 0.01422% | 85% | 0.85002
|  | Z2-C-CON-6960 | Fix Rebar Parapet - Z2 - TRF | 29019 | 29019 | 24666 | 100% | 0.03345% | 0.02844% | 85% | 0.84999
|  | Z2-C-CON-6970 | Pour Concrete Parapet - Z2 - TRF | 29019 | 29019 | 24666 | 100% | 0.03345% | 0.02844% | 85% | 0.84999
| Div 04 | Z123-C-FIN-18110 | Masonry Works Dry Area - Z123 - SRVF | 32535 | 32535 | 27655 | 100% | 0.03751% | 0.03188% | 85% | 0.85001
|  | Z2&3-C-FIN-18800 | Masonry Works - Z2&3 - B2 | 4593 | 4593 | 2329 | 100% | 0.005295% | 0.002685% | 50.71% | 0.50708
|  | Z2&3-C-FIN-19050 | Masonry Works - Z2&3 - B1 | 45508 | 45508 | 11377 | 100% | 0.05246% | 0.01312% | 25% | 0.25
|  | Z2&3-C-FIN-19270 | Masonry Works Wet + Dry Area - Z2&3 - F1 | 104153 | 104152 | 88529 | 100% | 0.1201% | 0.1021% | 85% | 0.85
|  | Z2&3-C-FIN-19540 | Masonry Works - Z2&3 - GF | 335154 | 335153 | 670308 | 100% | 0.3864% | 0.7727% | 200% | 2
|  | Z2&3-C-FIN-20010 | Masonry Works Wet Area - Z2&3 - F2 | 127099 | 127099 | 108034 | 100% | 0.1465% | 0.1245% | 85% | 0.85
|  | Z2&3-C-FIN-20040 | Masonry Works Dry Area - Z2&3 - F2 | 127099 | 127099 | 108034 | 100% | 0.1465% | 0.1245% | 85% | 0.85
|  | Z2&3-C-FIN-20440 | Masonry Works Wet Area - Z2&3 - RF | 108948 | 108947 | 92605 | 100% | 0.1256% | 0.1068% | 85% | 0.85
|  | Z2&3-C-FIN-20470 | Masonry Works Dry Area - Z2&3 - RF | 108948 | 108947 | 92605 | 100% | 0.1256% | 0.1068% | 85% | 0.85
| Div 05 | A11440 | Installation of BMU System | 55001 | 55000 | 46750 | 100% | 0.06341% | 0.05389% | 85% | 0.85
|  | C-FIN-ENVLP-9650 | Install Aluminum Wood Ground Features | 60000 | 60000 | 51000 | 100% | 0.06917% | 0.05879% | 85% | 0.85
|  | C-FIN-ENVLP-9710 | Fix Steel Decore - GF to SRVF (Elev. 2 & 3) | 59364 | 59364 | 50460 | 100% | 0.06844% | 0.05817% | 85% | 0.85001
|  | Z123-C-FIN-18370 | Install Aluminum Shades over GRP Water Tank - Z123 - SRVF | 43910 | 43910 | 37324 | 100% | 0.05062% | 0.04303% | 85% | 0.85001
| Div 06 | Z2&3-C-FIN-20150 | Fix Furniture & Counter Works kitchen/Pantry - Z2&3 - F2 | 89500 | 89500 | 76075 | 100% | 0.1032% | 0.0877% | 85% | 0.85
|  | Z2&3-C-FIN-20580 | Fix Furniture & Counter Works kitchen/Pantry - Z2&3 - RF | 89500 | 89500 | 76075 | 100% | 0.1032% | 0.0877% | 85% | 0.85
| Div 07 | C-FIN-ENVLP-9670 | Osmotic Cement Waterproof - GF to SRVF (Elev. 2 & 3) | 55965 | 55965 | 47570 | 100% | 0.06452% | 0.05484% | 85% | 0.85
|  | Z123-C-FIN-18170 | 4mm Waterproof Membrane Wet Area - Z123 - SRVF | 130693 | 130693 | 111089 | 100% | 0.1507% | 0.1281% | 85% | 0.85
|  | Z123-C-FIN-18180 | Protection Screed Wet Area - Z123 - SRVF | 130693 | 130693 | 111089 | 100% | 0.1507% | 0.1281% | 85% | 0.85
|  | Z123-C-FIN-18190 | Polystyrene Thermal Insulation - Z123 - SRVF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z123-C-FIN-18200 | Foam Concrete - Z123 - SRVF | 130694 | 130694 | 85539 | 100% | 0.1507% | 0.09861% | 65.45% | 0.6545
|  | Z123-C-FIN-18330 | Waterproof Filter & Pump Room - Z123 - SRVF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z123-C-FIN-18340 | Protection Screed Filter & Pump Room - Z123 - SRVF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-19330 | Protection Screed Wet Area - Z2&3 - F1 | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-19380 | Waterproof Wet Area - Z2&3 - F1 | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-19580 | Waterproof & Screed Garbage Room - Z2&3 - GF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20100 | Waterproof kitchen/Pantry - Z2&3 - F2 | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20110 | Protection Screed kitchen/Pantry - Z2&3 - F2 | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20190 | Waterproof Bath - Z2&3 - F2 | 3899 | 3898 | 3313 | 99.97% | 0.004494% | 0.003819% | 84.97% | 0.84992
|  | Z2&3-C-FIN-20200 | Protection Screed Bath - Z2&3 - F2 | 3899 | 3898 | 3313 | 99.97% | 0.004494% | 0.003819% | 84.97% | 0.84992
|  | Z2&3-C-FIN-20260 | Waterproof Garbage Room - Z2&3 - F2 | 3899 | 3898 | 3313 | 99.97% | 0.004494% | 0.003819% | 84.97% | 0.84992
|  | Z2&3-C-FIN-20270 | Protection Screed Garbage Room - Z2&3 - F2 | 3899 | 3898 | 3313 | 99.97% | 0.004494% | 0.003819% | 84.97% | 0.84992
|  | Z2&3-C-FIN-20530 | Waterproof kitchen/Pantry - Z2&3 - RF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20540 | Protection Screed kitchen/Pantry - Z2&3 - RF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20620 | Waterproof Bath - Z2&3 - RF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20630 | Protection Screed Bath - Z2&3 - RF | 3899 | 3898 | 3313 | 99.97% | 0.004494% | 0.003819% | 84.97% | 0.84992
|  | Z2&3-C-FIN-20690 | Waterproof Garbage Room - Z2&3 - RF | 3898 | 3898 | 3313 | 100% | 0.004494% | 0.003819% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20700 | Protection Screed Garbage Room - Z2&3 - RF | 3899 | 3898 | 3313 | 99.97% | 0.004494% | 0.003819% | 84.97% | 0.84992
| Div 08 | A11210 | Fix Windows & Door Frame & Leaf - F2 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | A11220 | Fix Ironmongery - F2 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | A11260 | Fix Windows & Door Frame & Leaf - RF | 20822 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | A11270 | Fix Ironmongery - RF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | C-FIN-ENVLP-9680 | Fix Aluminum Glazing Pannels - GF to SRVF (Elev. 2 & 3) | 822232 | 822234 | 509613 | 100% | 0.9479% | 0.5875% | 61.98% | 0.61979
|  | Z123-C-FIN-18130 | Fix Door Subframes Dry Area - Z123 - SRVF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z123-C-FIN-18220 | Install Aluminum Shades over FAHU - Z123 - SRVF | 42000 | 42000 | 35700 | 100% | 0.04842% | 0.04116% | 85% | 0.85
|  | Z123-C-FIN-18360 | Install Aluminum Shades over Chillers - Z123 - SRVF | 42000 | 42000 | 32725 | 100% | 0.04842% | 0.03773% | 77.92% | 0.77917
|  | Z123-C-FIN-8540 | Fix Windows & Door Frame & Leaf - Z123 - SRVF | 20821 | 20822 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.84997
|  | Z123-C-FIN-8550 | Fix Ironmongery - Z123 - SRVF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-18910 | Fix Doors - Z2&3 - B2 | 20822 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-18950 | Fix Doors - Z2&3 - B2 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-18990 | Fix Doors - Z2&3 - B2 | 20821 | 20821 | 13534 | 100% | 0.024% | 0.0156% | 65% | 0.65002
|  | Z2&3-C-FIN-19100 | Fix Doors - Z2&3 - B1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-19190 | Fix Doors - Z2&3 - B1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-19290 | Fix Door Subframes Wet + Dry Area - Z2&3 - F1 | 20821 | 20822 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.84997
|  | Z2&3-C-FIN-19360 | Fix Doors Wet Area - Z2&3 - F1 | 20821 | 20821 | 4778 | 100% | 0.024% | 0.005508% | 22.95% | 0.22948
|  | Z2&3-C-FIN-19420 | Fix Doors Lift Lobby - Z2&3 - F1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-19500 | Fix Doors IT Room - Z2&3 - F1 | 20821 | 20821 | 4778 | 100% | 0.024% | 0.005508% | 22.95% | 0.22948
|  | Z2&3-C-FIN-19570 | Fix Doors Garbage & Service Room - Z2&3 - GF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-19760 | Fix Doors Lift Lobby - Z2&3 - GF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-20030 | Fix Door Subframes Wet Area - Z2&3 - F2 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-20060 | Fix Door Subframes Dry Area - Z2&3 - F2 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-20460 | Fix Door Subframes Wet Area - Z2&3 - RF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-20490 | Fix Door Subframes Dry Area - Z2&3 - RF | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-20890 | Fix Doors - Z2&3 - B1 | 20821 | 20821 | 17698 | 100% | 0.024% | 0.0204% | 85% | 0.85001
|  | Z2&3-C-FIN-21010 | Fix Doors Serv. Rooms - Z2&3 - F1 | 20821 | 20821 | 4778 | 100% | 0.024% | 0.005508% | 22.95% | 0.22948
| Div 09 | A10890 | Traffic Deck Coating Drive - Z2 - B1 | 138667 | 138667 | 117867 | 100% | 0.1599% | 0.1359% | 85% | 0.85
|  | A10950 | Traffic Deck Coating Drive - Z2 - B2 | 138666 | 138667 | 117867 | 100% | 0.1599% | 0.1359% | 85% | 0.85
|  | A11400 | Fix Flower Box | 107000 | 107000 | 90950 | 100% | 0.1234% | 0.1048% | 85% | 0.85
|  | A11410 | Fix Outdoor Green Area | 19950 | 19950 | 16958 | 100% | 0.023% | 0.01955% | 85% | 0.85003
|  | A9690 | Fix Pavement Tiles & Granite Colored Land Scaping | 27930 | 27930 | 23740 | 100% | 0.0322% | 0.02737% | 85% | 0.84998
|  | A9710 | Install Precast Wheel Stoper | 4259 | 4259 | 3620 | 100% | 0.00491% | 0.004173% | 85% | 0.84996
|  | A9720 | Trafic & Road Marking | 4259 | 4258 | 3620 | 99.98% | 0.004909% | 0.004173% | 85% | 0.85016
|  | C-FIN-ENVLP-9690 | Fix Brackets for Natural Stone - GF to SRVF (Elev. 2 & 3) | 107625 | 107626 | 68611 | 100% | 0.1241% | 0.0791% | 63.75% | 0.63749
|  | C-FIN-ENVLP-9700 | Fix Natural Stone All types- GF to SRVF (Elev. 2 & 3) | 965476 | 968625 | 823331 | 100.3% | 1.117% | 0.9492% | 85.28% | 0.85
|  | C-FIN-ENVLP-9720 | Fix Wooden Decorarive Features (Elev. 2 & 3) | 104055 | 104055 | 88447 | 100% | 0.12% | 0.102% | 85% | 0.85
|  | C-FIN-ENVLP-9740 | External Plaster - GF to SRVF (Elev. 2 & 3) | 1822 | 1823 | 1550 | 100.1% | 0.002102% | 0.001787% | 85.07% | 0.85025
|  | Z123-C-FIN-18120 | Plaster Works Dry Area - Z123 - SRVF | 11122 | 11123 | 7766 | 100% | 0.01282% | 0.008953% | 69.83% | 0.69819
|  | Z123-C-FIN-18160 | Roof Floor Terrazo Tiles Wet Area - Z123 - SRVF | 231184 | 231183 | 196506 | 100% | 0.2665% | 0.2265% | 85% | 0.85
|  | Z123-C-FIN-18310 | Wall Paint (Acrylic) Filter & Pump Room - Z123 - SRVF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z123-C-FIN-18320 | Floor Epoxy Filter & Pump Room - Z123 - SRVF | 4834 | 4833 | 4108 | 99.98% | 0.005572% | 0.004736% | 84.98% | 0.84999
|  | Z123-C-FIN-18350 | Ceiling Paint (Acrylic) Filter & Pump Room - Z123 - SRVF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z123-C-FIN-18390 | Fix False Ceiling Suspension Lift Lobby - Z123 - SRVF | 1932 | 1932 | 1642 | 100% | 0.002227% | 0.001893% | 84.99% | 0.8499
|  | Z123-C-FIN-18400 | Porcelain Floor Tiles Lift Lobby - Z123 - SRVF | 6246 | 6246 | 5309 | 100% | 0.007201% | 0.00612% | 85% | 0.84998
|  | Z123-C-FIN-18410 | Wall Paint (Emulsion) Lift Lobby - Z123 - SRVF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z123-C-FIN-18420 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z123 - SRVF | 1932 | 1932 | 1642 | 100% | 0.002227% | 0.001893% | 84.99% | 0.8499
|  | Z123-C-FIN-18430 | Fix False Ceiling Gypsum Board Lift Lobby - Z123 - SRVF | 1932 | 1932 | 1642 | 100% | 0.002227% | 0.001893% | 84.99% | 0.8499
|  | Z123-C-FIN-18450 | Ceiling Paint (Acrylic) GSM & MCC Rooms - Z123 - SRVF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z123-C-FIN-18460 | Floor Epoxy GSM & MCC Rooms - Z123 - SRVF | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z123-C-FIN-18470 | Wall Paint (Acrylic) GSM & MCC Rooms - Z123 - SRVF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z123-C-FIN-18480 | Floor Paint (Antifungal) Lift Shaft - Z123 - SRVF | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z123-C-FIN-18490 | Wall Paint (Antifungal) Lift Shaft - Z123 - SRVF | 8203 | 8202 | 6972 | 99.99% | 0.009455% | 0.008037% | 84.99% | 0.85004
|  | Z2&3-C-FIN-18740 | Ceiling Paint (Anti-Carbonation) - Z2&3 - B2 | 46612 | 46613 | 39621 | 100% | 0.05374% | 0.04568% | 85% | 0.85
|  | Z2&3-C-FIN-18760 | Wall Paint (Anti-Carbonation) - Z2&3 - B2 | 46612 | 46613 | 30298 | 100% | 0.05374% | 0.03493% | 65% | 0.64999
|  | Z2&3-C-FIN-18810 | Plaster Works - Z2&3 - B2 | 97652 | 97651 | 54783 | 100% | 0.1126% | 0.06316% | 56.1% | 0.56101
|  | Z2&3-C-FIN-18870 | Fix False Ceiling Suspension - Z2&3 - B2 | 1794 | 1793 | 1524 | 99.94% | 0.002067% | 0.001757% | 84.95% | 0.84997
|  | Z2&3-C-FIN-18880 | Wall Paint (Emulsion) - Z2&3 - B2 | 6439 | 6439 | 1610 | 100% | 0.007423% | 0.001856% | 25% | 0.25004
|  | Z2&3-C-FIN-18890 | Porcelain Floor Tiles - Z2&3 - B2 | 6439 | 6439 | 1610 | 100% | 0.007423% | 0.001856% | 25% | 0.25004
|  | Z2&3-C-FIN-18900 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B2 | 1793 | 1794 | 1525 | 100.1% | 0.002068% | 0.001758% | 85.05% | 0.85006
|  | Z2&3-C-FIN-18920 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - B2 | 2432 | 2432 | 608 | 100% | 0.002804% | 0.0007009% | 25% | 0.25
|  | Z2&3-C-FIN-18930 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - B2 | 2432 | 2432 | 608 | 100% | 0.002804% | 0.0007009% | 25% | 0.25
|  | Z2&3-C-FIN-18940 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B2 | 4833 | 4833 | 1208 | 100% | 0.005572% | 0.001393% | 24.99% | 0.24995
|  | Z2&3-C-FIN-18960 | Ceiling Paint (Emulsion) Travelator - Z2&3 - B2 | 401 | 401 | 100 | 100% | 0.0004623% | 0.0001153% | 24.94% | 0.24938
|  | Z2&3-C-FIN-18970 | Wall Paint (Emulsion) Travelator - Z2&3 - B2 | 10000 | 10000 | 2500 | 100% | 0.01153% | 0.002882% | 25% | 0.25
|  | Z2&3-C-FIN-18980 | Porcelain Floor Tiles Travelator - Z2&3 - B2 | 6440 | 6439 | 1610 | 99.98% | 0.007423% | 0.001856% | 25% | 0.25004
|  | Z2&3-C-FIN-19060 | Plaster Works - Z2&3 - B1 | 103369 | 103369 | 178681 | 100% | 0.1192% | 0.206% | 172.9% | 1.7286
|  | Z2&3-C-FIN-19070 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - B1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-19080 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - B1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-19090 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B1 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z2&3-C-FIN-19160 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B1 | 2621 | 2622 | 2229 | 100% | 0.003023% | 0.00257% | 85.04% | 0.85011
|  | Z2&3-C-FIN-19170 | Wall Paint (Emulsion) - Z2&3 - B1 | 4734 | 4734 | 4024 | 100% | 0.005457% | 0.004639% | 85% | 0.85002
|  | Z2&3-C-FIN-19180 | Porcelain Floor Tiles - Z2&3 - B1 | 4734 | 4734 | 4024 | 100% | 0.005457% | 0.004639% | 85% | 0.85002
|  | Z2&3-C-FIN-19200 | Fix False Ceiling Suspension - Z2&3 - B1 | 2622 | 2622 | 2229 | 100% | 0.003023% | 0.00257% | 85.01% | 0.85011
|  | Z2&3-C-FIN-19230 | Ceiling Paint (Anti-Carbonation) - Z2&3 - B1 | 46613 | 46612 | 39620 | 100% | 0.05374% | 0.04567% | 85% | 0.85
|  | Z2&3-C-FIN-19250 | Wall Paint (Anti-Carbonation) - Z2&3 - B1 | 46613 | 46613 | 39621 | 100% | 0.05374% | 0.04568% | 85% | 0.85
|  | Z2&3-C-FIN-19280 | Plaster Works Wet + Dry Area - Z2&3 - F1 | 47439 | 47439 | 40323 | 100% | 0.05469% | 0.04649% | 85% | 0.85
|  | Z2&3-C-FIN-19300 | Fix False Ceiling Suspension - Z2&3 - F1 | 17190 | 17190 | 14612 | 100% | 0.01982% | 0.01685% | 85% | 0.85003
|  | Z2&3-C-FIN-19310 | Wall Ceramic Tiles Wet Area - Z2&3 - F1 | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z2&3-C-FIN-19320 | Floor Ceramic Tiles Wet Area - Z2&3 - F1 | 6660 | 6660 | 1528 | 100% | 0.007678% | 0.001762% | 22.94% | 0.22943
|  | Z2&3-C-FIN-19340 | Fix False Ceiling Gypsum Board - Z2&3 - F1 | 17189 | 17189 | 14611 | 100% | 0.01982% | 0.01684% | 85% | 0.85002
|  | Z2&3-C-FIN-19350 | Fix False Ceiling Aluminum Tiles - Z2&3 - F1 | 17189 | 17189 | 14611 | 100% | 0.01982% | 0.01684% | 85% | 0.85002
|  | Z2&3-C-FIN-19390 | Fix False Ceiling Suspension Lift Lobby - Z2&3 - F1 | 17190 | 17190 | 14612 | 100% | 0.01982% | 0.01685% | 85% | 0.85003
|  | Z2&3-C-FIN-19400 | Wall Paint (Emulsion) Lift Lobby - Z2&3 - F1 | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-19410 | Porcelain Floor Tiles Lift Lobby - Z2&3 - F1 | 80417 | 80417 | 68354 | 100% | 0.09271% | 0.0788% | 85% | 0.84999
|  | Z2&3-C-FIN-19430 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z2&3 - F1 | 17190 | 17189 | 14611 | 99.99% | 0.01982% | 0.01684% | 85% | 0.85002
|  | Z2&3-C-FIN-19440 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - F1 | 17190 | 17189 | 14611 | 99.99% | 0.01982% | 0.01684% | 85% | 0.85002
|  | Z2&3-C-FIN-19460 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - F1 | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z2&3-C-FIN-19470 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - F1 | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z2&3-C-FIN-19480 | Wall Paint (Acrylic) IT Room - Z2&3 - F1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-19490 | Anti Static Raised Floor IT Room - Z2&3 - F1 | 22200 | 22200 | 18870 | 100% | 0.02559% | 0.02175% | 85% | 0.85
|  | Z2&3-C-FIN-19510 | Ceiling Paint (Acrylic) IT Room - Z2&3 - F1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-19520 | Anti Fungal Paint - Z2&3 - F1 | 8946 | 8946 | 7604 | 100% | 0.01031% | 0.008766% | 85% | 0.84999
|  | Z2&3-C-FIN-19550 | Plaster Works - Z2&3 - GF | 70822 | 70822 | 60199 | 100% | 0.08165% | 0.0694% | 85% | 0.85
|  | Z2&3-C-FIN-19560 | Floor Epoxy Paint Garbage & Service Room - Z2&3 - GF | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z2&3-C-FIN-19590 | Ceiling Paint Garbage & Service Room (Acrylic/Emulsion)- Z2&3 - GF | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z2&3-C-FIN-19600 | Wall Paint Garbage & Service Room (Acrylic/Emulsion) - Z2&3 - GF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-19770 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-19790 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-19800 | Fix False Ceiling Suspension Lift Lobby - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-19810 | Wall Paint (Emulsion) Lift Lobby - Z2&3 - GF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-19820 | Porcelain Floor Tiles Lift Lobby - Z2&3 - GF | 27710 | 27710 | 23554 | 100% | 0.03194% | 0.02715% | 85% | 0.85002
|  | Z2&3-C-FIN-19830 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - GF | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z2&3-C-FIN-19840 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - GF | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z2&3-C-FIN-19940 | Anti Fungal Paint all Shops - Z2&3 - GF | 8946 | 8946 | 7604 | 100% | 0.01031% | 0.008766% | 85% | 0.84999
|  | Z2&3-C-FIN-20020 | Plaster Works Wet Area - Z2&3 - F2 | 58518 | 58517 | 51326 | 100% | 0.06746% | 0.05917% | 87.71% | 0.87711
|  | Z2&3-C-FIN-20050 | Plaster Works Dry Area - Z2&3 - F2 | 58518 | 58517 | 51326 | 100% | 0.06746% | 0.05917% | 87.71% | 0.87711
|  | Z2&3-C-FIN-20070 | Fix False Ceiling Suspension kitchen/Pantry - Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20080 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z2&3-C-FIN-20090 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z2&3-C-FIN-20120 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20130 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20160 | Fix False Ceiling Suspension Bath - Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20170 | Wall Ceramic Tiles Bath - Z2&3 - F2 | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z2&3-C-FIN-20180 | Floor Ceramic Tiles Bath - Z2&3 - F2 | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z2&3-C-FIN-20210 | Fix False Ceiling Gypsum Board Bath - Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20220 | Fix False Ceiling Aluminum Tiles Bath - Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20240 | Wall Paint (Emulsion) Garbage Room - Z2&3 - F2 | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-20250 | Floor Epoxy Paint Garbage Room - Z2&3 - F2 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z2&3-C-FIN-20280 | Ceiling Paint (Emulsion) Garbage Room - Z2&3 - F2 | 401 | 402 | 342 | 100.2% | 0.0004634% | 0.0003943% | 85.29% | 0.85075
|  | Z2&3-C-FIN-20290 | Fix False Ceiling Suspension Lobby Passage & Offices- Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20300 | Wall Paint (Emulsion) Lobby Passage & Offices - Z2&3 - F2 | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-20310 | Porcelain Floor Tiles Passage & Offices - Z2&3 - F2 | 208301 | 208302 | 177057 | 100% | 0.2401% | 0.2041% | 85% | 0.85
|  | Z2&3-C-FIN-20320 | Fix False Ceiling Aluminum Tiles Lobby Passage & Offices - Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20330 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - F2 | 24288 | 24288 | 20645 | 100% | 0.028% | 0.0238% | 85% | 0.85001
|  | Z2&3-C-FIN-20350 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - F2 | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z2&3-C-FIN-20360 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - F2 | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z2&3-C-FIN-20400 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - F2 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20410 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - F2 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20420 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F2 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z2&3-C-FIN-20450 | Plaster Works Wet Area - Z2&3 - RF | 49035 | 49036 | 41681 | 100% | 0.05653% | 0.04805% | 85% | 0.85001
|  | Z2&3-C-FIN-20480 | Plaster Works Dry Area - Z2&3 - RF | 49035 | 49036 | 41681 | 100% | 0.05653% | 0.04805% | 85% | 0.85001
|  | Z2&3-C-FIN-20500 | Fix False Ceiling Suspension kitchen/Pantry - Z2&3 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z2&3-C-FIN-20510 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z2&3-C-FIN-20520 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z2&3-C-FIN-20550 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - RF | 18599 | 18598 | 15808 | 99.99% | 0.02144% | 0.01822% | 84.99% | 0.84998
|  | Z2&3-C-FIN-20560 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z2&3 - RF | 18599 | 18598 | 15808 | 99.99% | 0.02144% | 0.01822% | 84.99% | 0.84998
|  | Z2&3-C-FIN-20590 | Fix False Ceiling Suspension Bath - Z2&3 - RF | 18599 | 18598 | 15808 | 99.99% | 0.02144% | 0.01822% | 84.99% | 0.84998
|  | Z2&3-C-FIN-20600 | Wall Ceramic Tiles Bath - Z2&3 - RF | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z2&3-C-FIN-20610 | Floor Ceramic Tiles Bath - Z2&3 - RF | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z2&3-C-FIN-20640 | Fix False Ceiling Gypsum Board Bath - Z2&3 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z2&3-C-FIN-20650 | Fix False Ceiling Aluminum Tiles Bath - Z2&3 - RF | 18599 | 18599 | 15809 | 100% | 0.02144% | 0.01822% | 85% | 0.84999
|  | Z2&3-C-FIN-20670 | Wall Paint (Emulsion) Garbage Room - Z2&3 - RF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-20680 | Floor Epoxy Paint Garbage Room - Z2&3 - RF | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z2&3-C-FIN-20710 | Ceiling Paint (Emulsion) Garbage Room - Z2&3 - RF | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z2&3-C-FIN-20750 | Fix False Ceiling Suspension Lobby Passage & Offices - Z2&3 - RF | 18599 | 18598 | 15808 | 99.99% | 0.02144% | 0.01822% | 84.99% | 0.84998
|  | Z2&3-C-FIN-20760 | Wall Paint (Emulsion) Lobby Passage & Offices - Z2&3 - RF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-20770 | Porcelain Floor Tiles Passage & Offices - Z2&3 - RF | 158821 | 158821 | 134998 | 100% | 0.1831% | 0.1556% | 85% | 0.85
|  | Z2&3-C-FIN-20780 | Fix False Ceiling Aluminum Tiles Lobby Passage & Offices - Z2&3 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z2&3-C-FIN-20790 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - RF | 18598 | 18598 | 15808 | 100% | 0.02144% | 0.01822% | 85% | 0.84998
|  | Z2&3-C-FIN-20810 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - RF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20820 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - RF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-20830 | Floor Epoxy Paint Serv. Rooms - Z2&3 - RF | 4833 | 4834 | 3081 | 100% | 0.005573% | 0.003552% | 63.75% | 0.63736
|  | Z2&3-C-FIN-20840 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - RF | 8202 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.02% | 0.85005
|  | Z2&3-C-FIN-20850 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - RF | 8203 | 8203 | 6973 | 100% | 0.009457% | 0.008039% | 85.01% | 0.85005
|  | Z2&3-C-FIN-20860 | Ceiling Paint (Emulsion) Travelator - Z2&3 - B1 | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z2&3-C-FIN-20870 | Wall Paint (Emulsion) Travelator - Z2&3 - B1 | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-20880 | Porcelain Floor Tiles Travelator - Z2&3 - B1 | 4734 | 4733 | 4024 | 99.98% | 0.005456% | 0.004639% | 85% | 0.8502
|  | Z2&3-C-FIN-20990 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - F1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-21000 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F1 | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z2&3-C-FIN-21020 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - F1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-21040 | Fix False Ceiling Gypsum Board Passage & Entrance - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21060 | Fix False Ceiling Aluminum Tiles Passage & Entrance - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21070 | Fix False Ceiling Suspension Passage & Entrance - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21080 | Wall Paint (Emulsion) Passage & Entrance - Z2&3 - GF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-21090 | Porcelain Floor Tiles Passage & Entrance - Z2&3 - GF | 27710 | 27710 | 23554 | 100% | 0.03194% | 0.02715% | 85% | 0.85002
|  | Z2&3-C-FIN-21100 | Fix False Ceiling Suspension Wet + Nursing Area - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21110 | Wall Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 28908 | 28908 | 24572 | 100% | 0.03333% | 0.02833% | 85% | 0.85001
|  | Z2&3-C-FIN-21120 | Floor Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 6660 | 6660 | 5661 | 100% | 0.007678% | 0.006526% | 85% | 0.85
|  | Z2&3-C-FIN-21140 | Fix False Ceiling Gypsum Board Wet + Nursing Area - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21150 | Fix False Ceiling Aluminum Tiles Wet + Nursing Area - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21200 | Fix False Ceiling Gypsum Board Passage H.Market - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21220 | Fix False Ceiling Aluminum Tiles Passage H.Market - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21230 | Fix False Ceiling Suspension Passage H.Market - Z2&3 - GF | 6812 | 6812 | 5790 | 100% | 0.007853% | 0.006675% | 85% | 0.84997
|  | Z2&3-C-FIN-21250 | Floor Stamp Concrete Passage H.Market- Z2&3 - GF | 21250 | 21250 | 18063 | 100% | 0.0245% | 0.02082% | 85% | 0.85002
|  | Z2&3-C-FIN-21260 | Floor Epoxy Paint IT & Maintanance Room - Z2&3 - GF | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z2&3-C-FIN-21290 | Ceiling Paint IT & Maintanance Room (Acrylic/Emulsion)- Z2&3 - GF | 401 | 401 | 341 | 100% | 0.0004623% | 0.0003931% | 85.04% | 0.85037
|  | Z2&3-C-FIN-21300 | Wall Paint IT & Maintanance Room (Acrylic/Emulsion) - Z2&3 - GF | 10000 | 10000 | 8500 | 100% | 0.01153% | 0.009799% | 85% | 0.85
|  | Z2&3-C-FIN-21310 | Wall Paint Outside Area (Acrylic) - Z2&3 - F1 | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-21320 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - F1 | 13600 | 13600 | 8901 | 100% | 0.01568% | 0.01026% | 65.45% | 0.65449
|  | Z2&3-C-FIN-21340 | Wall Paint Outside Area (Acrylic) - Z2&3 - RF | 2432 | 2432 | 2067 | 100% | 0.002804% | 0.002383% | 84.99% | 0.84992
|  | Z2&3-C-FIN-21350 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - RF | 13599 | 13599 | 11559 | 100% | 0.01568% | 0.01333% | 85% | 0.84999
|  | Z2&3-C-FIN-21360 | Floor Carpet Prayer Room - Z2&3 - F1 | 13558 | 13558 | 3112 | 100% | 0.01563% | 0.003588% | 22.95% | 0.22953
|  | Z2&3-C-FIN-SCASE-100 | on Staircase Acrylic Paint - Z2&3 - B2 - SRVF | 4258 | 4259 | 3620 | 100% | 0.00491% | 0.004173% | 85.02% | 0.84996
|  | Z2&3-C-FIN-SCASE-101 | on Staircase Floor Epoxy Paint - Z2&3 - B2 - SRVF | 4833 | 4833 | 4108 | 100% | 0.005572% | 0.004736% | 85% | 0.84999
|  | Z2-C-GRBCH-11370 | Install Garbage Chute Cylinder - Z2 - GF to SRVF | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
|  | Z2-C-GRBCH-11380 | Install Garbage Chute Supporting Frame - Z2 - GF to SRVF | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
|  | Z2-C-GRBCH-11390 | Block & Plaster Garbage Room - Z2 - GF to SRVF | 1391 | 1390 | 633 | 99.93% | 0.001602% | 0.0007297% | 45.51% | 0.4554
|  | Z2-C-GRBCH-11400 | Install Garbage Chute Openings & Doors - Z2 - GF to SRVF | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
|  | Z2-C-GRBCH-11410 | Install Garbage Chute Roof Top Unit with All Provisions | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
|  | Z2-C-GRBCH-11420 | Install Garbage Chute Bottom Unit with All Provisions | 16800 | 16800 | 14280 | 100% | 0.01937% | 0.01646% | 85% | 0.85
| Div 10 | A11450 | External Drainage Pipes & Connections | 80001 | 80000 | 68000 | 100% | 0.09223% | 0.07839% | 85% | 0.85
|  | A9700 | Install Man Holes Covers | 4400 | 4400 | 3740 | 100% | 0.005072% | 0.004312% | 85% | 0.85
|  | ADCE-MALL-WS-2200 | Installation of Water Meter & AADC Approval | 34210 | 34210 | 29078 | 100% | 0.03944% | 0.03352% | 85% | 0.84999
|  | T&C-10000 | Water Supply System Testing & Commissioning | 7000 | 7000 | 5950 | 100% | 0.00807% | 0.006859% | 85% | 0.85
|  | T&C-10010 | Water Drainage System Testing & Commissioning | 7000 | 7000 | 5950 | 100% | 0.00807% | 0.006859% | 85% | 0.85
|  | Z123-C-FIN-18210 | Fix Rain Water Outlets - Z123 - SRVF | 6000 | 6000 | 1377 | 100% | 0.006917% | 0.001587% | 22.95% | 0.2295
|  | Z123-C-MEP-14740 | Fix Drainage & Water Supply Pipes Block Wall - Z123 - SRVF | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z123-C-MEP-14880 | Fix Water Supply Pipes - Z123 - SRVF | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z123-C-MEP-14900 | Fix Drainage Pipes - Z123 - SRVF | 9368 | 9368 | 7963 | 100% | 0.0108% | 0.00918% | 85% | 0.85002
|  | Z123-C-MEP-15010 | Fix Water Heater & Sanitary Accessories - Z123 - SRVF | 75575 | 75575 | 64239 | 100% | 0.08712% | 0.07406% | 85% | 0.85
|  | Z123-C-MEP-15060 | Install GRP Water Tank & Accessories - Z123 - SRVF | 225500 | 225500 | 191675 | 100% | 0.26% | 0.221% | 85% | 0.85
|  | Z123-C-MEP-15070 | Install Filteration Plant System - Z123 - SRVF | 100000 | 100000 | 85000 | 100% | 0.1153% | 0.09799% | 85% | 0.85
|  | Z2&3-C-MEP-15240 | Fix Drainage Pipes - Z2&3 - B2 | 9366 | 9368 | 15454 | 100% | 0.0108% | 0.01782% | 165% | 1.6497
|  | Z2&3-C-MEP-15510 | Fix Drainage Pipes - Z2&3 - B1 | 9366 | 9368 | 7963 | 100% | 0.0108% | 0.00918% | 85.02% | 0.85002
|  | Z2&3-C-MEP-15710 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - F1 | 6591 | 6591 | 5603 | 100% | 0.007598% | 0.006459% | 85.01% | 0.8501
|  | Z2&3-C-MEP-15790 | Fix Drainage Pipes - Z2&3 - F1 | 9368 | 9368 | 7963 | 100% | 0.0108% | 0.00918% | 85% | 0.85002
|  | Z2&3-C-MEP-15850 | Fix Water Supply Pipes - Z2&3 - F1 | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z2&3-C-MEP-15940 | Fix Water Heater & Sanitary Accessories - Z2&3 - F1 | 75574 | 75575 | 64239 | 100% | 0.08712% | 0.07406% | 85% | 0.85
|  | Z2&3-C-MEP-16010 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - GF | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z2&3-C-MEP-16090 | Fix Drainage Pipes - Z2&3 - GF | 9368 | 9368 | 7963 | 100% | 0.0108% | 0.00918% | 85% | 0.85002
|  | Z2&3-C-MEP-16150 | Fix Water Supply Pipes - Z2&3 - GF | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z2&3-C-MEP-16260 | Fix Water Heater & Sanitary Accessories - Z2&3 - GF | 75574 | 75575 | 64239 | 100% | 0.08712% | 0.07406% | 85% | 0.85
|  | Z2&3-C-MEP-16310 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - F2 | 6591 | 6591 | 1513 | 100% | 0.007598% | 0.001744% | 22.96% | 0.22956
|  | Z2&3-C-MEP-16390 | Fix Drainage Pipes - Z2&3 - F2 | 9368 | 9367 | 7962 | 99.99% | 0.0108% | 0.009179% | 84.99% | 0.85001
|  | Z2&3-C-MEP-16450 | Fix Water Supply Pipes - Z2&3 - F2 | 6591 | 6591 | 5602 | 100% | 0.007598% | 0.006458% | 84.99% | 0.84995
|  | Z2&3-C-MEP-16560 | Fix Water Heater & Sanitary Accessories - Z2&3 - F2 | 75575 | 75575 | 64239 | 100% | 0.08712% | 0.07406% | 85% | 0.85
|  | Z2&3-C-MEP-16630 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - RF | 6591 | 6591 | 5603 | 100% | 0.007598% | 0.006459% | 85.01% | 0.8501
|  | Z2&3-C-MEP-16720 | Fix Drainage Pipes - Z2&3 - RF | 9368 | 9367 | 4266 | 99.99% | 0.0108% | 0.004918% | 45.54% | 0.45543
|  | Z2&3-C-MEP-16780 | Fix Water Supply Pipes - Z2&3 - RF | 6590 | 6590 | 2467 | 100% | 0.007597% | 0.002844% | 37.44% | 0.37436
|  | Z2&3-C-MEP-16900 | Fix Water Heater & Sanitary Accessories - Z2&3 - RF | 75574 | 75574 | 64238 | 100% | 0.08712% | 0.07405% | 85% | 0.85
|  | Z2-C-CON-5940 | Fix MEP Provisions - Z2 - Raft | 10500 | 10500 | 8925 | 100% | 0.0121% | 0.01029% | 85% | 0.85
|  | Z2-C-RSRS-11120 | Install Drainage Pipe Risers | 6591 | 6590 | 4687 | 99.98% | 0.007597% | 0.005403% | 71.11% | 0.71123
|  | Z2-C-RSRS-11130 | Install Water Supply Pipe Risers | 6591 | 6590 | 4687 | 99.98% | 0.007597% | 0.005403% | 71.11% | 0.71123
| Div 11 | T&C-9980 | Fire Fighting System Testing & Commissioning | 11000 | 11000 | 9350 | 100% | 0.01268% | 0.01078% | 85% | 0.85
|  | Z123-C-MEP-14830 | Fix Fire Fighting Pipes - Z123 - SRVF | 59346 | 59346 | 50444 | 100% | 0.06842% | 0.05815% | 85% | 0.85
|  | Z123-C-MEP-14860 | Fix Fire Fighting Dropers - Z123 - SRVF | 10627 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85.01% | 0.85002
|  | Z123-C-MEP-14980 | Fix Fire Hose Cabinets & Hose Reels - Z123 - SRVF | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z123-C-MEP-14990 | Fix Sprinklers - Z123 - SRVF | 20692 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
|  | Z2&3-C-MEP-15250 | Fix Fire Fighting Pipes - Z2&3 - B2 | 59346 | 59346 | 97921 | 100% | 0.06842% | 0.1129% | 165% | 1.65
|  | Z2&3-C-MEP-15280 | Fix Fire Fighting Dropers - Z2&3 - B2 | 10628 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85% | 0.85002
|  | Z2&3-C-MEP-15370 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - B2 | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z2&3-C-MEP-15380 | Fix Sprinklers - Z2&3 - B2 | 20692 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
|  | Z2&3-C-MEP-15520 | Fix Fire Fighting Pipes - Z2&3 - B1 | 59346 | 59346 | 50444 | 100% | 0.06842% | 0.05815% | 85% | 0.85
|  | Z2&3-C-MEP-15550 | Fix Fire Fighting Dropers - Z2&3 - B1 | 10627 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85.01% | 0.85002
|  | Z2&3-C-MEP-15640 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - B1 | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z2&3-C-MEP-15650 | Fix Sprinklers - Z2&3 - B1 | 20692 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
|  | Z2&3-C-MEP-15800 | Fix Fire Fighting Pipes - Z2&3 - F1 | 59346 | 59346 | 50444 | 100% | 0.06842% | 0.05815% | 85% | 0.85
|  | Z2&3-C-MEP-15830 | Fix Fire Fighting Dropers - Z2&3 - F1 | 10628 | 10627 | 9033 | 99.99% | 0.01225% | 0.01041% | 84.99% | 0.85
|  | Z2&3-C-MEP-15950 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - F1 | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z2&3-C-MEP-15960 | Fix Sprinklers - Z2&3 - F1 | 20692 | 20692 | 20520 | 100% | 0.02385% | 0.02366% | 99.17% | 0.99169
|  | Z2&3-C-MEP-16100 | Fix Fire Fighting Pipes - Z2&3 - GF | 59346 | 59346 | 50444 | 100% | 0.06842% | 0.05815% | 85% | 0.85
|  | Z2&3-C-MEP-16130 | Fix Fire Fighting Dropers - Z2&3 - GF | 10627 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85.01% | 0.85002
|  | Z2&3-C-MEP-16230 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - GF | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z2&3-C-MEP-16240 | Fix Sprinklers - Z2&3 - GF | 20692 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
|  | Z2&3-C-MEP-16400 | Fix Fire Fighting Pipes - Z2&3 - F2 | 59346 | 59346 | 50444 | 100% | 0.06842% | 0.05815% | 85% | 0.85
|  | Z2&3-C-MEP-16430 | Fix Fire Fighting Dropers - Z2&3 - F2 | 10627 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85.01% | 0.85002
|  | Z2&3-C-MEP-16540 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - F2 | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z2&3-C-MEP-16550 | Fix Sprinklers - Z2&3 - F2 | 20692 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
|  | Z2&3-C-MEP-16730 | Fix Fire Fighting Pipes - Z2&3 - RF | 59346 | 59346 | 27024 | 100% | 0.06842% | 0.03115% | 45.54% | 0.45536
|  | Z2&3-C-MEP-16760 | Fix Fire Fighting Dropers - Z2&3 - RF | 10628 | 10628 | 9034 | 100% | 0.01225% | 0.01041% | 85% | 0.85002
|  | Z2&3-C-MEP-16870 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - RF | 12692 | 12692 | 10788 | 100% | 0.01463% | 0.01244% | 85% | 0.84998
|  | Z2&3-C-MEP-16880 | Fix Sprinklers - Z2&3 - RF | 20692 | 20692 | 17588 | 100% | 0.02385% | 0.02028% | 85% | 0.84999
|  | Z2-C-RSRS-11150 | Install Fire Fighting Pipe Risers | 404400 | 404400 | 367802 | 100% | 0.4662% | 0.424% | 90.95% | 0.9095
| Div 12 | T&C-9920 | Chilled Water Pump Testing | 27666 | 27667 | 23517 | 100% | 0.0319% | 0.02711% | 85% | 0.85
|  | T&C-9930 | Chilled Water System Flushing & Cleaning | 27667 | 27666 | 23516 | 100% | 0.03189% | 0.02711% | 85% | 0.85
|  | T&C-9940 | HVAC Equipment Testing & Commissioning | 27668 | 27666 | 23516 | 99.99% | 0.03189% | 0.02711% | 84.99% | 0.85
|  | T&C-9950 | Air Balancing FCU & FAHU | 27668 | 27666 | 23516 | 99.99% | 0.03189% | 0.02711% | 84.99% | 0.85
|  | T&C-9960 | Chilled Water Balancing | 27666 | 27667 | 23517 | 100% | 0.0319% | 0.02711% | 85% | 0.85
|  | Z123-C-FIN-18440 | Fix MEP Droppers Lift Lobby - Z123 - SRVF | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z123-C-MEP-14840 | Fix Chill Water Pipes - Z123 - SRVF | 106571 | 106571 | 90585 | 100% | 0.1229% | 0.1044% | 85% | 0.85
|  | Z123-C-MEP-14850 | Fix HVAC Ducts & Insulation - Z123 - SRVF | 205840 | 205841 | 174965 | 100% | 0.2373% | 0.2017% | 85% | 0.85
|  | Z123-C-MEP-14870 | Fix FCU - Z123 - SRVF | 48984 | 48985 | 41637 | 100% | 0.05647% | 0.048% | 85% | 0.84999
|  | Z123-C-MEP-15000 | Fix Grills & Diffusers - Z123 - SRVF | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z123-C-MEP-15030 | Fix FAHU - Z123 - SRVF | 446000 | 446000 | 379100 | 100% | 0.5142% | 0.437% | 85% | 0.85
|  | Z123-C-MEP-15040 | Fix Chillers - Z123 - SRVF | 2570001 | 2570000 | 2184500 | 100% | 2.963% | 2.518% | 85% | 0.85
|  | Z123-C-MEP-15050 | Fix Extract Fans - Z123 - SRVF | 452180 | 452180 | 384353 | 100% | 0.5213% | 0.4431% | 85% | 0.85
|  | Z123-C-MEP-15090 | Install Chilled Water Pump - Z123 - SRVF | 145000 | 145000 | 123250 | 100% | 0.1672% | 0.1421% | 85% | 0.85
|  | Z123-C-MEP-15120 | Termination of MEP Equipment With Risers - Z123 - SRVF | 264001 | 264000 | 224400 | 100% | 0.3043% | 0.2587% | 85% | 0.85
|  | Z123-C-MEP-15130 | Fix Pressurization Guages & Units Lift & Stair - Z123 - SRVF | 259000 | 259000 | 220150 | 100% | 0.2986% | 0.2538% | 85% | 0.85
|  | Z123-C-MEP-15140 | Fix Chemical Dosing Pot - Z123 - SRVF | 22000 | 22000 | 18700 | 100% | 0.02536% | 0.02156% | 85% | 0.85
|  | Z2&3-C-FIN-19370 | Fix MEP Droppers - Z2&3 - F1 | 18388 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85.01% | 0.85002
|  | Z2&3-C-FIN-19450 | Fix MEP Droppers Lift Lobby - Z2&3 - F1 | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z2&3-C-FIN-19780 | Fix MEP Droppers Lift Lobby - Z2&3 - GF | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z2&3-C-FIN-20140 | Fix MEP Droppers kitchen/Pantry - Z2&3 - F2 | 10751 | 10750 | 9138 | 99.99% | 0.01239% | 0.01053% | 85% | 0.85005
|  | Z2&3-C-FIN-20230 | Fix MEP Droppers Bath - Z2&3 - F2 | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z2&3-C-FIN-20340 | Fix MEP Droppers Lobby Passage & Offices- Z2&3 - F2 | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z2&3-C-FIN-20570 | Fix MEP Droppers kitchen/Pantry - Z2&3 - RF | 10751 | 10750 | 9138 | 99.99% | 0.01239% | 0.01053% | 85% | 0.85005
|  | Z2&3-C-FIN-20660 | Fix MEP Droppers Bath - Z2&3 - RF | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z2&3-C-FIN-20800 | Fix MEP Droppers Lobby Passage & Offices - Z2&3 - RF | 18389 | 18389 | 15631 | 100% | 0.0212% | 0.01802% | 85% | 0.85002
|  | Z2&3-C-MEP-15260 | Fix Chill Water Pipes - Z2&3 - B2 | 106571 | 106572 | 175842 | 100% | 0.1229% | 0.2027% | 165% | 1.65
|  | Z2&3-C-MEP-15270 | Fix HVAC Ducts & Insulation - Z2&3 - B2 | 205842 | 205840 | 339639 | 100% | 0.2373% | 0.3915% | 165% | 1.65
|  | Z2&3-C-MEP-15290 | Fix FCU - Z2&3 - B2 | 19285 | 19285 | 16392 | 100% | 0.02223% | 0.0189% | 85% | 0.84999
|  | Z2&3-C-MEP-15390 | Fix Grills & Diffusers - Z2&3 - B2 | 17845 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z2&3-C-MEP-15530 | Fix Chill Water Pipes - Z2&3 - B1 | 106571 | 106571 | 90585 | 100% | 0.1229% | 0.1044% | 85% | 0.85
|  | Z2&3-C-MEP-15540 | Fix HVAC Ducts & Insulation - Z2&3 - B1 | 205842 | 205841 | 174965 | 100% | 0.2373% | 0.2017% | 85% | 0.85
|  | Z2&3-C-MEP-15560 | Fix FCU - Z2&3 - B1 | 39085 | 39085 | 33222 | 100% | 0.04506% | 0.0383% | 85% | 0.84999
|  | Z2&3-C-MEP-15660 | Fix Grills & Diffusers - Z2&3 - B1 | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z2&3-C-MEP-15810 | Fix Chill Water Pipes - Z2&3 - F1 | 106572 | 106571 | 90585 | 100% | 0.1229% | 0.1044% | 85% | 0.85
|  | Z2&3-C-MEP-15820 | Fix HVAC Ducts & Insulation - Z2&3 - F1 | 205840 | 205841 | 174965 | 100% | 0.2373% | 0.2017% | 85% | 0.85
|  | Z2&3-C-MEP-15840 | Fix FCU - Z2&3 - F1 | 129834 | 129834 | 84976 | 100% | 0.1497% | 0.09796% | 65.45% | 0.6545
|  | Z2&3-C-MEP-15930 | Fix Grills & Diffusers - Z2&3 - F1 | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z2&3-C-MEP-16110 | Fix Chill Water Pipes - Z2&3 - GF | 106571 | 106572 | 90586 | 100% | 0.1229% | 0.1044% | 85% | 0.85
|  | Z2&3-C-MEP-16120 | Fix HVAC Ducts & Insulation - Z2&3 - GF | 205840 | 205840 | 174964 | 100% | 0.2373% | 0.2017% | 85% | 0.85
|  | Z2&3-C-MEP-16140 | Fix FCU - Z2&3 - GF | 151284 | 151285 | 128592 | 100% | 0.1744% | 0.1482% | 85% | 0.85
|  | Z2&3-C-MEP-16250 | Fix Grills & Diffusers - Z2&3 - GF | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z2&3-C-MEP-16410 | Fix Chill Water Pipes - Z2&3 - F2 | 106572 | 106571 | 90586 | 100% | 0.1229% | 0.1044% | 85% | 0.85001
|  | Z2&3-C-MEP-16420 | Fix HVAC Ducts & Insulation - Z2&3 - F2 | 205840 | 205841 | 174965 | 100% | 0.2373% | 0.2017% | 85% | 0.85
|  | Z2&3-C-MEP-16440 | Fix FCU - Z2&3 - F2 | 151284 | 151285 | 128592 | 100% | 0.1744% | 0.1482% | 85% | 0.85
|  | Z2&3-C-MEP-16580 | Fix Grills & Diffusers - Z2&3 - F2 | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z2&3-C-MEP-16740 | Fix Chill Water Pipes - Z2&3 - RF | 106571 | 106571 | 39900 | 100% | 0.1229% | 0.046% | 37.44% | 0.3744
|  | Z2&3-C-MEP-16750 | Fix HVAC Ducts & Insulation - Z2&3 - RF | 205841 | 205841 | 93731 | 100% | 0.2373% | 0.1081% | 45.54% | 0.45536
|  | Z2&3-C-MEP-16770 | Fix FCU - Z2&3 - RF | 129835 | 129835 | 110360 | 100% | 0.1497% | 0.1272% | 85% | 0.85
|  | Z2&3-C-MEP-16890 | Fix Grills & Diffusers - Z2&3 - RF | 17846 | 17846 | 15169 | 100% | 0.02057% | 0.01749% | 85% | 0.84999
|  | Z2-C-RSRS-11140 | Install CHW Pipe Risers | 106570 | 106572 | 101456 | 100% | 0.1229% | 0.117% | 95.2% | 0.95199
|  | Z2-C-RSRS-11160 | Install Duct Risers | 202071 | 202071 | 214319 | 100% | 0.233% | 0.2471% | 106.1% | 1.0606
| Div 13 | T&C-10080 | Passenger Lift Testing & Commissioning | 3332 | 3333 | 2833 | 100% | 0.003842% | 0.003266% | 85.02% | 0.84998
|  | T&C-10090 | Travelators Testing & Commissioning | 3332 | 3333 | 2833 | 100% | 0.003842% | 0.003266% | 85.02% | 0.84998
|  | T&C-10110 | Escalator Testing & Commissioning | 3334 | 3333 | 2833 | 99.97% | 0.003842% | 0.003266% | 84.97% | 0.84998
|  | Z2-C-LIFT-10520 | Install Working Platform for PL-3 & 4 (B2 to SRVF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10530 | Install Steel Support Beams & Tracks PL-3 & 4 (B2 to SRVF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10540 | Repair Lift Shaft PL-3 & 4 (B2 to SRVF) | 97230 | 97231 | 86778 | 100% | 0.1121% | 0.1% | 89.25% | 0.89249
|  | Z2-C-LIFT-10550 | Install Working Platform for CL B2 to - F2 | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10560 | Install Steel Support Beams & Tracks CL B2 to - F2 | 97230 | 97231 | 82647 | 100% | 0.1121% | 0.09528% | 85% | 0.85001
|  | Z2-C-LIFT-10580 | Terminate Tracks & Cross Beams CL B2 to - F2 | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10610 | Install Lift Motors & Hydraulics CL B2 to - F2) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10620 | Install Lift Control Unit CL B2 to - F2 | 97230 | 97230 | 82645 | 100% | 0.1121% | 0.09527% | 85% | 0.84999
|  | Z2-C-LIFT-10630 | Power Connection & Test Runs CL B2 to - F2 | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10640 | Terminate Tracks & Cross Beams (B2 to GF) | 97231 | 97230 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85001
|  | Z2-C-LIFT-10650 | Install Lift Access Doors (B2 to GF) | 97230 | 97231 | 82647 | 100% | 0.1121% | 0.09528% | 85% | 0.85001
|  | Z2-C-LIFT-10660 | Install Lift Cabin (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10670 | Install Lift Motors, Cables, Counter Weight & Brakes (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10680 | Install Lift Control Unit (B2 to GF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10690 | Power Connection & Test Runs (B2 to GF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10700 | Install Working Platform for PL-5 (B2 to SRVF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10710 | Install Steel Support Beams & Tracks PL-5 (B2 to SRVF) | 97230 | 97231 | 82647 | 100% | 0.1121% | 0.09528% | 85% | 0.85001
|  | Z2-C-LIFT-10720 | Repair Lift Shaft PL-5 (B2 to SRVF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10730 | Terminate Tracks & Cross Beams (B2 to GF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10740 | Install Lift Access Doors (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10750 | Install Lift Cabin (B2 to GF) | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10760 | Install Lift Motors, Cables, Counter Weight & Brakes (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10770 | Install Lift Control Unit (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10780 | Power Connection & Test Runs (B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10790 | Install Working Platform for CL B2 to GF | 97230 | 97231 | 82647 | 100% | 0.1121% | 0.09528% | 85% | 0.85001
|  | Z2-C-LIFT-10800 | Install Steel Support Beams & Tracks CL B2 to GF | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10820 | Terminate Tracks & Cross Beams CL B2 to GF | 97230 | 97230 | 82645 | 100% | 0.1121% | 0.09527% | 85% | 0.84999
|  | Z2-C-LIFT-10850 | Install Lift Motors & Hydraulics CL B2 to GF) | 97231 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10860 | Install Lift Control Unit CL B2 to GF | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
|  | Z2-C-LIFT-10870 | Power Connection & Test Runs CL B2 to GF | 97230 | 97231 | 82646 | 100% | 0.1121% | 0.09528% | 85% | 0.85
| Div 14 | Z123-C-MEP-15020 | Fix Gas Detectors - Z123 - SRVF | 12341 | 12342 | 10491 | 100% | 0.01423% | 0.01209% | 85.01% | 0.85002
|  | Z123-C-MEP-15110 | Install LPG Tank - Z123 - SRVF | 12341 | 12342 | 10491 | 100% | 0.01423% | 0.01209% | 85.01% | 0.85002
|  | Z2&3-C-MEP-16460 | Fix LPG Pipes - Z2&3 - F2 | 12341 | 12342 | 10491 | 100% | 0.01423% | 0.01209% | 85.01% | 0.85002
|  | Z2&3-C-MEP-16570 | Fix Gas Detectors - Z2&3 - F2 | 12341 | 12342 | 10491 | 100% | 0.01423% | 0.01209% | 85.01% | 0.85002
|  | Z2&3-C-MEP-16710 | Fix LPG Pipes - Z2&3 - RF | 12342 | 12342 | 10491 | 100% | 0.01423% | 0.01209% | 85% | 0.85002
|  | Z2&3-C-MEP-16860 | Fix Gas Detectors - Z2&3 - RF | 12342 | 12342 | 10491 | 100% | 0.01423% | 0.01209% | 85% | 0.85002
|  | Z2-C-RSRS-11170 | Install LPG Pipe Risers | 12340 | 12342 | 13148 | 100% | 0.01423% | 0.01516% | 106.5% | 1.0653
| Div 15 | T&C-10040 | Telephone & Voice Evac. System Testing & Commissioning | 1428 | 1428 | 1214 | 100% | 0.001646% | 0.0014% | 85.01% | 0.85014
|  | T&C-10050 | Emergency Lighting System Testing & Commissioning | 1428 | 1428 | 1214 | 100% | 0.001646% | 0.0014% | 85.01% | 0.85014
|  | T&C-10060 | Access Control System Testing & Commissioning | 1428 | 1428 | 1214 | 100% | 0.001646% | 0.0014% | 85.01% | 0.85014
|  | T&C-10070 | Fire Alarm System Testing & Commissioning | 1428 | 1428 | 1214 | 100% | 0.001646% | 0.0014% | 85.01% | 0.85014
|  | T&C-10120 | BMS Testing & Commissioning | 1428 | 1428 | 1214 | 100% | 0.001646% | 0.0014% | 85.01% | 0.85014
|  | T&C-10130 | Security System Testing & Commissioning | 1428 | 1428 | 1214 | 100% | 0.001646% | 0.0014% | 85.01% | 0.85014
|  | Z123-C-MEP-14750 | Fix G.I Box and conduits - Z123 - SRVF | 26755 | 26755 | 22742 | 100% | 0.03084% | 0.02622% | 85% | 0.85001
|  | Z123-C-MEP-14760 | Fix ELV Trunkings - Z123 - SRVF | 35620 | 35620 | 30277 | 100% | 0.04106% | 0.0349% | 85% | 0.85
|  | Z123-C-MEP-14770 | Pull ELV Cables - Z123 - SRVF | 46003 | 46003 | 39103 | 100% | 0.05303% | 0.04508% | 85% | 0.85001
|  | Z123-C-MEP-14780 | Fix Power Cable Trays - Z123 - SRVF | 32905 | 32905 | 27969 | 100% | 0.03793% | 0.03224% | 85% | 0.84999
|  | Z123-C-MEP-14790 | Pull Electricl Wires (Ceiling & Walls) - Z123 - SRVF | 10782 | 10782 | 9165 | 100% | 0.01243% | 0.01057% | 85% | 0.85003
|  | Z123-C-MEP-14800 | Pull Earthing & Power Cables - Z123 - SRVF | 84717 | 84717 | 72009 | 100% | 0.09766% | 0.08301% | 85% | 0.84999
|  | Z123-C-MEP-14810 | Fix DBs - Z123 - SRVF | 64069 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z123-C-MEP-14820 | Cable Terminations - Z123 - SRVF | 61108 | 61109 | 51942 | 100% | 0.07045% | 0.05988% | 85% | 0.84999
|  | Z123-C-MEP-14910 | Fix CCTV Devices - Z123 - SRVF | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z123-C-MEP-14920 | Fix Light Fixtures - Z123 - SRVF | 115828 | 115829 | 98455 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z123-C-MEP-14930 | Fix Switches, Sockets & Isolators - Z123 - SRVF | 11417 | 11418 | 9706 | 100% | 0.01316% | 0.01119% | 85.01% | 0.85006
|  | Z123-C-MEP-14940 | Fix Fire Alarm Devices - Z123 - SRVF | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z123-C-MEP-14950 | Fix Telephone & Voice Evac. Devices - Z123 - SRVF | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z123-C-MEP-14960 | Fix LCS & ACS Devices - Z123 - SRVF | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z123-C-MEP-14970 | Fix Emergency & Exit Lights - Z123 - SRVF | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z123-C-MEP-15100 | Install MCC Pannels - Z123 - SRVF | 339718 | 339718 | 288760 | 100% | 0.3916% | 0.3329% | 85% | 0.85
|  | Z2&3-C-MEP-15160 | Fix G.I Box and conduits - Z2&3 - B2 | 26755 | 26755 | 15010 | 100% | 0.03084% | 0.0173% | 56.1% | 0.56102
|  | Z2&3-C-MEP-15170 | Fix ELV Trunkings - Z2&3 - B2 | 35621 | 35620 | 58775 | 100% | 0.04106% | 0.06776% | 165% | 1.6501
|  | Z2&3-C-MEP-15180 | Pull ELV Cables - Z2&3 - B2 | 46004 | 46003 | 39103 | 100% | 0.05303% | 0.04508% | 85% | 0.85001
|  | Z2&3-C-MEP-15190 | Fix Power Cable Trays - Z2&3 - B2 | 32905 | 32904 | 54293 | 100% | 0.03793% | 0.06259% | 165% | 1.65
|  | Z2&3-C-MEP-15200 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - B2 | 10783 | 10782 | 9165 | 99.99% | 0.01243% | 0.01057% | 84.99% | 0.85003
|  | Z2&3-C-MEP-15210 | Pull Earthing & Power Cables - Z2&3 - B2 | 84716 | 84717 | 72009 | 100% | 0.09766% | 0.08301% | 85% | 0.84999
|  | Z2&3-C-MEP-15220 | Fix DBs - Z2&3 - B2 | 64069 | 64069 | 54458 | 100% | 0.07386% | 0.06278% | 85% | 0.84999
|  | Z2&3-C-MEP-15230 | Cable Terminations - Z2&3 - B2 | 61108 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z2&3-C-MEP-15300 | Fix CCTV Devices - Z2&3 - B2 | 78094 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z2&3-C-MEP-15310 | Fix Light Fixtures - Z2&3 - B2 | 115829 | 115829 | 98454 | 100% | 0.1335% | 0.1135% | 85% | 0.84999
|  | Z2&3-C-MEP-15320 | Fix Switches, Sockets & Isolators - Z2&3 - B2 | 11418 | 11418 | 9705 | 100% | 0.01316% | 0.01119% | 85% | 0.84997
|  | Z2&3-C-MEP-15330 | Fix Fire Alarm Devices - Z2&3 - B2 | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z2&3-C-MEP-15340 | Fix Telephone & Voice Evac. Devices - Z2&3 - B2 | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z2&3-C-MEP-15350 | Fix LCS & ACS Devices - Z2&3 - B2 | 28738 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z2&3-C-MEP-15360 | Fix Emergency & Exit Lights - Z2&3 - B2 | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z2&3-C-MEP-15430 | Fix G.I Box and conduits - Z2&3 - B1 | 26755 | 26755 | 22742 | 100% | 0.03084% | 0.02622% | 85% | 0.85001
|  | Z2&3-C-MEP-15440 | Fix ELV Trunkings - Z2&3 - B1 | 35620 | 35620 | 30277 | 100% | 0.04106% | 0.0349% | 85% | 0.85
|  | Z2&3-C-MEP-15450 | Pull ELV Cables - Z2&3 - B1 | 46004 | 46003 | 39103 | 100% | 0.05303% | 0.04508% | 85% | 0.85001
|  | Z2&3-C-MEP-15460 | Fix Power Cable Trays - Z2&3 - B1 | 32904 | 32905 | 27969 | 100% | 0.03793% | 0.03224% | 85% | 0.84999
|  | Z2&3-C-MEP-15470 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - B1 | 10780 | 10782 | 9164 | 100% | 0.01243% | 0.01056% | 85.01% | 0.84994
|  | Z2&3-C-MEP-15480 | Pull Earthing & Power Cables - Z2&3 - B1 | 84718 | 84717 | 72009 | 100% | 0.09766% | 0.08301% | 85% | 0.84999
|  | Z2&3-C-MEP-15490 | Fix DBs - Z2&3 - B1 | 64068 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z2&3-C-MEP-15500 | Cable Terminations - Z2&3 - B1 | 61109 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z2&3-C-MEP-15570 | Fix CCTV Devices - Z2&3 - B1 | 78094 | 78093 | 17923 | 100% | 0.09003% | 0.02066% | 22.95% | 0.22951
|  | Z2&3-C-MEP-15580 | Fix Light Fixtures - Z2&3 - B1 | 115829 | 115829 | 26583 | 100% | 0.1335% | 0.03065% | 22.95% | 0.2295
|  | Z2&3-C-MEP-15590 | Fix Switches, Sockets & Isolators - Z2&3 - B1 | 11418 | 11418 | 2620 | 100% | 0.01316% | 0.00302% | 22.95% | 0.22946
|  | Z2&3-C-MEP-15600 | Fix Fire Alarm Devices - Z2&3 - B1 | 51070 | 51070 | 11721 | 100% | 0.05887% | 0.01351% | 22.95% | 0.22951
|  | Z2&3-C-MEP-15610 | Fix Telephone & Voice Evac. Devices - Z2&3 - B1 | 43578 | 43578 | 10001 | 100% | 0.05024% | 0.01153% | 22.95% | 0.2295
|  | Z2&3-C-MEP-15620 | Fix LCS & ACS Devices - Z2&3 - B1 | 28739 | 28739 | 6596 | 100% | 0.03313% | 0.007604% | 22.95% | 0.22951
|  | Z2&3-C-MEP-15630 | Fix Emergency & Exit Lights - Z2&3 - B1 | 45974 | 45974 | 10551 | 100% | 0.053% | 0.01216% | 22.95% | 0.2295
|  | Z2&3-C-MEP-15700 | Fix G.I Box and conduits - Z2&3 - F1 | 26755 | 26755 | 22741 | 100% | 0.03084% | 0.02622% | 85% | 0.84997
|  | Z2&3-C-MEP-15720 | Fix ELV Trunkings - Z2&3 - F1 | 35619 | 35620 | 30277 | 100% | 0.04106% | 0.0349% | 85% | 0.85
|  | Z2&3-C-MEP-15730 | Pull ELV Cables - Z2&3 - F1 | 46004 | 46003 | 47798 | 100% | 0.05303% | 0.0551% | 103.9% | 1.039
|  | Z2&3-C-MEP-15740 | Fix Power Cable Trays - Z2&3 - F1 | 32904 | 32905 | 27969 | 100% | 0.03793% | 0.03224% | 85% | 0.84999
|  | Z2&3-C-MEP-15750 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - F1 | 10782 | 10781 | 11202 | 99.99% | 0.01243% | 0.01291% | 103.9% | 1.0391
|  | Z2&3-C-MEP-15760 | Pull Earthing & Power Cables - Z2&3 - F1 | 84717 | 84717 | 88024 | 100% | 0.09766% | 0.1015% | 103.9% | 1.039
|  | Z2&3-C-MEP-15770 | Fix DBs - Z2&3 - F1 | 64069 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z2&3-C-MEP-15780 | Cable Terminations - Z2&3 - F1 | 61109 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z2&3-C-MEP-15860 | Fix CCTV Devices - Z2&3 - F1 | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z2&3-C-MEP-15870 | Fix Light Fixtures - Z2&3 - F1 | 115829 | 115828 | 87906 | 100% | 0.1335% | 0.1013% | 75.89% | 0.75894
|  | Z2&3-C-MEP-15880 | Fix Switches, Sockets & Isolators - Z2&3 - F1 | 11418 | 11418 | 10745 | 100% | 0.01316% | 0.01239% | 94.11% | 0.94106
|  | Z2&3-C-MEP-15890 | Fix Fire Alarm Devices - Z2&3 - F1 | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z2&3-C-MEP-15900 | Fix Telephone & Voice Evac. Devices - Z2&3 - F1 | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z2&3-C-MEP-15910 | Fix LCS & ACS Devices - Z2&3 - F1 | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z2&3-C-MEP-15920 | Fix Emergency & Exit Lights - Z2&3 - F1 | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z2&3-C-MEP-16000 | Fix G.I Box and conduits - Z2&3 - GF | 26755 | 26755 | 22742 | 100% | 0.03084% | 0.02622% | 85% | 0.85001
|  | Z2&3-C-MEP-16020 | Fix ELV Trunkings - Z2&3 - GF | 35620 | 35620 | 30277 | 100% | 0.04106% | 0.0349% | 85% | 0.85
|  | Z2&3-C-MEP-16030 | Pull ELV Cables - Z2&3 - GF | 46004 | 46003 | 39103 | 100% | 0.05303% | 0.04508% | 85% | 0.85001
|  | Z2&3-C-MEP-16040 | Fix Power Cable Trays - Z2&3 - GF | 32904 | 32905 | 27969 | 100% | 0.03793% | 0.03224% | 85% | 0.84999
|  | Z2&3-C-MEP-16050 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - GF | 10780 | 10782 | 9675 | 100% | 0.01243% | 0.01115% | 89.75% | 0.89733
|  | Z2&3-C-MEP-16060 | Pull Earthing & Power Cables - Z2&3 - GF | 84718 | 84718 | 76022 | 100% | 0.09766% | 0.08764% | 89.74% | 0.89735
|  | Z2&3-C-MEP-16070 | Fix DBs - Z2&3 - GF | 64068 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z2&3-C-MEP-16080 | Cable Terminations - Z2&3 - GF | 61109 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z2&3-C-MEP-16160 | Fix CCTV Devices - Z2&3 - GF | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z2&3-C-MEP-16170 | Fix Light Fixtures - Z2&3 - GF | 115829 | 115829 | 98455 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z2&3-C-MEP-16180 | Fix Switches, Sockets & Isolators - Z2&3 - GF | 11418 | 11418 | 9705 | 100% | 0.01316% | 0.01119% | 85% | 0.84997
|  | Z2&3-C-MEP-16190 | Fix Fire Alarm Devices - Z2&3 - GF | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z2&3-C-MEP-16200 | Fix Telephone & Voice Evac. Devices - Z2&3 - GF | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z2&3-C-MEP-16210 | Fix LCS & ACS Devices - Z2&3 - GF | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z2&3-C-MEP-16220 | Fix Emergency & Exit Lights - Z2&3 - GF | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z2&3-C-MEP-16300 | Fix G.I Box and conduits - Z2&3 - F2 | 26755 | 26755 | 22742 | 100% | 0.03084% | 0.02622% | 85% | 0.85001
|  | Z2&3-C-MEP-16320 | Fix ELV Trunkings - Z2&3 - F2 | 35619 | 35620 | 30277 | 100% | 0.04106% | 0.0349% | 85% | 0.85
|  | Z2&3-C-MEP-16330 | Pull ELV Cables - Z2&3 - F2 | 46003 | 46003 | 37706 | 100% | 0.05303% | 0.04347% | 81.96% | 0.81964
|  | Z2&3-C-MEP-16340 | Fix Power Cable Trays - Z2&3 - F2 | 32904 | 32905 | 27970 | 100% | 0.03793% | 0.03224% | 85% | 0.85002
|  | Z2&3-C-MEP-16350 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - F2 | 10783 | 10782 | 8837 | 99.99% | 0.01243% | 0.01019% | 81.95% | 0.81961
|  | Z2&3-C-MEP-16360 | Pull Earthing & Power Cables - Z2&3 - F2 | 84718 | 84717 | 69438 | 100% | 0.09766% | 0.08005% | 81.96% | 0.81965
|  | Z2&3-C-MEP-16370 | Fix DBs - Z2&3 - F2 | 64069 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z2&3-C-MEP-16380 | Cable Terminations - Z2&3 - F2 | 61109 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z2&3-C-MEP-16470 | Fix CCTV Devices - Z2&3 - F2 | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z2&3-C-MEP-16480 | Fix Light Fixtures - Z2&3 - F2 | 115829 | 115829 | 98455 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z2&3-C-MEP-16490 | Fix Switches, Sockets & Isolators - Z2&3 - F2 | 11418 | 11418 | 9705 | 100% | 0.01316% | 0.01119% | 85% | 0.84997
|  | Z2&3-C-MEP-16500 | Fix Fire Alarm Devices - Z2&3 - F2 | 51070 | 51070 | 43410 | 100% | 0.05887% | 0.05004% | 85% | 0.85001
|  | Z2&3-C-MEP-16510 | Fix Telephone & Voice Evac. Devices - Z2&3 - F2 | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z2&3-C-MEP-16520 | Fix LCS & ACS Devices - Z2&3 - F2 | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z2&3-C-MEP-16530 | Fix Emergency & Exit Lights - Z2&3 - F2 | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z2&3-C-MEP-16620 | Fix G.I Box and conduits - Z2&3 - RF | 26755 | 26755 | 22742 | 100% | 0.03084% | 0.02622% | 85% | 0.85001
|  | Z2&3-C-MEP-16640 | Fix ELV Trunkings - Z2&3 - RF | 35620 | 35620 | 13336 | 100% | 0.04106% | 0.01537% | 37.44% | 0.3744
|  | Z2&3-C-MEP-16650 | Pull ELV Cables - Z2&3 - RF | 46004 | 46003 | 39102 | 100% | 0.05303% | 0.04508% | 85% | 0.84999
|  | Z2&3-C-MEP-16660 | Fix Power Cable Trays - Z2&3 - RF | 32904 | 32905 | 12320 | 100% | 0.03793% | 0.0142% | 37.44% | 0.37441
|  | Z2&3-C-MEP-16670 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - RF | 10783 | 10782 | 9165 | 99.99% | 0.01243% | 0.01057% | 84.99% | 0.85003
|  | Z2&3-C-MEP-16680 | Pull Earthing & Power Cables - Z2&3 - RF | 84717 | 84717 | 72009 | 100% | 0.09766% | 0.08301% | 85% | 0.84999
|  | Z2&3-C-MEP-16690 | Fix DBs - Z2&3 - RF | 64069 | 64069 | 54459 | 100% | 0.07386% | 0.06278% | 85% | 0.85001
|  | Z2&3-C-MEP-16700 | Cable Terminations - Z2&3 - RF | 61109 | 61109 | 51943 | 100% | 0.07045% | 0.05988% | 85% | 0.85001
|  | Z2&3-C-MEP-16790 | Fix CCTV Devices - Z2&3 - RF | 78093 | 78093 | 66379 | 100% | 0.09003% | 0.07652% | 85% | 0.85
|  | Z2&3-C-MEP-16800 | Fix Light Fixtures - Z2&3 - RF | 115829 | 115829 | 98455 | 100% | 0.1335% | 0.1135% | 85% | 0.85
|  | Z2&3-C-MEP-16810 | Fix Switches, Sockets & Isolators - Z2&3 - RF | 11418 | 11418 | 9705 | 100% | 0.01316% | 0.01119% | 85% | 0.84997
|  | Z2&3-C-MEP-16820 | Fix Fire Alarm Devices - Z2&3 - RF | 51069 | 51070 | 43409 | 100% | 0.05887% | 0.05004% | 85% | 0.84999
|  | Z2&3-C-MEP-16830 | Fix Telephone & Voice Evac. Devices - Z2&3 - RF | 43578 | 43578 | 37041 | 100% | 0.05024% | 0.0427% | 85% | 0.84999
|  | Z2&3-C-MEP-16840 | Fix LCS & ACS Devices - Z2&3 - RF | 28739 | 28739 | 24428 | 100% | 0.03313% | 0.02816% | 85% | 0.84999
|  | Z2&3-C-MEP-16850 | Fix Emergency & Exit Lights - Z2&3 - RF | 45974 | 45974 | 39078 | 100% | 0.053% | 0.04505% | 85% | 0.85
|  | Z2-C-RSRS-11180 | Install Cable treys & Trunking Risers | 271608 | 271609 | 264344 | 100% | 0.3131% | 0.3047% | 97.33% | 0.97325
|  | Z2-C-RSRS-11190 | Install Busbar Risers | 158075 | 158075 | 134364 | 100% | 0.1822% | 0.1549% | 85% | 0.85
Z3 | Div 03 | Z3-11520 | Post Tensioning the Slab - Z3 - F1 | 18819 | 18819 | 12232 | 100% | 0.02169% | 0.0141% | 65% | 0.64998
|  | Z3-11530 | Post Tensioning the Slab - Z3 - F2 | 19103 | 19103 | 16238 | 100% | 0.02202% | 0.01872% | 85% | 0.85002
|  | Z3-11540 | Post Tensioning the Slab - Z3 - RF | 19044 | 19044 | 16187 | 100% | 0.02195% | 0.01866% | 85% | 0.84998
|  | Z3-11550 | Post Tensioning the Slab - Z3 - SRVF | 15998 | 15998 | 11443 | 100% | 0.01844% | 0.01319% | 71.53% | 0.71528
|  | Z3-C-CON-5840 | PCC Blind Concrete - Z3 - Lift Pit | 8610 | 8610 | 172 | 100% | 0.009926% | 0.0001983% | 1.998% | 0.019977
|  | Z3-C-CON-5850 | Waterproof Membrane - Z3 - Lift Pit | 51140 | 51140 | 1023 | 100% | 0.05896% | 0.001179% | 2% | 0.020004
|  | Z3-C-CON-5860 | Protection Screed - Z3 - Lift Pit | 5490 | 5490 | 55 | 100% | 0.006329% | 6.341e-05% | 1.002% | 0.010018
|  | Z3-C-CON-5870 | Fix Rebar - Z3 - Lift Pit | 15185 | 15186 | 152 | 100% | 0.01751% | 0.0001752% | 1.001% | 0.010009
|  | Z3-C-CON-5890 | Pour Concrete - Z3 - Lift Pit | 15186 | 15186 | 3227 | 100% | 0.01751% | 0.00372% | 21.25% | 0.2125
|  | Z3-C-CON-5900 | PCC Blind Concrete - Z3 - Raft | 345090 | 345090 | 293326 | 100% | 0.3978% | 0.3382% | 85% | 0.85
|  | Z3-C-CON-5910 | Waterproof Membrane - Z3 - Raft | 27450 | 27450 | 23332 | 100% | 0.03164% | 0.0269% | 85% | 0.84998
|  | Z3-C-CON-5920 | Protection Screed - Z3 - Raft | 255701 | 255700 | 217345 | 100% | 0.2948% | 0.2506% | 85% | 0.85
|  | Z3-C-CON-5930 | Fix Rebar - Z3 - Raft | 544585 | 544585 | 462897 | 100% | 0.6278% | 0.5336% | 85% | 0.85
|  | Z3-C-CON-5950 | Fix Formwork - Z3 - Raft | 30992 | 30991 | 26342 | 100% | 0.03573% | 0.03037% | 85% | 0.84999
|  | Z3-C-CON-5960 | Pour Concrete - Z3 - Raft | 548054 | 548054 | 465846 | 100% | 0.6318% | 0.537% | 85% | 0.85
|  | Z3-C-CON-5970 | Fix Rebar Columns - Z3 - B2 | 47431 | 47430 | 40316 | 100% | 0.05468% | 0.04648% | 85% | 0.85001
|  | Z3-C-CON-5980 | Fix Formwork Columns - Z3 - B2 | 23716 | 23715 | 3225 | 100% | 0.02734% | 0.003718% | 13.6% | 0.13599
|  | Z3-C-CON-5990 | Pour Concrete Columns - Z3 - B2 | 47430 | 47430 | 6450 | 100% | 0.05468% | 0.007436% | 13.6% | 0.13599
|  | Z3-C-CON-6000 | Fix Rebar Retaining Walls - Z3 - B2 | 65427 | 65427 | 55613 | 100% | 0.07543% | 0.06411% | 85% | 0.85
|  | Z3-C-CON-6010 | Fix Formwork Retaining Walls - Z3 - B2 | 32714 | 32714 | 4449 | 100% | 0.03771% | 0.005129% | 13.6% | 0.136
|  | Z3-C-CON-6020 | Pour Concrete Retaining Walls - Z3 - B2 | 65427 | 65427 | 654 | 100% | 0.07543% | 0.0007539% | 0.9996% | 0.0099959
|  | Z3-C-CON-6030 | Pour Concrete Core Walls - Z3 - B2 | 33489 | 33489 | 335 | 100% | 0.03861% | 0.0003862% | 1% | 0.010003
|  | Z3-C-CON-6040 | Fix Rebar Core Walls - Z3 - B2 | 25117 | 25117 | 251 | 100% | 0.02896% | 0.0002894% | 0.9993% | 0.0099932
|  | Z3-C-CON-6050 | Fix Formwork Core Walls - Z3 - B2 | 25118 | 25117 | 251 | 100% | 0.02896% | 0.0002894% | 0.9993% | 0.0099932
|  | Z3-C-CON-6060 | Fix Formwork Stairs - Z3 - B2 | 1865 | 1865 | 1585 | 100% | 0.00215% | 0.001827% | 84.99% | 0.84987
|  | Z3-C-CON-6070 | Fix Rebar Stairs - Z3 - B2 | 3729 | 3730 | 410 | 100% | 0.0043% | 0.0004727% | 10.99% | 0.10992
|  | Z3-C-CON-6080 | Pour Concrete Stairs - Z3 - B2 | 3729 | 3729 | 224 | 100% | 0.004299% | 0.0002582% | 6.007% | 0.06007
|  | Z3-C-CON-6090 | Fix Rebar Retaining Walls - Z3 - B1 | 65428 | 65427 | 3926 | 100% | 0.07543% | 0.004526% | 6% | 0.060006
|  | Z3-C-CON-6100 | Fix Formwork Retaining Walls - Z3 - B1 | 32714 | 32714 | 1963 | 100% | 0.03771% | 0.002263% | 6% | 0.060005
|  | Z3-C-CON-6110 | Pour Concrete Retaining Walls - Z3 - B1 | 65427 | 65427 | 30587 | 100% | 0.07543% | 0.03526% | 46.75% | 0.4675
|  | Z3-C-CON-6120 | Fix Formwork Core Walls - Z3 - B1 | 25117 | 25117 | 1507 | 100% | 0.02896% | 0.001737% | 6% | 0.059999
|  | Z3-C-CON-6130 | Fix Rebar Core Walls - Z3 - B1 | 25117 | 25117 | 17268 | 100% | 0.02896% | 0.01991% | 68.75% | 0.6875
|  | Z3-C-CON-6140 | Pour Concrete Core Walls - Z3 - B1 | 33489 | 33489 | 2009 | 100% | 0.03861% | 0.002316% | 5.999% | 0.05999
|  | Z3-C-CON-6150 | Fix Rebar Columns - Z3 - B1 | 47430 | 47431 | 40316 | 100% | 0.05468% | 0.04648% | 85% | 0.84999
|  | Z3-C-CON-6160 | Fix Formwork Columns - Z3 - B1 | 23715 | 23715 | 1423 | 100% | 0.02734% | 0.00164% | 6% | 0.060004
|  | Z3-C-CON-6170 | Pour Concrete Columns - Z3 - B1 | 47430 | 47430 | 2846 | 100% | 0.05468% | 0.003281% | 6% | 0.060004
|  | Z3-C-CON-6180 | Fix Formwork Stairs - Z3 - B1 | 1864 | 1865 | 93 | 100.1% | 0.00215% | 0.0001072% | 4.989% | 0.049866
|  | Z3-C-CON-6190 | Fix Rebar Stairs - Z3 - B1 | 3729 | 3729 | 1331 | 100% | 0.004299% | 0.001534% | 35.69% | 0.35693
|  | Z3-C-CON-6200 | Pour Concrete Stairs - Z3 - B1 | 3729 | 3729 | 559 | 100% | 0.004299% | 0.0006444% | 14.99% | 0.14991
|  | Z3-C-CON-6210 | Fix Formwork Slabs - Z3 - B1 | 100188 | 100188 | 3006 | 100% | 0.1155% | 0.003465% | 3% | 0.030004
|  | Z3-C-CON-6220 | Fix Rebar Slabs - Z3 - B1 | 200376 | 200376 | 4008 | 100% | 0.231% | 0.004621% | 2% | 0.020002
|  | Z3-C-CON-6230 | Pour Concrete Slabs - Z3 - B1 | 200376 | 200376 | 170320 | 100% | 0.231% | 0.1963% | 85% | 0.85
|  | Z3-C-CON-6240 | Fix MEP Containment & Provisions - Z3 - B1 | 5440 | 5440 | 740 | 100% | 0.006271% | 0.0008531% | 13.6% | 0.13603
|  | Z3-C-CON-6250 | Fix Rebar Core Walls - Z3 - GF | 54255 | 54254 | 2713 | 100% | 0.06255% | 0.003128% | 5% | 0.050006
|  | Z3-C-CON-6260 | Fix Formwork Core Walls - Z3 - GF | 28239 | 28238 | 25238 | 100% | 0.03255% | 0.02909% | 89.37% | 0.89376
|  | Z3-C-CON-6270 | Pour Concrete Core Walls - Z3 - GF | 55661 | 55661 | 31226 | 100% | 0.06417% | 0.036% | 56.1% | 0.561
|  | Z3-C-CON-6280 | Fix Rebar Columns - Z3 - GF | 72503 | 72503 | 3625 | 100% | 0.08358% | 0.004179% | 5% | 0.049998
|  | Z3-C-CON-6290 | Fix Formwork Columns - Z3 - GF | 38017 | 38017 | 33978 | 100% | 0.04383% | 0.03917% | 89.38% | 0.89376
|  | Z3-C-CON-6300 | Pour Concrete Columns - Z3 - GF | 76127 | 76127 | 42707 | 100% | 0.08776% | 0.04923% | 56.1% | 0.561
|  | Z3-C-CON-6310 | Fix Formwork Stairs - Z3 - GF | 2419 | 2419 | 605 | 100% | 0.002789% | 0.0006975% | 25.01% | 0.2501
|  | Z3-C-CON-6320 | Fix Rebar Stairs - Z3 - GF | 4839 | 4839 | 4113 | 100% | 0.005579% | 0.004742% | 85% | 0.84997
|  | Z3-C-CON-6330 | Pour Concrete Stairs - Z3 - GF | 4839 | 4839 | 3145 | 100% | 0.005579% | 0.003626% | 64.99% | 0.64993
|  | Z3-C-CON-6340 | Fix Formwork Slabs - Z3 - GF | 129638 | 129637 | 68384 | 100% | 0.1494% | 0.07883% | 52.75% | 0.5275
|  | Z3-C-CON-6350 | Fix Rebar Slabs - Z3 - GF | 259274 | 259275 | 25927 | 100% | 0.2989% | 0.02989% | 10% | 0.099998
|  | Z3-C-CON-6360 | Pour Concrete Slabs - Z3 - GF | 259275 | 259275 | 25928 | 100% | 0.2989% | 0.02989% | 10% | 0.1
|  | Z3-C-CON-6370 | Fix MEP Containment & Provisions - Z3 - GF | 5440 | 5440 | 544 | 100% | 0.006271% | 0.0006271% | 10% | 0.1
|  | Z3-C-CON-6380 | Fix Formwork Slabs - Z3 - F1 | 144523 | 144524 | 81077 | 100% | 0.1666% | 0.09347% | 56.1% | 0.56099
|  | Z3-C-CON-6390 | Fix Rebar Slabs - Z3 - F1 | 187928 | 187928 | 93964 | 100% | 0.2166% | 0.1083% | 50% | 0.5
|  | Z3-C-CON-6400 | Fix MEP Containment & Provisions - Z3 - F1 | 5440 | 5440 | 2720 | 100% | 0.006271% | 0.003136% | 50% | 0.5
|  | Z3-C-CON-6410 | Pour Concrete Slabs - Z3 - F1 | 119801 | 119801 | 29950 | 100% | 0.1381% | 0.03453% | 25% | 0.25
|  | Z3-C-CON-6420 | Fix Rebar Core Walls - Z3 - F1 | 53594 | 53594 | 13399 | 100% | 0.06178% | 0.01545% | 25% | 0.25001
|  | Z3-C-CON-6430 | Fix Formwork Core Walls - Z3 - F1 | 28287 | 28287 | 18387 | 100% | 0.03261% | 0.0212% | 65% | 0.65002
|  | Z3-C-CON-6440 | Pour Concrete Core Walls - Z3 - F1 | 56412 | 56412 | 56412 | 100% | 0.06503% | 0.06503% | 100% | 1
|  | Z3-C-CON-6450 | Fix Rebar Columns - Z3 - F1 | 73448 | 73448 | 18362 | 100% | 0.08467% | 0.02117% | 25% | 0.25
|  | Z3-C-CON-6460 | Fix Formwork Columns - Z3 - F1 | 37830 | 37831 | 24590 | 100% | 0.04361% | 0.02835% | 65% | 0.65
|  | Z3-C-CON-6470 | Pour Concrete Columns - Z3 - F1 | 75888 | 75889 | 49327 | 100% | 0.08749% | 0.05687% | 65% | 0.64999
|  | Z3-C-CON-6480 | Fix Formwork Stairs - Z3 - F1 | 2420 | 2419 | 1573 | 99.96% | 0.002789% | 0.001813% | 65% | 0.65027
|  | Z3-C-CON-6490 | Fix Rebar Stairs - Z3 - F1 | 4839 | 4839 | 4113 | 100% | 0.005579% | 0.004742% | 85% | 0.84997
|  | Z3-C-CON-6500 | Pour Concrete Stairs - Z3 - F1 | 4839 | 4839 | 4839 | 100% | 0.005579% | 0.005579% | 100% | 1
|  | Z3-C-CON-6510 | Fix Rebar Slabs - Z3 - F2 | 193299 | 193298 | 164303 | 100% | 0.2228% | 0.1894% | 85% | 0.85
|  | Z3-C-CON-6520 | Fix Formwork Slabs - Z3 - F2 | 145945 | 145945 | 291890 | 100% | 0.1682% | 0.3365% | 200% | 2
|  | Z3-C-CON-6530 | Pour Concrete Slabs - Z3 - F2 | 455692 | 455692 | 387338 | 100% | 0.5253% | 0.4465% | 85% | 0.85
|  | Z3-C-CON-6540 | Fix MEP Containment & Provisions - Z3 - F2 | 5440 | 5440 | 4624 | 100% | 0.006271% | 0.005331% | 85% | 0.85
|  | Z3-C-CON-6550 | Fix Rebar Core Walls - Z3 - F2 | 35418 | 35418 | 30105 | 100% | 0.04083% | 0.03471% | 85% | 0.84999
|  | Z3-C-CON-6560 | Fix Formwork Core Walls - Z3 - F2 | 16704 | 16705 | 14199 | 100% | 0.01926% | 0.01637% | 85% | 0.84999
|  | Z3-C-CON-6570 | Pour Concrete Core Walls - Z3 - F2 | 33899 | 33899 | 28814 | 100% | 0.03908% | 0.03322% | 85% | 0.85
|  | Z3-C-CON-6580 | Fix Rebar Columns - Z3 - F2 | 50067 | 50067 | 42557 | 100% | 0.05772% | 0.04906% | 85% | 0.85
|  | Z3-C-CON-6590 | Fix Formwork Columns - Z3 - F2 | 24315 | 24316 | 20669 | 100% | 0.02803% | 0.02383% | 85.01% | 0.85002
|  | Z3-C-CON-6600 | Pour Concrete Columns - Z3 - F2 | 48001 | 48002 | 40802 | 100% | 0.05534% | 0.04704% | 85% | 0.85001
|  | Z3-C-CON-6610 | Fix Formwork Stairs - Z3 - F2 | 2419 | 2419 | 2056 | 100% | 0.002789% | 0.00237% | 84.99% | 0.84994
|  | Z3-C-CON-6620 | Fix Rebar Stairs - Z3 - F2 | 4839 | 4839 | 4113 | 100% | 0.005579% | 0.004742% | 85% | 0.84997
|  | Z3-C-CON-6630 | Pour Concrete Stairs - Z3 - F2 | 4839 | 4839 | 4113 | 100% | 0.005579% | 0.004742% | 85% | 0.84997
|  | Z3-C-CON-6640 | Fix Formwork Slabs - Z3 - RF | 65648 | 65648 | 55801 | 100% | 0.07568% | 0.06433% | 85% | 0.85
|  | Z3-C-CON-6650 | Fix Rebar Slabs - Z3 - RF | 192257 | 192258 | 163420 | 100% | 0.2216% | 0.1884% | 85% | 0.85
|  | Z3-C-CON-6660 | Pour Concrete Slabs - Z3 - RF | 253253 | 253253 | 215265 | 100% | 0.292% | 0.2482% | 85% | 0.85
|  | Z3-C-CON-6670 | Fix MEP Containment & Provisions - Z3 - RF | 5440 | 5440 | 4624 | 100% | 0.006271% | 0.005331% | 85% | 0.85
|  | Z3-C-CON-6680 | Fix Rebar Core Walls - Z3 - RF | 34810 | 34810 | 29588 | 100% | 0.04013% | 0.03411% | 85% | 0.84999
|  | Z3-C-CON-6690 | Fix Formwork Core Walls - Z3 - RF | 16641 | 16642 | 14146 | 100% | 0.01919% | 0.01631% | 85.01% | 0.85002
|  | Z3-C-CON-6700 | Pour Concrete Core Walls - Z3 - RF | 33788 | 33788 | 28720 | 100% | 0.03895% | 0.03311% | 85% | 0.85001
|  | Z3-C-CON-6710 | Fix Rebar Columns - Z3 - RF | 40997 | 40997 | 34847 | 100% | 0.04726% | 0.04017% | 85% | 0.84999
|  | Z3-C-CON-6720 | Fix Formwork Columns - Z3 - RF | 18849 | 18849 | 16022 | 100% | 0.02173% | 0.01847% | 85% | 0.85002
|  | Z3-C-CON-6730 | Pour Concrete Columns - Z3 - RF | 38299 | 38299 | 32554 | 100% | 0.04415% | 0.03753% | 85% | 0.85
|  | Z3-C-CON-6740 | Fix Formwork Stairs - Z3 - RF | 2419 | 2419 | 2056 | 100% | 0.002789% | 0.00237% | 84.99% | 0.84994
|  | Z3-C-CON-6750 | Fix Rebar Stairs - Z3 - RF | 4032 | 4032 | 3427 | 100% | 0.004648% | 0.003951% | 85% | 0.84995
|  | Z3-C-CON-6760 | Pour Concrete Stairs - Z3 - RF | 4032 | 4032 | 3427 | 100% | 0.004648% | 0.003951% | 85% | 0.84995
|  | Z3-C-CON-6770 | Fix Formwork Slabs - Z3 - SRVF | 210418 | 210418 | 178855 | 100% | 0.2426% | 0.2062% | 85% | 0.85
|  | Z3-C-CON-6780 | Fix Rebar Slabs - Z3 - SRVF | 236165 | 236165 | 200740 | 100% | 0.2723% | 0.2314% | 85% | 0.85
|  | Z3-C-CON-6790 | Pour Concrete Slabs - Z3 - SRVF | 274411 | 274411 | 62977 | 100% | 0.3163% | 0.0726% | 22.95% | 0.2295
|  | Z3-C-CON-6800 | Fix MEP Containment & Provisions - Z3 - SRVF | 5440 | 5440 | 4624 | 100% | 0.006271% | 0.005331% | 85% | 0.85
|  | Z3-C-CON-6810 | Fix Rebar Core Walls - Z3 - SRVF | 20591 | 20590 | 4726 | 100% | 0.02374% | 0.005448% | 22.95% | 0.22953
|  | Z3-C-CON-6820 | Fix Formwork Core Walls - Z3 - SRVF | 9461 | 9461 | 8203 | 100% | 0.01091% | 0.009457% | 86.7% | 0.86703
|  | Z3-C-CON-6830 | Pour Concrete Core Walls - Z3 - SRVF | 18906 | 18906 | 16070 | 100% | 0.0218% | 0.01853% | 85% | 0.84999
|  | Z3-C-CON-6840 | Fix Rebar Columns - Z3 - SRVF | 3705 | 3706 | 850 | 100% | 0.004272% | 0.0009799% | 22.94% | 0.22936
|  | Z3-C-CON-6850 | Fix Formwork Columns - Z3 - SRVF | 1349 | 1349 | 310 | 100% | 0.001555% | 0.0003574% | 22.98% | 0.2298
|  | Z3-C-CON-6860 | Pour Concrete Columns - Z3 - SRVF | 2405 | 2405 | 552 | 100% | 0.002773% | 0.0006364% | 22.95% | 0.22952
|  | Z3-C-CON-6870 | Pour MEP RCC Pedastals - Z3 - SRVF | 807 | 807 | 185 | 100% | 0.0009303% | 0.0002133% | 22.92% | 0.22924
|  | Z3-C-CON-6880 | Fix Formwork Parapet - Z3 - SRVF | 14509 | 14509 | 3330 | 100% | 0.01673% | 0.003839% | 22.95% | 0.22951
|  | Z3-C-CON-6890 | Fix Rebar Parapet - Z3 - SRVF | 29018 | 29019 | 6660 | 100% | 0.03345% | 0.007678% | 22.95% | 0.2295
|  | Z3-C-CON-6900 | Pour Concrete Parapet - Z3 - SRVF | 29019 | 29019 | 6660 | 100% | 0.03345% | 0.007678% | 22.95% | 0.2295
|  | Z3-C-CON-6910 | Fix Formwork Slabs - Z3 - TRF | 7662 | 7663 | 6514 | 100% | 0.008834% | 0.007509% | 85.02% | 0.85006
|  | Z3-C-CON-6920 | Fix Rebar Slabs - Z3 - TRF | 15325 | 15325 | 13026 | 100% | 0.01767% | 0.01502% | 85% | 0.84998
|  | Z3-C-CON-6930 | Pour Concrete Slabs - Z3 - TRF | 15325 | 15325 | 13026 | 100% | 0.01767% | 0.01502% | 85% | 0.84998
|  | Z3-C-CON-6940 | Fix MEP Containment & Provisions - Z3 - TRF | 5440 | 5440 | 4624 | 100% | 0.006271% | 0.005331% | 85% | 0.85
|  | Z3-C-CON-6950 | Fix Formwork Parapet - Z3 - TRF | 14509 | 14509 | 12333 | 100% | 0.01673% | 0.01422% | 85% | 0.85002
|  | Z3-C-CON-6960 | Fix Rebar Parapet - Z3 - TRF | 29019 | 29019 | 24666 | 100% | 0.03345% | 0.02844% | 85% | 0.84999
|  | Z3-C-CON-6970 | Pour Concrete Parapet - Z3 - TRF | 29019 | 29019 | 24666 | 100% | 0.03345% | 0.02844% | 85% | 0.84999
| Div 10 | Z3-C-CON-5940 | Fix MEP Provisions - Z3 - Raft | 10500 | 10500 | 8925 | 100% | 0.0121% | 0.01029% | 85% | 0.85
Grand Total |  |  |  | 86743706 | 86650729 | 84700431 | 99.89% | 99.89% | 97.64% | 97.64% | 0.97749
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Detailed EVM ProfessionHrs
Row Labels | Activity ID | Activity Name | Indivisual Budget Hrs
Alum.Tech-1817 |  |  | 16117
Carpeter 1817 |  |  | 133613
Electrician 1817 |  |  | 28746
HVAC Tech. 1817 |  |  | 20130
Labor 1817 |  |  | 142851
Z1
Div 01 | PRL-MOB-1020 | Site Office Establishment | 100
| PRL-MOB-1050 | Project Sign Boards and Hoarding | 100
| PRL-MOB-1100 | Yards & Stores Establishment | 200
Div 02 | C-EW-10370 | Excavation Stage 1 - Z1 | 2271
| C-EW-10390 | Excavation Stage 2 - Z1 | 2271
| C-SHRNG-DCE-C-2330 | Place Guide Wall - Z1 | 83
| C-SHRNG-DCE-C-2350 | Install Capping Beam - Z1 | 60
| PRL-MOB-SCW-2330 | Clearing Existing Utilities | 500
Div 03 | Z1-C-CON-2400 | PCC Blind Concrete - Z1 - Lift Pit | 3
| Z1-C-CON-2440 | Waterproof Membrane - Z1 - Lift Pit | 40
| Z1-C-CON-2450 | Protection Screed - Z1 - Lift Pit | 12
| Z1-C-CON-2480 | Pour Concrete - Z1 - Lift Pit | 31
| Z1-C-CON-2500 | PCC Blind Concrete - Z1 - Raft | 98
| Z1-C-CON-2510 | Waterproof Membrane - Z1 - Raft | 1559
| Z1-C-CON-2520 | Protection Screed - Z1 - Raft | 48
| Z1-C-CON-2560 | Pour Concrete - Z1 - Raft | 1263
| Z1-C-CON-2620 | Pour Concrete Retaining Walls - Z1 - B2 | 241
| Z1-C-CON-2630 | Pour Concrete Core Walls - Z1 - B2 | 124
| Z1-C-CON-2660 | Pour Concrete Columns - Z1 - B2 | 87
| Z1-C-CON-2690 | Pour Concrete Stairs - Z1 - B2 | 4
| Z1-C-CON-2700 | Pour Concrete Slabs - Z1 - B1 | 713
| Z1-C-CON-2750 | Pour Concrete Retaining Walls - Z1 - B1 | 241
| Z1-C-CON-2780 | Pour Concrete Core Walls - Z1 - B1 | 142
| Z1-C-CON-2810 | Pour Concrete Columns - Z1 - B1 | 98
| Z1-C-CON-2840 | Pour Concrete Stairs - Z1 - B1 | 4
| Z1-C-CON-3020 | Pour Concrete Slabs - Z1 - GF | 954
| Z1-C-CON-3050 | Pour Concrete Core Walls - Z1 - GF | 157
| Z1-C-CON-3080 | Pour Concrete Columns - Z1 - GF | 149
| Z1-C-CON-3110 | Pour Concrete Stairs - Z1 - GF | 6
| Z1-C-CON-3170 | Pour Concrete Slabs - Z1 - F1 | 658
| Z1-C-CON-3210 | Pour Concrete Core Walls - Z1 - F1 | 159
| Z1-C-CON-3240 | Pour Concrete Columns - Z1 - F1 | 149
| Z1-C-CON-3270 | Pour Concrete Stairs - Z1 - F1 | 6
| Z1-C-CON-3300 | Pour Concrete Slabs - Z1 - F2 | 662
| Z1-C-CON-3340 | Pour Concrete Core Walls - Z1 - F2 | 96
| Z1-C-CON-3370 | Pour Concrete Columns - Z1 - F2 | 94
| Z1-C-CON-3400 | Pour Concrete Stairs - Z1 - F2 | 4
| Z1-C-CON-3430 | Pour Concrete Slabs - Z1 - RF | 660
| Z1-C-CON-3470 | Pour Concrete Core Walls - Z1 - RF | 95
| Z1-C-CON-3500 | Pour Concrete Columns - Z1 - RF | 75
| Z1-C-CON-3530 | Pour Concrete Stairs - Z1 - RF | 4
| Z1-C-CON-5640 | Pour Concrete Slabs - Z1 - SRVF | 566
| Z1-C-CON-5680 | Pour Concrete Core Walls - Z1 - SRVF | 53
| Z1-C-CON-5710 | Pour Concrete Columns - Z1 - SRVF | 5
| Z1-C-CON-5740 | Pour Concrete Parapet - Z1 - SRVF | 90
| Z1-C-CON-5770 | Pour Concrete Slabs - Z1 - TRF | 60
| Z1-C-CON-5790 | Pour MEP RCC Pedastals - Z1 - SRVF | 1
| Z1-C-CON-5830 | Pour Concrete Parapet - Z1 - TRF | 90
| Z1-C-CON-5860 | Pour Concrete Ramp - Z1 - B2 | 57
| Z1-C-CON-5890 | Pour Concrete Ramp - Z1 - B1 | 49
| Z1-C-CON-5920 | Pour Concrete Core Walls Ramp - Z1 - B2 | 76
| Z1-C-CON-5950 | Pour Concrete Core Walls Ramp - Z1 - B1 | 76
Div 04 | Z1-C-FIN-10120 | Masonry Works Wet Area - Z1 - F2 | 524
| Z1-C-FIN-10460 | Masonry Works Dry Area - Z1 - F2 | 524
| Z1-C-FIN-10760 | Masonry Works Wet Area - Z1 - RF | 449
| Z1-C-FIN-10940 | Masonry Works Dry Area - Z1 - RF | 448
| Z1-C-FIN-5790 | Masonry Works - Z1 - B2 | 19
| Z1-C-FIN-7040 | Masonry Works - Z1 - B1 | 188
| Z1-C-FIN-8330 | Masonry Works - Z1 - GF | 1381
| Z1-C-FIN-9490 | Masonry Works Wet + Dry Area - Z1 - F1 | 891
Div 05 | C-FIN-ENVLP-9550 | Fix Steel Decore - GF to SRVF (Elev. 1 & 4) | 539
| C-FIN-ENVLP-9640 | Install Aluminum & Wood Roof Features | 111
| Z1-C-FIN-7400 | Fix Galvonized Iron Cat Ladder - Z1 - B1 | 20
| Z1-C-FIN-SCASE-8810 | Install Haindrails Staircase - Z1 - B2 - SRVF | 333
Div 06 | Z1-C-FIN-10710 | Fix Furniture & Counter Works kitchen/Pantry - Z1 - F2 | 150
| Z1-C-FIN-11180 | Fix Furniture & Counter Works kitchen/Pantry - Z1 - RF | 150
Div 07 | C-FIN-ENVLP-9540 | Osmotic Cement Waterproof - GF to SRVF (Elev. 1 & 4) | 287
| Z123-C-FIN-18510 | Foam Concrete - Z123 - TRF | 980
| Z123-C-FIN-18520 | 4mm Waterproof Membrane Wet Area - Z123 - TRF | 980
| Z123-C-FIN-18530 | Protection Screed Wet Area - Z123 - TRF | 980
| Z123-C-FIN-18550 | Polystyrene Thermal Insulation - Z123 - TRF | 17
| Z123-C-FIN-18560 | Roof Floor Terrazo Tiles Wet Area - Z123 - TRF | 86
| Z1-C-FIN-10490 | Waterproof Bath - Z1 - F2 | 17
| Z1-C-FIN-10500 | Protection Screed Bath - Z1 - F2 | 17
| Z1-C-FIN-10590 | Waterproof kitchen/Pantry - Z1 - F2 | 17
| Z1-C-FIN-10600 | Protection Screed kitchen/Pantry - Z1 - F2 | 17
| Z1-C-FIN-10670 | Waterproof Garbage Room - Z1 - F2 | 17
| Z1-C-FIN-10680 | Protection Screed Garbage Room - Z1 - F2 | 17
| Z1-C-FIN-11000 | Waterproof Bath - Z1 - RF | 17
| Z1-C-FIN-11010 | Protection Screed Bath - Z1 - RF | 17
| Z1-C-FIN-11080 | Waterproof kitchen/Pantry - Z1 - RF | 17
| Z1-C-FIN-11090 | Protection Screed kitchen/Pantry - Z1 - RF | 17
| Z1-C-FIN-11150 | Waterproof Garbage Room - Z1 - RF | 17
| Z1-C-FIN-11160 | Protection Screed Garbage Room - Z1 - RF | 17
| Z1-C-FIN-8870 | Waterproof & Screed Garbage Room - Z1 - GF | 17
Div 08 | A7100 | Fix Windows & Door Frame & Leaf - F2 | 111
| A7110 | Fix Ironmongery - F2 | 111
| A7180 | Fix Windows & Door Frame & Leaf - RF | 111
| A7190 | Fix Ironmongery - RF | 111
| C-FIN-ENVLP-9530 | Fix Aluminum Glazing Pannels - GF to SRVF (Elev. 1 & 4) | 357
| Z1-C-FIN-10370 | Fix Door Subframes Wet Area - Z1 - F2 | 20
| Z1-C-FIN-10470 | Fix Door Subframes Dry Area - Z1 - F2 | 20
| Z1-C-FIN-10900 | Fix Door Subframes Wet Area - Z1 - RF | 20
| Z1-C-FIN-10960 | Fix Door Subframes Dry Area - Z1 - RF | 20
| Z1-C-FIN-18600 | Fix Doors - Z1 - B1 | 20
| Z1-C-FIN-18640 | Fix Doors - Z1 - B1 | 20
| Z1-C-FIN-18690 | Fix Doors Loading Room - Z1 - GF | 20
| Z1-C-FIN-18730 | Fix Doors Serv. Rooms - Z1 - F1 | 20
| Z1-C-FIN-6220 | Fix Doors - Z1 - B2 | 20
| Z1-C-FIN-6230 | Fix Doors - Z1 - B2 | 20
| Z1-C-FIN-6240 | Fix Doors - Z1 - B2 | 20
| Z1-C-FIN-7470 | Fix Doors - Z1 - B1 | 20
| Z1-C-FIN-7490 | Fix Doors - Z1 - B1 | 20
| Z1-C-FIN-8720 | Fix Doors Garbage & Service Room - Z1 - GF | 20
| Z1-C-FIN-8730 | Fix Doors Fire Pump & Cmd Room - Z1 - GF | 20
| Z1-C-FIN-8740 | Fix Doors Lift Lobby - Z1 - GF | 20
| Z1-C-FIN-8820 | Fix Steel Louver Frames & Doors Generator Room - Z1 - GF | 143
| Z1-C-FIN-8860 | Fix Doors LV & Trnsf. Room - Z1 - B1 | 20
| Z1-C-FIN-9560 | Fix Door Subframes Wet + Dry Area - Z1 - F1 | 20
| Z1-C-FIN-9630 | Fix Doors Lift Lobby & Passage - Z1 - F1 | 20
| Z1-C-FIN-9790 | Fix Doors Serv. Area - Z1 - F1 | 20
Div 09 | C-FIN-ENVLP-9490 | Fix Brackets for Natural Stone - GF to SRVF (Elev. 1 & 4) | 144
| C-FIN-ENVLP-9510 | Fix Natural Stone All types- GF to SRVF (Elev. 1 & 4) | 2653
| C-FIN-ENVLP-9610 | Fix Wooden Decorarive Features (Elev. 1 & 4) | 299
| C-FIN-ENVLP-9730 | External Plaster - GF to SRVF (Elev. 1 & 4) | 68
| Z1-C-FIN-10130 | Plaster Works Wet Area - Z1 - F2 | 2003
| Z1-C-FIN-10180 | Fix False Ceiling Suspension Lift Lobby - Z1 - F2 | 112
| Z1-C-FIN-10200 | Porcelain Floor Tiles Passage & Offices - Z1 - F2 | 1633
| Z1-C-FIN-10260 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 7
| Z1-C-FIN-10280 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - F2 | 112
| Z1-C-FIN-10300 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - F2 | 112
| Z1-C-FIN-10480 | Plaster Works Dry Area - Z1 - F2 | 2003
| Z1-C-FIN-10510 | Wall Ceramic Tiles Bath - Z1 - F2 | 178
| Z1-C-FIN-10520 | Floor Ceramic Tiles Bath - Z1 - F2 | 65
| Z1-C-FIN-10540 | Fix False Ceiling Suspension Bath - Z1 - F2 | 112
| Z1-C-FIN-10560 | Fix False Ceiling Gypsum Board Bath - Z1 - F2 | 112
| Z1-C-FIN-10570 | Fix False Ceiling Aluminum Tiles Bath - Z1 - F2 | 112
| Z1-C-FIN-10610 | Wall Ceramic Tiles kitchen/Pantry - Z1 - F2 | 178
| Z1-C-FIN-10620 | Fix False Ceiling Suspension kitchen/Pantry - Z1 - F2 | 112
| Z1-C-FIN-10640 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - F2 | 112
| Z1-C-FIN-10650 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z1 - F2 | 112
| Z1-C-FIN-10660 | Floor Ceramic Tiles kitchen/Pantry - Z1 - F2 | 65
| Z1-C-FIN-10750 | Floor Epoxy Paint Garbage Room - Z1 - F2 | 7
| Z1-C-FIN-10770 | Plaster Works Wet Area - Z1 - RF | 1679
| Z1-C-FIN-10790 | Fix False Ceiling Suspension Lift Lobby - Z1 - RF | 86
| Z1-C-FIN-10810 | Porcelain Floor Tiles Passage & Offices - Z1 - RF | 1246
| Z1-C-FIN-10860 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - RF | 86
| Z1-C-FIN-10870 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - RF | 86
| Z1-C-FIN-10880 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 7
| Z1-C-FIN-10950 | Plaster Works Dry Area - Z1 - RF | 1679
| Z1-C-FIN-10970 | Fix False Ceiling Suspension Bath - Z1 - RF | 86
| Z1-C-FIN-10980 | Wall Ceramic Tiles Bath - Z1 - RF | 178
| Z1-C-FIN-10990 | Floor Ceramic Tiles Bath - Z1 - RF | 65
| Z1-C-FIN-11020 | Fix False Ceiling Gypsum Board Bath - Z1 - RF | 86
| Z1-C-FIN-11030 | Fix False Ceiling Aluminum Tiles Bath - Z1 - RF | 86
| Z1-C-FIN-11050 | Fix False Ceiling Suspension kitchen/Pantry - Z1 - RF | 86
| Z1-C-FIN-11060 | Wall Ceramic Tiles kitchen/Pantry - Z1 - RF | 178
| Z1-C-FIN-11070 | Floor Ceramic Tiles kitchen/Pantry - Z1 - RF | 65
| Z1-C-FIN-11100 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - RF | 86
| Z1-C-FIN-11110 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z1 - RF | 86
| Z1-C-FIN-11140 | Floor Epoxy Paint Garbage Room - Z1 - RF | 7
| Z1-C-FIN-18590 | Floor Epoxy Paint (Secur. Ctrl & Eqpmt Room) - Z1 - B1 | 7
| Z1-C-FIN-18630 | Floor Epoxy Paint (Maint. & Serv. Provider Room) - Z1 - B1 | 7
| Z1-C-FIN-18710 | Floor Epoxy Paint Serv. Rooms - Z1 - F1 | 7
| Z1-C-FIN-21370 | Roof Floor Terrazo Tiles Outside Area - Z1 - RF | 323
| Z1-C-FIN-5800 | Plaster Works - Z1 - B2 | 3342
| Z1-C-FIN-6070 | Floor Epoxy Paint Serv. Rooms - Z1 - B2 | 7
| Z1-C-FIN-6100 | Floor Epoxy Paint - Z1 - B2 | 7
| Z1-C-FIN-6160 | Fix False Ceiling Suspension - Z1 - B2 | 8
| Z1-C-FIN-6180 | Porcelain Floor Tiles - Z1 - B2 | 51
| Z1-C-FIN-6330 | Fix False Ceiling Gypsum Board & Tiles - Z1 - B2 | 8
| Z1-C-FIN-7050 | Plaster Works - Z1 - B1 | 3537
| Z1-C-FIN-7320 | Raise Floor & Epoxy Paint Store & Serv. Rooms - Z1 - B1 | 7
| Z1-C-FIN-7410 | Fix False Ceiling Gypsum Board & Tiles Lift Lobby - Z1 - B1 | 12
| Z1-C-FIN-7430 | Porcelain Floor Tiles Lift Lobby - Z1 - B1 | 37
| Z1-C-FIN-7480 | Fix False Ceiling Suspension Lift Lobby - Z1 - B1 | 12
| Z1-C-FIN-8340 | Plaster Works - Z1 - GF | 2425
| Z1-C-FIN-8650 | Floor Epoxy Paint Garbage & Service Room - Z1 - GF | 7
| Z1-C-FIN-8680 | Floor Epoxy Paint Fire Pump & Cmd Room - Z1 - GF | 7
| Z1-C-FIN-8690 | Fix False Ceiling Suspension Lift Lobby - Z1 - GF | 32
| Z1-C-FIN-8710 | Porcelain Floor Tiles Lift Lobby - Z1 - GF | 217
| Z1-C-FIN-8810 | Floor Epoxy Paint Generator Room - Z1 - GF | 7
| Z1-C-FIN-8850 | Floor Epoxy Paint LV & Trnsf. Room- Z1 - B1 | 7
| Z1-C-FIN-8890 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - GF | 32
| Z1-C-FIN-9380 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - GF | 32
| Z1-C-FIN-9500 | Plaster Works Wet + Dry Area - Z1 - F1 | 1624
| Z1-C-FIN-9580 | Fix False Ceiling Suspension Lift Lobby & Passage - Z1 - F1 | 80
| Z1-C-FIN-9600 | Porcelain Floor Tiles Lift Lobby & Passage- Z1 - F1 | 631
| Z1-C-FIN-9780 | Epoxy Paint Serv. Area - Z1 - F1 | 7
| Z1-C-FIN-9880 | Fix False Ceiling Aluminum Tiles Lift Lobby & Passage - Z1 - F1 | 79
| Z1-C-FIN-9960 | Fix False Ceiling Gypsum Board Lift Lobby & Passage - Z1 - F1 | 79
| Z1-C-FIN-SCASE-8800 | Staircase Floor Epoxy Paint - Z1 - B2 - SRVF | 7
| Z1-C-GRBCH-9380 | Install Garbage Chute Cylinder - Z1 - GF to SRVF | 133
| Z1-C-GRBCH-9390 | Install Garbage Chute Supporting Frame - Z1 - GF to SRVF | 134
| Z1-C-GRBCH-9400 | Block & Plaster Garbage Room - Z1 - GF to SRVF | 71
| Z1-C-GRBCH-9410 | Install Garbage Chute Openings & Doors - Z1 - GF to SRVF | 134
| Z1-C-GRBCH-9460 | Install Garbage Chute Roof Top Unit with All Provisions | 133
| Z1-C-GRBCH-9470 | Install Garbage Chute Bottom Unit with All Provisions | 133
Div 15 | Z1-C-FIN-9330 | Fix MCC Pannels LV & Trnsf. Room- Z1 - B1 | 20
Z2
Div 02 | C-EW-10400 | Excavation Stage 2 - Z2&3 | 3407
| C-EW-10440 | Excavation Stage 1 - Z2&3 | 3407
| C-SHRNG-DCE-C-2360 | Place Guide Wall - Z2&3 | 84
| C-SHRNG-DCE-C-2380 | Install Capping Beam - Z2&3 | 90
Div 03 | Z2-C-CON-5840 | PCC Blind Concrete - Z2 - Lift Pit | 2
| Z2-C-CON-5850 | Waterproof Membrane - Z2 - Lift Pit | 20
| Z2-C-CON-5860 | Protection Screed - Z2 - Lift Pit | 13
| Z2-C-CON-5890 | Pour Concrete - Z2 - Lift Pit | 23
| Z2-C-CON-5900 | PCC Blind Concrete - Z2 - Raft | 74
| Z2-C-CON-5910 | Waterproof Membrane - Z2 - Raft | 1180
| Z2-C-CON-5920 | Protection Screed - Z2 - Raft | 37
| Z2-C-CON-5960 | Pour Concrete - Z2 - Raft | 948
| Z2-C-CON-5990 | Pour Concrete Columns - Z2 - B2 | 66
| Z2-C-CON-6020 | Pour Concrete Retaining Walls - Z2 - B2 | 121
| Z2-C-CON-6030 | Pour Concrete Core Walls - Z2 - B2 | 68
| Z2-C-CON-6080 | Pour Concrete Stairs - Z2 - B2 | 4
| Z2-C-CON-6110 | Pour Concrete Retaining Walls - Z2 - B1 | 121
| Z2-C-CON-6140 | Pour Concrete Core Walls - Z2 - B1 | 69
| Z2-C-CON-6170 | Pour Concrete Columns - Z2 - B1 | 73
| Z2-C-CON-6200 | Pour Concrete Stairs - Z2 - B1 | 4
| Z2-C-CON-6230 | Pour Concrete Slabs - Z2 - B1 | 518
| Z2-C-CON-6270 | Pour Concrete Core Walls - Z2 - GF | 118
| Z2-C-CON-6300 | Pour Concrete Columns - Z2 - GF | 112
| Z2-C-CON-6330 | Pour Concrete Stairs - Z2 - GF | 5
| Z2-C-CON-6360 | Pour Concrete Slabs - Z2 - GF | 639
| Z2-C-CON-6410 | Pour Concrete Slabs - Z2 - F1 | 494
| Z2-C-CON-6440 | Pour Concrete Core Walls - Z2 - F1 | 120
| Z2-C-CON-6470 | Pour Concrete Columns - Z2 - F1 | 112
| Z2-C-CON-6500 | Pour Concrete Stairs - Z2 - F1 | 5
| Z2-C-CON-6530 | Pour Concrete Slabs - Z2 - F2 | 497
| Z2-C-CON-6570 | Pour Concrete Core Walls - Z2 - F2 | 72
| Z2-C-CON-6600 | Pour Concrete Columns - Z2 - F2 | 71
| Z2-C-CON-6630 | Pour Concrete Stairs - Z2 - F2 | 5
| Z2-C-CON-6660 | Pour Concrete Slabs - Z2 - RF | 495
| Z2-C-CON-6700 | Pour Concrete Core Walls - Z2 - RF | 72
| Z2-C-CON-6730 | Pour Concrete Columns - Z2 - RF | 57
| Z2-C-CON-6760 | Pour Concrete Stairs - Z2 - RF | 4
| Z2-C-CON-6790 | Pour Concrete Slabs - Z2 - SRVF | 425
| Z2-C-CON-6830 | Pour Concrete Core Walls - Z2 - SRVF | 2
| Z2-C-CON-6860 | Pour Concrete Columns - Z2 - SRVF | 4
| Z2-C-CON-6870 | Pour MEP RCC Pedastals - Z2 - SRVF | 1
| Z2-C-CON-6900 | Pour Concrete Parapet - Z2 - SRVF | 68
| Z2-C-CON-6930 | Pour Concrete Slabs - Z2 - TRF | 45
| Z2-C-CON-6970 | Pour Concrete Parapet - Z2 - TRF | 68
Div 04 | Z123-C-FIN-18110 | Masonry Works Dry Area - Z123 - SRVF | 201
| Z2&3-C-FIN-18800 | Masonry Works - Z2&3 - B2 | 28
| Z2&3-C-FIN-19050 | Masonry Works - Z2&3 - B1 | 281
| Z2&3-C-FIN-19270 | Masonry Works Wet + Dry Area - Z2&3 - F1 | 1336
| Z2&3-C-FIN-19540 | Masonry Works - Z2&3 - GF | 2070
| Z2&3-C-FIN-20010 | Masonry Works Wet Area - Z2&3 - F2 | 785
| Z2&3-C-FIN-20040 | Masonry Works Dry Area - Z2&3 - F2 | 785
| Z2&3-C-FIN-20440 | Masonry Works Wet Area - Z2&3 - RF | 673
| Z2&3-C-FIN-20470 | Masonry Works Dry Area - Z2&3 - RF | 673
Div 05 | C-FIN-ENVLP-9650 | Install Aluminum Wood Ground Features | 111
| C-FIN-ENVLP-9710 | Fix Steel Decore - GF to SRVF (Elev. 2 & 3) | 970
| Z123-C-FIN-18370 | Install Aluminum Shades over GRP Water Tank - Z123 - SRVF | 111
Div 06 | Z2&3-C-FIN-20150 | Fix Furniture & Counter Works kitchen/Pantry - Z2&3 - F2 | 150
| Z2&3-C-FIN-20580 | Fix Furniture & Counter Works kitchen/Pantry - Z2&3 - RF | 150
Div 07 | C-FIN-ENVLP-9670 | Osmotic Cement Waterproof - GF to SRVF (Elev. 2 & 3) | 287
| Z123-C-FIN-18170 | 4mm Waterproof Membrane Wet Area - Z123 - SRVF | 980
| Z123-C-FIN-18180 | Protection Screed Wet Area - Z123 - SRVF | 980
| Z123-C-FIN-18190 | Polystyrene Thermal Insulation - Z123 - SRVF | 17
| Z123-C-FIN-18200 | Foam Concrete - Z123 - SRVF | 980
| Z123-C-FIN-18330 | Waterproof Filter & Pump Room - Z123 - SRVF | 17
| Z123-C-FIN-18340 | Protection Screed Filter & Pump Room - Z123 - SRVF | 17
| Z2&3-C-FIN-19330 | Protection Screed Wet Area - Z2&3 - F1 | 17
| Z2&3-C-FIN-19380 | Waterproof Wet Area - Z2&3 - F1 | 17
| Z2&3-C-FIN-19580 | Waterproof & Screed Garbage Room - Z2&3 - GF | 17
| Z2&3-C-FIN-20100 | Waterproof kitchen/Pantry - Z2&3 - F2 | 17
| Z2&3-C-FIN-20110 | Protection Screed kitchen/Pantry - Z2&3 - F2 | 17
| Z2&3-C-FIN-20190 | Waterproof Bath - Z2&3 - F2 | 17
| Z2&3-C-FIN-20200 | Protection Screed Bath - Z2&3 - F2 | 17
| Z2&3-C-FIN-20260 | Waterproof Garbage Room - Z2&3 - F2 | 17
| Z2&3-C-FIN-20270 | Protection Screed Garbage Room - Z2&3 - F2 | 17
| Z2&3-C-FIN-20530 | Waterproof kitchen/Pantry - Z2&3 - RF | 17
| Z2&3-C-FIN-20540 | Protection Screed kitchen/Pantry - Z2&3 - RF | 16
| Z2&3-C-FIN-20620 | Waterproof Bath - Z2&3 - RF | 17
| Z2&3-C-FIN-20630 | Protection Screed Bath - Z2&3 - RF | 17
| Z2&3-C-FIN-20690 | Waterproof Garbage Room - Z2&3 - RF | 17
| Z2&3-C-FIN-20700 | Protection Screed Garbage Room - Z2&3 - RF | 17
Div 08 | A11210 | Fix Windows & Door Frame & Leaf - F2 | 111
| A11220 | Fix Ironmongery - F2 | 111
| A11260 | Fix Windows & Door Frame & Leaf - RF | 111
| A11270 | Fix Ironmongery - RF | 111
| C-FIN-ENVLP-9680 | Fix Aluminum Glazing Pannels - GF to SRVF (Elev. 2 & 3) | 357
| Z123-C-FIN-18130 | Fix Door Subframes Dry Area - Z123 - SRVF | 20
| Z123-C-FIN-18220 | Install Aluminum Shades over FAHU - Z123 - SRVF | 143
| Z123-C-FIN-18360 | Install Aluminum Shades over Chillers - Z123 - SRVF | 143
| Z123-C-FIN-8540 | Fix Windows & Door Frame & Leaf - Z123 - SRVF | 111
| Z123-C-FIN-8550 | Fix Ironmongery - Z123 - SRVF | 111
| Z2&3-C-FIN-18910 | Fix Doors - Z2&3 - B2 | 20
| Z2&3-C-FIN-18950 | Fix Doors - Z2&3 - B2 | 20
| Z2&3-C-FIN-18990 | Fix Doors - Z2&3 - B2 | 20
| Z2&3-C-FIN-19100 | Fix Doors - Z2&3 - B1 | 20
| Z2&3-C-FIN-19190 | Fix Doors - Z2&3 - B1 | 20
| Z2&3-C-FIN-19290 | Fix Door Subframes Wet + Dry Area - Z2&3 - F1 | 20
| Z2&3-C-FIN-19360 | Fix Doors Wet Area - Z2&3 - F1 | 20
| Z2&3-C-FIN-19420 | Fix Doors Lift Lobby - Z2&3 - F1 | 20
| Z2&3-C-FIN-19500 | Fix Doors IT Room - Z2&3 - F1 | 20
| Z2&3-C-FIN-19570 | Fix Doors Garbage & Service Room - Z2&3 - GF | 20
| Z2&3-C-FIN-19760 | Fix Doors Lift Lobby - Z2&3 - GF | 20
| Z2&3-C-FIN-20030 | Fix Door Subframes Wet Area - Z2&3 - F2 | 20
| Z2&3-C-FIN-20060 | Fix Door Subframes Dry Area - Z2&3 - F2 | 20
| Z2&3-C-FIN-20460 | Fix Door Subframes Wet Area - Z2&3 - RF | 20
| Z2&3-C-FIN-20490 | Fix Door Subframes Dry Area - Z2&3 - RF | 20
| Z2&3-C-FIN-20890 | Fix Doors - Z2&3 - B1 | 20
| Z2&3-C-FIN-21010 | Fix Doors Serv. Rooms - Z2&3 - F1 | 20
Div 09 | A11400 | Fix Flower Box | 107
| A11410 | Fix Outdoor Green Area | 70
| A9690 | Fix Pavement Tiles & Granite Colored Land Scaping | 6648
| A9710 | Install Precast Wheel Stoper | 50
| A9720 | Trafic & Road Marking | 51
| C-FIN-ENVLP-9690 | Fix Brackets for Natural Stone - GF to SRVF (Elev. 2 & 3) | 144
| C-FIN-ENVLP-9700 | Fix Natural Stone All types- GF to SRVF (Elev. 2 & 3) | 2652
| C-FIN-ENVLP-9720 | Fix Wooden Decorarive Features (Elev. 2 & 3) | 299
| C-FIN-ENVLP-9740 | External Plaster - GF to SRVF (Elev. 2 & 3) | 68
| Z123-C-FIN-18120 | Plaster Works Dry Area - Z123 - SRVF | 571
| Z123-C-FIN-18160 | Roof Floor Terrazo Tiles Wet Area - Z123 - SRVF | 5493
| Z123-C-FIN-18320 | Floor Epoxy Filter & Pump Room - Z123 - SRVF | 7
| Z123-C-FIN-18390 | Fix False Ceiling Suspension Lift Lobby - Z123 - SRVF | 9
| Z123-C-FIN-18400 | Porcelain Floor Tiles Lift Lobby - Z123 - SRVF | 49
| Z123-C-FIN-18420 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z123 - SRVF | 9
| Z123-C-FIN-18430 | Fix False Ceiling Gypsum Board Lift Lobby - Z123 - SRVF | 9
| Z123-C-FIN-18460 | Floor Epoxy GSM & MCC Rooms - Z123 - SRVF | 7
| Z2&3-C-FIN-18810 | Plaster Works - Z2&3 - B2 | 5012
| Z2&3-C-FIN-18870 | Fix False Ceiling Suspension - Z2&3 - B2 | 8
| Z2&3-C-FIN-18880 | Wall Paint (Emulsion) - Z2&3 - B2 | 51
| Z2&3-C-FIN-18890 | Porcelain Floor Tiles - Z2&3 - B2 | 51
| Z2&3-C-FIN-18900 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B2 | 8
| Z2&3-C-FIN-18940 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B2 | 7
| Z2&3-C-FIN-18980 | Porcelain Floor Tiles Travelator - Z2&3 - B2 | 51
| Z2&3-C-FIN-19060 | Plaster Works - Z2&3 - B1 | 5306
| Z2&3-C-FIN-19090 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B1 | 7
| Z2&3-C-FIN-19160 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B1 | 12
| Z2&3-C-FIN-19170 | Wall Paint (Emulsion) - Z2&3 - B1 | 37
| Z2&3-C-FIN-19180 | Porcelain Floor Tiles - Z2&3 - B1 | 37
| Z2&3-C-FIN-19200 | Fix False Ceiling Suspension - Z2&3 - B1 | 12
| Z2&3-C-FIN-19280 | Plaster Works Wet + Dry Area - Z2&3 - F1 | 2435
| Z2&3-C-FIN-19300 | Fix False Ceiling Suspension - Z2&3 - F1 | 80
| Z2&3-C-FIN-19310 | Wall Ceramic Tiles Wet Area - Z2&3 - F1 | 178
| Z2&3-C-FIN-19320 | Floor Ceramic Tiles Wet Area - Z2&3 - F1 | 65
| Z2&3-C-FIN-19340 | Fix False Ceiling Gypsum Board - Z2&3 - F1 | 80
| Z2&3-C-FIN-19350 | Fix False Ceiling Aluminum Tiles - Z2&3 - F1 | 80
| Z2&3-C-FIN-19390 | Fix False Ceiling Suspension Lift Lobby - Z2&3 - F1 | 80
| Z2&3-C-FIN-19410 | Porcelain Floor Tiles Lift Lobby - Z2&3 - F1 | 631
| Z2&3-C-FIN-19430 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z2&3 - F1 | 80
| Z2&3-C-FIN-19440 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - F1 | 80
| Z2&3-C-FIN-19490 | Anti Static Raised Floor IT Room - Z2&3 - F1 | 120
| Z2&3-C-FIN-19550 | Plaster Works - Z2&3 - GF | 3636
| Z2&3-C-FIN-19560 | Floor Epoxy Paint Garbage & Service Room - Z2&3 - GF | 7
| Z2&3-C-FIN-19770 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - GF | 32
| Z2&3-C-FIN-19790 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z2&3 - GF | 32
| Z2&3-C-FIN-19800 | Fix False Ceiling Suspension Lift Lobby - Z2&3 - GF | 32
| Z2&3-C-FIN-19820 | Porcelain Floor Tiles Lift Lobby - Z2&3 - GF | 217
| Z2&3-C-FIN-20020 | Plaster Works Wet Area - Z2&3 - F2 | 3004
| Z2&3-C-FIN-20050 | Plaster Works Dry Area - Z2&3 - F2 | 3004
| Z2&3-C-FIN-20070 | Fix False Ceiling Suspension kitchen/Pantry - Z2&3 - F2 | 112
| Z2&3-C-FIN-20080 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 178
| Z2&3-C-FIN-20090 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 65
| Z2&3-C-FIN-20120 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - F2 | 112
| Z2&3-C-FIN-20130 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z2&3 - F2 | 112
| Z2&3-C-FIN-20160 | Fix False Ceiling Suspension Bath - Z2&3 - F2 | 112
| Z2&3-C-FIN-20170 | Wall Ceramic Tiles Bath - Z2&3 - F2 | 178
| Z2&3-C-FIN-20180 | Floor Ceramic Tiles Bath - Z2&3 - F2 | 65
| Z2&3-C-FIN-20210 | Fix False Ceiling Gypsum Board Bath - Z2&3 - F2 | 112
| Z2&3-C-FIN-20220 | Fix False Ceiling Aluminum Tiles Bath - Z2&3 - F2 | 112
| Z2&3-C-FIN-20250 | Floor Epoxy Paint Garbage Room - Z2&3 - F2 | 7
| Z2&3-C-FIN-20290 | Fix False Ceiling Suspension Lobby Passage & Offices- Z2&3 - F2 | 112
| Z2&3-C-FIN-20310 | Porcelain Floor Tiles Passage & Offices - Z2&3 - F2 | 1633
| Z2&3-C-FIN-20320 | Fix False Ceiling Aluminum Tiles Lobby Passage & Offices - Z2&3 - F2 | 113
| Z2&3-C-FIN-20330 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - F2 | 113
| Z2&3-C-FIN-20420 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F2 | 7
| Z2&3-C-FIN-20450 | Plaster Works Wet Area - Z2&3 - RF | 2517
| Z2&3-C-FIN-20480 | Plaster Works Dry Area - Z2&3 - RF | 2517
| Z2&3-C-FIN-20500 | Fix False Ceiling Suspension kitchen/Pantry - Z2&3 - RF | 86
| Z2&3-C-FIN-20510 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 178
| Z2&3-C-FIN-20520 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 65
| Z2&3-C-FIN-20550 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - RF | 86
| Z2&3-C-FIN-20560 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z2&3 - RF | 86
| Z2&3-C-FIN-20590 | Fix False Ceiling Suspension Bath - Z2&3 - RF | 86
| Z2&3-C-FIN-20600 | Wall Ceramic Tiles Bath - Z2&3 - RF | 178
| Z2&3-C-FIN-20610 | Floor Ceramic Tiles Bath - Z2&3 - RF | 65
| Z2&3-C-FIN-20640 | Fix False Ceiling Gypsum Board Bath - Z2&3 - RF | 86
| Z2&3-C-FIN-20650 | Fix False Ceiling Aluminum Tiles Bath - Z2&3 - RF | 86
| Z2&3-C-FIN-20680 | Floor Epoxy Paint Garbage Room - Z2&3 - RF | 7
| Z2&3-C-FIN-20750 | Fix False Ceiling Suspension Lobby Passage & Offices - Z2&3 - RF | 86
| Z2&3-C-FIN-20770 | Porcelain Floor Tiles Passage & Offices - Z2&3 - RF | 1246
| Z2&3-C-FIN-20780 | Fix False Ceiling Aluminum Tiles Lobby Passage & Offices - Z2&3 - RF | 86
| Z2&3-C-FIN-20790 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - RF | 86
| Z2&3-C-FIN-20830 | Floor Epoxy Paint Serv. Rooms - Z2&3 - RF | 7
| Z2&3-C-FIN-20880 | Porcelain Floor Tiles Travelator - Z2&3 - B1 | 37
| Z2&3-C-FIN-21000 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F1 | 7
| Z2&3-C-FIN-21040 | Fix False Ceiling Gypsum Board Passage & Entrance - Z2&3 - GF | 31
| Z2&3-C-FIN-21060 | Fix False Ceiling Aluminum Tiles Passage & Entrance - Z2&3 - GF | 31
| Z2&3-C-FIN-21070 | Fix False Ceiling Suspension Passage & Entrance - Z2&3 - GF | 32
| Z2&3-C-FIN-21090 | Porcelain Floor Tiles Passage & Entrance - Z2&3 - GF | 217
| Z2&3-C-FIN-21100 | Fix False Ceiling Suspension Wet + Nursing Area - Z2&3 - GF | 32
| Z2&3-C-FIN-21110 | Wall Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 178
| Z2&3-C-FIN-21120 | Floor Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 65
| Z2&3-C-FIN-21140 | Fix False Ceiling Gypsum Board Wet + Nursing Area - Z2&3 - GF | 32
| Z2&3-C-FIN-21150 | Fix False Ceiling Aluminum Tiles Wet + Nursing Area - Z2&3 - GF | 32
| Z2&3-C-FIN-21200 | Fix False Ceiling Gypsum Board Passage H.Market - Z2&3 - GF | 32
| Z2&3-C-FIN-21220 | Fix False Ceiling Aluminum Tiles Passage H.Market - Z2&3 - GF | 32
| Z2&3-C-FIN-21230 | Fix False Ceiling Suspension Passage H.Market - Z2&3 - GF | 32
| Z2&3-C-FIN-21250 | Floor Stamp Concrete Passage H.Market- Z2&3 - GF | 156
| Z2&3-C-FIN-21260 | Floor Epoxy Paint IT & Maintanance Room - Z2&3 - GF | 7
| Z2&3-C-FIN-21320 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - F1 | 323
| Z2&3-C-FIN-21350 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - RF | 323
| Z2&3-C-FIN-21360 | Floor Carpet Prayer Room - Z2&3 - F1 | 66
| Z2&3-C-FIN-SCASE-101 | on Staircase Floor Epoxy Paint - Z2&3 - B2 - SRVF | 7
| Z2-C-GRBCH-11370 | Install Garbage Chute Cylinder - Z2 - GF to SRVF | 134
| Z2-C-GRBCH-11380 | Install Garbage Chute Supporting Frame - Z2 - GF to SRVF | 133
| Z2-C-GRBCH-11390 | Block & Plaster Garbage Room - Z2 - GF to SRVF | 71
| Z2-C-GRBCH-11400 | Install Garbage Chute Openings & Doors - Z2 - GF to SRVF | 133
| Z2-C-GRBCH-11410 | Install Garbage Chute Roof Top Unit with All Provisions | 133
| Z2-C-GRBCH-11420 | Install Garbage Chute Bottom Unit with All Provisions | 133
Div 12 | Z123-C-MEP-15040 | Fix Chillers - Z123 - SRVF | 400
Div 13 | Z2-C-LIFT-10800 | Install Steel Support Beams & Tracks CL B2 to GF | 120
Z3
Div 03 | Z3-C-CON-5860 | Protection Screed - Z3 - Lift Pit | 13
| Z3-C-CON-5890 | Pour Concrete - Z3 - Lift Pit | 23
| Z3-C-CON-5900 | PCC Blind Concrete - Z3 - Raft | 74
| Z3-C-CON-5920 | Protection Screed - Z3 - Raft | 37
| Z3-C-CON-5960 | Pour Concrete - Z3 - Raft | 948
| Z3-C-CON-5990 | Pour Concrete Columns - Z3 - B2 | 66
| Z3-C-CON-6020 | Pour Concrete Retaining Walls - Z3 - B2 | 121
| Z3-C-CON-6030 | Pour Concrete Core Walls - Z3 - B2 | 68
| Z3-C-CON-6110 | Pour Concrete Retaining Walls - Z3 - B1 | 121
| Z3-C-CON-6140 | Pour Concrete Core Walls - Z3 - B1 | 69
| Z3-C-CON-6170 | Pour Concrete Columns - Z3 - B1 | 73
| Z3-C-CON-6230 | Pour Concrete Slabs - Z3 - B1 | 518
| Z3-C-CON-6270 | Pour Concrete Core Walls - Z3 - GF | 118
| Z3-C-CON-6300 | Pour Concrete Columns - Z3 - GF | 112
| Z3-C-CON-6360 | Pour Concrete Slabs - Z3 - GF | 639
| Z3-C-CON-6410 | Pour Concrete Slabs - Z3 - F1 | 494
| Z3-C-CON-6440 | Pour Concrete Core Walls - Z3 - F1 | 120
| Z3-C-CON-6470 | Pour Concrete Columns - Z3 - F1 | 112
| Z3-C-CON-6530 | Pour Concrete Slabs - Z3 - F2 | 497
| Z3-C-CON-6570 | Pour Concrete Core Walls - Z3 - F2 | 72
| Z3-C-CON-6600 | Pour Concrete Columns - Z3 - F2 | 71
| Z3-C-CON-6660 | Pour Concrete Slabs - Z3 - RF | 495
| Z3-C-CON-6700 | Pour Concrete Core Walls - Z3 - RF | 72
| Z3-C-CON-6730 | Pour Concrete Columns - Z3 - RF | 57
| Z3-C-CON-6760 | Pour Concrete Stairs - Z3 - RF | 4
| Z3-C-CON-6790 | Pour Concrete Slabs - Z3 - SRVF | 425
| Z3-C-CON-6830 | Pour Concrete Core Walls - Z3 - SRVF | 2
| Z3-C-CON-6860 | Pour Concrete Columns - Z3 - SRVF | 4
| Z3-C-CON-6870 | Pour MEP RCC Pedastals - Z3 - SRVF | 1
| Z3-C-CON-6900 | Pour Concrete Parapet - Z3 - SRVF | 68
| Z3-C-CON-6930 | Pour Concrete Slabs - Z3 - TRF | 45
| Z3-C-CON-6970 | Pour Concrete Parapet - Z3 - TRF | 68
Mason 1817 |  |  | 140010
Z1
Div 02 | C-SHRNG-DCE-C-2330 | Place Guide Wall - Z1 | 83
| C-SHRNG-DCE-C-2350 | Install Capping Beam - Z1 | 148
Div 03 | C-EW-2420 | Gunite Wall - Z1 | 333
| Z1-C-CON-2450 | Protection Screed - Z1 - Lift Pit | 12
| Z1-C-CON-2480 | Pour Concrete - Z1 - Lift Pit | 64
| Z1-C-CON-2500 | PCC Blind Concrete - Z1 - Raft | 98
| Z1-C-CON-2520 | Protection Screed - Z1 - Raft | 48
| Z1-C-CON-2560 | Pour Concrete - Z1 - Raft | 3162
| Z1-C-CON-2620 | Pour Concrete Retaining Walls - Z1 - B2 | 241
| Z1-C-CON-2630 | Pour Concrete Core Walls - Z1 - B2 | 124
| Z1-C-CON-2660 | Pour Concrete Columns - Z1 - B2 | 87
| Z1-C-CON-2700 | Pour Concrete Slabs - Z1 - B1 | 714
| Z1-C-CON-2750 | Pour Concrete Retaining Walls - Z1 - B1 | 241
| Z1-C-CON-2780 | Pour Concrete Core Walls - Z1 - B1 | 142
| Z1-C-CON-2810 | Pour Concrete Columns - Z1 - B1 | 98
| Z1-C-CON-3020 | Pour Concrete Slabs - Z1 - GF | 955
| Z1-C-CON-3050 | Pour Concrete Core Walls - Z1 - GF | 157
| Z1-C-CON-3080 | Pour Concrete Columns - Z1 - GF | 149
| Z1-C-CON-3170 | Pour Concrete Slabs - Z1 - F1 | 659
| Z1-C-CON-3210 | Pour Concrete Core Walls - Z1 - F1 | 159
| Z1-C-CON-3240 | Pour Concrete Columns - Z1 - F1 | 149
| Z1-C-CON-3300 | Pour Concrete Slabs - Z1 - F2 | 663
| Z1-C-CON-3340 | Pour Concrete Core Walls - Z1 - F2 | 96
| Z1-C-CON-3370 | Pour Concrete Columns - Z1 - F2 | 94
| Z1-C-CON-3430 | Pour Concrete Slabs - Z1 - RF | 661
| Z1-C-CON-3470 | Pour Concrete Core Walls - Z1 - RF | 95
| Z1-C-CON-3500 | Pour Concrete Columns - Z1 - RF | 75
| Z1-C-CON-5640 | Pour Concrete Slabs - Z1 - SRVF | 567
| Z1-C-CON-5680 | Pour Concrete Core Walls - Z1 - SRVF | 53
| Z1-C-CON-5740 | Pour Concrete Parapet - Z1 - SRVF | 90
| Z1-C-CON-5770 | Pour Concrete Slabs - Z1 - TRF | 60
| Z1-C-CON-5830 | Pour Concrete Parapet - Z1 - TRF | 90
| Z1-C-CON-5860 | Pour Concrete Ramp - Z1 - B2 | 57
| Z1-C-CON-5890 | Pour Concrete Ramp - Z1 - B1 | 49
| Z1-C-CON-5920 | Pour Concrete Core Walls Ramp - Z1 - B2 | 76
| Z1-C-CON-5950 | Pour Concrete Core Walls Ramp - Z1 - B1 | 76
| Z1-C-FIN-6140 | GRP Linning - Z1 - B2 | 100
| Z1-C-FIN-7390 | GRP Linning - Z1 - B1 | 100
Div 04 | Z1-C-FIN-10120 | Masonry Works Wet Area - Z1 - F2 | 525
| Z1-C-FIN-10460 | Masonry Works Dry Area - Z1 - F2 | 525
| Z1-C-FIN-10760 | Masonry Works Wet Area - Z1 - RF | 449
| Z1-C-FIN-10940 | Masonry Works Dry Area - Z1 - RF | 448
| Z1-C-FIN-5790 | Masonry Works - Z1 - B2 | 19
| Z1-C-FIN-7040 | Masonry Works - Z1 - B1 | 188
| Z1-C-FIN-8330 | Masonry Works - Z1 - GF | 1383
| Z1-C-FIN-9490 | Masonry Works Wet + Dry Area - Z1 - F1 | 892
Div 07 | Z123-C-FIN-18560 | Roof Floor Terrazo Tiles Wet Area - Z123 - TRF | 106
Div 09 | C-FIN-ENVLP-9510 | Fix Natural Stone All types- GF to SRVF (Elev. 1 & 4) | 3591
| C-FIN-ENVLP-9730 | External Plaster - GF to SRVF (Elev. 1 & 4) | 96
| Z1-C-FIN-10130 | Plaster Works Wet Area - Z1 - F2 | 2823
| Z1-C-FIN-10200 | Porcelain Floor Tiles Passage & Offices - Z1 - F2 | 2211
| Z1-C-FIN-10260 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 10
| Z1-C-FIN-10480 | Plaster Works Dry Area - Z1 - F2 | 2823
| Z1-C-FIN-10510 | Wall Ceramic Tiles Bath - Z1 - F2 | 913
| Z1-C-FIN-10520 | Floor Ceramic Tiles Bath - Z1 - F2 | 88
| Z1-C-FIN-10610 | Wall Ceramic Tiles kitchen/Pantry - Z1 - F2 | 913
| Z1-C-FIN-10660 | Floor Ceramic Tiles kitchen/Pantry - Z1 - F2 | 88
| Z1-C-FIN-10750 | Floor Epoxy Paint Garbage Room - Z1 - F2 | 10
| Z1-C-FIN-10770 | Plaster Works Wet Area - Z1 - RF | 2367
| Z1-C-FIN-10810 | Porcelain Floor Tiles Passage & Offices - Z1 - RF | 1686
| Z1-C-FIN-10880 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 10
| Z1-C-FIN-10950 | Plaster Works Dry Area - Z1 - RF | 2367
| Z1-C-FIN-10980 | Wall Ceramic Tiles Bath - Z1 - RF | 913
| Z1-C-FIN-10990 | Floor Ceramic Tiles Bath - Z1 - RF | 88
| Z1-C-FIN-11060 | Wall Ceramic Tiles kitchen/Pantry - Z1 - RF | 913
| Z1-C-FIN-11070 | Floor Ceramic Tiles kitchen/Pantry - Z1 - RF | 88
| Z1-C-FIN-11140 | Floor Epoxy Paint Garbage Room - Z1 - RF | 10
| Z1-C-FIN-18590 | Floor Epoxy Paint (Secur. Ctrl & Eqpmt Room) - Z1 - B1 | 10
| Z1-C-FIN-18630 | Floor Epoxy Paint (Maint. & Serv. Provider Room) - Z1 - B1 | 10
| Z1-C-FIN-18680 | Floor Stamp Concrete Loading Room - Z1 - GF | 94
| Z1-C-FIN-18710 | Floor Epoxy Paint Serv. Rooms - Z1 - F1 | 11
| Z1-C-FIN-21370 | Roof Floor Terrazo Tiles Outside Area - Z1 - RF | 397
| Z1-C-FIN-5800 | Plaster Works - Z1 - B2 | 4712
| Z1-C-FIN-6070 | Floor Epoxy Paint Serv. Rooms - Z1 - B2 | 10
| Z1-C-FIN-6100 | Floor Epoxy Paint - Z1 - B2 | 10
| Z1-C-FIN-6180 | Porcelain Floor Tiles - Z1 - B2 | 68
| Z1-C-FIN-7050 | Plaster Works - Z1 - B1 | 4988
| Z1-C-FIN-7320 | Raise Floor & Epoxy Paint Store & Serv. Rooms - Z1 - B1 | 10
| Z1-C-FIN-7430 | Porcelain Floor Tiles Lift Lobby - Z1 - B1 | 50
| Z1-C-FIN-8340 | Plaster Works - Z1 - GF | 3418
| Z1-C-FIN-8650 | Floor Epoxy Paint Garbage & Service Room - Z1 - GF | 10
| Z1-C-FIN-8680 | Floor Epoxy Paint Fire Pump & Cmd Room - Z1 - GF | 10
| Z1-C-FIN-8710 | Porcelain Floor Tiles Lift Lobby - Z1 - GF | 294
| Z1-C-FIN-8810 | Floor Epoxy Paint Generator Room - Z1 - GF | 10
| Z1-C-FIN-8850 | Floor Epoxy Paint LV & Trnsf. Room- Z1 - B1 | 10
| Z1-C-FIN-9500 | Plaster Works Wet + Dry Area - Z1 - F1 | 2288
| Z1-C-FIN-9600 | Porcelain Floor Tiles Lift Lobby & Passage- Z1 - F1 | 854
| Z1-C-FIN-9780 | Epoxy Paint Serv. Area - Z1 - F1 | 10
| Z1-C-FIN-SCASE-8800 | Staircase Floor Epoxy Paint - Z1 - B2 - SRVF | 10
| Z1-C-GRBCH-9400 | Block & Plaster Garbage Room - Z1 - GF to SRVF | 101
Z2
Div 02 | C-EW-10480 | Gunite Wall - Z3 | 333
| C-SHRNG-DCE-C-2360 | Place Guide Wall - Z2&3 | 84
| C-SHRNG-DCE-C-2380 | Install Capping Beam - Z2&3 | 222
Div 03 | C-EW-10410 | Gunite Wall - Z2 | 333
| Z2-C-CON-5860 | Protection Screed - Z2 - Lift Pit | 13
| Z2-C-CON-5890 | Pour Concrete - Z2 - Lift Pit | 49
| Z2-C-CON-5900 | PCC Blind Concrete - Z2 - Raft | 74
| Z2-C-CON-5920 | Protection Screed - Z2 - Raft | 37
| Z2-C-CON-5960 | Pour Concrete - Z2 - Raft | 2371
| Z2-C-CON-5990 | Pour Concrete Columns - Z2 - B2 | 66
| Z2-C-CON-6020 | Pour Concrete Retaining Walls - Z2 - B2 | 121
| Z2-C-CON-6030 | Pour Concrete Core Walls - Z2 - B2 | 68
| Z2-C-CON-6080 | Pour Concrete Stairs - Z2 - B2 | 4
| Z2-C-CON-6110 | Pour Concrete Retaining Walls - Z2 - B1 | 121
| Z2-C-CON-6140 | Pour Concrete Core Walls - Z2 - B1 | 69
| Z2-C-CON-6170 | Pour Concrete Columns - Z2 - B1 | 73
| Z2-C-CON-6200 | Pour Concrete Stairs - Z2 - B1 | 4
| Z2-C-CON-6230 | Pour Concrete Slabs - Z2 - B1 | 519
| Z2-C-CON-6270 | Pour Concrete Core Walls - Z2 - GF | 118
| Z2-C-CON-6300 | Pour Concrete Columns - Z2 - GF | 112
| Z2-C-CON-6330 | Pour Concrete Stairs - Z2 - GF | 5
| Z2-C-CON-6360 | Pour Concrete Slabs - Z2 - GF | 640
| Z2-C-CON-6410 | Pour Concrete Slabs - Z2 - F1 | 494
| Z2-C-CON-6440 | Pour Concrete Core Walls - Z2 - F1 | 120
| Z2-C-CON-6470 | Pour Concrete Columns - Z2 - F1 | 112
| Z2-C-CON-6500 | Pour Concrete Stairs - Z2 - F1 | 5
| Z2-C-CON-6530 | Pour Concrete Slabs - Z2 - F2 | 497
| Z2-C-CON-6570 | Pour Concrete Core Walls - Z2 - F2 | 72
| Z2-C-CON-6600 | Pour Concrete Columns - Z2 - F2 | 71
| Z2-C-CON-6630 | Pour Concrete Stairs - Z2 - F2 | 5
| Z2-C-CON-6660 | Pour Concrete Slabs - Z2 - RF | 495
| Z2-C-CON-6700 | Pour Concrete Core Walls - Z2 - RF | 72
| Z2-C-CON-6730 | Pour Concrete Columns - Z2 - RF | 57
| Z2-C-CON-6760 | Pour Concrete Stairs - Z2 - RF | 4
| Z2-C-CON-6790 | Pour Concrete Slabs - Z2 - SRVF | 425
| Z2-C-CON-6830 | Pour Concrete Core Walls - Z2 - SRVF | 2
| Z2-C-CON-6860 | Pour Concrete Columns - Z2 - SRVF | 4
| Z2-C-CON-6870 | Pour MEP RCC Pedastals - Z2 - SRVF | 1
| Z2-C-CON-6900 | Pour Concrete Parapet - Z2 - SRVF | 68
| Z2-C-CON-6930 | Pour Concrete Slabs - Z2 - TRF | 45
| Z2-C-CON-6970 | Pour Concrete Parapet - Z2 - TRF | 68
Div 04 | Z123-C-FIN-18110 | Masonry Works Dry Area - Z123 - SRVF | 201
| Z2&3-C-FIN-18800 | Masonry Works - Z2&3 - B2 | 28
| Z2&3-C-FIN-19050 | Masonry Works - Z2&3 - B1 | 281
| Z2&3-C-FIN-19270 | Masonry Works Wet + Dry Area - Z2&3 - F1 | 1337
| Z2&3-C-FIN-19540 | Masonry Works - Z2&3 - GF | 2073
| Z2&3-C-FIN-20010 | Masonry Works Wet Area - Z2&3 - F2 | 786
| Z2&3-C-FIN-20040 | Masonry Works Dry Area - Z2&3 - F2 | 786
| Z2&3-C-FIN-20440 | Masonry Works Wet Area - Z2&3 - RF | 674
| Z2&3-C-FIN-20470 | Masonry Works Dry Area - Z2&3 - RF | 674
Div 09 | A11400 | Fix Flower Box | 107
| A11410 | Fix Outdoor Green Area | 70
| A9690 | Fix Pavement Tiles & Granite Colored Land Scaping | 123
| A9710 | Install Precast Wheel Stoper | 50
| A9720 | Trafic & Road Marking | 51
| C-FIN-ENVLP-9700 | Fix Natural Stone All types- GF to SRVF (Elev. 2 & 3) | 3660
| C-FIN-ENVLP-9740 | External Plaster - GF to SRVF (Elev. 2 & 3) | 96
| Z123-C-FIN-18120 | Plaster Works Dry Area - Z123 - SRVF | 805
| Z123-C-FIN-18160 | Roof Floor Terrazo Tiles Wet Area - Z123 - SRVF | 6755
| Z123-C-FIN-18320 | Floor Epoxy Filter & Pump Room - Z123 - SRVF | 10
| Z123-C-FIN-18400 | Porcelain Floor Tiles Lift Lobby - Z123 - SRVF | 66
| Z123-C-FIN-18460 | Floor Epoxy GSM & MCC Rooms - Z123 - SRVF | 10
| Z2&3-C-FIN-18810 | Plaster Works - Z2&3 - B2 | 7066
| Z2&3-C-FIN-18880 | Wall Paint (Emulsion) - Z2&3 - B2 | 68
| Z2&3-C-FIN-18890 | Porcelain Floor Tiles - Z2&3 - B2 | 68
| Z2&3-C-FIN-18940 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B2 | 10
| Z2&3-C-FIN-18980 | Porcelain Floor Tiles Travelator - Z2&3 - B2 | 68
| Z2&3-C-FIN-19060 | Plaster Works - Z2&3 - B1 | 7482
| Z2&3-C-FIN-19090 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B1 | 10
| Z2&3-C-FIN-19170 | Wall Paint (Emulsion) - Z2&3 - B1 | 50
| Z2&3-C-FIN-19180 | Porcelain Floor Tiles - Z2&3 - B1 | 50
| Z2&3-C-FIN-19280 | Plaster Works Wet + Dry Area - Z2&3 - F1 | 3433
| Z2&3-C-FIN-19310 | Wall Ceramic Tiles Wet Area - Z2&3 - F1 | 913
| Z2&3-C-FIN-19320 | Floor Ceramic Tiles Wet Area - Z2&3 - F1 | 88
| Z2&3-C-FIN-19410 | Porcelain Floor Tiles Lift Lobby - Z2&3 - F1 | 854
| Z2&3-C-FIN-19550 | Plaster Works - Z2&3 - GF | 5125
| Z2&3-C-FIN-19560 | Floor Epoxy Paint Garbage & Service Room - Z2&3 - GF | 10
| Z2&3-C-FIN-19820 | Porcelain Floor Tiles Lift Lobby - Z2&3 - GF | 294
| Z2&3-C-FIN-20020 | Plaster Works Wet Area - Z2&3 - F2 | 4235
| Z2&3-C-FIN-20050 | Plaster Works Dry Area - Z2&3 - F2 | 4235
| Z2&3-C-FIN-20080 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 913
| Z2&3-C-FIN-20090 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 88
| Z2&3-C-FIN-20170 | Wall Ceramic Tiles Bath - Z2&3 - F2 | 913
| Z2&3-C-FIN-20180 | Floor Ceramic Tiles Bath - Z2&3 - F2 | 88
| Z2&3-C-FIN-20250 | Floor Epoxy Paint Garbage Room - Z2&3 - F2 | 10
| Z2&3-C-FIN-20310 | Porcelain Floor Tiles Passage & Offices - Z2&3 - F2 | 2211
| Z2&3-C-FIN-20420 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F2 | 10
| Z2&3-C-FIN-20450 | Plaster Works Wet Area - Z2&3 - RF | 3549
| Z2&3-C-FIN-20480 | Plaster Works Dry Area - Z2&3 - RF | 3549
| Z2&3-C-FIN-20510 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 913
| Z2&3-C-FIN-20520 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 88
| Z2&3-C-FIN-20600 | Wall Ceramic Tiles Bath - Z2&3 - RF | 913
| Z2&3-C-FIN-20610 | Floor Ceramic Tiles Bath - Z2&3 - RF | 88
| Z2&3-C-FIN-20680 | Floor Epoxy Paint Garbage Room - Z2&3 - RF | 10
| Z2&3-C-FIN-20770 | Porcelain Floor Tiles Passage & Offices - Z2&3 - RF | 1686
| Z2&3-C-FIN-20830 | Floor Epoxy Paint Serv. Rooms - Z2&3 - RF | 11
| Z2&3-C-FIN-20880 | Porcelain Floor Tiles Travelator - Z2&3 - B1 | 50
| Z2&3-C-FIN-21000 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F1 | 10
| Z2&3-C-FIN-21090 | Porcelain Floor Tiles Passage & Entrance - Z2&3 - GF | 294
| Z2&3-C-FIN-21110 | Wall Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 913
| Z2&3-C-FIN-21120 | Floor Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 88
| Z2&3-C-FIN-21250 | Floor Stamp Concrete Passage H.Market- Z2&3 - GF | 156
| Z2&3-C-FIN-21260 | Floor Epoxy Paint IT & Maintanance Room - Z2&3 - GF | 10
| Z2&3-C-FIN-21320 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - F1 | 397
| Z2&3-C-FIN-21350 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - RF | 397
| Z2&3-C-FIN-SCASE-101 | on Staircase Floor Epoxy Paint - Z2&3 - B2 - SRVF | 10
| Z2-C-GRBCH-11390 | Block & Plaster Garbage Room - Z2 - GF to SRVF | 101
Div 13 | Z2-C-LIFT-10800 | Install Steel Support Beams & Tracks CL B2 to GF | 120
Z3
Div 03 | Z3-C-CON-5860 | Protection Screed - Z3 - Lift Pit | 13
| Z3-C-CON-5890 | Pour Concrete - Z3 - Lift Pit | 49
| Z3-C-CON-5900 | PCC Blind Concrete - Z3 - Raft | 74
| Z3-C-CON-5920 | Protection Screed - Z3 - Raft | 37
| Z3-C-CON-5960 | Pour Concrete - Z3 - Raft | 2240
| Z3-C-CON-5990 | Pour Concrete Columns - Z3 - B2 | 66
| Z3-C-CON-6020 | Pour Concrete Retaining Walls - Z3 - B2 | 121
| Z3-C-CON-6030 | Pour Concrete Core Walls - Z3 - B2 | 68
| Z3-C-CON-6110 | Pour Concrete Retaining Walls - Z3 - B1 | 121
| Z3-C-CON-6140 | Pour Concrete Core Walls - Z3 - B1 | 69
| Z3-C-CON-6170 | Pour Concrete Columns - Z3 - B1 | 73
| Z3-C-CON-6230 | Pour Concrete Slabs - Z3 - B1 | 519
| Z3-C-CON-6270 | Pour Concrete Core Walls - Z3 - GF | 118
| Z3-C-CON-6300 | Pour Concrete Columns - Z3 - GF | 112
| Z3-C-CON-6360 | Pour Concrete Slabs - Z3 - GF | 640
| Z3-C-CON-6410 | Pour Concrete Slabs - Z3 - F1 | 494
| Z3-C-CON-6440 | Pour Concrete Core Walls - Z3 - F1 | 120
| Z3-C-CON-6470 | Pour Concrete Columns - Z3 - F1 | 112
| Z3-C-CON-6530 | Pour Concrete Slabs - Z3 - F2 | 497
| Z3-C-CON-6570 | Pour Concrete Core Walls - Z3 - F2 | 72
| Z3-C-CON-6600 | Pour Concrete Columns - Z3 - F2 | 71
| Z3-C-CON-6660 | Pour Concrete Slabs - Z3 - RF | 495
| Z3-C-CON-6700 | Pour Concrete Core Walls - Z3 - RF | 72
| Z3-C-CON-6730 | Pour Concrete Columns - Z3 - RF | 57
| Z3-C-CON-6790 | Pour Concrete Slabs - Z3 - SRVF | 425
| Z3-C-CON-6900 | Pour Concrete Parapet - Z3 - SRVF | 68
| Z3-C-CON-6930 | Pour Concrete Slabs - Z3 - TRF | 45
| Z3-C-CON-6970 | Pour Concrete Parapet - Z3 - TRF | 68
Painter 1817 |  |  | 39117
Z1
Div 09 | A9740 | Traffic Deck Coating Drive Way - B2 | 630
| A9790 | Traffic Marking Drive Way - B2 | 630
| A9810 | Traffic Deck Coating Drive Way - B1 | 630
| A9840 | Traffic Marking Drive Way - B1 | 630
| Z1-C-FIN-10050 | Anti Fungal Paint - Z1 - F1 | 302
| Z1-C-FIN-10190 | Wall Paint (Emulsion) Lobby Passage & Offices - Z1 - F2 | 648
| Z1-C-FIN-10230 | Floor Paint (Antifungal) Lift Shaft - Z1 - F2 | 271
| Z1-C-FIN-10240 | Wall Paint (Antifungal) Lift Shaft - Z1 - F2 | 271
| Z1-C-FIN-10250 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - F2 | 59
| Z1-C-FIN-10300 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - F2 | 260
| Z1-C-FIN-10310 | Wall Paint (Acrylic) Serv. Rooms - Z1 - F2 | 95
| Z1-C-FIN-10560 | Fix False Ceiling Gypsum Board Bath - Z1 - F2 | 260
| Z1-C-FIN-10640 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - F2 | 260
| Z1-C-FIN-10690 | Ceiling Paint (Emulsion) Garbage Room - Z1 - F2 | 26
| Z1-C-FIN-10700 | Wall Paint (Emulsion) Garbage Room - Z1 - F2 | 647
| Z1-C-FIN-10800 | Wall Paint (Emulsion) Lobby Passage & Offices - Z1 - RF | 647
| Z1-C-FIN-10820 | Floor Paint (Antifungal) Lift Shaft - Z1 - RF | 271
| Z1-C-FIN-10830 | Wall Paint (Antifungal) Lift Shaft - Z1 - RF | 271
| Z1-C-FIN-10840 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - RF | 59
| Z1-C-FIN-10850 | Wall Paint (Acrylic) Serv. Rooms - Z1 - RF | 94
| Z1-C-FIN-10870 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - RF | 199
| Z1-C-FIN-11020 | Fix False Ceiling Gypsum Board Bath - Z1 - RF | 199
| Z1-C-FIN-11100 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - RF | 199
| Z1-C-FIN-11130 | Wall Paint (Emulsion) Garbage Room - Z1 - RF | 647
| Z1-C-FIN-11170 | Ceiling Paint (Emulsion) Garbage Room - Z1 - RF | 26
| Z1-C-FIN-18570 | Ceiling Paint (Emulsion/Acrylic) Secur. Ctrl & Eqpmt Room - Z1 - B1 | 26
| Z1-C-FIN-18580 | Wall Paint (Emulsion/Acrylic) Secur. Ctrl & Eqpmt Room - Z1 - B1 | 647
| Z1-C-FIN-18610 | Ceiling Paint (Acrylic) Maint. & Serv. Provider Room) - Z1 - B1 | 59
| Z1-C-FIN-18620 | Wall Paint (Acrylic) Maint. & Serv. Provider Room) - Z1 - B1 | 94
| Z1-C-FIN-18650 | Ceiling Paint (Acrylic) Loading Room - Z1 - GF | 59
| Z1-C-FIN-18670 | Wall Paint (Acrylic) Loading Room - Z1 - GF | 94
| Z1-C-FIN-18700 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - F1 | 59
| Z1-C-FIN-21360 | Wall Paint Outside Area (Acrylic) - Z1 - RF | 94
| Z1-C-FIN-6050 | Ceiling Paint (Acrylic) - Z1 - B2 | 59
| Z1-C-FIN-6060 | Wall Paint (Acrylic) - Z1 - B2 | 94
| Z1-C-FIN-6080 | Ceiling Paint (Acrylic) - Z1 - B2 | 59
| Z1-C-FIN-6090 | Wall Paint (Acrylic) - Z1 - B2 | 94
| Z1-C-FIN-6170 | Wall Paint (Emulsion) - Z1 - B2 | 647
| Z1-C-FIN-6270 | Wall Paint (Antifungal) Lift Shaft - Z1 - B2 | 271
| Z1-C-FIN-6280 | Floor Paint (Antifungal) Lift Shaft - Z1 - B2 | 271
| Z1-C-FIN-6290 | Ceiling Paint (Anti-Carbonation) - Z1 - B2 | 770
| Z1-C-FIN-6310 | Wall Paint (Anti-Carbonation) - Z1 - B2 | 771
| Z1-C-FIN-6330 | Fix False Ceiling Gypsum Board & Tiles - Z1 - B2 | 19
| Z1-C-FIN-7300 | Ceiling Paint (Emulsion/Acrylic) Store & Serv. Rooms - Z1 - B1 | 26
| Z1-C-FIN-7310 | Wall Paint (Emulsion/Acrylic) Store & Serv. Rooms - Z1 - B1 | 647
| Z1-C-FIN-7410 | Fix False Ceiling Gypsum Board & Tiles Lift Lobby - Z1 - B1 | 28
| Z1-C-FIN-7420 | Wall Paint (Emulsion) Lift Lobby - Z1 - B1 | 647
| Z1-C-FIN-7540 | Ceiling Paint (Anti-Carbonation) - Z1 - B1 | 770
| Z1-C-FIN-7560 | Wall Paint (Anti-Carbonation) - Z1 - B1 | 770
| Z1-C-FIN-8630 | Ceiling Paint Garbage & Service Room (Acrylic/Emulsion) - Z1 - GF | 26
| Z1-C-FIN-8640 | Wall Paint Garbage & Service Room (Acrylic/Emulsion) - Z1 - GF | 647
| Z1-C-FIN-8660 | Ceiling Paint (Acrylic/Emulsion) Fire Pump & Cmd Room - Z1 - GF | 26
| Z1-C-FIN-8670 | Wall Paint (Acrylic/Emulsion) Fire Pump & Cmd Room - Z1 - GF | 647
| Z1-C-FIN-8700 | Wall Paint (Emulsion) Lift Lobby - Z1 - GF | 647
| Z1-C-FIN-8770 | Floor Paint (Antifungal) Lift Shaft - Z1 - GF | 271
| Z1-C-FIN-8780 | Wall Paint (Antifungal) Lift Shaft - Z1 - GF | 271
| Z1-C-FIN-8790 | Ceiling Paint Generator Room (Acrylic) - Z1 - GF | 94
| Z1-C-FIN-8800 | Wall Paint Generator Room (Acrylic) - Z1 - GF | 94
| Z1-C-FIN-8830 | Ceiling Paint LV & Trnsf. Room (Acrylic) - Z1 - B1 | 94
| Z1-C-FIN-8840 | Wall Paint LV & Trnsf. Room (Acrylic) - Z1 - B1 | 94
| Z1-C-FIN-8890 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - GF | 73
| Z1-C-FIN-8920 | Anti Fungal Paint all Shops - Z1 - GF | 302
| Z1-C-FIN-9590 | Wall Paint (Emulsion) Lift Lobby & Passage - Z1 - F1 | 647
| Z1-C-FIN-9660 | Floor Paint (Antifungal) Lift Shaft - Z1 - F1 | 271
| Z1-C-FIN-9670 | Wall Paint (Antifungal) Lift Shaft - Z1 - F1 | 271
| Z1-C-FIN-9770 | Ceiling Paint (Acrylic) Serv. Area - Z1 - F1 | 59
| Z1-C-FIN-9960 | Fix False Ceiling Gypsum Board Lift Lobby & Passage - Z1 - F1 | 184
| Z1-C-FIN-SCASE-8790 | Staircase Acrylic Paint - Z1 - B2 - SRVF | 1
Z2
Div 09 | A10890 | Traffic Deck Coating Drive - Z2 - B1 | 630
| A10950 | Traffic Deck Coating Drive - Z2 - B2 | 630
| Z123-C-FIN-18310 | Wall Paint (Acrylic) Filter & Pump Room - Z123 - SRVF | 94
| Z123-C-FIN-18350 | Ceiling Paint (Acrylic) Filter & Pump Room - Z123 - SRVF | 59
| Z123-C-FIN-18410 | Wall Paint (Emulsion) Lift Lobby - Z123 - SRVF | 647
| Z123-C-FIN-18430 | Fix False Ceiling Gypsum Board Lift Lobby - Z123 - SRVF | 21
| Z123-C-FIN-18450 | Ceiling Paint (Acrylic) GSM & MCC Rooms - Z123 - SRVF | 59
| Z123-C-FIN-18470 | Wall Paint (Acrylic) GSM & MCC Rooms - Z123 - SRVF | 94
| Z123-C-FIN-18480 | Floor Paint (Antifungal) Lift Shaft - Z123 - SRVF | 271
| Z123-C-FIN-18490 | Wall Paint (Antifungal) Lift Shaft - Z123 - SRVF | 271
| Z2&3-C-FIN-18740 | Ceiling Paint (Anti-Carbonation) - Z2&3 - B2 | 770
| Z2&3-C-FIN-18760 | Wall Paint (Anti-Carbonation) - Z2&3 - B2 | 770
| Z2&3-C-FIN-18900 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B2 | 19
| Z2&3-C-FIN-18920 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - B2 | 59
| Z2&3-C-FIN-18930 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - B2 | 94
| Z2&3-C-FIN-18960 | Ceiling Paint (Emulsion) Travelator - Z2&3 - B2 | 26
| Z2&3-C-FIN-18970 | Wall Paint (Emulsion) Travelator - Z2&3 - B2 | 647
| Z2&3-C-FIN-19070 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - B1 | 59
| Z2&3-C-FIN-19080 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - B1 | 94
| Z2&3-C-FIN-19160 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B1 | 28
| Z2&3-C-FIN-19230 | Ceiling Paint (Anti-Carbonation) - Z2&3 - B1 | 770
| Z2&3-C-FIN-19250 | Wall Paint (Anti-Carbonation) - Z2&3 - B1 | 770
| Z2&3-C-FIN-19340 | Fix False Ceiling Gypsum Board - Z2&3 - F1 | 184
| Z2&3-C-FIN-19400 | Wall Paint (Emulsion) Lift Lobby - Z2&3 - F1 | 647
| Z2&3-C-FIN-19440 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - F1 | 184
| Z2&3-C-FIN-19460 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - F1 | 271
| Z2&3-C-FIN-19470 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - F1 | 271
| Z2&3-C-FIN-19480 | Wall Paint (Acrylic) IT Room - Z2&3 - F1 | 94
| Z2&3-C-FIN-19510 | Ceiling Paint (Acrylic) IT Room - Z2&3 - F1 | 59
| Z2&3-C-FIN-19520 | Anti Fungal Paint - Z2&3 - F1 | 302
| Z2&3-C-FIN-19590 | Ceiling Paint Garbage & Service Room (Acrylic/Emulsion)- Z2&3 - GF | 26
| Z2&3-C-FIN-19600 | Wall Paint Garbage & Service Room (Acrylic/Emulsion) - Z2&3 - GF | 647
| Z2&3-C-FIN-19770 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - GF | 73
| Z2&3-C-FIN-19810 | Wall Paint (Emulsion) Lift Lobby - Z2&3 - GF | 647
| Z2&3-C-FIN-19830 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - GF | 271
| Z2&3-C-FIN-19840 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - GF | 271
| Z2&3-C-FIN-19940 | Anti Fungal Paint all Shops - Z2&3 - GF | 302
| Z2&3-C-FIN-20120 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - F2 | 260
| Z2&3-C-FIN-20210 | Fix False Ceiling Gypsum Board Bath - Z2&3 - F2 | 260
| Z2&3-C-FIN-20240 | Wall Paint (Emulsion) Garbage Room - Z2&3 - F2 | 647
| Z2&3-C-FIN-20280 | Ceiling Paint (Emulsion) Garbage Room - Z2&3 - F2 | 25
| Z2&3-C-FIN-20300 | Wall Paint (Emulsion) Lobby Passage & Offices - Z2&3 - F2 | 648
| Z2&3-C-FIN-20330 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - F2 | 260
| Z2&3-C-FIN-20350 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - F2 | 271
| Z2&3-C-FIN-20360 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - F2 | 271
| Z2&3-C-FIN-20400 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - F2 | 59
| Z2&3-C-FIN-20410 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - F2 | 94
| Z2&3-C-FIN-20550 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - RF | 199
| Z2&3-C-FIN-20640 | Fix False Ceiling Gypsum Board Bath - Z2&3 - RF | 199
| Z2&3-C-FIN-20670 | Wall Paint (Emulsion) Garbage Room - Z2&3 - RF | 647
| Z2&3-C-FIN-20710 | Ceiling Paint (Emulsion) Garbage Room - Z2&3 - RF | 26
| Z2&3-C-FIN-20760 | Wall Paint (Emulsion) Lobby Passage & Offices - Z2&3 - RF | 647
| Z2&3-C-FIN-20790 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - RF | 199
| Z2&3-C-FIN-20810 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - RF | 59
| Z2&3-C-FIN-20820 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - RF | 94
| Z2&3-C-FIN-20840 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - RF | 271
| Z2&3-C-FIN-20850 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - RF | 271
| Z2&3-C-FIN-20860 | Ceiling Paint (Emulsion) Travelator - Z2&3 - B1 | 26
| Z2&3-C-FIN-20870 | Wall Paint (Emulsion) Travelator - Z2&3 - B1 | 647
| Z2&3-C-FIN-20990 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - F1 | 59
| Z2&3-C-FIN-21020 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - F1 | 94
| Z2&3-C-FIN-21040 | Fix False Ceiling Gypsum Board Passage & Entrance - Z2&3 - GF | 73
| Z2&3-C-FIN-21080 | Wall Paint (Emulsion) Passage & Entrance - Z2&3 - GF | 647
| Z2&3-C-FIN-21140 | Fix False Ceiling Gypsum Board Wet + Nursing Area - Z2&3 - GF | 73
| Z2&3-C-FIN-21200 | Fix False Ceiling Gypsum Board Passage H.Market - Z2&3 - GF | 73
| Z2&3-C-FIN-21290 | Ceiling Paint IT & Maintanance Room (Acrylic/Emulsion)- Z2&3 - GF | 26
| Z2&3-C-FIN-21300 | Wall Paint IT & Maintanance Room (Acrylic/Emulsion) - Z2&3 - GF | 647
| Z2&3-C-FIN-21310 | Wall Paint Outside Area (Acrylic) - Z2&3 - F1 | 94
| Z2&3-C-FIN-21340 | Wall Paint Outside Area (Acrylic) - Z2&3 - RF | 94
| Z2&3-C-FIN-SCASE-100 | on Staircase Acrylic Paint - Z2&3 - B2 - SRVF | 1
Plumber 1817 |  |  | 40472
Z1
Div 03 | Z1-11460 | Post Tensioning the Slab - Z1 - F1 | 4
| Z1-11470 | Post Tensioning the Slab - Z1 - F2 | 4
| Z1-11480 | Post Tensioning the Slab - Z1 - RF | 4
| Z1-11490 | Post Tensioning the Slab - Z1 - SRVF | 4
Div 10 | A9670 | Casting Service Manholes | 167
| Z123-C-FIN-18500 | Fix Rain Water Outlets - Z123 - TRF | 100
| Z1-C-CON-2540 | Fix MEP Provisions - Z1 - Raft | 100
| Z1-C-FIN-6250 | Fix Pump - Z1 - B2 | 126
| Z1-C-FIN-6260 | Fix Final Connections of Pumps with Risers - Z1 - B2 | 125
| Z1-C-FIN-8750 | Fix Electric Pump Fire Pump Room - Z1 - GF | 250
| Z1-C-FIN-8760 | Fix Final Connections with Risers Fire Pump Room - Z1 - GF | 125
| Z1-C-FIN-9310 | Fix Diesel Pump Fire Pump Room- Z1 - GF | 250
| Z1-C-FIN-9320 | Fix Jockey Pump Fire Pump Room- Z1 - GF | 250
| Z1-C-FIN-9340 | Final Connections & Termination Fire Pump Room - Z1 - GF | 125
| Z1-C-MEP-5820 | Fix Drainage Pipes - Z1 - B2 | 250
| Z1-C-MEP-7070 | Fix Drainage Pipes - Z1 - B1 | 250
| Z1-C-MEP-8360 | Fix Drainage Pipes - Z1 - GF | 250
| Z1-C-MEP-8590 | Fix Water Supply Pipes - Z1 - GF | 250
| Z1-C-MEP-8630 | Fix Water Heater & Sanitary Accessories - Z1 - GF | 333
| Z1-C-MEP-8640 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - GF | 50
| Z1-C-MEP-8660 | Fix Drainage Pipes - Z1 - F1 | 250
| Z1-C-MEP-8920 | Fix Water Supply Pipes - Z1 - F1 | 250
| Z1-C-MEP-8930 | Fix Water Heater & Sanitary Accessories - Z1 - F1 | 333
| Z1-C-MEP-8940 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - F1 | 50
| Z1-C-MEP-8960 | Fix Drainage Pipes - Z1 - F2 | 250
| Z1-C-MEP-9220 | Fix Water Supply Pipes - Z1 - F2 | 250
| Z1-C-MEP-9230 | Fix Water Heater & Sanitary Accessories - Z1 - F2 | 333
| Z1-C-MEP-9240 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - F2 | 50
| Z1-C-MEP-9280 | Fix Drainage Pipes - Z1 - RF | 250
| Z1-C-MEP-9540 | Fix Water Supply Pipes - Z1 - RF | 250
| Z1-C-MEP-9550 | Fix Water Heater & Sanitary Accessories - Z1 - RF | 334
| Z1-C-MEP-9560 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - RF | 50
| Z1-C-RSRS-11020 | Install Drainage Pipe Risers | 1000
| Z1-C-RSRS-11030 | Install Water Supply Pipe Risers | 1000
Div 11 | Z1-C-MEP-5830 | Fix Fire Fighting Pipes - Z1 - B2 | 500
| Z1-C-MEP-5860 | Fix Fire Fighting Dropers - Z1 - B2 | 50
| Z1-C-MEP-6020 | Fix Fire Hose Cabinets & Hose Reels - Z1 - B2 | 50
| Z1-C-MEP-6030 | Fix Sprinklers - Z1 - B2 | 500
| Z1-C-MEP-7080 | Fix Fire Fighting Pipes - Z1 - B1 | 500
| Z1-C-MEP-7110 | Fix Fire Fighting Dropers - Z1 - B1 | 50
| Z1-C-MEP-7270 | Fix Fire Hose Cabinets & Hose Reels - Z1 - B1 | 50
| Z1-C-MEP-7280 | Fix Sprinklers - Z1 - B1 | 500
| Z1-C-MEP-8370 | Fix Fire Fighting Pipes - Z1 - GF | 500
| Z1-C-MEP-8400 | Fix Fire Fighting Dropers - Z1 - GF | 50
| Z1-C-MEP-8560 | Fix Fire Hose Cabinets & Hose Reels - Z1 - GF | 50
| Z1-C-MEP-8570 | Fix Sprinklers - Z1 - GF | 500
| Z1-C-MEP-8670 | Fix Fire Fighting Pipes - Z1 - F1 | 500
| Z1-C-MEP-8700 | Fix Fire Fighting Dropers - Z1 - F1 | 50
| Z1-C-MEP-8860 | Fix Fire Hose Cabinets & Hose Reels - Z1 - F1 | 50
| Z1-C-MEP-8870 | Fix Sprinklers - Z1 - F1 | 500
| Z1-C-MEP-8970 | Fix Fire Fighting Pipes - Z1 - F2 | 500
| Z1-C-MEP-9000 | Fix Fire Fighting Dropers - Z1 - F2 | 50
| Z1-C-MEP-9160 | Fix Fire Hose Cabinets & Hose Reels - Z1 - F2 | 50
| Z1-C-MEP-9170 | Fix Sprinklers - Z1 - F2 | 500
| Z1-C-MEP-9290 | Fix Fire Fighting Pipes - Z1 - RF | 500
| Z1-C-MEP-9320 | Fix Fire Fighting Dropers - Z1 - RF | 50
| Z1-C-MEP-9480 | Fix Fire Hose Cabinets & Hose Reels - Z1 - RF | 50
| Z1-C-MEP-9490 | Fix Sprinklers - Z1 - RF | 500
Div 12 | Z1-C-MEP-5840 | Fix Chill Water Pipes - Z1 - B2 | 333
| Z1-C-MEP-7090 | Fix Chill Water Pipes - Z1 - B1 | 333
| Z1-C-MEP-8380 | Fix Chill Water Pipes - Z1 - GF | 333
| Z1-C-MEP-8680 | Fix Chill Water Pipes - Z1 - F1 | 334
| Z1-C-MEP-8980 | Fix Chill Water Pipes - Z1 - F2 | 333
| Z1-C-MEP-9300 | Fix Chill Water Pipes - Z1 - RF | 334
| Z1-C-RSRS-11050 | Install Fire Fighting Pipe Risers | 1000
Div 14 | Z1-C-MEP-9250 | Fix LPG Pipes - Z1 - F2 | 167
| Z1-C-MEP-9260 | Fix Gas Detectors - Z1 - F2 | 167
| Z1-C-MEP-9570 | Fix LPG Pipes - Z1 - RF | 167
| Z1-C-MEP-9580 | Fix Gas Detectors - Z1 - RF | 166
| Z1-C-RSRS-11070 | Install LPG Pipe Risers | 166
Z2
Div 03 | Z2-11520 | Post Tensioning the Slab - Z2 - F1 | 2
| Z2-11530 | Post Tensioning the Slab - Z2 - F2 | 2
| Z2-11540 | Post Tensioning the Slab - Z2 - RF | 2
| Z2-11550 | Post Tensioning the Slab - Z2 - SRVF | 2
Div 10 | A11450 | External Drainage Pipes & Connections | 100
| A9700 | Install Man Holes Covers | 167
| ADCE-MALL-WS-2200 | Installation of Water Meter & AADC Approval | 100
| T&C-10000 | Water Supply System Testing & Commissioning | 100
| T&C-10010 | Water Drainage System Testing & Commissioning | 100
| Z123-C-FIN-18210 | Fix Rain Water Outlets - Z123 - SRVF | 100
| Z123-C-MEP-14740 | Fix Drainage & Water Supply Pipes Block Wall - Z123 - SRVF | 50
| Z123-C-MEP-14880 | Fix Water Supply Pipes - Z123 - SRVF | 250
| Z123-C-MEP-14900 | Fix Drainage Pipes - Z123 - SRVF | 250
| Z123-C-MEP-15010 | Fix Water Heater & Sanitary Accessories - Z123 - SRVF | 333
| Z123-C-MEP-15060 | Install GRP Water Tank & Accessories - Z123 - SRVF | 250
| Z123-C-MEP-15070 | Install Filteration Plant System - Z123 - SRVF | 333
| Z2&3-C-MEP-15240 | Fix Drainage Pipes - Z2&3 - B2 | 250
| Z2&3-C-MEP-15510 | Fix Drainage Pipes - Z2&3 - B1 | 250
| Z2&3-C-MEP-15710 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - F1 | 50
| Z2&3-C-MEP-15790 | Fix Drainage Pipes - Z2&3 - F1 | 250
| Z2&3-C-MEP-15850 | Fix Water Supply Pipes - Z2&3 - F1 | 250
| Z2&3-C-MEP-15940 | Fix Water Heater & Sanitary Accessories - Z2&3 - F1 | 333
| Z2&3-C-MEP-16010 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - GF | 50
| Z2&3-C-MEP-16090 | Fix Drainage Pipes - Z2&3 - GF | 250
| Z2&3-C-MEP-16150 | Fix Water Supply Pipes - Z2&3 - GF | 250
| Z2&3-C-MEP-16260 | Fix Water Heater & Sanitary Accessories - Z2&3 - GF | 333
| Z2&3-C-MEP-16310 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - F2 | 50
| Z2&3-C-MEP-16390 | Fix Drainage Pipes - Z2&3 - F2 | 250
| Z2&3-C-MEP-16450 | Fix Water Supply Pipes - Z2&3 - F2 | 250
| Z2&3-C-MEP-16560 | Fix Water Heater & Sanitary Accessories - Z2&3 - F2 | 333
| Z2&3-C-MEP-16630 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - RF | 50
| Z2&3-C-MEP-16720 | Fix Drainage Pipes - Z2&3 - RF | 250
| Z2&3-C-MEP-16780 | Fix Water Supply Pipes - Z2&3 - RF | 250
| Z2&3-C-MEP-16900 | Fix Water Heater & Sanitary Accessories - Z2&3 - RF | 333
| Z2-C-CON-5940 | Fix MEP Provisions - Z2 - Raft | 100
| Z2-C-RSRS-11120 | Install Drainage Pipe Risers | 1000
| Z2-C-RSRS-11130 | Install Water Supply Pipe Risers | 1000
Div 11 | T&C-9980 | Fire Fighting System Testing & Commissioning | 100
| Z123-C-MEP-14830 | Fix Fire Fighting Pipes - Z123 - SRVF | 500
| Z123-C-MEP-14860 | Fix Fire Fighting Dropers - Z123 - SRVF | 50
| Z123-C-MEP-14980 | Fix Fire Hose Cabinets & Hose Reels - Z123 - SRVF | 50
| Z123-C-MEP-14990 | Fix Sprinklers - Z123 - SRVF | 500
| Z2&3-C-MEP-15250 | Fix Fire Fighting Pipes - Z2&3 - B2 | 500
| Z2&3-C-MEP-15280 | Fix Fire Fighting Dropers - Z2&3 - B2 | 50
| Z2&3-C-MEP-15370 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - B2 | 50
| Z2&3-C-MEP-15380 | Fix Sprinklers - Z2&3 - B2 | 500
| Z2&3-C-MEP-15520 | Fix Fire Fighting Pipes - Z2&3 - B1 | 500
| Z2&3-C-MEP-15550 | Fix Fire Fighting Dropers - Z2&3 - B1 | 50
| Z2&3-C-MEP-15640 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - B1 | 50
| Z2&3-C-MEP-15650 | Fix Sprinklers - Z2&3 - B1 | 500
| Z2&3-C-MEP-15800 | Fix Fire Fighting Pipes - Z2&3 - F1 | 500
| Z2&3-C-MEP-15830 | Fix Fire Fighting Dropers - Z2&3 - F1 | 50
| Z2&3-C-MEP-15950 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - F1 | 50
| Z2&3-C-MEP-15960 | Fix Sprinklers - Z2&3 - F1 | 500
| Z2&3-C-MEP-16100 | Fix Fire Fighting Pipes - Z2&3 - GF | 500
| Z2&3-C-MEP-16130 | Fix Fire Fighting Dropers - Z2&3 - GF | 50
| Z2&3-C-MEP-16230 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - GF | 50
| Z2&3-C-MEP-16240 | Fix Sprinklers - Z2&3 - GF | 500
| Z2&3-C-MEP-16400 | Fix Fire Fighting Pipes - Z2&3 - F2 | 500
| Z2&3-C-MEP-16430 | Fix Fire Fighting Dropers - Z2&3 - F2 | 50
| Z2&3-C-MEP-16540 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - F2 | 50
| Z2&3-C-MEP-16550 | Fix Sprinklers - Z2&3 - F2 | 500
| Z2&3-C-MEP-16730 | Fix Fire Fighting Pipes - Z2&3 - RF | 500
| Z2&3-C-MEP-16760 | Fix Fire Fighting Dropers - Z2&3 - RF | 50
| Z2&3-C-MEP-16870 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - RF | 50
| Z2&3-C-MEP-16880 | Fix Sprinklers - Z2&3 - RF | 500
| Z2-C-RSRS-11150 | Install Fire Fighting Pipe Risers | 1000
Div 12 | Z123-C-MEP-14840 | Fix Chill Water Pipes - Z123 - SRVF | 333
| Z123-C-MEP-15090 | Install Chilled Water Pump - Z123 - SRVF | 200
| Z123-C-MEP-15140 | Fix Chemical Dosing Pot - Z123 - SRVF | 500
| Z2&3-C-MEP-15260 | Fix Chill Water Pipes - Z2&3 - B2 | 333
| Z2&3-C-MEP-15530 | Fix Chill Water Pipes - Z2&3 - B1 | 333
| Z2&3-C-MEP-15810 | Fix Chill Water Pipes - Z2&3 - F1 | 333
| Z2&3-C-MEP-16110 | Fix Chill Water Pipes - Z2&3 - GF | 333
| Z2&3-C-MEP-16410 | Fix Chill Water Pipes - Z2&3 - F2 | 333
| Z2&3-C-MEP-16740 | Fix Chill Water Pipes - Z2&3 - RF | 334
| Z2-C-RSRS-11140 | Install CHW Pipe Risers | 999
Div 14 | Z123-C-MEP-15020 | Fix Gas Detectors - Z123 - SRVF | 167
| Z123-C-MEP-15110 | Install LPG Tank - Z123 - SRVF | 167
| Z2&3-C-MEP-16460 | Fix LPG Pipes - Z2&3 - F2 | 167
| Z2&3-C-MEP-16570 | Fix Gas Detectors - Z2&3 - F2 | 167
| Z2&3-C-MEP-16710 | Fix LPG Pipes - Z2&3 - RF | 167
| Z2&3-C-MEP-16860 | Fix Gas Detectors - Z2&3 - RF | 167
| Z2-C-RSRS-11170 | Install LPG Pipe Risers | 166
Z3
Div 10 | Z3-C-CON-5940 | Fix MEP Provisions - Z3 - Raft | 100
STeel Fixer 1817 |  |  | 220292
Z1
Div 02 | C-SHRNG-DCE-C-2350 | Install Capping Beam - Z1 | 1942
Div 03 | Z1-C-CON-2460 | Fix Rebar - Z1 - Lift Pit | 497
| Z1-C-CON-2530 | Fix Rebar - Z1 - Raft | 18160
| Z1-C-CON-2570 | Fix Rebar Core Walls - Z1 - B2 | 1609
| Z1-C-CON-2600 | Fix Rebar Retaining Walls - Z1 - B2 | 2863
| Z1-C-CON-2640 | Fix Rebar Columns - Z1 - B2 | 3019
| Z1-C-CON-2680 | Fix Rebar Stairs - Z1 - B2 | 43
| Z1-C-CON-2720 | Fix Rebar Slabs - Z1 - B1 | 5966
| Z1-C-CON-2730 | Fix Rebar Retaining Walls - Z1 - B1 | 2275
| Z1-C-CON-2760 | Fix Rebar Core Walls - Z1 - B1 | 1493
| Z1-C-CON-2790 | Fix Rebar Columns - Z1 - B1 | 2313
| Z1-C-CON-2830 | Fix Rebar Stairs - Z1 - B1 | 43
| Z1-C-CON-3010 | Fix Rebar Slabs - Z1 - GF | 11393
| Z1-C-CON-3030 | Fix Rebar Core Walls - Z1 - GF | 2275
| Z1-C-CON-3060 | Fix Rebar Columns - Z1 - GF | 3007
| Z1-C-CON-3100 | Fix Rebar Stairs - Z1 - GF | 21
| Z1-C-CON-3180 | Fix Rebar Slabs - Z1 - F1 | 4939
| Z1-C-CON-3190 | Fix Rebar Core Walls - Z1 - F1 | 2248
| Z1-C-CON-3220 | Fix Rebar Columns - Z1 - F1 | 3046
| Z1-C-CON-3260 | Fix Rebar Stairs - Z1 - F1 | 22
| Z1-C-CON-3290 | Fix Rebar Slabs - Z1 - F2 | 5071
| Z1-C-CON-3320 | Fix Rebar Core Walls - Z1 - F2 | 1485
| Z1-C-CON-3350 | Fix Rebar Columns - Z1 - F2 | 2076
| Z1-C-CON-3390 | Fix Rebar Stairs - Z1 - F2 | 16
| Z1-C-CON-3420 | Fix Rebar Slabs - Z1 - RF | 5045
| Z1-C-CON-3450 | Fix Rebar Core Walls - Z1 - RF | 1460
| Z1-C-CON-3480 | Fix Rebar Columns - Z1 - RF | 1700
| Z1-C-CON-3520 | Fix Rebar Stairs - Z1 - RF | 16
| Z1-C-CON-5630 | Fix Rebar Slabs - Z1 - SRVF | 4156
| Z1-C-CON-5660 | Fix Rebar Core Walls - Z1 - SRVF | 864
| Z1-C-CON-5690 | Fix Rebar Columns - Z1 - SRVF | 154
| Z1-C-CON-5730 | Fix Rebar Parapet - Z1 - SRVF | 314
| Z1-C-CON-5760 | Fix Rebar Slabs - Z1 - TRF | 404
| Z1-C-CON-5810 | Fix Rebar Parapet - Z1 - TRF | 314
| Z1-C-CON-5850 | Fix Rebar Ramp - Z1 - B2 | 96
| Z1-C-CON-5880 | Fix Rebar Ramp - Z1 - B1 | 372
| Z1-C-CON-5900 | Fix Rebar Core Walls Ramp - Z1 - B2 | 1054
| Z1-C-CON-5930 | Fix Rebar Core Walls Ramp - Z1 - B1 | 1015
Z2
Div 02 | C-SHRNG-DCE-C-2380 | Install Capping Beam - Z2&3 | 2913
Div 03 | Z2-C-CON-5870 | Fix Rebar - Z2 - Lift Pit | 249
| Z2-C-CON-5930 | Fix Rebar - Z2 - Raft | 13736
| Z2-C-CON-5970 | Fix Rebar Columns - Z2 - B2 | 2265
| Z2-C-CON-6000 | Fix Rebar Retaining Walls - Z2 - B2 | 1432
| Z2-C-CON-6040 | Fix Rebar Core Walls - Z2 - B2 | 949
| Z2-C-CON-6070 | Fix Rebar Stairs - Z2 - B2 | 32
| Z2-C-CON-6090 | Fix Rebar Retaining Walls - Z2 - B1 | 1138
| Z2-C-CON-6130 | Fix Rebar Core Walls - Z2 - B1 | 914
| Z2-C-CON-6150 | Fix Rebar Columns - Z2 - B1 | 1735
| Z2-C-CON-6190 | Fix Rebar Stairs - Z2 - B1 | 32
| Z2-C-CON-6220 | Fix Rebar Slabs - Z2 - B1 | 4028
| Z2-C-CON-6250 | Fix Rebar Core Walls - Z2 - GF | 1707
| Z2-C-CON-6280 | Fix Rebar Columns - Z2 - GF | 2256
| Z2-C-CON-6320 | Fix Rebar Stairs - Z2 - GF | 16
| Z2-C-CON-6350 | Fix Rebar Slabs - Z2 - GF | 7050
| Z2-C-CON-6390 | Fix Rebar Slabs - Z2 - F1 | 3627
| Z2-C-CON-6420 | Fix Rebar Core Walls - Z2 - F1 | 1686
| Z2-C-CON-6450 | Fix Rebar Columns - Z2 - F1 | 2284
| Z2-C-CON-6490 | Fix Rebar Stairs - Z2 - F1 | 16
| Z2-C-CON-6510 | Fix Rebar Slabs - Z2 - F2 | 3726
| Z2-C-CON-6550 | Fix Rebar Core Walls - Z2 - F2 | 1114
| Z2-C-CON-6580 | Fix Rebar Columns - Z2 - F2 | 1558
| Z2-C-CON-6620 | Fix Rebar Stairs - Z2 - F2 | 16
| Z2-C-CON-6650 | Fix Rebar Slabs - Z2 - RF | 3707
| Z2-C-CON-6680 | Fix Rebar Core Walls - Z2 - RF | 1095
| Z2-C-CON-6710 | Fix Rebar Columns - Z2 - RF | 1275
| Z2-C-CON-6750 | Fix Rebar Stairs - Z2 - RF | 14
| Z2-C-CON-6780 | Fix Rebar Slabs - Z2 - SRVF | 3040
| Z2-C-CON-6810 | Fix Rebar Core Walls - Z2 - SRVF | 648
| Z2-C-CON-6840 | Fix Rebar Columns - Z2 - SRVF | 116
| Z2-C-CON-6890 | Fix Rebar Parapet - Z2 - SRVF | 236
| Z2-C-CON-6920 | Fix Rebar Slabs - Z2 - TRF | 303
| Z2-C-CON-6960 | Fix Rebar Parapet - Z2 - TRF | 236
Div 13 | Z2-C-LIFT-10800 | Install Steel Support Beams & Tracks CL B2 to GF | 120
Z3
Div 03 | Z3-C-CON-5870 | Fix Rebar - Z3 - Lift Pit | 249
| Z3-C-CON-5930 | Fix Rebar - Z3 - Raft | 13736
| Z3-C-CON-5970 | Fix Rebar Columns - Z3 - B2 | 2265
| Z3-C-CON-6000 | Fix Rebar Retaining Walls - Z3 - B2 | 1432
| Z3-C-CON-6040 | Fix Rebar Core Walls - Z3 - B2 | 949
| Z3-C-CON-6070 | Fix Rebar Stairs - Z3 - B2 | 32
| Z3-C-CON-6090 | Fix Rebar Retaining Walls - Z3 - B1 | 1138
| Z3-C-CON-6130 | Fix Rebar Core Walls - Z3 - B1 | 914
| Z3-C-CON-6150 | Fix Rebar Columns - Z3 - B1 | 1735
| Z3-C-CON-6190 | Fix Rebar Stairs - Z3 - B1 | 32
| Z3-C-CON-6220 | Fix Rebar Slabs - Z3 - B1 | 4028
| Z3-C-CON-6250 | Fix Rebar Core Walls - Z3 - GF | 1707
| Z3-C-CON-6280 | Fix Rebar Columns - Z3 - GF | 2256
| Z3-C-CON-6320 | Fix Rebar Stairs - Z3 - GF | 16
| Z3-C-CON-6350 | Fix Rebar Slabs - Z3 - GF | 7049
| Z3-C-CON-6390 | Fix Rebar Slabs - Z3 - F1 | 3628
| Z3-C-CON-6420 | Fix Rebar Core Walls - Z3 - F1 | 1686
| Z3-C-CON-6450 | Fix Rebar Columns - Z3 - F1 | 2285
| Z3-C-CON-6490 | Fix Rebar Stairs - Z3 - F1 | 16
| Z3-C-CON-6510 | Fix Rebar Slabs - Z3 - F2 | 3726
| Z3-C-CON-6550 | Fix Rebar Core Walls - Z3 - F2 | 1114
| Z3-C-CON-6580 | Fix Rebar Columns - Z3 - F2 | 1558
| Z3-C-CON-6620 | Fix Rebar Stairs - Z3 - F2 | 16
| Z3-C-CON-6650 | Fix Rebar Slabs - Z3 - RF | 3707
| Z3-C-CON-6680 | Fix Rebar Core Walls - Z3 - RF | 1095
| Z3-C-CON-6710 | Fix Rebar Columns - Z3 - RF | 1275
| Z3-C-CON-6750 | Fix Rebar Stairs - Z3 - RF | 14
| Z3-C-CON-6780 | Fix Rebar Slabs - Z3 - SRVF | 3040
| Z3-C-CON-6810 | Fix Rebar Core Walls - Z3 - SRVF | 648
| Z3-C-CON-6840 | Fix Rebar Columns - Z3 - SRVF | 116
| Z3-C-CON-6890 | Fix Rebar Parapet - Z3 - SRVF | 236
| Z3-C-CON-6920 | Fix Rebar Slabs - Z3 - TRF | 303
| Z3-C-CON-6960 | Fix Rebar Parapet - Z3 - TRF | 236
Waterproof Tech 1817 |  |  | 9345
Z1
Div 02 | C-EW-10450 | Waterproof Membrane on Gunite Wall - Z1-B1 | 200
| C-EW-2430 | Waterproof Membrane on Gunite Wall - Z1-B2 | 200
Div 07 | C-FIN-ENVLP-9540 | Osmotic Cement Waterproof - GF to SRVF (Elev. 1 & 4) | 861
| Z123-C-FIN-18510 | Foam Concrete - Z123 - TRF | 980
| Z123-C-FIN-18520 | 4mm Waterproof Membrane Wet Area - Z123 - TRF | 980
| Z123-C-FIN-18530 | Protection Screed Wet Area - Z123 - TRF | 980
| Z123-C-FIN-18550 | Polystyrene Thermal Insulation - Z123 - TRF | 17
| Z1-C-FIN-10490 | Waterproof Bath - Z1 - F2 | 17
| Z1-C-FIN-10500 | Protection Screed Bath - Z1 - F2 | 17
| Z1-C-FIN-10590 | Waterproof kitchen/Pantry - Z1 - F2 | 17
| Z1-C-FIN-10600 | Protection Screed kitchen/Pantry - Z1 - F2 | 17
| Z1-C-FIN-10670 | Waterproof Garbage Room - Z1 - F2 | 17
| Z1-C-FIN-10680 | Protection Screed Garbage Room - Z1 - F2 | 17
| Z1-C-FIN-11000 | Waterproof Bath - Z1 - RF | 17
| Z1-C-FIN-11010 | Protection Screed Bath - Z1 - RF | 17
| Z1-C-FIN-11080 | Waterproof kitchen/Pantry - Z1 - RF | 17
| Z1-C-FIN-11090 | Protection Screed kitchen/Pantry - Z1 - RF | 17
| Z1-C-FIN-11150 | Waterproof Garbage Room - Z1 - RF | 17
| Z1-C-FIN-11160 | Protection Screed Garbage Room - Z1 - RF | 17
| Z1-C-FIN-8870 | Waterproof & Screed Garbage Room - Z1 - GF | 17
Z2
Div 02 | C-EW-10460 | Waterproof Membrane on Gunite Wall - Z2-B1 | 200
| Z2-C-EW-10420 | Waterproof Membrane on Gunite Wall - Z2-B2 | 200
Div 07 | C-FIN-ENVLP-9670 | Osmotic Cement Waterproof - GF to SRVF (Elev. 2 & 3) | 861
| Z123-C-FIN-18170 | 4mm Waterproof Membrane Wet Area - Z123 - SRVF | 980
| Z123-C-FIN-18180 | Protection Screed Wet Area - Z123 - SRVF | 980
| Z123-C-FIN-18190 | Polystyrene Thermal Insulation - Z123 - SRVF | 17
| Z123-C-FIN-18200 | Foam Concrete - Z123 - SRVF | 980
| Z123-C-FIN-18330 | Waterproof Filter & Pump Room - Z123 - SRVF | 17
| Z123-C-FIN-18340 | Protection Screed Filter & Pump Room - Z123 - SRVF | 17
| Z2&3-C-FIN-19330 | Protection Screed Wet Area - Z2&3 - F1 | 17
| Z2&3-C-FIN-19380 | Waterproof Wet Area - Z2&3 - F1 | 17
| Z2&3-C-FIN-19580 | Waterproof & Screed Garbage Room - Z2&3 - GF | 17
| Z2&3-C-FIN-20100 | Waterproof kitchen/Pantry - Z2&3 - F2 | 17
| Z2&3-C-FIN-20110 | Protection Screed kitchen/Pantry - Z2&3 - F2 | 17
| Z2&3-C-FIN-20190 | Waterproof Bath - Z2&3 - F2 | 17
| Z2&3-C-FIN-20200 | Protection Screed Bath - Z2&3 - F2 | 17
| Z2&3-C-FIN-20260 | Waterproof Garbage Room - Z2&3 - F2 | 17
| Z2&3-C-FIN-20270 | Protection Screed Garbage Room - Z2&3 - F2 | 17
| Z2&3-C-FIN-20530 | Waterproof kitchen/Pantry - Z2&3 - RF | 17
| Z2&3-C-FIN-20540 | Protection Screed kitchen/Pantry - Z2&3 - RF | 16
| Z2&3-C-FIN-20620 | Waterproof Bath - Z2&3 - RF | 17
| Z2&3-C-FIN-20630 | Protection Screed Bath - Z2&3 - RF | 17
| Z2&3-C-FIN-20690 | Waterproof Garbage Room - Z2&3 - RF | 17
| Z2&3-C-FIN-20700 | Protection Screed Garbage Room - Z2&3 - RF | 17
Z3
Div 02 | C-EW-10490 | Waterproof Membrane on Gunite Wall - Z3-B2 | 200
| C-EW-10520 | Waterproof Membrane on Gunite Wall - Z3-B1 | 200

## MonthlyPlannedCost (hidden)
Note: This report is not for printing, use it for only analysis purpose
Sum of MonthlyPlannedCost | Month ID
BOQ Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Grand Total
Div 01 | 1077139 | 181873 | 176006 | 181873 | 176006 | 181873 | 181873 | 176006 | 181873 | 176006 | 181873 | 181873 | 164272 | 181873 | 176006 | 181873 | 176006 | 181873 | 181873 | 176006 | 181873 | 176006 | 181873 | 181873 | 164272 | 213873 | 5573826
Div 02 | 250225 | 2164514 | 3750590 | 1017197 | 609699 | 110115 | [16 empty] | 149625 | 49875 |  |  | 8101840
Div 03 |  |  |  | 82602 | 628253 | 2260443 | 2566062 | 3083759 | 1144987 | 1602490 | 1825103 | 2164361 | 1953437 | 1834963 | 2360921 | 1097960 | 2159316 | 1515321 | 301599 | 33855 | [6 empty] | 26615432
Div 04 | [10 empty] | 3062 | 3215 | 143434 | 250324 | 365571 | 124738 | 242094 | 277547 | 267180 | 32535 | [6 empty] | 1709700
Div 05 | [11 empty] | 600 |  | 600 | [6 empty] | 97477 | 141804 | 166590 | 25667 |  |  | 432738
Div 06 | [19 empty] | 179000 | 179000 | [5 empty] | 358000
Div 07 | [14 empty] | 3898 | 3898 |  | 92633 | 357917 | 546702 | 19676 | [5 empty] | 1024724
Div 08 | [11 empty] | 41642 | 20821 | 166568 | 104105 | 72874 | 135337 | 145747 | 104105 | 648367 | 955624 | 271960 | 81549 |  |  |  | 2748699
Div 09 | [11 empty] | 170853 | 140646 | 401421 | 288531 | 202863 | 341760 | 319765 | 887988 | 1122149 | 1963092 | 1369602 | 621536 | 438602 | 2129 |  | 8270937
Div 10 | [5 empty] | 21000 | 6125 | 14875 |  |  |  | 37910 | 46708 | 18189 | 64916 | 726566 | 101135 | 54126 | 119130 | 195439 | 253799 | 305132 | 195503 | 153939 | 34210 |  | 2348702
Div 11 | [11 empty] | 7810 | 74199 | 114040 | 117121 | 172172 | 125344 | 213121 | 373704 | 260315 | 154652 | 106165 | 52076 | 11000 |  |  | 1781719
Div 12 | [11 empty] | 29754 | 301944 | 404642 | 712387 | 554034 | 692326 | 844766 | 1060698 | 4035759 | 1393786 | 465547 | 259584 | 102761 | 35571 | 58167 | 10951726
Div 13 | [18 empty] | 145846 | 507221 | 901007 | 1015598 | 944529 | 285739 | 2063 |  | 3802003
Div 14 | [17 empty] | 13645 | 24821 | 34146 | 13782 | 46282 | 15427 |  |  |  | 148103
Div 15 | [10 empty] | 11466 | 43384 | 337325 | 910723 | 568939 | 1848080 | 793948 | 1046991 | 800489 | 2937476 | 1521926 | 1415735 | 631777 | 4216 | 272 | 2856 | 12875603
Grand Total | 1327364 | 2346387 | 3926596 | 1281672 | 1413958 | 2573431 | 2754060 | 3274640 | 1326860 | 1778496 | 2021504 | 2681402 | 3182786 | 4283343 | 4762395 | 4985058 | 4767266 | 4705535 | 4625350 | 10708970 | 7635694 | 5313831 | 3300069 | 1253672 | 238517 | 274896 | 86743752
Earned Values
Sum of EarnedCost | Column Labels
Row Labels | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Div 01 | 4279886 | 2578191 | 2578191 |  | 2727796 | 93752 | 996119 | 149605 | 154592 | 93752 |  | 515638 | 703143 | 1171905 | 4687620 | 154592 | 149605 | 154592 | 1075809 | 149605 | 154592 | 149605 | 154592 | 154592 | 139631 | 154592
Div 02 | 229764 | 1198314 | 3030148 | 302990 | 1311173 | 4405 | [16 empty] | 127181 | 42394
Div 03 |  |  |  |  | 275003 | 312584 | 1285232 | 633079 | 2868808 | 51103 | 347469 | 991831 | 1096297 | 815877 | 1403163 | 2269968 | 1835414 | 941565 | 282633 | 28777
Div 04 | [11 empty] | 1824 | 73568 | 391013 | 440143 | 117404 | 205780 | 217305 | 228338 | 27655
Div 05 | [11 empty] | 60 |  |  |  | 150 |  |  |  |  | 82856 | 120534 | 141601 | 21817
Div 06 | [19 empty] | 152150 | 152150
Div 07 | [15 empty] | 6626 |  | 10206 | 336012 | 464693 | 25973
Div 08 | [11 empty] | 6246 | 11681 | 91613 | 88490 | 110873 | 115037 | 80348 | 93268 | 551112 | 430733 | 231167 | 69317
Div 09 | [11 empty] | 26882 | 91821 | 177651 | 199613 | 433037 | 290496 | 242019 | 768215 | 953831 | 1641000 | 1164161 | 528305 | 372812 | 1810
Div 10 | [6 empty] | 4463 | 5206 | 12644 |  |  | 5531 | 30675 | 6088 | 55611 | 637550 | 85964 | 36843 | 97602 | 166124 | 210032 | 259363 | 166177 | 130849 | 29078
Div 11 | [12 empty] | 75370 | 64020 | 147128 | 238021 | 106542 | 197216 | 317648 | 221268 | 110965 | 90240 | 44264 | 9350
Div 12 | [12 empty] | 297941 | 218237 | 639064 | 1062963 | 588476 | 670554 | 849813 | 3430396 | 1022866 | 395717 | 220646 | 87346 | 30236 | 0
Div 13 | [18 empty] | 123969 | 431137 | 783760 | 863258 | 802845 | 242877 | 1754
Div 14 | [17 empty] | 5665 | 23930 | 29025 | 11715 | 39341 | 13113
Div 15 | [10 empty] | 12508 | 11884 | 242119 | 863766 | 233345 | 2349640 | 674855 | 684275 | 719042 | 2496856 | 1222897 | 1203376 | 537013 | 3583 | 231 | 0
Months | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31 | 2020-11-30 | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31
Planned Value | 1327364 | 2346387 | 3926596 | 1281672 | 1413958 | 2573431 | 2754060 | 3274640 | 1326860 | 1778496 | 2021504 | 2681402 | 3182786 | 4283343 | 4762395 | 4985058 | 4767266 | 4705535 | 4625350 | 10708970 | 7635694 | 5313831 | 3300069 | 1253672 | 238517 | 274896
Planned % | 1.53% | 2.705% | 4.527% | 1.478% | 1.63% | 2.967% | 3.175% | 3.775% | 1.53% | 2.05% | 2.33% | 3.091% | 3.669% | 4.938% | 5.49% | 5.747% | 5.496% | 5.425% | 5.332% | 12.35% | 8.803% | 6.126% | 3.804% | 1.445% | 0.275% | 0.3169%
Cum.Planned Value | 1327364 | 3673751 | 7600347 | 8882019 | 10295977 | 12869408 | 15623468 | 18898108 | 20224968 | 22003464 | 24024968 | 26706370 | 29889156 | 34172499 | 38934894 | 43919952 | 48687218 | 53392753 | 58018103 | 68727073 | 76362767 | 81676598 | 84976667 | 86230339 | 86468856 | 86743752
Cum.Planned % | 1.53% | 4.235% | 8.762% | 10.24% | 11.87% | 14.84% | 18.01% | 21.79% | 23.32% | 25.37% | 27.7% | 30.79% | 34.46% | 39.39% | 44.88% | 50.63% | 56.13% | 61.55% | 66.88% | 79.23% | 88.03% | 94.16% | 97.96% | 99.41% | 99.68% | 100%
Actual Value | 4509650 | 3776505 | 5608339 | 302990 | 4313972 | 410741 | 2285814 | 787890 | 3036044 | 144855 | 359977 | 1559896 | 2622615 | 3800170 | 7894177 | 7380824 | 4052169 | 3240588 | 4916279 | 9102629 | 5849539 | 4516762 | 2805054 | 1065620 | 202740 | 154592
Actual % | 5.199% | 4.354% | 6.465% | 0.3493% | 4.973% | 0.4735% | 2.635% | 0.9083% | 3.5% | 0.167% | 0.415% | 1.798% | 3.023% | 4.381% | 9.101% | 8.509% | 4.671% | 3.736% | 5.668% | 10.49% | 6.743% | 5.207% | 3.234% | 1.228% | 0.2337% | 0.1782%
Cum. Actual Value | 4509650 | 3776505 | 5608339 | 302990 | 4313972 | 410741 | 2285814 | 787890 | 3036044 | 144855 | 359977 | 1559896 | 2622615 | 3800170 | 7894177 | 7380824 | 4052169 | 3240588 | 4916279 | 9102629 | 5849539 | 4516762 | 2805054 | 1065620 | 202740 | 154592
Cum.Actual % | 5.199% | 9.552% | 16.02% | 16.37% | 21.34% | 21.81% | 24.45% | 25.36% | 28.86% | 29.02% | 29.44% | 31.24% | 34.26% | 38.64% | 47.74% | 56.25% | 60.92% | 64.66% | 70.33% | 80.82% | 87.56% | 92.77% | 96% | 97.23% | 97.47% | 97.64%
Duration of Project | 30 | 61 | 91 | 122 | 152 | 183 | 214 | 244 | 275 | 305 | 336 | 367 | 397 | 428 | 458 | 489 | 519 | 550 | 581 | 611 | 642 | 672 | 703 | 734 | 764 | 790
Months | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31 | 2020-11-30 | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31
BAC | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752 | 86743752
SAC | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790
AT | 30 | 61 | 91 | 122 | 152 | 183 | 214 | 244 | 275 | 305 | 336 | 367 | 397 | 428 | 458 | 489 | 519 | 550 | 581 | 611 | 642 | 672 | 703 | 734 | 764 | 790
PAR | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177 | 109802.2177
ES | 41.0707 | 34.3937 | 51.0767 | 2.7594 | 39.2886 | 3.7407 | 20.8176 | 7.1755 | 27.6501 | 1.3192 | 3.2784 | 14.2064 | 23.8849 | 34.6092 | 71.8945 | 67.2193 | 36.9043 | 29.513 | 44.7739 | 82.9002 | 53.2734 | 41.1354 | 25.5464 | 9.7049 | 1.8464 | 1.4079
TV | 11.0707 | -26.6063 | -39.9233 | -119.2406 | -112.7114 | -179.2593 | -193.1824 | -236.8245 | -247.3499 | -303.6808 | -332.7216 | -352.7936 | -373.1151 | -393.3908 | -386.1055 | -421.7807 | -482.0957 | -520.487 | -536.2261 | -528.0998 | -588.7266 | -630.8646 | -677.4536 | -724.2951 | -762.1536 | -788.5921
TPI | 1.369 | 0.56383 | 0.56128 | 0.022618 | 0.25848 | 0.020441 | 0.097278 | 0.029408 | 0.10055 | 0.0043254 | 0.0097572 | 0.03871 | 0.060163 | 0.080863 | 0.15697 | 0.13746 | 0.071106 | 0.05366 | 0.077064 | 0.13568 | 0.08298 | 0.061213 | 0.036339 | 0.013222 | 0.0024168 | 0.0017822
Target Productivty/day | 2688.5197 | 2802.8464 | 2923.1402 | 3058.7949 | 3202.6254 | 3366.1862 | 3547.3524 | 3742.2619 | 3967.5243 | 4212.9381 | 4500.6057 | 4830.4374 | 5199.173 | 5644.4061 | 6154.4428 | 6788.289 | 7539.7601 | 8513.6458 | 9776.4354 | 11414.9441 | 13805.9122 | 17315.8898 | 23485.9195 | 36487.0536 | 78587.5 | #DIV/0!
Cumm. PAR | 109802.2177 | 219604.4354 | 329406.6532 | 439208.8709 | 549011.0886 | 658813.3063 | 768615.5241 | 878417.7418 | 988219.9595 | 1098022.1772 | 1207824.3949 | 1317626.6127 | 1427428.8304 | 1537231.0481 | 1647033.2658 | 1756835.4835 | 1866637.7013 | 1976439.919 | 2086242.1367 | 2196044.3544 | 2305846.5722 | 2415648.7899 | 2525451.0076 | 2635253.2253 | 2745055.443 | 2854857.6608
Cumm. Target PAR | 2688.5197 | 5491.3661 | 8414.5063 | 11473.3012 | 14675.9266 | 18042.1128 | 21589.4652 | 25331.7271 | 29299.2514 | 33512.1895 | 38012.7952 | 42843.2326 | 48042.4056 | 53686.8117 | 59841.2545 | 66629.5435 | 74169.3037 | 82682.9495 | 92459.3849 | 103874.329 | 117680.2412 | 134996.131 | 158482.0506 | 194969.1041 | 273556.6041
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Monthly Planned B.Hrs (hidden)
MonthID
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Grand Total
Sum of Monthly Planned Hrs | 1031 | 450 | 5065 | 8969 | 5685 | 28107 | 23768 | 44582 | 26622 | 28647 | 33924 | 48531 | 49656 | 60096 | 57067 | 50242 | 51555 | 44842 | 60706 | 69315 | 41806 | 26773 | 11668 | 11236 | 388 | 567 | 791298
MonthID
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Sum of Earned Hrs | 802 | 137 | 1627 | 1249 | 10412 | 1712 | 6833 | 9973 | 44744 | 941 | 5197 | 23486 | 29331 | 39653 | 41226 | 81767 | 43815 | 33051 | 52395 | 58909 | 33022 | 22722 | 9637 | 9400 | 329 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Planned hrs | 1031 | 450 | 5065 | 8969 | 5685 | 28107 | 23768 | 44582 | 26622 | 28647 | 33924 | 48531 | 49656 | 60096 | 57067 | 50242 | 51555 | 44842 | 60706 | 69315 | 41806 | 26773 | 11668 | 11236 | 388 | 567
Cumm. Planned Hrs | 1031 | 1481 | 6546 | 15515 | 21200 | 49307 | 73075 | 117657 | 144279 | 172926 | 206850 | 255381 | 305037 | 365133 | 422200 | 472442 | 523997 | 568839 | 629545 | 698860 | 740666 | 767439 | 779107 | 790343 | 790731 | 791298
Planned % | 0.1303% | 0.05687% | 0.6401% | 1.133% | 0.7184% | 3.552% | 3.004% | 5.634% | 3.364% | 3.62% | 4.287% | 6.133% | 6.275% | 7.595% | 7.212% | 6.349% | 6.515% | 5.667% | 7.672% | 8.76% | 5.283% | 3.383% | 1.475% | 1.42% | 0.04903% | 0.07165%
Cum. Planned % | 0.1303% | 0.1872% | 0.8272% | 1.961% | 2.679% | 6.231% | 9.235% | 14.87% | 18.23% | 21.85% | 26.14% | 32.27% | 38.55% | 46.14% | 53.36% | 59.7% | 66.22% | 71.89% | 79.56% | 88.32% | 93.6% | 96.98% | 98.46% | 99.88% | 99.93% | 100%
Earned hrs | 802 | 137 | 1627 | 1249 | 10412 | 1712 | 6833 | 9973 | 44744 | 941 | 5197 | 23486 | 29331 | 39653 | 41226 | 81767 | 43815 | 33051 | 52395 | 58909 | 33022 | 22722 | 9637 | 9400 | 329 | 0
Cumm. Earned Hrs | 802 | 939 | 2566 | 3815 | 14227 | 15939 | 22772 | 32745 | 77489 | 78430 | 83627 | 107113 | 136444 | 176097 | 217323 | 299090 | 342905 | 375956 | 428351 | 487260 | 520282 | 543004 | 552641 | 562041 | 562370 | 562370
Earned % | 0.1014% | 0.01731% | 0.2056% | 0.1578% | 1.316% | 0.2164% | 0.8635% | 1.26% | 5.655% | 0.1189% | 0.6568% | 2.968% | 3.707% | 5.011% | 5.21% | 10.33% | 5.537% | 4.177% | 6.621% | 7.445% | 4.173% | 2.871% | 1.218% | 1.188% | 0.04158% | 0%
Cumm. Earned % | 0.1014% | 0.1187% | 0.3243% | 0.4821% | 1.798% | 2.014% | 2.878% | 4.138% | 9.793% | 9.912% | 10.57% | 13.54% | 17.24% | 22.25% | 27.46% | 37.8% | 43.33% | 47.51% | 54.13% | 61.58% | 65.75% | 68.62% | 69.84% | 71.03% | 71.07% | 71.07%

## MonthDates (hidden)
MonthID | MonthDates
1 | 2020-02-29
2 | 2020-03-31
3 | 2020-04-30
4 | 2020-05-31
5 | 2020-06-30
6 | 2020-07-31
7 | 2020-08-31
8 | 2020-09-30
9 | 2020-10-31
10 | 2020-11-30
11 | 2020-12-31
12 | 2021-01-31
13 | 2021-02-28
14 | 2021-03-31
15 | 2021-04-30
16 | 2021-05-31
17 | 2021-06-30
18 | 2021-07-31
19 | 2021-08-31
20 | 2021-09-30
21 | 2021-10-31
22 | 2021-11-30
23 | 2021-12-31
24 | 2022-01-31
25 | 2022-02-28
26 | 2022-03-31

## WeekDates (hidden)
WeekID | WeekDates | Month Name | Year
1 | 2020-02-02 | February | 2020
2 | 2020-02-09 | February | 2020
3 | 2020-02-16 | February | 2020
4 | 2020-02-23 | February | 2020
5 | 2020-03-01 | March | 2020
6 | 2020-03-08 | March | 2020
7 | 2020-03-15 | March | 2020
8 | 2020-03-22 | March | 2020
9 | 2020-03-29 | March | 2020
10 | 2020-04-05 | April | 2020
11 | 2020-04-12 | April | 2020
12 | 2020-04-19 | April | 2020
13 | 2020-04-26 | April | 2020
14 | 2020-05-03 | May | 2020
15 | 2020-05-10 | May | 2020
16 | 2020-05-17 | May | 2020
17 | 2020-05-24 | May | 2020
18 | 2020-05-31 | May | 2020
19 | 2020-06-07 | June | 2020
20 | 2020-06-14 | June | 2020
21 | 2020-06-21 | June | 2020
22 | 2020-06-28 | June | 2020
23 | 2020-07-05 | July | 2020
24 | 2020-07-12 | July | 2020
25 | 2020-07-19 | July | 2020
26 | 2020-07-26 | July | 2020
27 | 2020-08-02 | August | 2020
28 | 2020-08-09 | August | 2020
29 | 2020-08-16 | August | 2020
30 | 2020-08-23 | August | 2020
31 | 2020-08-30 | August | 2020
32 | 2020-09-06 | September | 2020
33 | 2020-09-13 | September | 2020
34 | 2020-09-20 | September | 2020
35 | 2020-09-27 | September | 2020
36 | 2020-10-04 | October | 2020
37 | 2020-10-11 | October | 2020
38 | 2020-10-18 | October | 2020
39 | 2020-10-25 | October | 2020
40 | 2020-11-01 | November | 2020
41 | 2020-11-08 | November | 2020
42 | 2020-11-15 | November | 2020
43 | 2020-11-22 | November | 2020
44 | 2020-11-29 | November | 2020
45 | 2020-12-06 | December | 2020
46 | 2020-12-13 | December | 2020
47 | 2020-12-20 | December | 2020
48 | 2020-12-27 | December | 2020
49 | 2021-01-03 | January | 2021
50 | 2021-01-10 | January | 2021
51 | 2021-01-17 | January | 2021
52 | 2021-01-24 | January | 2021
53 | 2021-01-31 | January | 2021
54 | 2021-02-07 | February | 2021
55 | 2021-02-14 | February | 2021
56 | 2021-02-21 | February | 2021
57 | 2021-02-28 | February | 2021
58 | 2021-03-07 | March | 2021
59 | 2021-03-14 | March | 2021
60 | 2021-03-21 | March | 2021
61 | 2021-03-28 | March | 2021
62 | 2021-04-04 | April | 2021
63 | 2021-04-11 | April | 2021
64 | 2021-04-18 | April | 2021
65 | 2021-04-25 | April | 2021
66 | 2021-05-02 | May | 2021
67 | 2021-05-09 | May | 2021
68 | 2021-05-16 | May | 2021
69 | 2021-05-23 | May | 2021
70 | 2021-05-30 | May | 2021
71 | 2021-06-06 | June | 2021
72 | 2021-06-13 | June | 2021
73 | 2021-06-20 | June | 2021
74 | 2021-06-27 | June | 2021
75 | 2021-07-04 | July | 2021
76 | 2021-07-11 | July | 2021
77 | 2021-07-18 | July | 2021
78 | 2021-07-25 | July | 2021
79 | 2021-08-01 | August | 2021
80 | 2021-08-08 | August | 2021
81 | 2021-08-15 | August | 2021
82 | 2021-08-22 | August | 2021
83 | 2021-08-29 | August | 2021
84 | 2021-09-05 | September | 2021
85 | 2021-09-12 | September | 2021
86 | 2021-09-19 | September | 2021
87 | 2021-09-26 | September | 2021
88 | 2021-10-03 | October | 2021
89 | 2021-10-10 | October | 2021
90 | 2021-10-17 | October | 2021
91 | 2021-10-24 | October | 2021
92 | 2021-10-31 | October | 2021
93 | 2021-11-07 | November | 2021
94 | 2021-11-14 | November | 2021
95 | 2021-11-21 | November | 2021
96 | 2021-11-28 | November | 2021
97 | 2021-12-05 | December | 2021
98 | 2021-12-12 | December | 2021
99 | 2021-12-19 | December | 2021
100 | 2021-12-26 | December | 2021
101 | 2022-01-02 | January | 2022
102 | 2022-01-09 | January | 2022
103 | 2022-01-16 | January | 2022
104 | 2022-01-23 | January | 2022
105 | 2022-01-30 | January | 2022
106 | 2022-02-06 | February | 2022
107 | 2022-02-13 | February | 2022
108 | 2022-02-20 | February | 2022
109 | 2022-02-27 | February | 2022
110 | 2022-03-06 | March | 2022
111 | 2022-03-13 | March | 2022
112 | 2022-03-20 | March | 2022
113 | 2022-03-27 | March | 2022
114 | 2022-04-03 | April | 2022

## ActivitySum (hidden)
Activity ID | Activity Name | BudgetCOst | BudgetHrs
A10890 | Traffic Deck Coating Drive - Z2 - B1 | 138667 | 630
A10910 | Install Road Signages Drive - Z2 - B1 |  | 20
A10950 | Traffic Deck Coating Drive - Z2 - B2 | 138666 | 630
A10970 | Install Road Signages Drive - Z2 - B2 |  | 20
A11210 | Fix Windows & Door Frame & Leaf - F2 | 20821 | 224
A11220 | Fix Ironmongery - F2 | 20821 | 222
A11230 | Signages - F2 |  | 20
A11260 | Fix Windows & Door Frame & Leaf - RF | 20822 | 224
A11270 | Fix Ironmongery - RF | 20821 | 224
A11280 | Signages - RF |  | 20
A11400 | Fix Flower Box | 107000 | 212
A11410 | Fix Outdoor Green Area | 19950 | 140
A11440 | Installation of BMU System | 55001 | 499
A11450 | External Drainage Pipes & Connections | 80001 | 99
A7100 | Fix Windows & Door Frame & Leaf - F2 | 20820 | 222
A7110 | Fix Ironmongery - F2 | 20821 | 222
A7120 | Signages - F2 |  | 20
A7180 | Fix Windows & Door Frame & Leaf - RF | 20821 | 224
A7190 | Fix Ironmongery - RF | 20821 | 222
A7200 | Signages - RF |  | 20
A9670 | Casting Service Manholes | 78300 | 166
A9690 | Fix Pavement Tiles & Granite Colored Land Scaping | 27930 | 6723
A9700 | Install Man Holes Covers | 4400 | 167
A9710 | Install Precast Wheel Stoper | 4259 | 100
A9720 | Trafic & Road Marking | 4259 | 100
A9740 | Traffic Deck Coating Drive Way - B2 | 138667 | 631
A9750 | Install Steel Grating Drive Way - B2 |  | 50
A9760 | Install Road Signages Drive Way - B2 |  | 50
A9790 | Traffic Marking Drive Way - B2 | 138667 | 630
A9800 | Install Steel Grating Drive Way - B1 |  | 51
A9810 | Traffic Deck Coating Drive Way - B1 | 138667 | 631
A9830 | Install Road Signages Drive Way - B1 |  | 50
A9840 | Traffic Marking Drive Way - B1 | 138666 | 630
A9860 | Install Stamped Concrete | 199500
ADCE-MALL-EL-2280 | Installation of HV Panels, Transformers & etc by AADC | 1210608
ADCE-MALL-WS-2200 | Installation of Water Meter & AADC Approval | 34210 | 100
C-EW-10370 | Excavation Stage 1 - Z1 | 293640 | 2271
C-EW-10380 | Strut Pipe Bracing - Z1 | 162250
C-EW-10390 | Excavation Stage 2 - Z1 | 293641 | 2272
C-EW-10400 | Excavation Stage 2 - Z2&3 | 440461 | 3408
C-EW-10410 | Gunite Wall - Z2 | 228837 | 333
C-EW-10430 | Strut Pipe Bracing - Z2&3 | 254480
C-EW-10440 | Excavation Stage 1 - Z2&3 | 348229 | 3409
C-EW-10450 | Waterproof Membrane on Gunite Wall - Z1-B1 |  | 200
C-EW-10460 | Waterproof Membrane on Gunite Wall - Z2-B1 |  | 200
C-EW-10480 | Gunite Wall - Z3 |  | 333
C-EW-10490 | Waterproof Membrane on Gunite Wall - Z3-B2 |  | 200
C-EW-10520 | Waterproof Membrane on Gunite Wall - Z3-B1 |  | 200
C-EW-2420 | Gunite Wall - Z1 | 152558 | 333
C-EW-2430 | Waterproof Membrane on Gunite Wall - Z1-B2 |  | 200
C-FIN-ENVLP-9490 | Fix Brackets for Natural Stone - GF to SRVF (Elev. 1 & 4) | 107625 | 286
C-FIN-ENVLP-9510 | Fix Natural Stone All types- GF to SRVF (Elev. 1 & 4) | 968627 | 6241
C-FIN-ENVLP-9530 | Fix Aluminum Glazing Pannels - GF to SRVF (Elev. 1 & 4) | 822232 | 2736
C-FIN-ENVLP-9540 | Osmotic Cement Waterproof - GF to SRVF (Elev. 1 & 4) | 55965 | 1149
C-FIN-ENVLP-9550 | Fix Steel Decore - GF to SRVF (Elev. 1 & 4) | 59364 | 1508
C-FIN-ENVLP-9610 | Fix Wooden Decorarive Features (Elev. 1 & 4) | 104055 | 598
C-FIN-ENVLP-9640 | Install Aluminum & Wood Roof Features | 70700 | 611
C-FIN-ENVLP-9650 | Install Aluminum Wood Ground Features | 60000 | 612
C-FIN-ENVLP-9670 | Osmotic Cement Waterproof - GF to SRVF (Elev. 2 & 3) | 55965 | 1149
C-FIN-ENVLP-9680 | Fix Aluminum Glazing Pannels - GF to SRVF (Elev. 2 & 3) | 822232 | 2737
C-FIN-ENVLP-9690 | Fix Brackets for Natural Stone - GF to SRVF (Elev. 2 & 3) | 107625 | 290
C-FIN-ENVLP-9700 | Fix Natural Stone All types- GF to SRVF (Elev. 2 & 3) | 965476 | 6241
C-FIN-ENVLP-9710 | Fix Steel Decore - GF to SRVF (Elev. 2 & 3) | 59364 | 1940
C-FIN-ENVLP-9720 | Fix Wooden Decorarive Features (Elev. 2 & 3) | 104055 | 598
C-FIN-ENVLP-9730 | External Plaster - GF to SRVF (Elev. 1 & 4) | 1822 | 165
C-FIN-ENVLP-9740 | External Plaster - GF to SRVF (Elev. 2 & 3) | 1822 | 165
C-SHRNG-DCE-C-2330 | Place Guide Wall - Z1 | 162250 | 249
C-SHRNG-DCE-C-2340 | Install Shoring System - Z1 | 2016502
C-SHRNG-DCE-C-2350 | Install Capping Beam - Z1 | 180856 | 2461
C-SHRNG-DCE-C-2360 | Place Guide Wall - Z2&3 | 162250 | 249
C-SHRNG-DCE-C-2370 | Install Shoring System - Z2&3 | 2987501
C-SHRNG-DCE-C-2380 | Install Capping Beam - Z2&3 | 271284 | 3692
PRL-MOB-1020 | Site Office Establishment | 767001 | 162
PRL-MOB-1050 | Project Sign Boards and Hoarding | 60000 | 162
PRL-MOB-1100 | Yards & Stores Establishment | 80000 | 190
PRL-MOB-SCW-1600 | Soil Investigation & Report Submit | 55000
PRL-MOB-SCW-2310 | Dewatering System Installation | 95000
PRL-MOB-SCW-2320 | Demolition of Existing Structure | 140001
PRL-MOB-SCW-2330 | Clearing Existing Utilities | 39000 | 495
PRL-RCR-6980 | Recurring Preliminaries through out the project | 4687620
T&C-10000 | Water Supply System Testing & Commissioning | 7000 | 100
T&C-10010 | Water Drainage System Testing & Commissioning | 7000 | 100
T&C-10020 | LV Pannels & Live Accessories Testing & Commissioning |  | 246
T&C-10030 | Busbar Testing & Commissioning |  | 250
T&C-10040 | Telephone & Voice Evac. System Testing & Commissioning | 1428 | 250
T&C-10050 | Emergency Lighting System Testing & Commissioning | 1428 | 250
T&C-10060 | Access Control System Testing & Commissioning | 1428 | 250
T&C-10070 | Fire Alarm System Testing & Commissioning | 1428 | 250
T&C-10080 | Passenger Lift Testing & Commissioning | 3332 | 101
T&C-10090 | Travelators Testing & Commissioning | 3332 | 101
T&C-10110 | Escalator Testing & Commissioning | 3334 | 100
T&C-10120 | BMS Testing & Commissioning | 1428 | 249
T&C-10130 | Security System Testing & Commissioning | 1428 | 250
T&C-9920 | Chilled Water Pump Testing | 27666 | 100
T&C-9930 | Chilled Water System Flushing & Cleaning | 27667 | 101
T&C-9940 | HVAC Equipment Testing & Commissioning | 27668 | 98
T&C-9950 | Air Balancing FCU & FAHU | 27668 | 98
T&C-9960 | Chilled Water Balancing | 27666 | 100
T&C-9970 | HVAC System Performance Test |  | 104
T&C-9980 | Fire Fighting System Testing & Commissioning | 11000 | 101
T&C-9990 | LPG System Testing & Commissioning |  | 168
Z1-11460 | Post Tensioning the Slab - Z1 - F1 | 25092 | 8
Z1-11470 | Post Tensioning the Slab - Z1 - F2 | 25471 | 8
Z1-11480 | Post Tensioning the Slab - Z1 - RF | 25392 | 8
Z1-11490 | Post Tensioning the Slab - Z1 - SRVF | 21331 | 8
Z123-C-FIN-18110 | Masonry Works Dry Area - Z123 - SRVF | 32535 | 402
Z123-C-FIN-18120 | Plaster Works Dry Area - Z123 - SRVF | 11122 | 1375
Z123-C-FIN-18130 | Fix Door Subframes Dry Area - Z123 - SRVF | 20821 | 71
Z123-C-FIN-18160 | Roof Floor Terrazo Tiles Wet Area - Z123 - SRVF | 231184 | 12242
Z123-C-FIN-18170 | 4mm Waterproof Membrane Wet Area - Z123 - SRVF | 130693 | 1960
Z123-C-FIN-18180 | Protection Screed Wet Area - Z123 - SRVF | 130693 | 1960
Z123-C-FIN-18190 | Polystyrene Thermal Insulation - Z123 - SRVF | 3898 | 34
Z123-C-FIN-18200 | Foam Concrete - Z123 - SRVF | 130694 | 1960
Z123-C-FIN-18210 | Fix Rain Water Outlets - Z123 - SRVF | 6000 | 100
Z123-C-FIN-18220 | Install Aluminum Shades over FAHU - Z123 - SRVF | 42000 | 286
Z123-C-FIN-18310 | Wall Paint (Acrylic) Filter & Pump Room - Z123 - SRVF | 2432 | 94
Z123-C-FIN-18320 | Floor Epoxy Filter & Pump Room - Z123 - SRVF | 4834 | 16
Z123-C-FIN-18330 | Waterproof Filter & Pump Room - Z123 - SRVF | 3898 | 34
Z123-C-FIN-18340 | Protection Screed Filter & Pump Room - Z123 - SRVF | 3898 | 34
Z123-C-FIN-18350 | Ceiling Paint (Acrylic) Filter & Pump Room - Z123 - SRVF | 2432 | 58
Z123-C-FIN-18360 | Install Aluminum Shades over Chillers - Z123 - SRVF | 42000 | 286
Z123-C-FIN-18370 | Install Aluminum Shades over GRP Water Tank - Z123 - SRVF | 43910 | 224
Z123-C-FIN-18390 | Fix False Ceiling Suspension Lift Lobby - Z123 - SRVF | 1932 | 31
Z123-C-FIN-18400 | Porcelain Floor Tiles Lift Lobby - Z123 - SRVF | 6246 | 115
Z123-C-FIN-18410 | Wall Paint (Emulsion) Lift Lobby - Z123 - SRVF | 10000 | 647
Z123-C-FIN-18420 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z123 - SRVF | 1932 | 31
Z123-C-FIN-18430 | Fix False Ceiling Gypsum Board Lift Lobby - Z123 - SRVF | 1932 | 52
Z123-C-FIN-18440 | Fix MEP Droppers Lift Lobby - Z123 - SRVF | 18389 | 200
Z123-C-FIN-18450 | Ceiling Paint (Acrylic) GSM & MCC Rooms - Z123 - SRVF | 2432 | 59
Z123-C-FIN-18460 | Floor Epoxy GSM & MCC Rooms - Z123 - SRVF | 4833 | 17
Z123-C-FIN-18470 | Wall Paint (Acrylic) GSM & MCC Rooms - Z123 - SRVF | 2432 | 94
Z123-C-FIN-18480 | Floor Paint (Antifungal) Lift Shaft - Z123 - SRVF | 8203 | 271
Z123-C-FIN-18490 | Wall Paint (Antifungal) Lift Shaft - Z123 - SRVF | 8203 | 271
Z123-C-FIN-18500 | Fix Rain Water Outlets - Z123 - TRF | 6000 | 100
Z123-C-FIN-18510 | Foam Concrete - Z123 - TRF | 130693 | 1960
Z123-C-FIN-18520 | 4mm Waterproof Membrane Wet Area - Z123 - TRF | 130693 | 1960
Z123-C-FIN-18530 | Protection Screed Wet Area - Z123 - TRF | 130693 | 1960
Z123-C-FIN-18550 | Polystyrene Thermal Insulation - Z123 - TRF | 3898 | 32
Z123-C-FIN-18560 | Roof Floor Terrazo Tiles Wet Area - Z123 - TRF | 3898 | 192
Z123-C-FIN-8540 | Fix Windows & Door Frame & Leaf - Z123 - SRVF | 20821 | 222
Z123-C-FIN-8550 | Fix Ironmongery - Z123 - SRVF | 20821 | 222
Z123-C-MEP-14740 | Fix Drainage & Water Supply Pipes Block Wall - Z123 - SRVF | 6591 | 50
Z123-C-MEP-14750 | Fix G.I Box and conduits - Z123 - SRVF | 26755 | 50
Z123-C-MEP-14760 | Fix ELV Trunkings - Z123 - SRVF | 35620 | 250
Z123-C-MEP-14770 | Pull ELV Cables - Z123 - SRVF | 46003 | 101
Z123-C-MEP-14780 | Fix Power Cable Trays - Z123 - SRVF | 32905 | 500
Z123-C-MEP-14790 | Pull Electricl Wires (Ceiling & Walls) - Z123 - SRVF | 10782 | 101
Z123-C-MEP-14800 | Pull Earthing & Power Cables - Z123 - SRVF | 84717 | 250
Z123-C-MEP-14810 | Fix DBs - Z123 - SRVF | 64069 | 50
Z123-C-MEP-14820 | Cable Terminations - Z123 - SRVF | 61108 | 34
Z123-C-MEP-14830 | Fix Fire Fighting Pipes - Z123 - SRVF | 59346 | 500
Z123-C-MEP-14840 | Fix Chill Water Pipes - Z123 - SRVF | 106571 | 333
Z123-C-MEP-14850 | Fix HVAC Ducts & Insulation - Z123 - SRVF | 205840 | 667
Z123-C-MEP-14860 | Fix Fire Fighting Dropers - Z123 - SRVF | 10627 | 50
Z123-C-MEP-14870 | Fix FCU - Z123 - SRVF | 48984 | 100
Z123-C-MEP-14880 | Fix Water Supply Pipes - Z123 - SRVF | 6591 | 250
Z123-C-MEP-14900 | Fix Drainage Pipes - Z123 - SRVF | 9368 | 250
Z123-C-MEP-14910 | Fix CCTV Devices - Z123 - SRVF | 78093 | 50
Z123-C-MEP-14920 | Fix Light Fixtures - Z123 - SRVF | 115828 | 100
Z123-C-MEP-14930 | Fix Switches, Sockets & Isolators - Z123 - SRVF | 11417 | 49
Z123-C-MEP-14940 | Fix Fire Alarm Devices - Z123 - SRVF | 51070 | 50
Z123-C-MEP-14950 | Fix Telephone & Voice Evac. Devices - Z123 - SRVF | 43578 | 250
Z123-C-MEP-14960 | Fix LCS & ACS Devices - Z123 - SRVF | 28739 | 50
Z123-C-MEP-14970 | Fix Emergency & Exit Lights - Z123 - SRVF | 45974 | 50
Z123-C-MEP-14980 | Fix Fire Hose Cabinets & Hose Reels - Z123 - SRVF | 12692 | 51
Z123-C-MEP-14990 | Fix Sprinklers - Z123 - SRVF | 20692 | 500
Z123-C-MEP-15000 | Fix Grills & Diffusers - Z123 - SRVF | 17846 | 286
Z123-C-MEP-15010 | Fix Water Heater & Sanitary Accessories - Z123 - SRVF | 75575 | 333
Z123-C-MEP-15020 | Fix Gas Detectors - Z123 - SRVF | 12341 | 167
Z123-C-MEP-15030 | Fix FAHU - Z123 - SRVF | 446000 | 400
Z123-C-MEP-15040 | Fix Chillers - Z123 - SRVF | 2570001 | 845
Z123-C-MEP-15050 | Fix Extract Fans - Z123 - SRVF | 452180 | 200
Z123-C-MEP-15060 | Install GRP Water Tank & Accessories - Z123 - SRVF | 225500 | 250
Z123-C-MEP-15070 | Install Filteration Plant System - Z123 - SRVF | 100000 | 333
Z123-C-MEP-15090 | Install Chilled Water Pump - Z123 - SRVF | 145000 | 200
Z123-C-MEP-15100 | Install MCC Pannels - Z123 - SRVF | 339718 | 250
Z123-C-MEP-15110 | Install LPG Tank - Z123 - SRVF | 12341 | 167
Z123-C-MEP-15120 | Termination of MEP Equipment With Risers - Z123 - SRVF | 264001 | 101
Z123-C-MEP-15130 | Fix Pressurization Guages & Units Lift & Stair - Z123 - SRVF | 259000 | 100
Z123-C-MEP-15140 | Fix Chemical Dosing Pot - Z123 - SRVF | 22000 | 500
Z1-C-CON-2400 | PCC Blind Concrete - Z1 - Lift Pit | 17220 | 6
Z1-C-CON-2440 | Waterproof Membrane - Z1 - Lift Pit | 102280 | 40
Z1-C-CON-2450 | Protection Screed - Z1 - Lift Pit | 10980 | 24
Z1-C-CON-2460 | Fix Rebar - Z1 - Lift Pit | 20247 | 497
Z1-C-CON-2480 | Pour Concrete - Z1 - Lift Pit | 20247 | 95
Z1-C-CON-2500 | PCC Blind Concrete - Z1 - Raft | 51660 | 196
Z1-C-CON-2510 | Waterproof Membrane - Z1 - Raft | 306840 | 1560
Z1-C-CON-2520 | Protection Screed - Z1 - Raft | 32940 | 96
Z1-C-CON-2530 | Fix Rebar - Z1 - Raft | 687066 | 18159
Z1-C-CON-2540 | Fix MEP Provisions - Z1 - Raft | 21000 | 100
Z1-C-CON-2550 | Fix Formwork - Z1 - Raft | 41321 | 261
Z1-C-CON-2560 | Pour Concrete - Z1 - Raft | 1004127 | 4422
Z1-C-CON-2570 | Fix Rebar Core Walls - Z1 - B2 | 49489 | 1609
Z1-C-CON-2580 | Fix Formwork Core Walls - Z1 - B2 | 41489 | 1547
Z1-C-CON-2600 | Fix Rebar Retaining Walls - Z1 - B2 | 87236 | 2863
Z1-C-CON-2610 | Fix Formwork Retaining Walls - Z1 - B2 | 144300 | 2342
Z1-C-CON-2620 | Pour Concrete Retaining Walls - Z1 - B2 | 288597 | 482
Z1-C-CON-2630 | Pour Concrete Core Walls - Z1 - B2 | 161333 | 248
Z1-C-CON-2640 | Fix Rebar Columns - Z1 - B2 | 63240 | 3020
Z1-C-CON-2650 | Fix Formwork Columns - Z1 - B2 | 132301 | 889
Z1-C-CON-2660 | Pour Concrete Columns - Z1 - B2 | 163921 | 174
Z1-C-CON-2670 | Fix Formwork Stairs - Z1 - B2 | 2486 | 4
Z1-C-CON-2680 | Fix Rebar Stairs - Z1 - B2 | 4972 | 43
Z1-C-CON-2690 | Pour Concrete Stairs - Z1 - B2 | 4972 | 8
Z1-C-CON-2700 | Pour Concrete Slabs - Z1 - B1 | 315168 | 1426
Z1-C-CON-2710 | Fix Formwork Slabs - Z1 - B1 | 157584 | 4167
Z1-C-CON-2720 | Fix Rebar Slabs - Z1 - B1 | 315168 | 5965
Z1-C-CON-2730 | Fix Rebar Retaining Walls - Z1 - B1 | 87236 | 2275
Z1-C-CON-2740 | Fix Formwork Retaining Walls - Z1 - B1 | 43618 | 2342
Z1-C-CON-2750 | Pour Concrete Retaining Walls - Z1 - B1 | 87236 | 484
Z1-C-CON-2760 | Fix Rebar Core Walls - Z1 - B1 | 49489 | 1493
Z1-C-CON-2770 | Fix Formwork Core Walls - Z1 - B1 | 41489 | 1539
Z1-C-CON-2780 | Pour Concrete Core Walls - Z1 - B1 | 60652 | 284
Z1-C-CON-2790 | Fix Rebar Columns - Z1 - B1 | 63240 | 2314
Z1-C-CON-2800 | Fix Formwork Columns - Z1 - B1 | 31620 | 991
Z1-C-CON-2810 | Pour Concrete Columns - Z1 - B1 | 63240 | 194
Z1-C-CON-2820 | Fix Formwork Stairs - Z1 - B1 | 2486 | 4
Z1-C-CON-2830 | Fix Rebar Stairs - Z1 - B1 | 4972 | 43
Z1-C-CON-2840 | Pour Concrete Stairs - Z1 - B1 | 4972 | 8
Z1-C-CON-3000 | Fix Formwork Slabs - Z1 - GF | 196850 | 4684
Z1-C-CON-3010 | Fix Rebar Slabs - Z1 - GF | 393700 | 11392
Z1-C-CON-3020 | Pour Concrete Slabs - Z1 - GF | 393699 | 1908
Z1-C-CON-3030 | Fix Rebar Core Walls - Z1 - GF | 72339 | 2275
Z1-C-CON-3040 | Fix Formwork Core Walls - Z1 - GF | 37650 | 2295
Z1-C-CON-3050 | Pour Concrete Core Walls - Z1 - GF | 74214 | 314
Z1-C-CON-3060 | Fix Rebar Columns - Z1 - GF | 96670 | 3008
Z1-C-CON-3070 | Fix Formwork Columns - Z1 - GF | 50689 | 1515
Z1-C-CON-3080 | Pour Concrete Columns - Z1 - GF | 101503 | 300
Z1-C-CON-3090 | Fix Formwork Stairs - Z1 - GF | 4838 | 7
Z1-C-CON-3100 | Fix Rebar Stairs - Z1 - GF | 6451 | 21
Z1-C-CON-3110 | Pour Concrete Stairs - Z1 - GF | 49823 | 12
Z1-C-CON-3120 | Fix MEP Containment & Provisions - Z1 - B1 | 10880
Z1-C-CON-3140 | Fix MEP Containment & Provisions - Z1 - GF | 10880
Z1-C-CON-3150 | Fix MEP Containment & Provisions - Z1 - F1 | 10880
Z1-C-CON-3160 | Fix Formwork Slabs - Z1 - F1 | 226317 | 3790
Z1-C-CON-3170 | Pour Concrete Slabs - Z1 - F1 | 326686 | 1316
Z1-C-CON-3180 | Fix Rebar Slabs - Z1 - F1 | 250571 | 4939
Z1-C-CON-3190 | Fix Rebar Core Walls - Z1 - F1 | 71458 | 2248
Z1-C-CON-3200 | Fix Formwork Core Walls - Z1 - F1 | 37716 | 2298
Z1-C-CON-3210 | Pour Concrete Core Walls - Z1 - F1 | 75216 | 318
Z1-C-CON-3220 | Fix Rebar Columns - Z1 - F1 | 97930 | 3046
Z1-C-CON-3230 | Fix Formwork Columns - Z1 - F1 | 50440 | 1507
Z1-C-CON-3240 | Pour Concrete Columns - Z1 - F1 | 101184 | 300
Z1-C-CON-3250 | Fix Formwork Stairs - Z1 - F1 | 4839 | 7
Z1-C-CON-3260 | Fix Rebar Stairs - Z1 - F1 | 6451 | 21
Z1-C-CON-3270 | Pour Concrete Stairs - Z1 - F1 | 6451 | 12
Z1-C-CON-3280 | Fix Formwork Slabs - Z1 - F2 | 228211 | 3776
Z1-C-CON-3290 | Fix Rebar Slabs - Z1 - F2 | 157731 | 5071
Z1-C-CON-3300 | Pour Concrete Slabs - Z1 - F2 | 230096 | 1324
Z1-C-CON-3310 | Fix MEP Containment & Provisions - Z1 - F2 | 10881
Z1-C-CON-3320 | Fix Rebar Core Walls - Z1 - F2 | 47223 | 1485
Z1-C-CON-3330 | Fix Formwork Core Walls - Z1 - F2 | 22272 | 1357
Z1-C-CON-3340 | Pour Concrete Core Walls - Z1 - F2 | 45198 | 192
Z1-C-CON-3350 | Fix Rebar Columns - Z1 - F2 | 66757 | 2077
Z1-C-CON-3360 | Fix Formwork Columns - Z1 - F2 | 32421 | 968
Z1-C-CON-3370 | Pour Concrete Columns - Z1 - F2 | 64003 | 190
Z1-C-CON-3380 | Fix Formwork Stairs - Z1 - F2 | 4838 | 8
Z1-C-CON-3390 | Fix Rebar Stairs - Z1 - F2 | 4838 | 16
Z1-C-CON-3400 | Pour Concrete Stairs - Z1 - F2 | 4838 | 8
Z1-C-CON-3410 | Fix Formwork Slabs - Z1 - RF | 461149 | 3775
Z1-C-CON-3420 | Fix Rebar Slabs - Z1 - RF | 156343 | 5045
Z1-C-CON-3430 | Pour Concrete Slabs - Z1 - RF | 149383 | 1320
Z1-C-CON-3440 | Fix MEP Containment & Provisions - Z1 - RF | 10880
Z1-C-CON-3450 | Fix Rebar Core Walls - Z1 - RF | 46414 | 1460
Z1-C-CON-3460 | Fix Formwork Core Walls - Z1 - RF | 22188 | 1352
Z1-C-CON-3470 | Pour Concrete Core Walls - Z1 - RF | 45050 | 190
Z1-C-CON-3480 | Fix Rebar Columns - Z1 - RF | 54661 | 1700
Z1-C-CON-3490 | Fix Formwork Columns - Z1 - RF | 25132 | 750
Z1-C-CON-3500 | Pour Concrete Columns - Z1 - RF | 51065 | 150
Z1-C-CON-3510 | Fix Formwork Stairs - Z1 - RF | 4838 | 8
Z1-C-CON-3520 | Fix Rebar Stairs - Z1 - RF | 4838 | 16
Z1-C-CON-3530 | Pour Concrete Stairs - Z1 - RF | 4838 | 8
Z1-C-CON-5620 | Fix Formwork Slabs - Z1 - SRVF | 207509 | 3234
Z1-C-CON-5630 | Fix Rebar Slabs - Z1 - SRVF | 308219 | 4156
Z1-C-CON-5640 | Pour Concrete Slabs - Z1 - SRVF | 392832 | 1132
Z1-C-CON-5650 | Fix MEP Containment & Provisions - Z1 - SRVF | 10880
Z1-C-CON-5660 | Fix Rebar Core Walls - Z1 - SRVF | 27454 | 864
Z1-C-CON-5670 | Fix Formwork Core Walls - Z1 - SRVF | 12615 | 769
Z1-C-CON-5680 | Pour Concrete Core Walls - Z1 - SRVF | 25208 | 106
Z1-C-CON-5690 | Fix Rebar Columns - Z1 - SRVF | 4941 | 153
Z1-C-CON-5700 | Fix Formwork Columns - Z1 - SRVF | 1799 | 54
Z1-C-CON-5710 | Pour Concrete Columns - Z1 - SRVF | 3206 | 10
Z1-C-CON-5720 | Fix Formwork Parapet - Z1 - SRVF | 19346 | 151
Z1-C-CON-5730 | Fix Rebar Parapet - Z1 - SRVF | 38692 | 314
Z1-C-CON-5740 | Pour Concrete Parapet - Z1 - SRVF | 38691 | 180
Z1-C-CON-5750 | Fix Formwork Slabs - Z1 - TRF | 10217 | 397
Z1-C-CON-5760 | Fix Rebar Slabs - Z1 - TRF | 20434 | 404
Z1-C-CON-5770 | Pour Concrete Slabs - Z1 - TRF | 20434 | 120
Z1-C-CON-5780 | Fix MEP Containment & Provisions - Z1 - TRF | 10880
Z1-C-CON-5790 | Pour MEP RCC Pedastals - Z1 - SRVF | 1613 | 2
Z1-C-CON-5810 | Fix Rebar Parapet - Z1 - TRF | 38691 | 315
Z1-C-CON-5820 | Fix Formwork Parapet - Z1 - TRF | 19346 | 151
Z1-C-CON-5830 | Pour Concrete Parapet - Z1 - TRF | 38691 | 180
Z1-C-CON-5840 | Fix Formwork Ramp - Z1 - B2 | 11760 | 270
Z1-C-CON-5850 | Fix Rebar Ramp - Z1 - B2 | 23520 | 97
Z1-C-CON-5860 | Pour Concrete Ramp - Z1 - B2 | 23520 | 114
Z1-C-CON-5870 | Fix Formwork Ramp - Z1 - B1 | 11760 | 231
Z1-C-CON-5880 | Fix Rebar Ramp - Z1 - B1 | 23520 | 372
Z1-C-CON-5890 | Pour Concrete Ramp - Z1 - B1 | 23520 | 98
Z1-C-CON-5900 | Fix Rebar Core Walls Ramp - Z1 - B2 | 27909 | 1055
Z1-C-CON-5910 | Fix Formwork Walls Ramp - Z1 - B2 | 27909 | 1040
Z1-C-CON-5920 | Pour Concrete Core Walls Ramp - Z1 - B2 | 37210 | 152
Z1-C-CON-5930 | Fix Rebar Core Walls Ramp - Z1 - B1 | 27907 | 1015
Z1-C-CON-5940 | Fix Formwork Walls Ramp - Z1 - B1 | 27908 | 1050
Z1-C-CON-5950 | Pour Concrete Core Walls Ramp - Z1 - B1 | 37210 | 152
Z1-C-FIN-10000 | Fix MEP Droppers Lift Lobby & Passage - Z1 - F1 | 18389 | 200
Z1-C-FIN-10050 | Anti Fungal Paint - Z1 - F1 | 8946 | 302
Z1-C-FIN-10120 | Masonry Works Wet Area - Z1 - F2 | 84732 | 1048
Z1-C-FIN-10130 | Plaster Works Wet Area - Z1 - F2 | 39011 | 4823
Z1-C-FIN-10180 | Fix False Ceiling Suspension Lift Lobby - Z1 - F2 | 24288 | 390
Z1-C-FIN-10190 | Wall Paint (Emulsion) Lobby Passage & Offices - Z1 - F2 | 10000 | 648
Z1-C-FIN-10200 | Porcelain Floor Tiles Passage & Offices - Z1 - F2 | 208302 | 3842
Z1-C-FIN-10230 | Floor Paint (Antifungal) Lift Shaft - Z1 - F2 | 8203 | 271
Z1-C-FIN-10240 | Wall Paint (Antifungal) Lift Shaft - Z1 - F2 | 8203 | 271
Z1-C-FIN-10250 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - F2 | 2432 | 59
Z1-C-FIN-10260 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 4833 | 17
Z1-C-FIN-10280 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - F2 | 24287 | 391
Z1-C-FIN-10300 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - F2 | 24287 | 651
Z1-C-FIN-10310 | Wall Paint (Acrylic) Serv. Rooms - Z1 - F2 | 2432 | 94
Z1-C-FIN-10320 | Fix MEP Droppers Lift Lobby - Z1 - F2 | 18389 | 200
Z1-C-FIN-10370 | Fix Door Subframes Wet Area - Z1 - F2 | 20822 | 70
Z1-C-FIN-10460 | Masonry Works Dry Area - Z1 - F2 | 84732 | 1048
Z1-C-FIN-10470 | Fix Door Subframes Dry Area - Z1 - F2 | 20822 | 70
Z1-C-FIN-10480 | Plaster Works Dry Area - Z1 - F2 | 39011 | 4823
Z1-C-FIN-10490 | Waterproof Bath - Z1 - F2 | 3898 | 34
Z1-C-FIN-10500 | Protection Screed Bath - Z1 - F2 | 3898 | 32
Z1-C-FIN-10510 | Wall Ceramic Tiles Bath - Z1 - F2 | 28908 | 1090
Z1-C-FIN-10520 | Floor Ceramic Tiles Bath - Z1 - F2 | 6660 | 153
Z1-C-FIN-10540 | Fix False Ceiling Suspension Bath - Z1 - F2 | 24288 | 391
Z1-C-FIN-10550 | Fix MEP Droppers Bath - Z1 - F2 | 18389 | 200
Z1-C-FIN-10560 | Fix False Ceiling Gypsum Board Bath - Z1 - F2 | 24288 | 651
Z1-C-FIN-10570 | Fix False Ceiling Aluminum Tiles Bath - Z1 - F2 | 24288 | 391
Z1-C-FIN-10590 | Waterproof kitchen/Pantry - Z1 - F2 | 3898 | 34
Z1-C-FIN-10600 | Protection Screed kitchen/Pantry - Z1 - F2 | 3898 | 34
Z1-C-FIN-10610 | Wall Ceramic Tiles kitchen/Pantry - Z1 - F2 | 28908 | 1091
Z1-C-FIN-10620 | Fix False Ceiling Suspension kitchen/Pantry - Z1 - F2 | 24288 | 391
Z1-C-FIN-10630 | Fix MEP Droppers kitchen/Pantry - Z1 - F2 | 10750 | 200
Z1-C-FIN-10640 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - F2 | 24288 | 651
Z1-C-FIN-10650 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z1 - F2 | 24288 | 391
Z1-C-FIN-10660 | Floor Ceramic Tiles kitchen/Pantry - Z1 - F2 | 6660 | 153
Z1-C-FIN-10670 | Waterproof Garbage Room - Z1 - F2 | 3898 | 34
Z1-C-FIN-10680 | Protection Screed Garbage Room - Z1 - F2 | 3898 | 32
Z1-C-FIN-10690 | Ceiling Paint (Emulsion) Garbage Room - Z1 - F2 | 401 | 26
Z1-C-FIN-10700 | Wall Paint (Emulsion) Garbage Room - Z1 - F2 | 10000 | 647
Z1-C-FIN-10710 | Fix Furniture & Counter Works kitchen/Pantry - Z1 - F2 | 89500 | 450
Z1-C-FIN-10750 | Floor Epoxy Paint Garbage Room - Z1 - F2 | 4833 | 17
Z1-C-FIN-10760 | Masonry Works Wet Area - Z1 - RF | 72632 | 896
Z1-C-FIN-10770 | Plaster Works Wet Area - Z1 - RF | 32690 | 4043
Z1-C-FIN-10790 | Fix False Ceiling Suspension Lift Lobby - Z1 - RF | 18598 | 299
Z1-C-FIN-10800 | Wall Paint (Emulsion) Lobby Passage & Offices - Z1 - RF | 10000 | 647
Z1-C-FIN-10810 | Porcelain Floor Tiles Passage & Offices - Z1 - RF | 158821 | 2930
Z1-C-FIN-10820 | Floor Paint (Antifungal) Lift Shaft - Z1 - RF | 8203 | 271
Z1-C-FIN-10830 | Wall Paint (Antifungal) Lift Shaft - Z1 - RF | 8203 | 271
Z1-C-FIN-10840 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - RF | 2432 | 59
Z1-C-FIN-10850 | Wall Paint (Acrylic) Serv. Rooms - Z1 - RF | 2432 | 94
Z1-C-FIN-10860 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - RF | 18598 | 299
Z1-C-FIN-10870 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - RF | 18598 | 498
Z1-C-FIN-10880 | Floor Epoxy Paint Serv. Rooms - Z1 - F2 | 4833 | 17
Z1-C-FIN-10890 | Fix MEP Droppers Lift Lobby - Z1 - RF | 18389 | 200
Z1-C-FIN-10900 | Fix Door Subframes Wet Area - Z1 - RF | 20822 | 70
Z1-C-FIN-10940 | Masonry Works Dry Area - Z1 - RF | 72632 | 896
Z1-C-FIN-10950 | Plaster Works Dry Area - Z1 - RF | 32690 | 4043
Z1-C-FIN-10960 | Fix Door Subframes Dry Area - Z1 - RF | 20821 | 70
Z1-C-FIN-10970 | Fix False Ceiling Suspension Bath - Z1 - RF | 18598 | 299
Z1-C-FIN-10980 | Wall Ceramic Tiles Bath - Z1 - RF | 28908 | 1090
Z1-C-FIN-10990 | Floor Ceramic Tiles Bath - Z1 - RF | 6660 | 153
Z1-C-FIN-11000 | Waterproof Bath - Z1 - RF | 3899 | 34
Z1-C-FIN-11010 | Protection Screed Bath - Z1 - RF | 3898 | 34
Z1-C-FIN-11020 | Fix False Ceiling Gypsum Board Bath - Z1 - RF | 18598 | 500
Z1-C-FIN-11030 | Fix False Ceiling Aluminum Tiles Bath - Z1 - RF | 18598 | 300
Z1-C-FIN-11040 | Fix MEP Droppers Bath - Z1 - RF | 18389 | 200
Z1-C-FIN-11050 | Fix False Ceiling Suspension kitchen/Pantry - Z1 - RF | 18599 | 299
Z1-C-FIN-11060 | Wall Ceramic Tiles kitchen/Pantry - Z1 - RF | 28908 | 1091
Z1-C-FIN-11070 | Floor Ceramic Tiles kitchen/Pantry - Z1 - RF | 6660 | 153
Z1-C-FIN-11080 | Waterproof kitchen/Pantry - Z1 - RF | 3898 | 34
Z1-C-FIN-11090 | Protection Screed kitchen/Pantry - Z1 - RF | 3898 | 32
Z1-C-FIN-11100 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z1 - RF | 18598 | 498
Z1-C-FIN-11110 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z1 - RF | 18598 | 299
Z1-C-FIN-11120 | Fix MEP Droppers kitchen/Pantry - Z1 - RF | 10751 | 200
Z1-C-FIN-11130 | Wall Paint (Emulsion) Garbage Room - Z1 - RF | 10000 | 647
Z1-C-FIN-11140 | Floor Epoxy Paint Garbage Room - Z1 - RF | 4834 | 16
Z1-C-FIN-11150 | Waterproof Garbage Room - Z1 - RF | 3899 | 34
Z1-C-FIN-11160 | Protection Screed Garbage Room - Z1 - RF | 3898 | 34
Z1-C-FIN-11170 | Ceiling Paint (Emulsion) Garbage Room - Z1 - RF | 401 | 25
Z1-C-FIN-11180 | Fix Furniture & Counter Works kitchen/Pantry - Z1 - RF | 89500 | 450
Z1-C-FIN-18570 | Ceiling Paint (Emulsion/Acrylic) Secur. Ctrl & Eqpmt Room - Z1 - B1 | 401 | 26
Z1-C-FIN-18580 | Wall Paint (Emulsion/Acrylic) Secur. Ctrl & Eqpmt Room - Z1 - B1 | 10000 | 647
Z1-C-FIN-18590 | Floor Epoxy Paint (Secur. Ctrl & Eqpmt Room) - Z1 - B1 | 4833 | 17
Z1-C-FIN-18600 | Fix Doors - Z1 - B1 | 20821 | 103
Z1-C-FIN-18610 | Ceiling Paint (Acrylic) Maint. & Serv. Provider Room) - Z1 - B1 | 2432 | 59
Z1-C-FIN-18620 | Wall Paint (Acrylic) Maint. & Serv. Provider Room) - Z1 - B1 | 2432 | 94
Z1-C-FIN-18630 | Floor Epoxy Paint (Maint. & Serv. Provider Room) - Z1 - B1 | 4833 | 17
Z1-C-FIN-18640 | Fix Doors - Z1 - B1 | 20821 | 103
Z1-C-FIN-18650 | Ceiling Paint (Acrylic) Loading Room - Z1 - GF | 2432 | 59
Z1-C-FIN-18670 | Wall Paint (Acrylic) Loading Room - Z1 - GF | 2432 | 94
Z1-C-FIN-18680 | Floor Stamp Concrete Loading Room - Z1 - GF | 21250 | 94
Z1-C-FIN-18690 | Fix Doors Loading Room - Z1 - GF | 20821 | 103
Z1-C-FIN-18700 | Ceiling Paint (Acrylic) Serv. Rooms - Z1 - F1 | 2432 | 59
Z1-C-FIN-18710 | Floor Epoxy Paint Serv. Rooms - Z1 - F1 | 4833 | 17
Z1-C-FIN-18730 | Fix Doors Serv. Rooms - Z1 - F1 | 20821 | 103
Z1-C-FIN-21360 | Wall Paint Outside Area (Acrylic) - Z1 - RF | 2432 | 95
Z1-C-FIN-21370 | Roof Floor Terrazo Tiles Outside Area - Z1 - RF | 13599 | 720
Z1-C-FIN-5790 | Masonry Works - Z1 - B2 | 3061 | 38
Z1-C-FIN-5800 | Plaster Works - Z1 - B2 | 65100 | 8050
Z1-C-FIN-6050 | Ceiling Paint (Acrylic) - Z1 - B2 | 2432 | 58
Z1-C-FIN-6060 | Wall Paint (Acrylic) - Z1 - B2 | 2432 | 94
Z1-C-FIN-6070 | Floor Epoxy Paint Serv. Rooms - Z1 - B2 | 4833 | 17
Z1-C-FIN-6080 | Ceiling Paint (Acrylic) - Z1 - B2 | 2432 | 58
Z1-C-FIN-6090 | Wall Paint (Acrylic) - Z1 - B2 | 2432 | 94
Z1-C-FIN-6100 | Floor Epoxy Paint - Z1 - B2 | 4833 | 17
Z1-C-FIN-6140 | GRP Linning - Z1 - B2 | 45350 | 100
Z1-C-FIN-6150 | Fix Galvonized Iron Cat Ladder - Z1 - B2 | 600 | 25
Z1-C-FIN-6160 | Fix False Ceiling Suspension - Z1 - B2 | 1793 | 28
Z1-C-FIN-6170 | Wall Paint (Emulsion) - Z1 - B2 | 10000 | 647
Z1-C-FIN-6180 | Porcelain Floor Tiles - Z1 - B2 | 6439 | 119
Z1-C-FIN-6220 | Fix Doors - Z1 - B2 | 20822 | 104
Z1-C-FIN-6230 | Fix Doors - Z1 - B2 | 20822 | 104
Z1-C-FIN-6240 | Fix Doors - Z1 - B2 | 20821 | 103
Z1-C-FIN-6250 | Fix Pump - Z1 - B2 | 36876 | 126
Z1-C-FIN-6260 | Fix Final Connections of Pumps with Risers - Z1 - B2 | 36875 | 125
Z1-C-FIN-6270 | Wall Paint (Antifungal) Lift Shaft - Z1 - B2 | 8200 | 272
Z1-C-FIN-6280 | Floor Paint (Antifungal) Lift Shaft - Z1 - B2 | 8200 | 271
Z1-C-FIN-6290 | Ceiling Paint (Anti-Carbonation) - Z1 - B2 | 46613 | 770
Z1-C-FIN-6310 | Wall Paint (Anti-Carbonation) - Z1 - B2 | 46612 | 771
Z1-C-FIN-6330 | Fix False Ceiling Gypsum Board & Tiles - Z1 - B2 | 1794 | 48
Z1-C-FIN-7040 | Masonry Works - Z1 - B1 | 30339 | 378
Z1-C-FIN-7050 | Plaster Works - Z1 - B1 | 68913 | 8522
Z1-C-FIN-7300 | Ceiling Paint (Emulsion/Acrylic) Store & Serv. Rooms - Z1 - B1 | 401 | 26
Z1-C-FIN-7310 | Wall Paint (Emulsion/Acrylic) Store & Serv. Rooms - Z1 - B1 | 10000 | 647
Z1-C-FIN-7320 | Raise Floor & Epoxy Paint Store & Serv. Rooms - Z1 - B1 | 4833 | 17
Z1-C-FIN-7390 | GRP Linning - Z1 - B1 | 45350 | 100
Z1-C-FIN-7400 | Fix Galvonized Iron Cat Ladder - Z1 - B1 | 600 | 45
Z1-C-FIN-7410 | Fix False Ceiling Gypsum Board & Tiles Lift Lobby - Z1 - B1 | 2621 | 71
Z1-C-FIN-7420 | Wall Paint (Emulsion) Lift Lobby - Z1 - B1 | 10000 | 647
Z1-C-FIN-7430 | Porcelain Floor Tiles Lift Lobby - Z1 - B1 | 4734 | 88
Z1-C-FIN-7470 | Fix Doors - Z1 - B1 | 20821 | 103
Z1-C-FIN-7480 | Fix False Ceiling Suspension Lift Lobby - Z1 - B1 | 2622 | 42
Z1-C-FIN-7490 | Fix Doors - Z1 - B1 | 20821 | 103
Z1-C-FIN-7540 | Ceiling Paint (Anti-Carbonation) - Z1 - B1 | 46613 | 770
Z1-C-FIN-7560 | Wall Paint (Anti-Carbonation) - Z1 - B1 | 46612 | 771
Z1-C-FIN-8330 | Masonry Works - Z1 - GF | 223435 | 2762
Z1-C-FIN-8340 | Plaster Works - Z1 - GF | 47215 | 5838
Z1-C-FIN-8630 | Ceiling Paint Garbage & Service Room (Acrylic/Emulsion) - Z1 - GF | 401 | 26
Z1-C-FIN-8640 | Wall Paint Garbage & Service Room (Acrylic/Emulsion) - Z1 - GF | 10000 | 648
Z1-C-FIN-8650 | Floor Epoxy Paint Garbage & Service Room - Z1 - GF | 4833 | 17
Z1-C-FIN-8660 | Ceiling Paint (Acrylic/Emulsion) Fire Pump & Cmd Room - Z1 - GF | 401 | 26
Z1-C-FIN-8670 | Wall Paint (Acrylic/Emulsion) Fire Pump & Cmd Room - Z1 - GF | 10000 | 647
Z1-C-FIN-8680 | Floor Epoxy Paint Fire Pump & Cmd Room - Z1 - GF | 4834 | 16
Z1-C-FIN-8690 | Fix False Ceiling Suspension Lift Lobby - Z1 - GF | 6812 | 111
Z1-C-FIN-8700 | Wall Paint (Emulsion) Lift Lobby - Z1 - GF | 10000 | 647
Z1-C-FIN-8710 | Porcelain Floor Tiles Lift Lobby - Z1 - GF | 27711 | 510
Z1-C-FIN-8720 | Fix Doors Garbage & Service Room - Z1 - GF | 20821 | 103
Z1-C-FIN-8730 | Fix Doors Fire Pump & Cmd Room - Z1 - GF | 20821 | 103
Z1-C-FIN-8740 | Fix Doors Lift Lobby - Z1 - GF | 20821 | 103
Z1-C-FIN-8750 | Fix Electric Pump Fire Pump Room - Z1 - GF | 220779 | 250
Z1-C-FIN-8760 | Fix Final Connections with Risers Fire Pump Room - Z1 - GF | 36875 | 125
Z1-C-FIN-8770 | Floor Paint (Antifungal) Lift Shaft - Z1 - GF | 8200 | 272
Z1-C-FIN-8780 | Wall Paint (Antifungal) Lift Shaft - Z1 - GF | 8203 | 271
Z1-C-FIN-8790 | Ceiling Paint Generator Room (Acrylic) - Z1 - GF | 2432 | 94
Z1-C-FIN-8800 | Wall Paint Generator Room (Acrylic) - Z1 - GF | 2432 | 94
Z1-C-FIN-8810 | Floor Epoxy Paint Generator Room - Z1 - GF | 4834 | 16
Z1-C-FIN-8820 | Fix Steel Louver Frames & Doors Generator Room - Z1 - GF | 20821 | 343
Z1-C-FIN-8830 | Ceiling Paint LV & Trnsf. Room (Acrylic) - Z1 - B1 | 2432 | 94
Z1-C-FIN-8840 | Wall Paint LV & Trnsf. Room (Acrylic) - Z1 - B1 | 2432 | 94
Z1-C-FIN-8850 | Floor Epoxy Paint LV & Trnsf. Room- Z1 - B1 | 4834 | 16
Z1-C-FIN-8860 | Fix Doors LV & Trnsf. Room - Z1 - B1 | 20821 | 103
Z1-C-FIN-8870 | Waterproof & Screed Garbage Room - Z1 - GF | 3898 | 34
Z1-C-FIN-8880 | Final Connections & Termination Generator Room - Z1 - GF | 61109 | 251
Z1-C-FIN-8890 | Fix False Ceiling Gypsum Board Lift Lobby - Z1 - GF | 6812 | 183
Z1-C-FIN-8900 | Fix MEP Droppers Lift Lobby - Z1 - GF | 18389 | 200
Z1-C-FIN-8920 | Anti Fungal Paint all Shops - Z1 - GF | 8946 | 301
Z1-C-FIN-9300 | Fix Generator Generator Room - Z1 - GF | 703940 | 250
Z1-C-FIN-9310 | Fix Diesel Pump Fire Pump Room- Z1 - GF | 220780 | 250
Z1-C-FIN-9320 | Fix Jockey Pump Fire Pump Room- Z1 - GF | 220780 | 250
Z1-C-FIN-9330 | Fix MCC Pannels LV & Trnsf. Room- Z1 - B1 | 442610 | 270
Z1-C-FIN-9340 | Final Connections & Termination Fire Pump Room - Z1 - GF | 36875 | 125
Z1-C-FIN-9350 | Connections & Termonation LV & Trnsf. Room - Z1 - B1 | 31615 | 250
Z1-C-FIN-9380 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z1 - GF | 6812 | 110
Z1-C-FIN-9490 | Masonry Works Wet + Dry Area - Z1 - F1 | 144102 | 1784
Z1-C-FIN-9500 | Plaster Works Wet + Dry Area - Z1 - F1 | 31626 | 3910
Z1-C-FIN-9560 | Fix Door Subframes Wet + Dry Area - Z1 - F1 | 20821 | 70
Z1-C-FIN-9580 | Fix False Ceiling Suspension Lift Lobby & Passage - Z1 - F1 | 17190 | 277
Z1-C-FIN-9590 | Wall Paint (Emulsion) Lift Lobby & Passage - Z1 - F1 | 10000 | 647
Z1-C-FIN-9600 | Porcelain Floor Tiles Lift Lobby & Passage- Z1 - F1 | 80416 | 1482
Z1-C-FIN-9630 | Fix Doors Lift Lobby & Passage - Z1 - F1 | 20821 | 103
Z1-C-FIN-9660 | Floor Paint (Antifungal) Lift Shaft - Z1 - F1 | 8203 | 271
Z1-C-FIN-9670 | Wall Paint (Antifungal) Lift Shaft - Z1 - F1 | 8203 | 271
Z1-C-FIN-9770 | Ceiling Paint (Acrylic) Serv. Area - Z1 - F1 | 2432 | 59
Z1-C-FIN-9780 | Epoxy Paint Serv. Area - Z1 - F1 | 4833 | 17
Z1-C-FIN-9790 | Fix Doors Serv. Area - Z1 - F1 | 20821 | 103
Z1-C-FIN-9880 | Fix False Ceiling Aluminum Tiles Lift Lobby & Passage - Z1 - F1 | 17189 | 277
Z1-C-FIN-9960 | Fix False Ceiling Gypsum Board Lift Lobby & Passage - Z1 - F1 | 17189 | 461
Z1-C-FIN-SCASE-8790 | Staircase Acrylic Paint - Z1 - B2 - SRVF | 4259
Z1-C-FIN-SCASE-8800 | Staircase Floor Epoxy Paint - Z1 - B2 - SRVF | 4832 | 16
Z1-C-FIN-SCASE-8810 | Install Haindrails Staircase - Z1 - B2 - SRVF | 83199 | 610
Z1-C-FIN-SCASE-8910 | Install MEP Final Fixes Staircase - Z1 - B2 - SRVF | 7203 | 250
Z1-C-GRBCH-9380 | Install Garbage Chute Cylinder - Z1 - GF to SRVF | 16800 | 268
Z1-C-GRBCH-9390 | Install Garbage Chute Supporting Frame - Z1 - GF to SRVF | 16800 | 268
Z1-C-GRBCH-9400 | Block & Plaster Garbage Room - Z1 - GF to SRVF | 1391 | 172
Z1-C-GRBCH-9410 | Install Garbage Chute Openings & Doors - Z1 - GF to SRVF | 16800 | 268
Z1-C-GRBCH-9460 | Install Garbage Chute Roof Top Unit with All Provisions | 16800 | 266
Z1-C-GRBCH-9470 | Install Garbage Chute Bottom Unit with All Provisions | 16800 | 266
Z1-C-LIFT-9110 | Install Working Platm for PL-1 & 2 (B2 to SRVF) | 97230 | 100
Z1-C-LIFT-9120 | Install Steel Support Beams & Tracks PL-1 & 2 (B2 to SRVF) | 97230 | 100
Z1-C-LIFT-9190 | Repair Lift Shaft PL-1 & 2 (B2 to SRVF) | 97230 | 100
Z1-C-LIFT-9230 | Terminate Tracks & Cross Beams (B2 to GF) | 97231 | 100
Z1-C-LIFT-9240 | Install Lift Access Doors (B2 to GF) | 97230 | 100
Z1-C-LIFT-9250 | Install Lift Cabin (B2 to GF) | 97231 | 100
Z1-C-LIFT-9260 | Install Lift Motors Cables, Counter Weight & Brakes (B2 to GF) | 97231 | 100
Z1-C-LIFT-9270 | Install Lift Control Unit (B2 to GF) | 97230 | 100
Z1-C-LIFT-9280 | Power Connection & Test Runs (B2 to GF) | 97230 | 100
Z1-C-MEP-5810 | Fix G.I Box and conduits - Z1 - B2 | 26755 | 50
Z1-C-MEP-5820 | Fix Drainage Pipes - Z1 - B2 | 10868 | 249
Z1-C-MEP-5830 | Fix Fire Fighting Pipes - Z1 - B2 | 82008 | 501
Z1-C-MEP-5840 | Fix Chill Water Pipes - Z1 - B2 | 106572 | 333
Z1-C-MEP-5850 | Fix HVAC Ducts & Insulation - Z1 - B2 | 205842 | 665
Z1-C-MEP-5860 | Fix Fire Fighting Dropers - Z1 - B2 | 10627 | 50
Z1-C-MEP-5870 | Fix FCU - Z1 - B2 | 19285 | 100
Z1-C-MEP-5880 | Fix ELV Trunkings - Z1 - B2 | 35620 | 250
Z1-C-MEP-5890 | Pull ELV Cables - Z1 - B2 | 46004 | 101
Z1-C-MEP-5900 | Fix Power Cable Trays - Z1 - B2 | 32904 | 500
Z1-C-MEP-5910 | Pull Electricl Wires (Ceiling & Walls) - Z1 - B2 | 10783 | 101
Z1-C-MEP-5920 | Pull Earthing & Power Cables - Z1 - B2 | 84717 | 250
Z1-C-MEP-5930 | Fix DBs - Z1 - B2 | 64069 | 50
Z1-C-MEP-5940 | Cable Terminations - Z1 - B2 | 61109 | 33
Z1-C-MEP-5950 | Fix CCTV Devices - Z1 - B2 | 78093 | 50
Z1-C-MEP-5960 | Fix Light Fixtures - Z1 - B2 | 115829 | 100
Z1-C-MEP-5970 | Fix Switches, Sockets & Isolators - Z1 - B2 | 11418 | 50
Z1-C-MEP-5980 | Fix Fire Alarm Devices - Z1 - B2 | 51070 | 50
Z1-C-MEP-5990 | Fix Telephone & Voice Evac. Devices - Z1 - B2 | 43578 | 250
Z1-C-MEP-6000 | Fix LCS & ACS Devices - Z1 - B2 | 28739 | 50
Z1-C-MEP-6010 | Fix Emergency & Exit Lights - Z1 - B2 | 45974 | 50
Z1-C-MEP-6020 | Fix Fire Hose Cabinets & Hose Reels - Z1 - B2 | 12692 | 50
Z1-C-MEP-6030 | Fix Sprinklers - Z1 - B2 | 20692 | 500
Z1-C-MEP-6040 | Fix Grills & Diffusers - Z1 - B2 | 17846 | 286
Z1-C-MEP-7060 | Fix G.I Box and conduits - Z1 - B1 | 26755 | 50
Z1-C-MEP-7070 | Fix Drainage Pipes - Z1 - B1 | 9366 | 249
Z1-C-MEP-7080 | Fix Fire Fighting Pipes - Z1 - B1 | 59346 | 500
Z1-C-MEP-7090 | Fix Chill Water Pipes - Z1 - B1 | 106571 | 333
Z1-C-MEP-7100 | Fix HVAC Ducts & Insulation - Z1 - B1 | 205842 | 665
Z1-C-MEP-7110 | Fix Fire Fighting Dropers - Z1 - B1 | 10628 | 50
Z1-C-MEP-7120 | Fix FCU - Z1 - B1 | 39085 | 100
Z1-C-MEP-7130 | Fix ELV Trunkings - Z1 - B1 | 35621 | 250
Z1-C-MEP-7140 | Pull ELV Cables - Z1 - B1 | 46004 | 100
Z1-C-MEP-7150 | Fix Power Cable Trays - Z1 - B1 | 32905 | 500
Z1-C-MEP-7160 | Pull Electricl Wires (Ceiling & Walls) - Z1 - B1 | 10783 | 102
Z1-C-MEP-7170 | Pull Earthing & Power Cables - Z1 - B1 | 84716 | 250
Z1-C-MEP-7180 | Fix DBs - Z1 - B1 | 64069 | 50
Z1-C-MEP-7190 | Cable Terminations - Z1 - B1 | 61108 | 34
Z1-C-MEP-7200 | Fix CCTV Devices - Z1 - B1 | 78093 | 50
Z1-C-MEP-7210 | Fix Light Fixtures - Z1 - B1 | 115829 | 100
Z1-C-MEP-7220 | Fix Switches, Sockets & Isolators - Z1 - B1 | 11418 | 50
Z1-C-MEP-7230 | Fix Fire Alarm Devices - Z1 - B1 | 51070 | 50
Z1-C-MEP-7240 | Fix Telephone & Voice Evac. Devices - Z1 - B1 | 43578 | 250
Z1-C-MEP-7250 | Fix LCS & ACS Devices - Z1 - B1 | 28739 | 50
Z1-C-MEP-7260 | Fix Emergency & Exit Lights - Z1 - B1 | 45974 | 50
Z1-C-MEP-7270 | Fix Fire Hose Cabinets & Hose Reels - Z1 - B1 | 12692 | 51
Z1-C-MEP-7280 | Fix Sprinklers - Z1 - B1 | 20692 | 500
Z1-C-MEP-7290 | Fix Grills & Diffusers - Z1 - B1 | 17845 | 285
Z1-C-MEP-8350 | Fix G.I Box and conduits - Z1 - GF | 26755 | 50
Z1-C-MEP-8360 | Fix Drainage Pipes - Z1 - GF | 9367 | 250
Z1-C-MEP-8370 | Fix Fire Fighting Pipes - Z1 - GF | 59346 | 500
Z1-C-MEP-8380 | Fix Chill Water Pipes - Z1 - GF | 106571 | 332
Z1-C-MEP-8390 | Fix HVAC Ducts & Insulation - Z1 - GF | 205841 | 666
Z1-C-MEP-8400 | Fix Fire Fighting Dropers - Z1 - GF | 10627 | 50
Z1-C-MEP-8410 | Fix FCU - Z1 - GF | 151284 | 100
Z1-C-MEP-8420 | Fix ELV Trunkings - Z1 - GF | 35620 | 250
Z1-C-MEP-8430 | Pull ELV Cables - Z1 - GF | 46003 | 101
Z1-C-MEP-8440 | Fix Power Cable Trays - Z1 - GF | 32904 | 500
Z1-C-MEP-8450 | Pull Electricl Wires (Ceiling & Walls) - Z1 - GF | 10780 | 102
Z1-C-MEP-8460 | Pull Earthing & Power Cables - Z1 - GF | 84718 | 252
Z1-C-MEP-8470 | Fix DBs - Z1 - GF | 64069 | 50
Z1-C-MEP-8480 | Cable Terminations - Z1 - GF | 61109 | 34
Z1-C-MEP-8490 | Fix CCTV Devices - Z1 - GF | 78093 | 50
Z1-C-MEP-8500 | Fix Light Fixtures - Z1 - GF | 115828 | 100
Z1-C-MEP-8510 | Fix Switches, Sockets & Isolators - Z1 - GF | 11417 | 49
Z1-C-MEP-8520 | Fix Fire Alarm Devices - Z1 - GF | 51070 | 50
Z1-C-MEP-8530 | Fix Telephone & Voice Evac. Devices - Z1 - GF | 43578 | 250
Z1-C-MEP-8540 | Fix LCS & ACS Devices - Z1 - GF | 28739 | 50
Z1-C-MEP-8550 | Fix Emergency & Exit Lights - Z1 - GF | 45974 | 50
Z1-C-MEP-8560 | Fix Fire Hose Cabinets & Hose Reels - Z1 - GF | 12692 | 50
Z1-C-MEP-8570 | Fix Sprinklers - Z1 - GF | 20692 | 500
Z1-C-MEP-8580 | Fix Grills & Diffusers - Z1 - GF | 17846 | 286
Z1-C-MEP-8590 | Fix Water Supply Pipes - Z1 - GF | 6590 | 250
Z1-C-MEP-8630 | Fix Water Heater & Sanitary Accessories - Z1 - GF | 75575 | 333
Z1-C-MEP-8640 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - GF | 6591 | 50
Z1-C-MEP-8650 | Fix G.I Box and conduits - Z1 - F1 | 26755 | 50
Z1-C-MEP-8660 | Fix Drainage Pipes - Z1 - F1 | 9367 | 249
Z1-C-MEP-8670 | Fix Fire Fighting Pipes - Z1 - F1 | 59346 | 500
Z1-C-MEP-8680 | Fix Chill Water Pipes - Z1 - F1 | 106571 | 332
Z1-C-MEP-8690 | Fix HVAC Ducts & Insulation - Z1 - F1 | 205841 | 666
Z1-C-MEP-8700 | Fix Fire Fighting Dropers - Z1 - F1 | 10628 | 50
Z1-C-MEP-8710 | Fix FCU - Z1 - F1 | 129834 | 100
Z1-C-MEP-8720 | Fix ELV Trunkings - Z1 - F1 | 35620 | 250
Z1-C-MEP-8730 | Pull ELV Cables - Z1 - F1 | 46004 | 102
Z1-C-MEP-8740 | Fix Power Cable Trays - Z1 - F1 | 32904 | 500
Z1-C-MEP-8750 | Pull Electricl Wires (Ceiling & Walls) - Z1 - F1 | 10780 | 103
Z1-C-MEP-8760 | Pull Earthing & Power Cables - Z1 - F1 | 84719 | 252
Z1-C-MEP-8770 | Fix DBs - Z1 - F1 | 64069 | 50
Z1-C-MEP-8780 | Cable Terminations - Z1 - F1 | 61109 | 33
Z1-C-MEP-8790 | Fix CCTV Devices - Z1 - F1 | 78093 | 50
Z1-C-MEP-8800 | Fix Light Fixtures - Z1 - F1 | 115829 | 101
Z1-C-MEP-8810 | Fix Switches, Sockets & Isolators - Z1 - F1 | 11418 | 50
Z1-C-MEP-8820 | Fix Fire Alarm Devices - Z1 - F1 | 51070 | 50
Z1-C-MEP-8830 | Fix Telephone & Voice Evac. Devices - Z1 - F1 | 43578 | 250
Z1-C-MEP-8840 | Fix LCS & ACS Devices - Z1 - F1 | 28739 | 50
Z1-C-MEP-8850 | Fix Emergency & Exit Lights - Z1 - F1 | 45974 | 50
Z1-C-MEP-8860 | Fix Fire Hose Cabinets & Hose Reels - Z1 - F1 | 12692 | 50
Z1-C-MEP-8870 | Fix Sprinklers - Z1 - F1 | 20692 | 500
Z1-C-MEP-8880 | Fix Grills & Diffusers - Z1 - F1 | 17846 | 285
Z1-C-MEP-8920 | Fix Water Supply Pipes - Z1 - F1 | 6590 | 250
Z1-C-MEP-8930 | Fix Water Heater & Sanitary Accessories - Z1 - F1 | 75575 | 333
Z1-C-MEP-8940 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - F1 | 6591 | 50
Z1-C-MEP-8950 | Fix G.I Box and conduits - Z1 - F2 | 26755 | 50
Z1-C-MEP-8960 | Fix Drainage Pipes - Z1 - F2 | 9368 | 250
Z1-C-MEP-8970 | Fix Fire Fighting Pipes - Z1 - F2 | 59346 | 499
Z1-C-MEP-8980 | Fix Chill Water Pipes - Z1 - F2 | 106571 | 332
Z1-C-MEP-8990 | Fix HVAC Ducts & Insulation - Z1 - F2 | 205840 | 667
Z1-C-MEP-9000 | Fix Fire Fighting Dropers - Z1 - F2 | 10628 | 50
Z1-C-MEP-9010 | Fix FCU - Z1 - F2 | 151284 | 100
Z1-C-MEP-9020 | Fix ELV Trunkings - Z1 - F2 | 35620 | 250
Z1-C-MEP-9030 | Pull ELV Cables - Z1 - F2 | 46004 | 102
Z1-C-MEP-9040 | Fix Power Cable Trays - Z1 - F2 | 32904 | 500
Z1-C-MEP-9050 | Pull Electricl Wires (Ceiling & Walls) - Z1 - F2 | 10780 | 102
Z1-C-MEP-9060 | Pull Earthing & Power Cables - Z1 - F2 | 84718 | 252
Z1-C-MEP-9070 | Fix DBs - Z1 - F2 | 64069 | 50
Z1-C-MEP-9080 | Cable Terminations - Z1 - F2 | 61109 | 33
Z1-C-MEP-9090 | Fix CCTV Devices - Z1 - F2 | 78093 | 50
Z1-C-MEP-9100 | Fix Light Fixtures - Z1 - F2 | 115829 | 100
Z1-C-MEP-9110 | Fix Switches, Sockets & Isolators - Z1 - F2 | 11418 | 50
Z1-C-MEP-9120 | Fix Fire Alarm Devices - Z1 - F2 | 51070 | 50
Z1-C-MEP-9130 | Fix Telephone & Voice Evac. Devices - Z1 - F2 | 43578 | 250
Z1-C-MEP-9140 | Fix LCS & ACS Devices - Z1 - F2 | 28739 | 50
Z1-C-MEP-9150 | Fix Emergency & Exit Lights - Z1 - F2 | 45974 | 50
Z1-C-MEP-9160 | Fix Fire Hose Cabinets & Hose Reels - Z1 - F2 | 12692 | 51
Z1-C-MEP-9170 | Fix Sprinklers - Z1 - F2 | 20692 | 500
Z1-C-MEP-9180 | Fix Grills & Diffusers - Z1 - F2 | 17846 | 285
Z1-C-MEP-9220 | Fix Water Supply Pipes - Z1 - F2 | 6590 | 250
Z1-C-MEP-9230 | Fix Water Heater & Sanitary Accessories - Z1 - F2 | 75575 | 333
Z1-C-MEP-9240 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - F2 | 6591 | 50
Z1-C-MEP-9250 | Fix LPG Pipes - Z1 - F2 | 12342 | 167
Z1-C-MEP-9260 | Fix Gas Detectors - Z1 - F2 | 12341 | 167
Z1-C-MEP-9270 | Fix G.I Box and conduits - Z1 - RF | 26755 | 50
Z1-C-MEP-9280 | Fix Drainage Pipes - Z1 - RF | 9368 | 250
Z1-C-MEP-9290 | Fix Fire Fighting Pipes - Z1 - RF | 59346 | 500
Z1-C-MEP-9300 | Fix Chill Water Pipes - Z1 - RF | 106571 | 333
Z1-C-MEP-9310 | Fix HVAC Ducts & Insulation - Z1 - RF | 205841 | 667
Z1-C-MEP-9320 | Fix Fire Fighting Dropers - Z1 - RF | 10627 | 50
Z1-C-MEP-9330 | Fix FCU - Z1 - RF | 129835 | 100
Z1-C-MEP-9340 | Fix ELV Trunkings - Z1 - RF | 35620 | 249
Z1-C-MEP-9350 | Pull ELV Cables - Z1 - RF | 46003 | 101
Z1-C-MEP-9360 | Fix Power Cable Trays - Z1 - RF | 32904 | 500
Z1-C-MEP-9370 | Pull Electricl Wires (Ceiling & Walls) - Z1 - RF | 10780 | 102
Z1-C-MEP-9380 | Pull Earthing & Power Cables - Z1 - RF | 84718 | 252
Z1-C-MEP-9390 | Fix DBs - Z1 - RF | 64069 | 50
Z1-C-MEP-9400 | Cable Terminations - Z1 - RF | 61109 | 34
Z1-C-MEP-9410 | Fix CCTV Devices - Z1 - RF | 78093 | 50
Z1-C-MEP-9420 | Fix Light Fixtures - Z1 - RF | 115828 | 100
Z1-C-MEP-9430 | Fix Switches, Sockets & Isolators - Z1 - RF | 11417 | 49
Z1-C-MEP-9440 | Fix Fire Alarm Devices - Z1 - RF | 51070 | 50
Z1-C-MEP-9450 | Fix Telephone & Voice Evac. Devices - Z1 - RF | 43578 | 250
Z1-C-MEP-9460 | Fix LCS & ACS Devices - Z1 - RF | 28739 | 50
Z1-C-MEP-9470 | Fix Emergency & Exit Lights - Z1 - RF | 45974 | 50
Z1-C-MEP-9480 | Fix Fire Hose Cabinets & Hose Reels - Z1 - RF | 12692 | 51
Z1-C-MEP-9490 | Fix Sprinklers - Z1 - RF | 20691 | 501
Z1-C-MEP-9500 | Fix Grills & Diffusers - Z1 - RF | 17846 | 286
Z1-C-MEP-9540 | Fix Water Supply Pipes - Z1 - RF | 6591 | 249
Z1-C-MEP-9550 | Fix Water Heater & Sanitary Accessories - Z1 - RF | 75575 | 333
Z1-C-MEP-9560 | Fix Drainage & Water Supply Pipes Block Wall - Z1 - RF | 6591 | 50
Z1-C-MEP-9570 | Fix LPG Pipes - Z1 - RF | 12341 | 167
Z1-C-MEP-9580 | Fix Gas Detectors - Z1 - RF | 12341 | 167
Z1-C-RSRS-11020 | Install Drainage Pipe Risers | 6591 | 999
Z1-C-RSRS-11030 | Install Water Supply Pipe Risers | 6591 | 999
Z1-C-RSRS-11050 | Install Fire Fighting Pipe Risers | 404399 | 997
Z1-C-RSRS-11070 | Install LPG Pipe Risers | 12344 | 166
Z1-C-RSRS-11110 | Power Cable Pulling & Termination Risers | 61105 | 97
Z2&3-C-FIN-18740 | Ceiling Paint (Anti-Carbonation) - Z2&3 - B2 | 46612 | 771
Z2&3-C-FIN-18760 | Wall Paint (Anti-Carbonation) - Z2&3 - B2 | 46612 | 771
Z2&3-C-FIN-18800 | Masonry Works - Z2&3 - B2 | 4593 | 56
Z2&3-C-FIN-18810 | Plaster Works - Z2&3 - B2 | 97652 | 12074
Z2&3-C-FIN-18870 | Fix False Ceiling Suspension - Z2&3 - B2 | 1794 | 29
Z2&3-C-FIN-18880 | Wall Paint (Emulsion) - Z2&3 - B2 | 6439 | 119
Z2&3-C-FIN-18890 | Porcelain Floor Tiles - Z2&3 - B2 | 6439 | 119
Z2&3-C-FIN-18900 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B2 | 1793 | 47
Z2&3-C-FIN-18910 | Fix Doors - Z2&3 - B2 | 20822 | 104
Z2&3-C-FIN-18920 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - B2 | 2432 | 59
Z2&3-C-FIN-18930 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - B2 | 2432 | 95
Z2&3-C-FIN-18940 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B2 | 4833 | 17
Z2&3-C-FIN-18950 | Fix Doors - Z2&3 - B2 | 20821 | 103
Z2&3-C-FIN-18960 | Ceiling Paint (Emulsion) Travelator - Z2&3 - B2 | 401 | 26
Z2&3-C-FIN-18970 | Wall Paint (Emulsion) Travelator - Z2&3 - B2 | 10000 | 647
Z2&3-C-FIN-18980 | Porcelain Floor Tiles Travelator - Z2&3 - B2 | 6440 | 118
Z2&3-C-FIN-18990 | Fix Doors - Z2&3 - B2 | 20821 | 103
Z2&3-C-FIN-19050 | Masonry Works - Z2&3 - B1 | 45508 | 562
Z2&3-C-FIN-19060 | Plaster Works - Z2&3 - B1 | 103369 | 12782
Z2&3-C-FIN-19070 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - B1 | 2432 | 58
Z2&3-C-FIN-19080 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - B1 | 2432 | 94
Z2&3-C-FIN-19090 | Floor Epoxy Paint Serv. Rooms - Z2&3 - B1 | 4833 | 17
Z2&3-C-FIN-19100 | Fix Doors - Z2&3 - B1 | 20821 | 103
Z2&3-C-FIN-19160 | Fix False Ceiling Gypsum Board & Tiles - Z2&3 - B1 | 2621 | 71
Z2&3-C-FIN-19170 | Wall Paint (Emulsion) - Z2&3 - B1 | 4734 | 88
Z2&3-C-FIN-19180 | Porcelain Floor Tiles - Z2&3 - B1 | 4734 | 87
Z2&3-C-FIN-19190 | Fix Doors - Z2&3 - B1 | 20821 | 103
Z2&3-C-FIN-19200 | Fix False Ceiling Suspension - Z2&3 - B1 | 2622 | 42
Z2&3-C-FIN-19230 | Ceiling Paint (Anti-Carbonation) - Z2&3 - B1 | 46613 | 770
Z2&3-C-FIN-19250 | Wall Paint (Anti-Carbonation) - Z2&3 - B1 | 46613 | 770
Z2&3-C-FIN-19270 | Masonry Works Wet + Dry Area - Z2&3 - F1 | 104153 | 2674
Z2&3-C-FIN-19280 | Plaster Works Wet + Dry Area - Z2&3 - F1 | 47439 | 5866
Z2&3-C-FIN-19290 | Fix Door Subframes Wet + Dry Area - Z2&3 - F1 | 20821 | 70
Z2&3-C-FIN-19300 | Fix False Ceiling Suspension - Z2&3 - F1 | 17190 | 277
Z2&3-C-FIN-19310 | Wall Ceramic Tiles Wet Area - Z2&3 - F1 | 28908 | 1090
Z2&3-C-FIN-19320 | Floor Ceramic Tiles Wet Area - Z2&3 - F1 | 6660 | 153
Z2&3-C-FIN-19330 | Protection Screed Wet Area - Z2&3 - F1 | 3898 | 34
Z2&3-C-FIN-19340 | Fix False Ceiling Gypsum Board - Z2&3 - F1 | 17189 | 461
Z2&3-C-FIN-19350 | Fix False Ceiling Aluminum Tiles - Z2&3 - F1 | 17189 | 277
Z2&3-C-FIN-19360 | Fix Doors Wet Area - Z2&3 - F1 | 20821 | 103
Z2&3-C-FIN-19370 | Fix MEP Droppers - Z2&3 - F1 | 18388 | 200
Z2&3-C-FIN-19380 | Waterproof Wet Area - Z2&3 - F1 | 3898 | 32
Z2&3-C-FIN-19390 | Fix False Ceiling Suspension Lift Lobby - Z2&3 - F1 | 17190 | 277
Z2&3-C-FIN-19400 | Wall Paint (Emulsion) Lift Lobby - Z2&3 - F1 | 10000 | 646
Z2&3-C-FIN-19410 | Porcelain Floor Tiles Lift Lobby - Z2&3 - F1 | 80417 | 1482
Z2&3-C-FIN-19420 | Fix Doors Lift Lobby - Z2&3 - F1 | 20821 | 103
Z2&3-C-FIN-19430 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z2&3 - F1 | 17190 | 276
Z2&3-C-FIN-19440 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - F1 | 17190 | 460
Z2&3-C-FIN-19450 | Fix MEP Droppers Lift Lobby - Z2&3 - F1 | 18389 | 200
Z2&3-C-FIN-19460 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - F1 | 8203 | 271
Z2&3-C-FIN-19470 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - F1 | 8203 | 271
Z2&3-C-FIN-19480 | Wall Paint (Acrylic) IT Room - Z2&3 - F1 | 2432 | 94
Z2&3-C-FIN-19490 | Anti Static Raised Floor IT Room - Z2&3 - F1 | 22200 | 240
Z2&3-C-FIN-19500 | Fix Doors IT Room - Z2&3 - F1 | 20821 | 103
Z2&3-C-FIN-19510 | Ceiling Paint (Acrylic) IT Room - Z2&3 - F1 | 2432 | 59
Z2&3-C-FIN-19520 | Anti Fungal Paint - Z2&3 - F1 | 8946 | 301
Z2&3-C-FIN-19540 | Masonry Works - Z2&3 - GF | 335154 | 4146
Z2&3-C-FIN-19550 | Plaster Works - Z2&3 - GF | 70822 | 8758
Z2&3-C-FIN-19560 | Floor Epoxy Paint Garbage & Service Room - Z2&3 - GF | 4833 | 17
Z2&3-C-FIN-19570 | Fix Doors Garbage & Service Room - Z2&3 - GF | 20821 | 103
Z2&3-C-FIN-19580 | Waterproof & Screed Garbage Room - Z2&3 - GF | 3898 | 34
Z2&3-C-FIN-19590 | Ceiling Paint Garbage & Service Room (Acrylic/Emulsion)- Z2&3 - GF | 401 | 26
Z2&3-C-FIN-19600 | Wall Paint Garbage & Service Room (Acrylic/Emulsion) - Z2&3 - GF | 10000 | 648
Z2&3-C-FIN-19760 | Fix Doors Lift Lobby - Z2&3 - GF | 20821 | 103
Z2&3-C-FIN-19770 | Fix False Ceiling Gypsum Board Lift Lobby - Z2&3 - GF | 6812 | 182
Z2&3-C-FIN-19780 | Fix MEP Droppers Lift Lobby - Z2&3 - GF | 18389 | 200
Z2&3-C-FIN-19790 | Fix False Ceiling Aluminum Tiles Lift Lobby - Z2&3 - GF | 6812 | 110
Z2&3-C-FIN-19800 | Fix False Ceiling Suspension Lift Lobby - Z2&3 - GF | 6812 | 110
Z2&3-C-FIN-19810 | Wall Paint (Emulsion) Lift Lobby - Z2&3 - GF | 10000 | 647
Z2&3-C-FIN-19820 | Porcelain Floor Tiles Lift Lobby - Z2&3 - GF | 27710 | 511
Z2&3-C-FIN-19830 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - GF | 8203 | 271
Z2&3-C-FIN-19840 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - GF | 8203 | 271
Z2&3-C-FIN-19940 | Anti Fungal Paint all Shops - Z2&3 - GF | 8946 | 302
Z2&3-C-FIN-20010 | Masonry Works Wet Area - Z2&3 - F2 | 127099 | 1572
Z2&3-C-FIN-20020 | Plaster Works Wet Area - Z2&3 - F2 | 58518 | 7234
Z2&3-C-FIN-20030 | Fix Door Subframes Wet Area - Z2&3 - F2 | 20821 | 70
Z2&3-C-FIN-20040 | Masonry Works Dry Area - Z2&3 - F2 | 127099 | 1572
Z2&3-C-FIN-20050 | Plaster Works Dry Area - Z2&3 - F2 | 58518 | 7234
Z2&3-C-FIN-20060 | Fix Door Subframes Dry Area - Z2&3 - F2 | 20821 | 70
Z2&3-C-FIN-20070 | Fix False Ceiling Suspension kitchen/Pantry - Z2&3 - F2 | 24288 | 391
Z2&3-C-FIN-20080 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 28908 | 1090
Z2&3-C-FIN-20090 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - F2 | 6660 | 152
Z2&3-C-FIN-20100 | Waterproof kitchen/Pantry - Z2&3 - F2 | 3898 | 32
Z2&3-C-FIN-20110 | Protection Screed kitchen/Pantry - Z2&3 - F2 | 3898 | 34
Z2&3-C-FIN-20120 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - F2 | 24288 | 651
Z2&3-C-FIN-20130 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z2&3 - F2 | 24288 | 391
Z2&3-C-FIN-20140 | Fix MEP Droppers kitchen/Pantry - Z2&3 - F2 | 10751 | 200
Z2&3-C-FIN-20150 | Fix Furniture & Counter Works kitchen/Pantry - Z2&3 - F2 | 89500 | 450
Z2&3-C-FIN-20160 | Fix False Ceiling Suspension Bath - Z2&3 - F2 | 24288 | 391
Z2&3-C-FIN-20170 | Wall Ceramic Tiles Bath - Z2&3 - F2 | 28908 | 1091
Z2&3-C-FIN-20180 | Floor Ceramic Tiles Bath - Z2&3 - F2 | 6660 | 153
Z2&3-C-FIN-20190 | Waterproof Bath - Z2&3 - F2 | 3899 | 34
Z2&3-C-FIN-20200 | Protection Screed Bath - Z2&3 - F2 | 3899 | 34
Z2&3-C-FIN-20210 | Fix False Ceiling Gypsum Board Bath - Z2&3 - F2 | 24288 | 651
Z2&3-C-FIN-20220 | Fix False Ceiling Aluminum Tiles Bath - Z2&3 - F2 | 24288 | 391
Z2&3-C-FIN-20230 | Fix MEP Droppers Bath - Z2&3 - F2 | 18389 | 200
Z2&3-C-FIN-20240 | Wall Paint (Emulsion) Garbage Room - Z2&3 - F2 | 10000 | 647
Z2&3-C-FIN-20250 | Floor Epoxy Paint Garbage Room - Z2&3 - F2 | 4833 | 17
Z2&3-C-FIN-20260 | Waterproof Garbage Room - Z2&3 - F2 | 3899 | 34
Z2&3-C-FIN-20270 | Protection Screed Garbage Room - Z2&3 - F2 | 3899 | 34
Z2&3-C-FIN-20280 | Ceiling Paint (Emulsion) Garbage Room - Z2&3 - F2 | 401 | 26
Z2&3-C-FIN-20290 | Fix False Ceiling Suspension Lobby Passage & Offices- Z2&3 - F2 | 24288 | 391
Z2&3-C-FIN-20300 | Wall Paint (Emulsion) Lobby Passage & Offices - Z2&3 - F2 | 10000 | 647
Z2&3-C-FIN-20310 | Porcelain Floor Tiles Passage & Offices - Z2&3 - F2 | 208301 | 3843
Z2&3-C-FIN-20320 | Fix False Ceiling Aluminum Tiles Lobby Passage & Offices - Z2&3 - F2 | 24288 | 391
Z2&3-C-FIN-20330 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - F2 | 24288 | 651
Z2&3-C-FIN-20340 | Fix MEP Droppers Lobby Passage & Offices- Z2&3 - F2 | 18389 | 200
Z2&3-C-FIN-20350 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - F2 | 8203 | 271
Z2&3-C-FIN-20360 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - F2 | 8203 | 271
Z2&3-C-FIN-20400 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - F2 | 2432 | 58
Z2&3-C-FIN-20410 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - F2 | 2432 | 94
Z2&3-C-FIN-20420 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F2 | 4833 | 17
Z2&3-C-FIN-20440 | Masonry Works Wet Area - Z2&3 - RF | 108948 | 1348
Z2&3-C-FIN-20450 | Plaster Works Wet Area - Z2&3 - RF | 49035 | 6063
Z2&3-C-FIN-20460 | Fix Door Subframes Wet Area - Z2&3 - RF | 20821 | 71
Z2&3-C-FIN-20470 | Masonry Works Dry Area - Z2&3 - RF | 108948 | 1348
Z2&3-C-FIN-20480 | Plaster Works Dry Area - Z2&3 - RF | 49035 | 6063
Z2&3-C-FIN-20490 | Fix Door Subframes Dry Area - Z2&3 - RF | 20821 | 71
Z2&3-C-FIN-20500 | Fix False Ceiling Suspension kitchen/Pantry - Z2&3 - RF | 18598 | 299
Z2&3-C-FIN-20510 | Wall Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 28908 | 1090
Z2&3-C-FIN-20520 | Floor Ceramic Tiles kitchen/Pantry - Z2&3 - RF | 6660 | 153
Z2&3-C-FIN-20530 | Waterproof kitchen/Pantry - Z2&3 - RF | 3898 | 34
Z2&3-C-FIN-20540 | Protection Screed kitchen/Pantry - Z2&3 - RF | 3898 | 34
Z2&3-C-FIN-20550 | Fix False Ceiling Gypsum Board kitchen/Pantry - Z2&3 - RF | 18599 | 499
Z2&3-C-FIN-20560 | Fix False Ceiling Aluminum Tiles kitchen/Pantry - Z2&3 - RF | 18599 | 300
Z2&3-C-FIN-20570 | Fix MEP Droppers kitchen/Pantry - Z2&3 - RF | 10751 | 200
Z2&3-C-FIN-20580 | Fix Furniture & Counter Works kitchen/Pantry - Z2&3 - RF | 89500 | 450
Z2&3-C-FIN-20590 | Fix False Ceiling Suspension Bath - Z2&3 - RF | 18599 | 300
Z2&3-C-FIN-20600 | Wall Ceramic Tiles Bath - Z2&3 - RF | 28908 | 1090
Z2&3-C-FIN-20610 | Floor Ceramic Tiles Bath - Z2&3 - RF | 6660 | 152
Z2&3-C-FIN-20620 | Waterproof Bath - Z2&3 - RF | 3898 | 34
Z2&3-C-FIN-20630 | Protection Screed Bath - Z2&3 - RF | 3899 | 34
Z2&3-C-FIN-20640 | Fix False Ceiling Gypsum Board Bath - Z2&3 - RF | 18598 | 498
Z2&3-C-FIN-20650 | Fix False Ceiling Aluminum Tiles Bath - Z2&3 - RF | 18599 | 300
Z2&3-C-FIN-20660 | Fix MEP Droppers Bath - Z2&3 - RF | 18389 | 200
Z2&3-C-FIN-20670 | Wall Paint (Emulsion) Garbage Room - Z2&3 - RF | 10000 | 647
Z2&3-C-FIN-20680 | Floor Epoxy Paint Garbage Room - Z2&3 - RF | 4833 | 17
Z2&3-C-FIN-20690 | Waterproof Garbage Room - Z2&3 - RF | 3898 | 34
Z2&3-C-FIN-20700 | Protection Screed Garbage Room - Z2&3 - RF | 3899 | 34
Z2&3-C-FIN-20710 | Ceiling Paint (Emulsion) Garbage Room - Z2&3 - RF | 401 | 25
Z2&3-C-FIN-20750 | Fix False Ceiling Suspension Lobby Passage & Offices - Z2&3 - RF | 18599 | 299
Z2&3-C-FIN-20760 | Wall Paint (Emulsion) Lobby Passage & Offices - Z2&3 - RF | 10000 | 647
Z2&3-C-FIN-20770 | Porcelain Floor Tiles Passage & Offices - Z2&3 - RF | 158821 | 2929
Z2&3-C-FIN-20780 | Fix False Ceiling Aluminum Tiles Lobby Passage & Offices - Z2&3 - RF | 18598 | 299
Z2&3-C-FIN-20790 | Fix False Ceiling Gypsum Board Lobby Passage & Offices - Z2&3 - RF | 18598 | 498
Z2&3-C-FIN-20800 | Fix MEP Droppers Lobby Passage & Offices - Z2&3 - RF | 18389 | 200
Z2&3-C-FIN-20810 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - RF | 2432 | 59
Z2&3-C-FIN-20820 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - RF | 2432 | 94
Z2&3-C-FIN-20830 | Floor Epoxy Paint Serv. Rooms - Z2&3 - RF | 4833 | 18
Z2&3-C-FIN-20840 | Floor Paint (Antifungal) Lift Shaft - Z2&3 - RF | 8202 | 272
Z2&3-C-FIN-20850 | Wall Paint (Antifungal) Lift Shaft - Z2&3 - RF | 8203 | 271
Z2&3-C-FIN-20860 | Ceiling Paint (Emulsion) Travelator - Z2&3 - B1 | 401 | 26
Z2&3-C-FIN-20870 | Wall Paint (Emulsion) Travelator - Z2&3 - B1 | 10000 | 647
Z2&3-C-FIN-20880 | Porcelain Floor Tiles Travelator - Z2&3 - B1 | 4734 | 88
Z2&3-C-FIN-20890 | Fix Doors - Z2&3 - B1 | 20821 | 103
Z2&3-C-FIN-20990 | Ceiling Paint (Acrylic) Serv. Rooms - Z2&3 - F1 | 2432 | 59
Z2&3-C-FIN-21000 | Floor Epoxy Paint Serv. Rooms - Z2&3 - F1 | 4833 | 17
Z2&3-C-FIN-21010 | Fix Doors Serv. Rooms - Z2&3 - F1 | 20821 | 103
Z2&3-C-FIN-21020 | Wall Paint (Acrylic) Serv. Rooms - Z2&3 - F1 | 2432 | 94
Z2&3-C-FIN-21040 | Fix False Ceiling Gypsum Board Passage & Entrance - Z2&3 - GF | 6812 | 182
Z2&3-C-FIN-21060 | Fix False Ceiling Aluminum Tiles Passage & Entrance - Z2&3 - GF | 6812 | 110
Z2&3-C-FIN-21070 | Fix False Ceiling Suspension Passage & Entrance - Z2&3 - GF | 6812 | 110
Z2&3-C-FIN-21080 | Wall Paint (Emulsion) Passage & Entrance - Z2&3 - GF | 10000 | 646
Z2&3-C-FIN-21090 | Porcelain Floor Tiles Passage & Entrance - Z2&3 - GF | 27710 | 511
Z2&3-C-FIN-21100 | Fix False Ceiling Suspension Wet + Nursing Area - Z2&3 - GF | 6812 | 110
Z2&3-C-FIN-21110 | Wall Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 28908 | 1090
Z2&3-C-FIN-21120 | Floor Ceramic Tiles Wet + Nursing Area - Z2&3 - GF | 6660 | 153
Z2&3-C-FIN-21140 | Fix False Ceiling Gypsum Board Wet + Nursing Area - Z2&3 - GF | 6812 | 183
Z2&3-C-FIN-21150 | Fix False Ceiling Aluminum Tiles Wet + Nursing Area - Z2&3 - GF | 6812 | 110
Z2&3-C-FIN-21200 | Fix False Ceiling Gypsum Board Passage H.Market - Z2&3 - GF | 6812 | 182
Z2&3-C-FIN-21220 | Fix False Ceiling Aluminum Tiles Passage H.Market - Z2&3 - GF | 6812 | 110
Z2&3-C-FIN-21230 | Fix False Ceiling Suspension Passage H.Market - Z2&3 - GF | 6812 | 110
Z2&3-C-FIN-21250 | Floor Stamp Concrete Passage H.Market- Z2&3 - GF | 21250 | 314
Z2&3-C-FIN-21260 | Floor Epoxy Paint IT & Maintanance Room - Z2&3 - GF | 4833 | 17
Z2&3-C-FIN-21290 | Ceiling Paint IT & Maintanance Room (Acrylic/Emulsion)- Z2&3 - GF | 401 | 26
Z2&3-C-FIN-21300 | Wall Paint IT & Maintanance Room (Acrylic/Emulsion) - Z2&3 - GF | 10000 | 648
Z2&3-C-FIN-21310 | Wall Paint Outside Area (Acrylic) - Z2&3 - F1 | 2432 | 94
Z2&3-C-FIN-21320 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - F1 | 13600 | 720
Z2&3-C-FIN-21340 | Wall Paint Outside Area (Acrylic) - Z2&3 - RF | 2432 | 95
Z2&3-C-FIN-21350 | Roof Floor Terrazo Tiles Outside Area - Z2&3 - RF | 13599 | 720
Z2&3-C-FIN-21360 | Floor Carpet Prayer Room - Z2&3 - F1 | 13558 | 134
Z2&3-C-FIN-SCASE-100 | on Staircase Acrylic Paint - Z2&3 - B2 - SRVF | 4258
Z2&3-C-FIN-SCASE-101 | on Staircase Floor Epoxy Paint - Z2&3 - B2 - SRVF | 4833 | 16
Z2&3-C-MEP-15160 | Fix G.I Box and conduits - Z2&3 - B2 | 26755 | 50
Z2&3-C-MEP-15170 | Fix ELV Trunkings - Z2&3 - B2 | 35621 | 250
Z2&3-C-MEP-15180 | Pull ELV Cables - Z2&3 - B2 | 46004 | 100
Z2&3-C-MEP-15190 | Fix Power Cable Trays - Z2&3 - B2 | 32905 | 500
Z2&3-C-MEP-15200 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - B2 | 10783 | 102
Z2&3-C-MEP-15210 | Pull Earthing & Power Cables - Z2&3 - B2 | 84716 | 250
Z2&3-C-MEP-15220 | Fix DBs - Z2&3 - B2 | 64069 | 50
Z2&3-C-MEP-15230 | Cable Terminations - Z2&3 - B2 | 61108 | 34
Z2&3-C-MEP-15240 | Fix Drainage Pipes - Z2&3 - B2 | 9366 | 249
Z2&3-C-MEP-15250 | Fix Fire Fighting Pipes - Z2&3 - B2 | 59346 | 500
Z2&3-C-MEP-15260 | Fix Chill Water Pipes - Z2&3 - B2 | 106571 | 333
Z2&3-C-MEP-15270 | Fix HVAC Ducts & Insulation - Z2&3 - B2 | 205842 | 665
Z2&3-C-MEP-15280 | Fix Fire Fighting Dropers - Z2&3 - B2 | 10628 | 50
Z2&3-C-MEP-15290 | Fix FCU - Z2&3 - B2 | 19285 | 100
Z2&3-C-MEP-15300 | Fix CCTV Devices - Z2&3 - B2 | 78094 | 50
Z2&3-C-MEP-15310 | Fix Light Fixtures - Z2&3 - B2 | 115829 | 100
Z2&3-C-MEP-15320 | Fix Switches, Sockets & Isolators - Z2&3 - B2 | 11418 | 50
Z2&3-C-MEP-15330 | Fix Fire Alarm Devices - Z2&3 - B2 | 51070 | 50
Z2&3-C-MEP-15340 | Fix Telephone & Voice Evac. Devices - Z2&3 - B2 | 43578 | 250
Z2&3-C-MEP-15350 | Fix LCS & ACS Devices - Z2&3 - B2 | 28738 | 50
Z2&3-C-MEP-15360 | Fix Emergency & Exit Lights - Z2&3 - B2 | 45974 | 50
Z2&3-C-MEP-15370 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - B2 | 12692 | 51
Z2&3-C-MEP-15380 | Fix Sprinklers - Z2&3 - B2 | 20692 | 500
Z2&3-C-MEP-15390 | Fix Grills & Diffusers - Z2&3 - B2 | 17845 | 285
Z2&3-C-MEP-15430 | Fix G.I Box and conduits - Z2&3 - B1 | 26755 | 50
Z2&3-C-MEP-15440 | Fix ELV Trunkings - Z2&3 - B1 | 35620 | 249
Z2&3-C-MEP-15450 | Pull ELV Cables - Z2&3 - B1 | 46004 | 101
Z2&3-C-MEP-15460 | Fix Power Cable Trays - Z2&3 - B1 | 32904 | 500
Z2&3-C-MEP-15470 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - B1 | 10780 | 102
Z2&3-C-MEP-15480 | Pull Earthing & Power Cables - Z2&3 - B1 | 84718 | 252
Z2&3-C-MEP-15490 | Fix DBs - Z2&3 - B1 | 64068 | 50
Z2&3-C-MEP-15500 | Cable Terminations - Z2&3 - B1 | 61109 | 34
Z2&3-C-MEP-15510 | Fix Drainage Pipes - Z2&3 - B1 | 9366 | 249
Z2&3-C-MEP-15520 | Fix Fire Fighting Pipes - Z2&3 - B1 | 59346 | 500
Z2&3-C-MEP-15530 | Fix Chill Water Pipes - Z2&3 - B1 | 106571 | 333
Z2&3-C-MEP-15540 | Fix HVAC Ducts & Insulation - Z2&3 - B1 | 205842 | 665
Z2&3-C-MEP-15550 | Fix Fire Fighting Dropers - Z2&3 - B1 | 10627 | 50
Z2&3-C-MEP-15560 | Fix FCU - Z2&3 - B1 | 39085 | 100
Z2&3-C-MEP-15570 | Fix CCTV Devices - Z2&3 - B1 | 78094 | 50
Z2&3-C-MEP-15580 | Fix Light Fixtures - Z2&3 - B1 | 115829 | 100
Z2&3-C-MEP-15590 | Fix Switches, Sockets & Isolators - Z2&3 - B1 | 11418 | 50
Z2&3-C-MEP-15600 | Fix Fire Alarm Devices - Z2&3 - B1 | 51070 | 50
Z2&3-C-MEP-15610 | Fix Telephone & Voice Evac. Devices - Z2&3 - B1 | 43578 | 250
Z2&3-C-MEP-15620 | Fix LCS & ACS Devices - Z2&3 - B1 | 28739 | 50
Z2&3-C-MEP-15630 | Fix Emergency & Exit Lights - Z2&3 - B1 | 45974 | 50
Z2&3-C-MEP-15640 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - B1 | 12692 | 51
Z2&3-C-MEP-15650 | Fix Sprinklers - Z2&3 - B1 | 20692 | 500
Z2&3-C-MEP-15660 | Fix Grills & Diffusers - Z2&3 - B1 | 17846 | 286
Z2&3-C-MEP-15700 | Fix G.I Box and conduits - Z2&3 - F1 | 26755 | 50
Z2&3-C-MEP-15710 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - F1 | 6591 | 50
Z2&3-C-MEP-15720 | Fix ELV Trunkings - Z2&3 - F1 | 35619 | 250
Z2&3-C-MEP-15730 | Pull ELV Cables - Z2&3 - F1 | 46004 | 101
Z2&3-C-MEP-15740 | Fix Power Cable Trays - Z2&3 - F1 | 32904 | 501
Z2&3-C-MEP-15750 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - F1 | 10782 | 101
Z2&3-C-MEP-15760 | Pull Earthing & Power Cables - Z2&3 - F1 | 84717 | 250
Z2&3-C-MEP-15770 | Fix DBs - Z2&3 - F1 | 64069 | 50
Z2&3-C-MEP-15780 | Cable Terminations - Z2&3 - F1 | 61109 | 34
Z2&3-C-MEP-15790 | Fix Drainage Pipes - Z2&3 - F1 | 9368 | 250
Z2&3-C-MEP-15800 | Fix Fire Fighting Pipes - Z2&3 - F1 | 59346 | 499
Z2&3-C-MEP-15810 | Fix Chill Water Pipes - Z2&3 - F1 | 106572 | 333
Z2&3-C-MEP-15820 | Fix HVAC Ducts & Insulation - Z2&3 - F1 | 205840 | 667
Z2&3-C-MEP-15830 | Fix Fire Fighting Dropers - Z2&3 - F1 | 10628 | 50
Z2&3-C-MEP-15840 | Fix FCU - Z2&3 - F1 | 129834 | 100
Z2&3-C-MEP-15850 | Fix Water Supply Pipes - Z2&3 - F1 | 6591 | 250
Z2&3-C-MEP-15860 | Fix CCTV Devices - Z2&3 - F1 | 78093 | 50
Z2&3-C-MEP-15870 | Fix Light Fixtures - Z2&3 - F1 | 115829 | 101
Z2&3-C-MEP-15880 | Fix Switches, Sockets & Isolators - Z2&3 - F1 | 11418 | 50
Z2&3-C-MEP-15890 | Fix Fire Alarm Devices - Z2&3 - F1 | 51070 | 50
Z2&3-C-MEP-15900 | Fix Telephone & Voice Evac. Devices - Z2&3 - F1 | 43578 | 250
Z2&3-C-MEP-15910 | Fix LCS & ACS Devices - Z2&3 - F1 | 28739 | 50
Z2&3-C-MEP-15920 | Fix Emergency & Exit Lights - Z2&3 - F1 | 45974 | 50
Z2&3-C-MEP-15930 | Fix Grills & Diffusers - Z2&3 - F1 | 17846 | 286
Z2&3-C-MEP-15940 | Fix Water Heater & Sanitary Accessories - Z2&3 - F1 | 75574 | 334
Z2&3-C-MEP-15950 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - F1 | 12692 | 50
Z2&3-C-MEP-15960 | Fix Sprinklers - Z2&3 - F1 | 20692 | 500
Z2&3-C-MEP-16000 | Fix G.I Box and conduits - Z2&3 - GF | 26755 | 50
Z2&3-C-MEP-16010 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - GF | 6591 | 50
Z2&3-C-MEP-16020 | Fix ELV Trunkings - Z2&3 - GF | 35620 | 249
Z2&3-C-MEP-16030 | Pull ELV Cables - Z2&3 - GF | 46004 | 101
Z2&3-C-MEP-16040 | Fix Power Cable Trays - Z2&3 - GF | 32904 | 500
Z2&3-C-MEP-16050 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - GF | 10780 | 102
Z2&3-C-MEP-16060 | Pull Earthing & Power Cables - Z2&3 - GF | 84718 | 252
Z2&3-C-MEP-16070 | Fix DBs - Z2&3 - GF | 64068 | 50
Z2&3-C-MEP-16080 | Cable Terminations - Z2&3 - GF | 61109 | 33
Z2&3-C-MEP-16090 | Fix Drainage Pipes - Z2&3 - GF | 9368 | 250
Z2&3-C-MEP-16100 | Fix Fire Fighting Pipes - Z2&3 - GF | 59346 | 499
Z2&3-C-MEP-16110 | Fix Chill Water Pipes - Z2&3 - GF | 106571 | 333
Z2&3-C-MEP-16120 | Fix HVAC Ducts & Insulation - Z2&3 - GF | 205840 | 667
Z2&3-C-MEP-16130 | Fix Fire Fighting Dropers - Z2&3 - GF | 10627 | 50
Z2&3-C-MEP-16140 | Fix FCU - Z2&3 - GF | 151284 | 100
Z2&3-C-MEP-16150 | Fix Water Supply Pipes - Z2&3 - GF | 6591 | 249
Z2&3-C-MEP-16160 | Fix CCTV Devices - Z2&3 - GF | 78093 | 50
Z2&3-C-MEP-16170 | Fix Light Fixtures - Z2&3 - GF | 115829 | 100
Z2&3-C-MEP-16180 | Fix Switches, Sockets & Isolators - Z2&3 - GF | 11418 | 50
Z2&3-C-MEP-16190 | Fix Fire Alarm Devices - Z2&3 - GF | 51070 | 50
Z2&3-C-MEP-16200 | Fix Telephone & Voice Evac. Devices - Z2&3 - GF | 43578 | 250
Z2&3-C-MEP-16210 | Fix LCS & ACS Devices - Z2&3 - GF | 28739 | 50
Z2&3-C-MEP-16220 | Fix Emergency & Exit Lights - Z2&3 - GF | 45974 | 50
Z2&3-C-MEP-16230 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - GF | 12692 | 50
Z2&3-C-MEP-16240 | Fix Sprinklers - Z2&3 - GF | 20692 | 500
Z2&3-C-MEP-16250 | Fix Grills & Diffusers - Z2&3 - GF | 17846 | 285
Z2&3-C-MEP-16260 | Fix Water Heater & Sanitary Accessories - Z2&3 - GF | 75574 | 334
Z2&3-C-MEP-16300 | Fix G.I Box and conduits - Z2&3 - F2 | 26755 | 50
Z2&3-C-MEP-16310 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - F2 | 6591 | 50
Z2&3-C-MEP-16320 | Fix ELV Trunkings - Z2&3 - F2 | 35619 | 249
Z2&3-C-MEP-16330 | Pull ELV Cables - Z2&3 - F2 | 46003 | 101
Z2&3-C-MEP-16340 | Fix Power Cable Trays - Z2&3 - F2 | 32904 | 501
Z2&3-C-MEP-16350 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - F2 | 10783 | 101
Z2&3-C-MEP-16360 | Pull Earthing & Power Cables - Z2&3 - F2 | 84718 | 250
Z2&3-C-MEP-16370 | Fix DBs - Z2&3 - F2 | 64069 | 50
Z2&3-C-MEP-16380 | Cable Terminations - Z2&3 - F2 | 61109 | 34
Z2&3-C-MEP-16390 | Fix Drainage Pipes - Z2&3 - F2 | 9368 | 250
Z2&3-C-MEP-16400 | Fix Fire Fighting Pipes - Z2&3 - F2 | 59346 | 500
Z2&3-C-MEP-16410 | Fix Chill Water Pipes - Z2&3 - F2 | 106572 | 333
Z2&3-C-MEP-16420 | Fix HVAC Ducts & Insulation - Z2&3 - F2 | 205840 | 668
Z2&3-C-MEP-16430 | Fix Fire Fighting Dropers - Z2&3 - F2 | 10627 | 50
Z2&3-C-MEP-16440 | Fix FCU - Z2&3 - F2 | 151284 | 100
Z2&3-C-MEP-16450 | Fix Water Supply Pipes - Z2&3 - F2 | 6591 | 249
Z2&3-C-MEP-16460 | Fix LPG Pipes - Z2&3 - F2 | 12341 | 167
Z2&3-C-MEP-16470 | Fix CCTV Devices - Z2&3 - F2 | 78093 | 50
Z2&3-C-MEP-16480 | Fix Light Fixtures - Z2&3 - F2 | 115829 | 100
Z2&3-C-MEP-16490 | Fix Switches, Sockets & Isolators - Z2&3 - F2 | 11418 | 50
Z2&3-C-MEP-16500 | Fix Fire Alarm Devices - Z2&3 - F2 | 51070 | 50
Z2&3-C-MEP-16510 | Fix Telephone & Voice Evac. Devices - Z2&3 - F2 | 43578 | 250
Z2&3-C-MEP-16520 | Fix LCS & ACS Devices - Z2&3 - F2 | 28739 | 50
Z2&3-C-MEP-16530 | Fix Emergency & Exit Lights - Z2&3 - F2 | 45974 | 50
Z2&3-C-MEP-16540 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - F2 | 12692 | 51
Z2&3-C-MEP-16550 | Fix Sprinklers - Z2&3 - F2 | 20692 | 500
Z2&3-C-MEP-16560 | Fix Water Heater & Sanitary Accessories - Z2&3 - F2 | 75575 | 333
Z2&3-C-MEP-16570 | Fix Gas Detectors - Z2&3 - F2 | 12341 | 167
Z2&3-C-MEP-16580 | Fix Grills & Diffusers - Z2&3 - F2 | 17846 | 286
Z2&3-C-MEP-16620 | Fix G.I Box and conduits - Z2&3 - RF | 26755 | 50
Z2&3-C-MEP-16630 | Fix Drainage & Water Supply Pipes Block Wall - Z2&3 - RF | 6591 | 50
Z2&3-C-MEP-16640 | Fix ELV Trunkings - Z2&3 - RF | 35620 | 250
Z2&3-C-MEP-16650 | Pull ELV Cables - Z2&3 - RF | 46004 | 102
Z2&3-C-MEP-16660 | Fix Power Cable Trays - Z2&3 - RF | 32904 | 500
Z2&3-C-MEP-16670 | Pull Electricl Wires (Ceiling & Walls) - Z2&3 - RF | 10783 | 102
Z2&3-C-MEP-16680 | Pull Earthing & Power Cables - Z2&3 - RF | 84717 | 249
Z2&3-C-MEP-16690 | Fix DBs - Z2&3 - RF | 64069 | 50
Z2&3-C-MEP-16700 | Cable Terminations - Z2&3 - RF | 61109 | 33
Z2&3-C-MEP-16710 | Fix LPG Pipes - Z2&3 - RF | 12342 | 167
Z2&3-C-MEP-16720 | Fix Drainage Pipes - Z2&3 - RF | 9368 | 250
Z2&3-C-MEP-16730 | Fix Fire Fighting Pipes - Z2&3 - RF | 59346 | 500
Z2&3-C-MEP-16740 | Fix Chill Water Pipes - Z2&3 - RF | 106571 | 332
Z2&3-C-MEP-16750 | Fix HVAC Ducts & Insulation - Z2&3 - RF | 205841 | 667
Z2&3-C-MEP-16760 | Fix Fire Fighting Dropers - Z2&3 - RF | 10628 | 50
Z2&3-C-MEP-16770 | Fix FCU - Z2&3 - RF | 129835 | 100
Z2&3-C-MEP-16780 | Fix Water Supply Pipes - Z2&3 - RF | 6590 | 250
Z2&3-C-MEP-16790 | Fix CCTV Devices - Z2&3 - RF | 78093 | 50
Z2&3-C-MEP-16800 | Fix Light Fixtures - Z2&3 - RF | 115829 | 100
Z2&3-C-MEP-16810 | Fix Switches, Sockets & Isolators - Z2&3 - RF | 11418 | 50
Z2&3-C-MEP-16820 | Fix Fire Alarm Devices - Z2&3 - RF | 51069 | 50
Z2&3-C-MEP-16830 | Fix Telephone & Voice Evac. Devices - Z2&3 - RF | 43578 | 250
Z2&3-C-MEP-16840 | Fix LCS & ACS Devices - Z2&3 - RF | 28739 | 50
Z2&3-C-MEP-16850 | Fix Emergency & Exit Lights - Z2&3 - RF | 45974 | 50
Z2&3-C-MEP-16860 | Fix Gas Detectors - Z2&3 - RF | 12342 | 166
Z2&3-C-MEP-16870 | Fix Fire Hose Cabinets & Hose Reels - Z2&3 - RF | 12692 | 50
Z2&3-C-MEP-16880 | Fix Sprinklers - Z2&3 - RF | 20692 | 500
Z2&3-C-MEP-16890 | Fix Grills & Diffusers - Z2&3 - RF | 17846 | 286
Z2&3-C-MEP-16900 | Fix Water Heater & Sanitary Accessories - Z2&3 - RF | 75574 | 334
Z2-11520 | Post Tensioning the Slab - Z2 - F1 | 18819 | 4
Z2-11530 | Post Tensioning the Slab - Z2 - F2 | 19103 | 4
Z2-11540 | Post Tensioning the Slab - Z2 - RF | 19044 | 4
Z2-11550 | Post Tensioning the Slab - Z2 - SRVF | 15998 | 4
Z2-C-CON-5840 | PCC Blind Concrete - Z2 - Lift Pit | 8610 | 4
Z2-C-CON-5850 | Waterproof Membrane - Z2 - Lift Pit | 51140 | 20
Z2-C-CON-5860 | Protection Screed - Z2 - Lift Pit | 5490 | 26
Z2-C-CON-5870 | Fix Rebar - Z2 - Lift Pit | 15186 | 249
Z2-C-CON-5890 | Pour Concrete - Z2 - Lift Pit | 15186 | 72
Z2-C-CON-5900 | PCC Blind Concrete - Z2 - Raft | 43050 | 148
Z2-C-CON-5910 | Waterproof Membrane - Z2 - Raft | 27450 | 1180
Z2-C-CON-5920 | Protection Screed - Z2 - Raft | 255700 | 72
Z2-C-CON-5930 | Fix Rebar - Z2 - Raft | 746627 | 13737
Z2-C-CON-5940 | Fix MEP Provisions - Z2 - Raft | 10500 | 100
Z2-C-CON-5950 | Fix Formwork - Z2 - Raft | 30991 | 196
Z2-C-CON-5960 | Pour Concrete - Z2 - Raft | 548054 | 3317
Z2-C-CON-5970 | Fix Rebar Columns - Z2 - B2 | 47430 | 2266
Z2-C-CON-5980 | Fix Formwork Columns - Z2 - B2 | 23715 | 667
Z2-C-CON-5990 | Pour Concrete Columns - Z2 - B2 | 47431 | 130
Z2-C-CON-6000 | Fix Rebar Retaining Walls - Z2 - B2 | 65426 | 1432
Z2-C-CON-6010 | Fix Formwork Retaining Walls - Z2 - B2 | 32713 | 1171
Z2-C-CON-6020 | Pour Concrete Retaining Walls - Z2 - B2 | 65427 | 240
Z2-C-CON-6030 | Pour Concrete Core Walls - Z2 - B2 | 33489 | 136
Z2-C-CON-6040 | Fix Rebar Core Walls - Z2 - B2 | 25118 | 950
Z2-C-CON-6050 | Fix Formwork Core Walls - Z2 - B2 | 25117 | 936
Z2-C-CON-6060 | Fix Formwork Stairs - Z2 - B2 | 1864 | 3
Z2-C-CON-6070 | Fix Rebar Stairs - Z2 - B2 | 3729 | 32
Z2-C-CON-6080 | Pour Concrete Stairs - Z2 - B2 | 3729 | 8
Z2-C-CON-6090 | Fix Rebar Retaining Walls - Z2 - B1 | 65428 | 1138
Z2-C-CON-6100 | Fix Formwork Retaining Walls - Z2 - B1 | 32713 | 1171
Z2-C-CON-6110 | Pour Concrete Retaining Walls - Z2 - B1 | 65427 | 240
Z2-C-CON-6120 | Fix Formwork Core Walls - Z2 - B1 | 25118 | 946
Z2-C-CON-6130 | Fix Rebar Core Walls - Z2 - B1 | 25117 | 913
Z2-C-CON-6140 | Pour Concrete Core Walls - Z2 - B1 | 33489 | 138
Z2-C-CON-6150 | Fix Rebar Columns - Z2 - B1 | 47430 | 1735
Z2-C-CON-6160 | Fix Formwork Columns - Z2 - B1 | 23714 | 743
Z2-C-CON-6170 | Pour Concrete Columns - Z2 - B1 | 47431 | 146
Z2-C-CON-6180 | Fix Formwork Stairs - Z2 - B1 | 1864 | 4
Z2-C-CON-6190 | Fix Rebar Stairs - Z2 - B1 | 3729 | 32
Z2-C-CON-6200 | Pour Concrete Stairs - Z2 - B1 | 3729 | 8
Z2-C-CON-6210 | Fix Formwork Slabs - Z2 - B1 | 100188 | 3041
Z2-C-CON-6220 | Fix Rebar Slabs - Z2 - B1 | 200376 | 4027
Z2-C-CON-6230 | Pour Concrete Slabs - Z2 - B1 | 200376 | 1036
Z2-C-CON-6240 | Fix MEP Containment & Provisions - Z2 - B1 | 5440
Z2-C-CON-6250 | Fix Rebar Core Walls - Z2 - GF | 54255 | 1707
Z2-C-CON-6260 | Fix Formwork Core Walls - Z2 - GF | 28239 | 1721
Z2-C-CON-6270 | Pour Concrete Core Walls - Z2 - GF | 55661 | 236
Z2-C-CON-6280 | Fix Rebar Columns - Z2 - GF | 72503 | 2256
Z2-C-CON-6290 | Fix Formwork Columns - Z2 - GF | 38017 | 1136
Z2-C-CON-6300 | Pour Concrete Columns - Z2 - GF | 76127 | 224
Z2-C-CON-6310 | Fix Formwork Stairs - Z2 - GF | 2419 | 4
Z2-C-CON-6320 | Fix Rebar Stairs - Z2 - GF | 4838 | 16
Z2-C-CON-6330 | Pour Concrete Stairs - Z2 - GF | 4839 | 10
Z2-C-CON-6340 | Fix Formwork Slabs - Z2 - GF | 129638 | 2844
Z2-C-CON-6350 | Fix Rebar Slabs - Z2 - GF | 259274 | 7049
Z2-C-CON-6360 | Pour Concrete Slabs - Z2 - GF | 259275 | 1278
Z2-C-CON-6370 | Fix MEP Containment & Provisions - Z2 - GF | 5440
Z2-C-CON-6380 | Fix Formwork Slabs - Z2 - F1 | 144523 | 2843
Z2-C-CON-6390 | Fix Rebar Slabs - Z2 - F1 | 187928 | 3628
Z2-C-CON-6400 | Fix MEP Containment & Provisions - Z2 - F1 | 5440
Z2-C-CON-6410 | Pour Concrete Slabs - Z2 - F1 | 219801 | 988
Z2-C-CON-6420 | Fix Rebar Core Walls - Z2 - F1 | 53594 | 1686
Z2-C-CON-6430 | Fix Formwork Core Walls - Z2 - F1 | 28287 | 1724
Z2-C-CON-6440 | Pour Concrete Core Walls - Z2 - F1 | 56412 | 240
Z2-C-CON-6450 | Fix Rebar Columns - Z2 - F1 | 73448 | 2284
Z2-C-CON-6460 | Fix Formwork Columns - Z2 - F1 | 37830 | 1130
Z2-C-CON-6470 | Pour Concrete Columns - Z2 - F1 | 75888 | 224
Z2-C-CON-6480 | Fix Formwork Stairs - Z2 - F1 | 2419 | 4
Z2-C-CON-6490 | Fix Rebar Stairs - Z2 - F1 | 4839 | 16
Z2-C-CON-6500 | Pour Concrete Stairs - Z2 - F1 | 4839 | 10
Z2-C-CON-6510 | Fix Rebar Slabs - Z2 - F2 | 193299 | 3726
Z2-C-CON-6520 | Fix Formwork Slabs - Z2 - F2 | 145945 | 2832
Z2-C-CON-6530 | Pour Concrete Slabs - Z2 - F2 | 455692 | 994
Z2-C-CON-6540 | Fix MEP Containment & Provisions - Z2 - F2 | 5440
Z2-C-CON-6550 | Fix Rebar Core Walls - Z2 - F2 | 35418 | 1114
Z2-C-CON-6560 | Fix Formwork Core Walls - Z2 - F2 | 16704 | 1018
Z2-C-CON-6570 | Pour Concrete Core Walls - Z2 - F2 | 33899 | 144
Z2-C-CON-6580 | Fix Rebar Columns - Z2 - F2 | 50067 | 1557
Z2-C-CON-6590 | Fix Formwork Columns - Z2 - F2 | 24315 | 727
Z2-C-CON-6600 | Pour Concrete Columns - Z2 - F2 | 48001 | 142
Z2-C-CON-6610 | Fix Formwork Stairs - Z2 - F2 | 2419 | 4
Z2-C-CON-6620 | Fix Rebar Stairs - Z2 - F2 | 4839 | 16
Z2-C-CON-6630 | Pour Concrete Stairs - Z2 - F2 | 4839 | 10
Z2-C-CON-6640 | Fix Formwork Slabs - Z2 - RF | 145648 | 2831
Z2-C-CON-6650 | Fix Rebar Slabs - Z2 - RF | 114257 | 3707
Z2-C-CON-6660 | Pour Concrete Slabs - Z2 - RF | 41824 | 990
Z2-C-CON-6670 | Fix MEP Containment & Provisions - Z2 - RF | 5440
Z2-C-CON-6680 | Fix Rebar Core Walls - Z2 - RF | 34810 | 1096
Z2-C-CON-6690 | Fix Formwork Core Walls - Z2 - RF | 16641 | 1015
Z2-C-CON-6700 | Pour Concrete Core Walls - Z2 - RF | 33788 | 144
Z2-C-CON-6710 | Fix Rebar Columns - Z2 - RF | 40997 | 1275
Z2-C-CON-6720 | Fix Formwork Columns - Z2 - RF | 18849 | 563
Z2-C-CON-6730 | Pour Concrete Columns - Z2 - RF | 38299 | 112
Z2-C-CON-6740 | Fix Formwork Stairs - Z2 - RF | 2419 | 3
Z2-C-CON-6750 | Fix Rebar Stairs - Z2 - RF | 4032 | 14
Z2-C-CON-6760 | Pour Concrete Stairs - Z2 - RF | 4032 | 8
Z2-C-CON-6770 | Fix Formwork Slabs - Z2 - SRVF | 130418 | 2426
Z2-C-CON-6780 | Fix Rebar Slabs - Z2 - SRVF | 236165 | 3040
Z2-C-CON-6790 | Pour Concrete Slabs - Z2 - SRVF | 274411 | 850
Z2-C-CON-6800 | Fix MEP Containment & Provisions - Z2 - SRVF | 5440
Z2-C-CON-6810 | Fix Rebar Core Walls - Z2 - SRVF | 20590 | 648
Z2-C-CON-6820 | Fix Formwork Core Walls - Z2 - SRVF | 9461 | 576
Z2-C-CON-6830 | Pour Concrete Core Walls - Z2 - SRVF | 18906 | 4
Z2-C-CON-6840 | Fix Rebar Columns - Z2 - SRVF | 3706 | 116
Z2-C-CON-6850 | Fix Formwork Columns - Z2 - SRVF | 1349 | 41
Z2-C-CON-6860 | Pour Concrete Columns - Z2 - SRVF | 2405 | 8
Z2-C-CON-6870 | Pour MEP RCC Pedastals - Z2 - SRVF | 807 | 2
Z2-C-CON-6880 | Fix Formwork Parapet - Z2 - SRVF | 14509 | 113
Z2-C-CON-6890 | Fix Rebar Parapet - Z2 - SRVF | 29019 | 236
Z2-C-CON-6900 | Pour Concrete Parapet - Z2 - SRVF | 29019 | 136
Z2-C-CON-6910 | Fix Formwork Slabs - Z2 - TRF | 7663 | 298
Z2-C-CON-6920 | Fix Rebar Slabs - Z2 - TRF | 15325 | 304
Z2-C-CON-6930 | Pour Concrete Slabs - Z2 - TRF | 15325 | 90
Z2-C-CON-6940 | Fix MEP Containment & Provisions - Z2 - TRF | 5440
Z2-C-CON-6950 | Fix Formwork Parapet - Z2 - TRF | 14509 | 113
Z2-C-CON-6960 | Fix Rebar Parapet - Z2 - TRF | 29019 | 236
Z2-C-CON-6970 | Pour Concrete Parapet - Z2 - TRF | 29019 | 136
Z2-C-EW-10420 | Waterproof Membrane on Gunite Wall - Z2-B2 |  | 200
Z2-C-GRBCH-11370 | Install Garbage Chute Cylinder - Z2 - GF to SRVF | 16800 | 268
Z2-C-GRBCH-11380 | Install Garbage Chute Supporting Frame - Z2 - GF to SRVF | 16800 | 268
Z2-C-GRBCH-11390 | Block & Plaster Garbage Room - Z2 - GF to SRVF | 1391 | 172
Z2-C-GRBCH-11400 | Install Garbage Chute Openings & Doors - Z2 - GF to SRVF | 16800 | 268
Z2-C-GRBCH-11410 | Install Garbage Chute Roof Top Unit with All Provisions | 16800 | 266
Z2-C-GRBCH-11420 | Install Garbage Chute Bottom Unit with All Provisions | 16800 | 266
Z2-C-LIFT-10520 | Install Working Platform for PL-3 & 4 (B2 to SRVF) | 97230 | 100
Z2-C-LIFT-10530 | Install Steel Support Beams & Tracks PL-3 & 4 (B2 to SRVF) | 97230 | 100
Z2-C-LIFT-10540 | Repair Lift Shaft PL-3 & 4 (B2 to SRVF) | 97230 | 100
Z2-C-LIFT-10550 | Install Working Platform for CL B2 to - F2 | 97230 | 100
Z2-C-LIFT-10560 | Install Steel Support Beams & Tracks CL B2 to - F2 | 97230 | 100
Z2-C-LIFT-10580 | Terminate Tracks & Cross Beams CL B2 to - F2 | 97230 | 100
Z2-C-LIFT-10610 | Install Lift Motors & Hydraulics CL B2 to - F2) | 97230 | 100
Z2-C-LIFT-10620 | Install Lift Control Unit CL B2 to - F2 | 97230 | 100
Z2-C-LIFT-10630 | Power Connection & Test Runs CL B2 to - F2 | 97231 | 100
Z2-C-LIFT-10640 | Terminate Tracks & Cross Beams (B2 to GF) | 97231 | 100
Z2-C-LIFT-10650 | Install Lift Access Doors (B2 to GF) | 97230 | 100
Z2-C-LIFT-10660 | Install Lift Cabin (B2 to GF) | 97231 | 100
Z2-C-LIFT-10670 | Install Lift Motors, Cables, Counter Weight & Brakes (B2 to GF) | 97231 | 100
Z2-C-LIFT-10680 | Install Lift Control Unit (B2 to GF) | 97230 | 100
Z2-C-LIFT-10690 | Power Connection & Test Runs (B2 to GF) | 97230 | 100
Z2-C-LIFT-10700 | Install Working Platform for PL-5 (B2 to SRVF) | 97230 | 100
Z2-C-LIFT-10710 | Install Steel Support Beams & Tracks PL-5 (B2 to SRVF) | 97230 | 100
Z2-C-LIFT-10720 | Repair Lift Shaft PL-5 (B2 to SRVF) | 97231 | 100
Z2-C-LIFT-10730 | Terminate Tracks & Cross Beams (B2 to GF) | 97230 | 100
Z2-C-LIFT-10740 | Install Lift Access Doors (B2 to GF) | 97231 | 100
Z2-C-LIFT-10750 | Install Lift Cabin (B2 to GF) | 97230 | 100
Z2-C-LIFT-10760 | Install Lift Motors, Cables, Counter Weight & Brakes (B2 to GF) | 97231 | 100
Z2-C-LIFT-10770 | Install Lift Control Unit (B2 to GF) | 97231 | 100
Z2-C-LIFT-10780 | Power Connection & Test Runs (B2 to GF) | 97231 | 100
Z2-C-LIFT-10790 | Install Working Platform for CL B2 to GF | 97230 | 100
Z2-C-LIFT-10800 | Install Steel Support Beams & Tracks CL B2 to GF | 97230 | 580
Z2-C-LIFT-10820 | Terminate Tracks & Cross Beams CL B2 to GF | 97230 | 100
Z2-C-LIFT-10850 | Install Lift Motors & Hydraulics CL B2 to GF) | 97231 | 100
Z2-C-LIFT-10860 | Install Lift Control Unit CL B2 to GF | 97230 | 100
Z2-C-LIFT-10870 | Power Connection & Test Runs CL B2 to GF | 97230 | 100
Z2-C-RSRS-11120 | Install Drainage Pipe Risers | 6591 | 999
Z2-C-RSRS-11130 | Install Water Supply Pipe Risers | 6591 | 999
Z2-C-RSRS-11140 | Install CHW Pipe Risers | 106570 | 1000
Z2-C-RSRS-11150 | Install Fire Fighting Pipe Risers | 404400 | 997
Z2-C-RSRS-11160 | Install Duct Risers | 202071 | 998
Z2-C-RSRS-11170 | Install LPG Pipe Risers | 12340 | 170
Z2-C-RSRS-11180 | Install Cable treys & Trunking Risers | 271608 | 251
Z2-C-RSRS-11190 | Install Busbar Risers | 158075 | 251
Z3-11520 | Post Tensioning the Slab - Z3 - F1 | 18819
Z3-11530 | Post Tensioning the Slab - Z3 - F2 | 19103
Z3-11540 | Post Tensioning the Slab - Z3 - RF | 19044
Z3-11550 | Post Tensioning the Slab - Z3 - SRVF | 15998
Z3-C-CON-5840 | PCC Blind Concrete - Z3 - Lift Pit | 8610 | 4
Z3-C-CON-5850 | Waterproof Membrane - Z3 - Lift Pit | 51140
Z3-C-CON-5860 | Protection Screed - Z3 - Lift Pit | 5490 | 26
Z3-C-CON-5870 | Fix Rebar - Z3 - Lift Pit | 15185 | 248
Z3-C-CON-5890 | Pour Concrete - Z3 - Lift Pit | 15186 | 72
Z3-C-CON-5900 | PCC Blind Concrete - Z3 - Raft | 345090 | 148
Z3-C-CON-5910 | Waterproof Membrane - Z3 - Raft | 27450
Z3-C-CON-5920 | Protection Screed - Z3 - Raft | 255701 | 74
Z3-C-CON-5930 | Fix Rebar - Z3 - Raft | 544585 | 13737
Z3-C-CON-5940 | Fix MEP Provisions - Z3 - Raft | 10500 | 100
Z3-C-CON-5950 | Fix Formwork - Z3 - Raft | 30992 | 196
Z3-C-CON-5960 | Pour Concrete - Z3 - Raft | 548054 | 3317
Z3-C-CON-5970 | Fix Rebar Columns - Z3 - B2 | 47431 | 2265
Z3-C-CON-5980 | Fix Formwork Columns - Z3 - B2 | 23716 | 668
Z3-C-CON-5990 | Pour Concrete Columns - Z3 - B2 | 47430 | 132
Z3-C-CON-6000 | Fix Rebar Retaining Walls - Z3 - B2 | 65427 | 1433
Z3-C-CON-6010 | Fix Formwork Retaining Walls - Z3 - B2 | 32714 | 1172
Z3-C-CON-6020 | Pour Concrete Retaining Walls - Z3 - B2 | 65427 | 242
Z3-C-CON-6030 | Pour Concrete Core Walls - Z3 - B2 | 33489 | 136
Z3-C-CON-6040 | Fix Rebar Core Walls - Z3 - B2 | 25117 | 949
Z3-C-CON-6050 | Fix Formwork Core Walls - Z3 - B2 | 25118 | 936
Z3-C-CON-6060 | Fix Formwork Stairs - Z3 - B2 | 1865 | 3
Z3-C-CON-6070 | Fix Rebar Stairs - Z3 - B2 | 3729 | 32
Z3-C-CON-6080 | Pour Concrete Stairs - Z3 - B2 | 3729 | 8
Z3-C-CON-6090 | Fix Rebar Retaining Walls - Z3 - B1 | 65428 | 1138
Z3-C-CON-6100 | Fix Formwork Retaining Walls - Z3 - B1 | 32714 | 1171
Z3-C-CON-6110 | Pour Concrete Retaining Walls - Z3 - B1 | 65427 | 240
Z3-C-CON-6120 | Fix Formwork Core Walls - Z3 - B1 | 25117 | 945
Z3-C-CON-6130 | Fix Rebar Core Walls - Z3 - B1 | 25117 | 914
Z3-C-CON-6140 | Pour Concrete Core Walls - Z3 - B1 | 33489 | 138
Z3-C-CON-6150 | Fix Rebar Columns - Z3 - B1 | 47430 | 1735
Z3-C-CON-6160 | Fix Formwork Columns - Z3 - B1 | 23715 | 743
Z3-C-CON-6170 | Pour Concrete Columns - Z3 - B1 | 47430 | 146
Z3-C-CON-6180 | Fix Formwork Stairs - Z3 - B1 | 1864 | 4
Z3-C-CON-6190 | Fix Rebar Stairs - Z3 - B1 | 3729 | 32
Z3-C-CON-6200 | Pour Concrete Stairs - Z3 - B1 | 3729 | 8
Z3-C-CON-6210 | Fix Formwork Slabs - Z3 - B1 | 100188 | 3040
Z3-C-CON-6220 | Fix Rebar Slabs - Z3 - B1 | 200376 | 4028
Z3-C-CON-6230 | Pour Concrete Slabs - Z3 - B1 | 200376 | 1036
Z3-C-CON-6240 | Fix MEP Containment & Provisions - Z3 - B1 | 5440
Z3-C-CON-6250 | Fix Rebar Core Walls - Z3 - GF | 54255 | 1707
Z3-C-CON-6260 | Fix Formwork Core Walls - Z3 - GF | 28239 | 1721
Z3-C-CON-6270 | Pour Concrete Core Walls - Z3 - GF | 55661 | 236
Z3-C-CON-6280 | Fix Rebar Columns - Z3 - GF | 72503 | 2256
Z3-C-CON-6290 | Fix Formwork Columns - Z3 - GF | 38017 | 1136
Z3-C-CON-6300 | Pour Concrete Columns - Z3 - GF | 76127 | 224
Z3-C-CON-6310 | Fix Formwork Stairs - Z3 - GF | 2419 | 4
Z3-C-CON-6320 | Fix Rebar Stairs - Z3 - GF | 4839 | 16
Z3-C-CON-6330 | Pour Concrete Stairs - Z3 - GF | 4839 | 10
Z3-C-CON-6340 | Fix Formwork Slabs - Z3 - GF | 129638 | 2844
Z3-C-CON-6350 | Fix Rebar Slabs - Z3 - GF | 259274 | 7049
Z3-C-CON-6360 | Pour Concrete Slabs - Z3 - GF | 259275 | 1278
Z3-C-CON-6370 | Fix MEP Containment & Provisions - Z3 - GF | 5440
Z3-C-CON-6380 | Fix Formwork Slabs - Z3 - F1 | 144523 | 2843
Z3-C-CON-6390 | Fix Rebar Slabs - Z3 - F1 | 187928 | 3628
Z3-C-CON-6400 | Fix MEP Containment & Provisions - Z3 - F1 | 5440
Z3-C-CON-6410 | Pour Concrete Slabs - Z3 - F1 | 119801 | 988
Z3-C-CON-6420 | Fix Rebar Core Walls - Z3 - F1 | 53594 | 1686
Z3-C-CON-6430 | Fix Formwork Core Walls - Z3 - F1 | 28287 | 1725
Z3-C-CON-6440 | Pour Concrete Core Walls - Z3 - F1 | 56412 | 240
Z3-C-CON-6450 | Fix Rebar Columns - Z3 - F1 | 73448 | 2285
Z3-C-CON-6460 | Fix Formwork Columns - Z3 - F1 | 37830 | 1130
Z3-C-CON-6470 | Pour Concrete Columns - Z3 - F1 | 75888 | 224
Z3-C-CON-6480 | Fix Formwork Stairs - Z3 - F1 | 2420 | 4
Z3-C-CON-6490 | Fix Rebar Stairs - Z3 - F1 | 4839 | 16
Z3-C-CON-6500 | Pour Concrete Stairs - Z3 - F1 | 4839 | 10
Z3-C-CON-6510 | Fix Rebar Slabs - Z3 - F2 | 193299 | 3726
Z3-C-CON-6520 | Fix Formwork Slabs - Z3 - F2 | 145945 | 2832
Z3-C-CON-6530 | Pour Concrete Slabs - Z3 - F2 | 455692 | 994
Z3-C-CON-6540 | Fix MEP Containment & Provisions - Z3 - F2 | 5440
Z3-C-CON-6550 | Fix Rebar Core Walls - Z3 - F2 | 35418 | 1114
Z3-C-CON-6560 | Fix Formwork Core Walls - Z3 - F2 | 16704 | 1018
Z3-C-CON-6570 | Pour Concrete Core Walls - Z3 - F2 | 33899 | 144
Z3-C-CON-6580 | Fix Rebar Columns - Z3 - F2 | 50067 | 1557
Z3-C-CON-6590 | Fix Formwork Columns - Z3 - F2 | 24315 | 727
Z3-C-CON-6600 | Pour Concrete Columns - Z3 - F2 | 48001 | 142
Z3-C-CON-6610 | Fix Formwork Stairs - Z3 - F2 | 2419 | 4
Z3-C-CON-6620 | Fix Rebar Stairs - Z3 - F2 | 4839 | 16
Z3-C-CON-6630 | Pour Concrete Stairs - Z3 - F2 | 4839 | 10
Z3-C-CON-6640 | Fix Formwork Slabs - Z3 - RF | 65648 | 2831
Z3-C-CON-6650 | Fix Rebar Slabs - Z3 - RF | 192257 | 3707
Z3-C-CON-6660 | Pour Concrete Slabs - Z3 - RF | 253253 | 990
Z3-C-CON-6670 | Fix MEP Containment & Provisions - Z3 - RF | 5440
Z3-C-CON-6680 | Fix Rebar Core Walls - Z3 - RF | 34810 | 1096
Z3-C-CON-6690 | Fix Formwork Core Walls - Z3 - RF | 16641 | 1015
Z3-C-CON-6700 | Pour Concrete Core Walls - Z3 - RF | 33788 | 144
Z3-C-CON-6710 | Fix Rebar Columns - Z3 - RF | 40997 | 1275
Z3-C-CON-6720 | Fix Formwork Columns - Z3 - RF | 18849 | 563
Z3-C-CON-6730 | Pour Concrete Columns - Z3 - RF | 38299 | 112
Z3-C-CON-6740 | Fix Formwork Stairs - Z3 - RF | 2419 | 3
Z3-C-CON-6750 | Fix Rebar Stairs - Z3 - RF | 4032 | 14
Z3-C-CON-6760 | Pour Concrete Stairs - Z3 - RF | 4032 | 8
Z3-C-CON-6770 | Fix Formwork Slabs - Z3 - SRVF | 210418 | 2426
Z3-C-CON-6780 | Fix Rebar Slabs - Z3 - SRVF | 236165 | 3040
Z3-C-CON-6790 | Pour Concrete Slabs - Z3 - SRVF | 274411 | 850
Z3-C-CON-6800 | Fix MEP Containment & Provisions - Z3 - SRVF | 5440
Z3-C-CON-6810 | Fix Rebar Core Walls - Z3 - SRVF | 20591 | 648
Z3-C-CON-6820 | Fix Formwork Core Walls - Z3 - SRVF | 9461 | 576
Z3-C-CON-6830 | Pour Concrete Core Walls - Z3 - SRVF | 18906 | 4
Z3-C-CON-6840 | Fix Rebar Columns - Z3 - SRVF | 3705 | 116
Z3-C-CON-6850 | Fix Formwork Columns - Z3 - SRVF | 1349 | 41
Z3-C-CON-6860 | Pour Concrete Columns - Z3 - SRVF | 2405 | 8
Z3-C-CON-6870 | Pour MEP RCC Pedastals - Z3 - SRVF | 807 | 2
Z3-C-CON-6880 | Fix Formwork Parapet - Z3 - SRVF | 14509 | 113
Z3-C-CON-6890 | Fix Rebar Parapet - Z3 - SRVF | 29018 | 236
Z3-C-CON-6900 | Pour Concrete Parapet - Z3 - SRVF | 29019 | 136
Z3-C-CON-6910 | Fix Formwork Slabs - Z3 - TRF | 7662 | 298
Z3-C-CON-6920 | Fix Rebar Slabs - Z3 - TRF | 15325 | 303
Z3-C-CON-6930 | Pour Concrete Slabs - Z3 - TRF | 15325 | 90
Z3-C-CON-6940 | Fix MEP Containment & Provisions - Z3 - TRF | 5440
Z3-C-CON-6950 | Fix Formwork Parapet - Z3 - TRF | 14509 | 113
Z3-C-CON-6960 | Fix Rebar Parapet - Z3 - TRF | 29019 | 236
Z3-C-CON-6970 | Pour Concrete Parapet - Z3 - TRF | 29019 | 136
Grand Total |  | 86743706 | 791298

## MonthlyPlannedIndHrs (hidden)
Note: This report is not for printing, use it for only analysis purpose
| 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31 | 2020-11-30 | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31
Sum of Monthly Indv Trade Hrs | 2020-02-29: Month ID
BOQ Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Alum.Tech-1817 | 2021-01-31: 25; 2021-03-31: 25; 2021-04-30: 200; 2021-08-31: 388; 2021-09-30: 2566; 2021-10-31: 4853; 2021-11-30: 4430; 2021-12-31: 2687; 2022-01-31: 876; 2022-02-28: 67
Carpeter 1817 | 208 | 142 | 327 | 465 |  | 261 | 5090 | 7709 | 10569 | 11313 | 9894 | 11328 | 12049 | 13505 | 10753 | 8210 | 11361 | 4667 | 4186 | 3460 | 4333 | 3119 | 664
Electrician 1817 | [10 empty] | 14 | 97 | 1199 | 2233 | 2106 | 3005 | 2681 | 2752 | 2146 | 3884 | 3785 | 2074 | 1925 | 785 | 60 | 500
HVAC Tech. 1817 | 2021-01-31: 32; 2021-02-28: 735; 2021-03-31: 1249; 2021-04-30: 1468; 2021-05-31: 1844; 2021-06-30: 1812; 2021-07-31: 1609; 2021-08-31: 2681; 2021-09-30: 4013; 2021-10-31: 3152; 2021-11-30: 1535
Labor 1817 | 908 | 142 | 2348 | 5284 | 4520 | 2556 | 1817 | 1211 | 2150 | 1634 | 1503 | 5156 | 7952 | 8377 | 10997 | 7162 | 7912 | 9237 | 17922 | 20286 | 8994 | 6593 | 1264 | 6888 | 38
Mason 1817 | 8 | 142 | 165 | 317 | 448 | 4001 | 637 | 2634 | 3443 | 1632 | 1500 | 6627 | 10164 | 10281 | 13626 | 8755 | 10303 | 11554 | 19985 | 20863 | 8712 | 3714 | 98 | 363 | 38
Painter 1817 | 2021-01-31: 1916; 2021-02-28: 578; 2021-03-31: 6801; 2021-04-30: 3925; 2021-05-31: 3010; 2021-06-30: 2738; 2021-07-31: 1730; 2021-08-31: 3514; 2021-09-30: 4229; 2021-10-31: 4234; 2021-11-30: 2397; 2021-12-31: 2785; 2022-01-31: 1260
Plumber 1817 | [5 empty] | 100 | 50 | 150 |  |  |  | 115 | 1223 | 1765 | 2304 | 4051 | 3016 | 4951 | 6419 | 6469 | 3681 | 3292 | 2068 | 885 | 100
STeel Fixer 1817 |  |  | 1942 | 2913 | 497 | 20506 | 15749 | 29032 | 13844 | 13474 | 20872 | 23009 | 14416 | 16145 | 12633 | 14335 | 11539 | 8031 | 1235 |  |  | 120
Waterproof Tech 1817 | 2020-06-30: 200; 2020-07-31: 280; 2020-08-31: 120; 2020-10-31: 200; 2020-11-30: 300; 2020-12-31: 100; 2021-04-30: 17; 2021-05-31: 17; 2021-07-31: 355; 2021-08-31: 2840; 2021-09-30: 4688; 2021-10-31: 228
Earned Values
Sum of Monthly Indv Trade Hrs | 2020-02-29: Column Labels
Row Labels | 2020-02-29: (blank); 2020-03-31: Grand Total
(blank) | 2020-02-29: 0; 2020-03-31: 0
Grand Total | 2020-02-29: 0; 2020-03-31: 0
Months | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31 | 2020-11-30 | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31
Planned Value | 4.3231 | 1.6385 | 18.3923 | 34.5346 | 21.7885 | 106.5538 | 90.2423 | 156.6769 | 116.1769 | 109.05 | 130.3192 | 185.7885 | 185.8308 | 232.2346 | 223.1885 | 193.8038 | 197.5462 | 172.6385 | 235.8308 | 270.9923 | 161.4308 | 104.9 | 44.1962 | 42.5269 | 1.1654 | 1.9231
Planned % | 0.142% | 0.05384% | 0.6043% | 1.135% | 0.7159% | 3.501% | 2.965% | 5.148% | 3.817% | 3.583% | 4.282% | 6.105% | 6.106% | 7.631% | 7.333% | 6.368% | 6.491% | 5.672% | 7.749% | 8.904% | 5.304% | 3.447% | 1.452% | 1.397% | 0.03829% | 0.06319%
Cum.Planned Value | 4.3231 | 5.9615 | 24.3538 | 58.8885 | 80.6769 | 187.2308 | 277.4731 | 434.15 | 550.3269 | 659.3769 | 789.6962 | 975.4846 | 1161.3154 | 1393.55 | 1616.7385 | 1810.5423 | 2008.0885 | 2180.7269 | 2416.5577 | 2687.55 | 2848.9808 | 2953.8808 | 2998.0769 | 3040.6038 | 3041.7692 | 3043.6923
Cum.Planned % | 0.142% | 0.1959% | 0.8002% | 1.935% | 2.651% | 6.152% | 9.117% | 14.27% | 18.08% | 21.67% | 25.95% | 32.05% | 38.16% | 45.79% | 53.12% | 59.49% | 65.98% | 71.65% | 79.4% | 88.31% | 93.61% | 97.06% | 98.51% | 99.91% | 99.94% | 100%
Actual Value
Actual %
Cum. Actual Value
Cum.Actual %
| 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31 | 2020-11-30 | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31
Alum.Tech-1817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 200 | 0 | 0 | 0 | 388 | 2566 | 4853 | 4430 | 2687 | 876 | 67 | 0
Carpeter 1817 | 208 | 142 | 327 | 465 | 0 | 261 | 5090 | 7709 | 10569 | 11313 | 9894 | 11328 | 12049 | 13505 | 10753 | 8210 | 11361 | 4667 | 4186 | 3460 | 4333 | 3119 | 664 | 0 | 0 | 0
Electrician 1817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 97 | 1199 | 2233 | 2106 | 3005 | 2681 | 2752 | 2146 | 3884 | 3785 | 2074 | 1925 | 785 | 60 | 500
HVAC Tech. 1817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 735 | 1249 | 1468 | 1844 | 1812 | 1609 | 2681 | 4013 | 3152 | 1535 | 0 | 0 | 0 | 0
Labor 1817 | 908 | 142 | 2348 | 5284 | 4520 | 2556 | 1817 | 1211 | 2150 | 1634 | 1503 | 5156 | 7952 | 8377 | 10997 | 7162 | 7912 | 9237 | 17922 | 20286 | 8994 | 6593 | 1264 | 6888 | 38 | 0
Mason 1817 | 8 | 142 | 165 | 317 | 448 | 4001 | 637 | 2634 | 3443 | 1632 | 1500 | 6627 | 10164 | 10281 | 13626 | 8755 | 10303 | 11554 | 19985 | 20863 | 8712 | 3714 | 98 | 363 | 38 | 0
Painter 1817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1916 | 578 | 6801 | 3925 | 3010 | 2738 | 1730 | 3514 | 4229 | 4234 | 2397 | 2785 | 1260 | 0 | 0
Plumber 1817 | 0 | 0 | 0 | 0 | 0 | 100 | 50 | 150 | 0 | 0 | 0 | 115 | 1223 | 1765 | 2304 | 4051 | 3016 | 4951 | 6419 | 6469 | 3681 | 3292 | 2068 | 885 | 100 | 0
STeel Fixer 1817 | 0 | 0 | 1942 | 2913 | 497 | 20506 | 15749 | 29032 | 13844 | 13474 | 20872 | 23009 | 14416 | 16145 | 12633 | 14335 | 11539 | 8031 | 1235 | 0 | 0 | 120 | 0 | 0 | 0 | 0
Waterproof Tech 1817 | 0 | 0 | 0 | 0 | 200 | 280 | 120 | 0 | 200 | 300 | 100 | 0 | 0 | 0 | 17 | 17 | 0 | 355 | 2840 | 4688 | 228 | 0 | 0 | 0 | 0 | 0
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.