## Dashboard
Project Dashboard
| Contractual Data |  |  | Project Progress Data | [12 empty] | Planned this period
Actual this period
| Project Name |  |  | Cut off Date | 2016-01-28 | Expected Time at Completion (Days) |  | #REF! | [8 empty] | Planned Cumm
| Project Code | [15 empty] | Actual Cumm |  |  |  | Payment
| The Contract Type |  |  | Expected Completion Date | 2016-03-09 | Expected Cost at Completion (EGP) |  | #REF!
| The Employer |  |  | Expected Milestone Date | - | [14 empty] | Contract Amount | 8265340.43 | 8265340.43
| The Employer |  |  | Current Delay | 9 | [14 empty] | IPC | 2803040.85 | 2803040.85 | 2076559.93 |  | 904456.6878
| The Consultant |  |  | Requested EOT | 0 | [11 empty] | 3528 |  |  | Remaining Payment | 5462299.58 | 5462299.58
| The Contractor |  |  | Granted EOT | 0
| The Contract Amount (EGP) |  | 8860290.43 | Elapsed Days | 82
| Variation Orders Amount |  | -594950 | Remaining Days | 33 | [17 empty] | 726480.92
| Revised Contract Amount |  | 8265340.43 | Current Week | 11.7143
| Advance Payment |  | 0% | Remaining Weeks | 4.7143
| Retention (1) |  | 5% | Current Month | 2.7333 | [17 empty] | 277994.384
| Retention (2) |  | 5% | Remaining Months | 1.1 | [13 empty] | Earned Value | 3263156.4018
| Delay Damage (Per Week) |  | - | Planned This Period % | 15% | [13 empty] | Planned Value | 3957444.9979 | 694288.5961 | #REF! |  |  | 460115.5518
| Commencement Date |  | 2015-11-07 | Actual This Period % | 7% | [13 empty] | Actual Cost | 2054656.36 |  | 363181.802
| The Contract Duration (days) |  | 115 | Planned Cumulative % | 57%
| Time of Completion Date |  | 2016-03-01 | Actual Cumulative % | 47% | [14 empty] | 29250000
| Milestone Date |  | - | Variance Progress % | -10% | [11 empty] | Planned last period |  | 6.38%
| Revised Time of Completion |  | - | Period to Receive Payment | 30 Days | [11 empty] | Actual last period |  | 6.44%
694288.5961
| Area of Concern (Main Issue Register) |  |  | Manpower Average per day for this Period
| Item | Description |  | Item | Number | [11 empty] | Actual This Period % | 7%
| 1 |  |  | Carpenter | 11 | [11 empty] | Planned This Period % | 15%
|  |  |  | Steel Fixer | 12 | [11 empty] | Actual Cumulative % | 47% |  |  | 1076734.1521
| 2 |  |  | Masonry | 12 | [11 empty] | Planned Cumulative % | 57%
|  |  |  | Plaster | 11 | [12 empty] | 100%
| 3 |  |  | Painting | 10 | [17 empty] | 694288.5961
|  |  |  | Tiles | 0
| 4 |  |  | Curtain Walls | 26 | [14 empty] | 460115.5518
|  |  |  | Gypsum Works | 0
| 5 |  |  | Steel Sructure | 10 | [14 empty] | 455970.1518 |  |  | 693406.5961
|  |  |  | MEP | 43 | [23 empty] | Actual Cost
| 6 |  |  | Labors | 25
|  |  |  | Total | 160 | [20 empty] | 0 | 0
[26 empty] | 1 | 0
[26 empty] | 1 | 0 | 46655 | 0
| Quality Performance | [5 empty] | Safety Performance |  | Activity Name | Duration | Performance % Complete |  | Schedule % Complete |  | Start | Finish | [9 empty] | 2 | 0 | 104701.5 | 1
[26 empty] | 2 | 1640000 | 660074.2 | 2
[9 empty] | xxx | -42315 | 46.67% | 46.67% | 57.05% | 57.05% | 2015-11-07 | 2016-03-09 | [9 empty] | 3 | 1640000 | 2054656.36 | 3
[9 empty] | xxxx | 13 | 100% | 100% | 100% | 100% | 07-Nov-15 A | 06-Jan-16 A | [9 empty] | 3 | 2354554.314 |  | 4
[9 empty] | 1-Mobilization | 23 | 100% | 100% | 100% | 100% | 14-Nov-15 A | 28-Dec-15 A | [9 empty] | 4 | 2354554.314 |  | 5
[9 empty] | 2-General & Preliminaries | 4 | 100% | 100% | 100% | 100% | 14-Nov-15 A | 19-Nov-15 A | [6 empty] | 299897.954 |  |  | 4 |  |  | 6
[9 empty] | 3-Procurement | 5 | 100% | 100% | 100% | 100% | 24-Nov-15 A | 28-Dec-15 A | [7 empty] | 299897.954 |  | 5 |  |  | 7
[9 empty] | 4-Main Building | 64 | 52.08% | 52.08% | 65.66% | 65.66% | 23-Nov-15 A | 2016-03-07 | [9 empty] | 5 |  |  | 8
[9 empty] | 4a- Second Basement | 29 | 100% | 100% | 100% | 100% | 23-Nov-15 A | 14-Jan-16 A | 195000000 | [8 empty] | 6
[9 empty] | 4b- First Basement | 32 | 17.38% | 17.38% | 30.76% | 30.76% | 11-Jan-16 A | 2016-03-03 | [9 empty] | 6
[9 empty] | 4c- Ground Floor | 30 | 21.79% | 21.79% | 59.89% | 59.89% | 23-Jan-16 A | 2016-03-07 | [9 empty] | 7
[9 empty] | 4d- First Floor | 55 | 60.78% | 60.78% | 75.93% | 75.93% | 08-Dec-15 A | 2016-03-03 | [9 empty] | 7
[9 empty] | 4e- Second Floor | 8 | 100% | 100% | 100% | 100% | 08-Dec-15 A | 22-Dec-15 A | [9 empty] | 8
[9 empty] | 4f- Third Floor | 32 | 31.04% | 31.04% | 65.71% | 65.71% | 07-Jan-16 A | 2016-02-25 | [9 empty] | 8
[9 empty] | 4g- Fourth Floor | 39 | 54.48% | 54.48% | 59.89% | 59.89% | 16-Jan-16 A | 2016-03-03 | [9 empty] | 9
[9 empty] | 4h- Fifth Floor | 47 | 57.99% | 57.99% | 60.6% | 60.6% | 24-Dec-15 A | 2016-03-03 | [9 empty] | 9
[9 empty] | 4i- Sixth Floor | 8 | 100% | 100% | 100% | 100% | 24-Dec-15 A | 07-Jan-16 A | [9 empty] | 10 | 8000000
[9 empty] | 4j- Roof Floor | 30 | 24.06% | 24.06% | 27.09% | 27.09% | 16-Jan-16 A | 2016-02-23
[9 empty] | 4k- Upper Floor | 30 | 54.48% | 54.48% | 59.89% | 59.89% | 21-Jan-16 A | 2016-03-03
[9 empty] | 5- Façade Works | 34 | 18.88% | 18.88% | 33.52% | 33.52% | 09-Jan-16 A | 2016-02-28
[9 empty] | 5a- Northern facade | 24 | 69.13% | 69.13% | 69.13% | 69.13% | 09-Jan-16 A | 2016-02-14
[9 empty] | 5b- Southern facade | 23 | 5.95% | 5.95% | 12.08% | 12.08% | 16-Jan-16 A | 2016-02-25
[9 empty] | 5a- Eastern facade | 20 | 0% | 0% | 56.2% | 56.2% | 2016-01-30 | 2016-02-28
[9 empty] | 5a- Western facade | 19 | 0% | 0% | 0% | 0% | 2016-02-08 | 2016-03-06
[9 empty] | 6- External Works | 28 | 1.04% | 1.04% | 6.92% | 6.92% | 24-Jan-16 A | 2016-03-01
[9 empty] | 7- Testing & Commissioning | 22 | 0% | 0% | 29.09% | 29.09% | 2016-01-28 | 2016-02-27
Masonry Works
xxxxx
xxxxxx
xxxxxx
xxxxx
xxxxx
xxxxx
The Current Net Profit= 299,897.9 EGP

## Sheet1
Shop Drawing | [14 empty] | Month | Planned Progress |  | Actual Progress |  | Dry Cost
Submitted | Approved | Rejected | On Going | [12 empty] | This Period | Cumulative | This Period | Cumulative | This Period | Cumulative
[14 empty] | 1 | 2015-11-07 | 0.6106% | 0.6106% | 0.61% | 0.61% | 0.07249% | 0.07249% | 50400 | 4666.67
[14 empty] | 2 | 2015-11-14 | 1.357% | 1.967% | 1.36% | 1.97% | 0.6522% | 0.7247% | 112000 | 41988.33
[14 empty] | 3 | 2015-11-21 | 4.858% | 6.826% | 4.86% | 6.83% | 1.441% | 2.166% | 401037.5 | 92782.5
[14 empty] | 4 | 2015-11-28 | 4.387% | 11.21% | 4.387% | 11.22% | 5.674% | 7.84% | 362106.9 | 365264
32 | 32 | 0 | 0 | [10 empty] | 5 | 2015-12-05 | 4.91% | 16.12% | 4.91% | 16.13% | 2.085% | 9.924% | 405317.6 | 134201.5
[14 empty] | 6 | 2015-12-12 | 2.237% | 18.36% | 2.237% | 18.36% | 4.989% | 14.91% | 184646 | 321171.2
RFI |  |  |  | IR |  |  |  |  | MIR |  |  |  |  | 7 | 2015-12-19 | 6.184% | 24.54% | 6.184% | 24.55% | 2.708% | 17.62% | 510489.47 | 174316.8
Submitted | Replied | On Going |  | Submitted | Approved | Rejected | On Going |  | Submitted | Approved | Rejected | On Going |  | 8 | 2015-12-26 | 3.683% | 28.23% | 3.683% | 28.23% | 4.067% | 21.69% | 304059.02 | 261847.48
[14 empty] | 9 | 2016-01-02 | 7.91% | 36.14% | 7.91% | 38% | 5.227% | 26.91% | 652940.34 | 336513.33
[14 empty] | 10 | 2016-01-09 | 5.889% | 42.03% | 2% | 40% | 7.172% | 34.09% | 486161.5 | 461746.19
[14 empty] | 11 | 2016-01-16 | 8.377% | 50.4% | 3% | 43% | 6.168% | 40.26% | 691479.75 | 397104.34
[14 empty] | 12 | 2016-01-23 | 7.986% | 58.39% | 4% | 47% | 8.381% | 48.64% | 659199 | 539594.44
0 | 0 | 0 |  | 27 | 27 | 0 | 0 |  | 9 | 9 | 0 | 0 |  | 13 | 2016-01-30 | 12.69% | 71.07% |  |  | 9.494% | 58.13% | 1047172.01 | 611241.22
[14 empty] | 14 | 2016-02-06 | 7.567% | 78.64% |  |  | 13.45% | 71.58% | 624616.73 | 865890.8
[14 empty] | 15 | 2016-02-13 | 11.2% | 89.84% |  |  | 11.76% | 83.35% | 924916.61 | 757365.03
Engineering Progress % | [7 empty] | Engineering Performance | [5 empty] | 16 | 2016-02-20 | 10.03% | 99.88% |  |  | 8.993% | 92.34% | 828347.5 | 578980.64
Total | Submitted | Remaining | Progress % | [5 empty] | Submitted | Approved | Rejected | On Going | Performance % | 17 | 2016-02-27 | 0.1205% | 100% |  |  | 7.662% | 100% | 9950.5 | 493250.5
[15 empty] | Total | 100% | 100% |  |  | 100% |  | 8254840.43 | 6437924.97
0 | 0 | 0 | #DIV/0! | [5 empty] | 0 | 0 | 0 | 0 | #DIV/0!