## DB
WEEKLY DASHBOARD REPORT
[17 empty] | Date: | 2018-07-12
[17 empty] | Data Date: | 2018-07-05
|  |  |  | PROJECT INFORMATION |  |  |  |  | SUBMITTAL KPI's |  |  |  |  | MANMONTHS
|  |  |  | Project Title |  | :
|  |  |  | Owner |  | :
|  |  |  | Consultant |  | :
|  |  |  | Contractor |  | :
|  |  |  | MEP Subcontractor |  | :
|  |  |  | ID Subcontractor |  | :
|  |  |  | PT Subcontractor |  | :
|  |  |  | Commencement Date |  | :
|  |  |  | Substructure Completion |  | :
|  |  |  | Superstructure Completion |  | :
|  |  |  | Contract Completion Date |  | :
PROGRESS S - CURVE | [5 empty] | KEY DATES & STATUS | [5 empty] | PROGRESS HIGHLIGHTS
[6 empty] | Milestone Activities |  |  | Milestone Dates | Forecast / Actual | Variance | 1 | Compoud wall works are in progress.
[12 empty] | 2 | Casting of footings for compound walls is in progress.
[6 empty] | Original Contract |  |  | 2015-03-15 | 2015-03-15 | 0 | 3 | Staircase works in Area 2 are in progress.
[6 empty] | Annexure - 1 |  |  | 2016-05-24 | 2016-05-24 | 0 | 4 | MEP First Fix is in progress in all areas.
[6 empty] | Annexure - 2 |  |  | 2017-05-29 | 2017-05-29 | 0 | 5 | MEP Second Fix is in progress in all areas.
[6 empty] | Building permit |  |  | 2016-03-01 | 2016-03-01 | 0 | 6
[6 empty] | Issue of Preliminary Design |  |  | 2017-05-29 | 2017-05-29 | 0 | 7
[6 empty] | Authorities Approvals (NOC / Permits) |  |  | 2017-06-15 | 2017-09-04 | -81 | 8
[6 empty] | Recieved Approved Final Drawings |  |  | 2017-06-15 | 2017-09-04 | -81 | 9
[6 empty] | ID Designs Drawings & Details |  |  | 2017-07-01 | 2018-07-05 | -369 | 10
[6 empty] | Submit & Nominate - MEP Subcontractor |  |  | 2016-02-28 | 2016-02-28 | 0 | AUTHORITY APPROVALS
[6 empty] | Submit & Nominate - Interior Subcontractor |  |  | 2017-07-09 | 2017-12-31 | -175
[6 empty] | Completion - Substructure |  |  | 2017-09-13 | 2018-07-31 | -321 | Description |  | Authority | Planned Approval | Forecast / Actual Approval |  | Variance
[6 empty] | Completion - Superstructure |  |  | 2017-11-30 | 2018-07-05 | -217
[6 empty] | Completion - Finishes & MEP |  |  | 2018-06-17 | 2019-04-08 | -295
[6 empty] | Power On |  |  | 2018-05-28 | 2019-03-14 | -290 | 1 | Authorities Approvals (NOC / Permits) | DCCA | 2017-05-29 | 2017-09-04 |  | -98
[6 empty] | Permanent Power Supply |  |  | 2018-05-28 | 2019-03-14 | -290 | 2 | Chilled Water Supply from Empower | EMPOWER | 2018-04-05 | 2018-10-22 |  | -200
[6 empty] | Permanent Water Supply |  |  | 2018-06-27 | 2019-05-05 | -312 | 3 | Inspection from Etisalat / DU | ETISALAT / DU | 2018-04-05 | 2018-10-22 |  | -200
[6 empty] | Handing Over |  |  | 2018-06-30 | 2019-05-05 | -309 | 4 | Inspection by Authority. for release of Power | DEWA | 2018-05-28 | 2019-03-14 |  | -290
[12 empty] | 5 | Water Supply Inspection by Authority | DEWA | 2018-06-20 | 2019-04-30 |  | -314
TOP 5 - KEY ISSUES & RISKS | [5 empty] | RECOMMENDATIONS & ACTIONS | [5 empty] | LOOK AHEAD
Description |  |  |  | Status |  | Description |  |  |  | Who | Date | Activities |  |  |  |  | Who | When
1. | Delay in receipt of Final ID Design ( False Ceilng Layout). |  |  |  |  | 1. | Finalization of ID design has to be done at the earliest as the same will affect MEP works. |  |  | ID Contractor |  | 1. | Completion of Parapet / Toproof
2. | Variation Approvals. |  |  |  |  | 2. |  |  |  | CEC |  | 2. | Completion of Staircases.
3. | Delay in Payment for PC 14 , PC 17 , PC 18. |  |  |  |  | 3. |  |  |  | Client |  | 4. | Completion of Boundary Wall.
4. | [5 empty] | 4. | [5 empty] | 5 | Completion of Stone Cladding
5 | [5 empty] | 5 | [5 empty] | 6 | Starting of Roof Water proofing works
6 | [5 empty] | 6 | [5 empty] | 7 | Starting of Substation works
VARIATION ORDER | [5 empty] | PROGRESS PAYMENT | [5 empty] | PROCUREMENT
Description |  | Status | Submitted | Approval Date | Variance | Description |  | Payment Certificate |  | Payment Received |  | Description |  | Package Status | Selected Vendor | Original / Planned Date | Forecast / Actual Date | Variance
[8 empty] | Value (AED) | Status | Value (AED) | Status
1 | Prolongation Cost for duration up to 29-May-17 | Approved | 2017-03-19 | 2017-12-05 | -261 |  |  |  | Submitted |  | Invoiced
2 | Accelaration Cost | Approved | 2017-06-24 | 2017-07-10 | -16 | Payment Application 14 |  | 5091767.24 | 2017-12-24 | 3000000 | 2017-12-25 |  | Key Subcontract Packages
3 | Rework substructure modification Phase 2 | Approved | 2017-10-24 | 2017-10-30 | -6 |  |  |  |  | 1000000 | 2018-01-08 | 1 | MEP | Approved |  | 2016-02-27 | 2016-02-27 | 0
4 | Sub & Sup related to revised drawings 04-Sep-17 | Under Review | 2017-12-03 |  | -214 |  |  |  |  | 1000000 | 2018-01-30 | 2 | ID Subcontractor | Approved |  | 2017-07-09 | 2017-12-31 | -175
5 | Revised MEP price | Under Review | 2017-11-21 |  | -226 | Payment Application 17 |  | 7569528.59 | 2018-04-05 |  |  | 3 | Shoring | Approved |  | 2016-03-12 | 2016-03-13 | -1
6 | Design change for steel reinforcement | Under Review | 2018-01-10 |  | -176 | Payment Application 18 |  | 4601454.76 | 2018-04-25 |  |  | 4 | Waterproofing | Approved |  | 2016-11-28 | 2016-11-28 | 0
7 | Change in material rates for Steel,Concrete | Under Review | 2018-01-10 |  | -176 | Total |  | 17262750.59 | Total | 5000000 |  | 5 | Post Tension | Approved |  | 2017-02-04 | 2017-02-04 | 0
| ,Block works & Road base |  |  |  |  | VARIATION PAYMENT | [5 empty] | 6 | Steel Works | Approved |  | 2017-10-25 | 2017-11-09 | -15
8 | Aluminum changes in drawings and in systems | Approved | 2018-02-20 | 2018-03-05 | -135 | [6 empty] | 7 | Passenger Lifts | Approved |  | 2017-07-15 | 2017-09-14 | -61
9 | Lift modification (Lift opening L4,L5,L6 ) | Not Submitted | [6 empty] | Submitted |  | Invoiced | 8 | Aluminium | Approved |  |  | 2018-01-25
10 | MEP reworks - Underground drainage piping | Not Submitted |  |  |  | Accelaration Cost |  | 8500000 |  | 7500000 |  | 9 | Stone Cladding | Approved |  |  | 2018-02-07
11 | Changing of parapets into steel works |  |  |  |  | Payment 1 |  |  |  | 2000000 | 2017-07-13 | 10 | Lighting fixtures | Approved |  | 2017-08-03 | 2018-03-18 | -227
| & Steel bridge in Area 3 first floor | Under Review | 2018-02-12 |  | -143 | Payment 2 |  |  |  | 1500000 | 2017-08-03 | 11 | Landscape | Not Submitted |  | 2017-09-28
12 | Additional lift in A2 SS & A2 | Under Review | 2018-02-20 |  | -135 | Payment 3 |  |  |  | 1000000 | 2017-08-28 | 12 | Sanitary wares & accessoreis | Not Submitted |  | 2017-10-18
13 | Roofing Material Quantity Variance | Not Submitted |  |  |  | Payment 4 |  |  |  | 1000000 | 2017-09-17 | 13 | Footing switch for operation rooms | Not Submitted |  | 2017-10-28
14 | Rework for Phase 1 | Not Submitted |  |  |  | Payment 5 |  |  |  | 1000000 | 2017-12-25 | 14 | Security & CCTV system | Not Submitted |  | 2017-10-31
15 | MEP additional works in bunker area | Under Review | 2018-04-01 |  | -95 | Payment 5 |  |  |  | 1000000 | 2018-02-21 | 15 | SMATV equipment | Not Submitted |  | 2017-11-06
16 | Enabling Works (Light Distribution) | Under Review | 2018-04-24 |  |  | Prolongation Cost |  | 2800000 | 2017-03-19 | 2800000 | 2017-12-06 | 16 | Master clock system | Not Submitted |  | 2017-11-18
17 | Enabling Works (Power Distribution) | Under Review | 2018-04-24 |  |  | Rework For Phase 2 |  | 1273664 | 2017-10-24 | 1273664 |  | 17 | PABX system | Not Submitted |  | 2017-11-22
[12 empty] | 18 | Access system for radio therpy area | Not Submitted |  | 2017-11-25
[6 empty] | Total |  | 12573664 | Total | 11573664
PLAN : 100%
ACTUAL : 60.73%
FORECAST COMPLETION : 05-May-19
PROJECT PIC to be Inserted
Consultant Logo
Client Logo
Contractor Logo

## CIVIL PICS
CIVIL PROGRESS WORKS
(30-Jun-2018 to 05-Jul-2018) |  | (27-01-2018 to 01-02-2018)
Area 2 - Stone Cladding Works | Area 3 -Compound Wall Works - Bitumen Painting |  | Elevation 2 - Aluminium First Fix Works | Elevation 2 - Stone Cladding Works
Elevation 2 & 3 - Stone Cladding Works | Elevation 4 - Stone Cladding Works |  | Front Side view - 1 | Elevation 3 - Internal Aluminium first fix works
Elevation 1 - Roof Stone Cladding Works | Hospital Front SIde Elevation 1 view |  | Elevation 3 - Internal Aluminium first fix works | Elevation 5 - Stone Cladding Works
PROJECT PIC to be Inserted

## MEP PICS
MEP PROGRESS WORKS
(30-Jun-2018 to 05-Jul-2018) |  | (27-01-2018 to 01-02-2018)
AC Duct Installation (Basement Floor) | AC Duct Installation (Ground Floor) |  | AC Duct Installation (1st Floor) | AC Duct Installation (2nd Floor)
Cable Tray & Trunking Installation (2nd Floor) | Wiring Installation (Basement Floor) |  | DB's Installation (1st Floor) | Cable Tray & Trunking Installation (Ground Floor)
Installation of PPR Pipes and Valves (1st Floor) | Installation of WC Frame (Ground Floor) |  | Instlatallation of PEX Pipes & Drainage Pipes (Basement Kitchen Floor) | Installation of WC Frame (Second Floor)
PROJECT PIC to be Inserted

## Data
PROJECT PROGRESS
PROJECT PROGRESS S-CURVE (Progress/WEEK)
TOTAL
Start Date of the Week | time axis 2016-03-03 to 2018-10-04
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
Project Progress
Weekly Planned |  | 0.01273% | 0.2197% | 0.393% | 0.4065% | 0.4065% | 0.4065% | 0.2137% | 0.04494% | 0.04494% | 0.04494% | 0.04494% | 0.04494% | 0.04494% | 0.04494% | 0.1995% | 1.197% | 1.197% | 1.197% | 1.197% | 0.1995% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.08773% | 0.1972% | 0.2263% | 0.2101% | 0.3581% | 0.4887% | 1.116% | 1.293% | 2.954% | 2.577% | 4.049% | 3.247% | 3.619% | 2.299% | 1.853% | 1.598% | 0.9354% | 1.099% | 1.695% | 1.817% | 1.153% | 1.463% | 1.475% | 1.689% | 1.355% | 1.352% | 1.088% | 1.14% | 2.008% | 2.06% | 1.931% | 1.674% | 2.053% | 1.781% | 1.739% | 2.532% | 2.299% | 2.962% | 2.462% | 4.546% | 4.483% | 3.367% | 1.891% | 2.457% | 2.51% | 1.154% | 0.7647% | 0.9874% | 1.361% | 1.107% | 0.642% | 0.3938% | 0.227% | 0.1505% | 0.3267% | 0.1167% | 0.01938% | 0% | [13 empty] | 100%
Cum. Planned |  | 0.01273% | 0.2324% | 0.6254% | 1.032% | 1.438% | 1.845% | 2.059% | 2.104% | 2.149% | 2.193% | 2.238% | 2.283% | 2.328% | 2.373% | 2.573% | 3.77% | 4.967% | 6.164% | 7.361% | 7.561% | 7.561% | 7.561% | 7.561% | 7.561% | 7.561% | 7.561% | 7.561% | 7.648% | 7.846% | 8.072% | 8.282% | 8.64% | 9.129% | 10.24% | 11.54% | 14.49% | 17.07% | 21.12% | 24.36% | 27.98% | 30.28% | 32.13% | 33.73% | 34.67% | 35.77% | 37.46% | 39.28% | 40.43% | 41.89% | 43.37% | 45.06% | 46.41% | 47.77% | 48.85% | 49.99% | 52% | 54.06% | 55.99% | 57.67% | 59.72% | 61.5% | 63.24% | 65.77% | 68.07% | 71.03% | 73.5% | 78.04% | 82.53% | 85.89% | 87.78% | 90.24% | 92.75% | 93.9% | 94.67% | 95.66% | 97.02% | 98.12% | 98.77% | 99.16% | 99.39% | 99.54% | 99.86% | 99.98% | 100% | 100%
Weekly Actual |  | 0.01273% | 0.2197% | 0.393% | 0.4065% | 0.4065% | 0.4065% | 0.2137% | 0.04494% | 0.04494% | 0.04494% | 0.04494% | 0.04494% | 0.04494% | 0.04494% | 0.1995% | 1.197% | 1.197% | 1.197% | 1.197% | 0.1995% | 0.0229% | 0.1696% | 0.2099% | 0.4203% | 0.1317% | 0.05563% | 0.1303% | 0.1873% | 0.2342% | 0.5909% | 0.376% | 0.5041% | 0.5828% | 0.6715% | 0.6334% | 0.735% | 1.017% | 1.023% | 1.02% | 1.062% | 1.136% | 1.148% | 1.335% | 1.288% | 1.344% | 1.409% | 1.144% | 1.006% | 1.042% | 1.113% | 1.051% | 1.106% | 0.976% | 0.9879% | 0.7588% | 0.7329% | 0.757% | 1.042% | 1.014% | 0.9801% | 0.9813% | 0.8614% | 0.4168% | 0.4161% | 0.3493% | 0.4374% | 0.4242% | 0.2465% | 0.7779% | 0.16% | 0.4% | 3.31% | 3.27% | 1.26% | 1.71% | 1% | 0.47% | -0.1% | 1.89% | 2.04% | 0.68% | 0.18% | 0.51% | 0.17% | 0.16% | [13 empty] | 60.73%
Cum. Actual |  | 0.01273% | 0.2324% | 0.6254% | 1.032% | 1.438% | 1.845% | 2.059% | 2.104% | 2.149% | 2.193% | 2.238% | 2.283% | 2.328% | 2.373% | 2.573% | 3.77% | 4.967% | 6.164% | 7.361% | 7.561% | 7.584% | 7.753% | 7.963% | 8.383% | 8.515% | 8.571% | 8.701% | 8.888% | 9.122% | 9.713% | 10.09% | 10.59% | 11.18% | 11.85% | 12.48% | 13.22% | 14.23% | 15.26% | 16.28% | 17.34% | 18.47% | 19.62% | 20.96% | 22.24% | 23.59% | 25% | 26.14% | 27.15% | 28.19% | 29.3% | 30.35% | 31.46% | 32.44% | 33.42% | 34.18% | 34.92% | 35.67% | 36.71% | 37.73% | 38.71% | 39.69% | 40.55% | 40.97% | 41.38% | 41.73% | 42.17% | 42.6% | 42.84% | 43.62% | 43.78% | 44.18% | 47.49% | 50.76% | 52.02% | 53.73% | 54.73% | 55.2% | 55.1% | 56.99% | 59.03% | 59.71% | 59.89% | 60.4% | 60.57% | 60.73%
Plan | [100 empty] | 0
ACTUAL

## Submittal Status
Submittal
| IR | RFI | SD | MS | NCR
Civil - Submitted / Issued | 954 | 62 | 89 | 120
Civil - Approved / Closed | 949 | 56 | 83 | 115
MEP - Submitted / Issued | 599 | 66 | 289 | 155
MEP - Approved / Closed | 588 | 60 | 267 | 147
ID - Submitted / Issued | 118 | 34 | 22 | 44
ID - Approved / Closed | 114 | 30 | 11 | 38
General - Submitted / Issued |  |  |  |  | 94
General - Approved / Closed |  |  |  |  | 47

## Manpower
Manpower ( Accelration vs Actual )
|  | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01
| Planned | 16 | 69 | 75 | 111 | 128.04 | 171.6 | 255.42 | 316.14 | 442.2 | 411.18 | 438.24 | 296.34 | 198.66 | 14.52 | 0
| Actual | 116 | 109 | 174 | 305 | 326 | 450 | 461 | 777 | 632 | 387 | 343 | 553 | 517 | 405 | 373
Accelaration Resources
|  | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01
A | Man Months | 16 | 69 | 75 | 111 | 194 | 260 | 387 | 479 | 670 | 623 | 664 | 449 | 301 | 22

## Sheet2 (hidden)
Milestones |  | Concept (CD) | Schematic (SD) | Detailed (DD) | Tender
Planned Start |  | #REF!
Planned Finish |  | #REF!
Actual Start |  | #REF!
Actual Finish
Variance (Finish)
#REF!
#REF!
CD
| Project Start | 2015-10-01
| Project Finish | 2015-10-30
|  | 29 | -1599
| Actual Start | 2015-10-05
| Today | 2020-03-16
1624
|  | Elapsed Duration | 5600%
|  | Remaining Duration | -5500%
2016-05-05 | Preliminary Design Approval
2016-05-05 | Enabling Works Permit
2016-05-05 | Master developer
2016-06-09 | Roads and Transports
2016-06-23 | Tourism & Cultural Authority
2016-06-30 | National Water Company
2016-06-30 | Gas Authority
2016-07-07 | Saudi Electric company
2016-07-07 | Riyadh Civil Defence
2016-07-07 | Sewrage Authority
2016-07-07 | District Cooling
2016-07-07 | Telecommunication Authority
2016-07-07 | Hoarding Permit
2016-07-07 | Airport Authority
2016-07-07 | Riyadh Police
2016-08-04 | Building Permit

## Sheet3 (hidden)
Soil Investigation NOC 10 15-Nov-15 26-Nov-15
MMU-DS-NCD010 NOC for soil investigation (TBC) 10 15-Nov-15 26-Nov-15
Site set up & Hoarding NOC 10 11-Nov-15 24-Nov-15
MMU-DS-NCD020 RM- Permit for Hoarding, Fencimg and Demarcation Certificate 10 11-Nov-15 24-Nov-15
Master Developer 50 31-Jan-16 07-Apr-16
MMU-AA-A1000 Preparations and Submissions 20 31-Jan-16 25-Feb-16
MMU-AA-A1010 Review and Approval 30 28-Feb-16 07-Apr-16
Roads & Transport Authority - Riyadh 50 06-Mar-16 12-May-16
MMU-AA-A1020 Preparations and Submissions 20 06-Mar-16 31-Mar-16
MMU-AA-A1030 Review and Approval 30 03-Apr-16 12-May-16
Riyadh Municipality - Preliminary Architectural Approval 50 31-Jan-16 07-Apr-16
MMU-AA-A1040 Preparations and Submissions 20 31-Jan-16 25-Feb-16
MMU-AA-A1050 Review and Approval 30 28-Feb-16 07-Apr-16
Riyadh Municipality - Final Architectural and Structural Approval 50 20-Mar-16 26-May-16
MMU-AA-A1060 Architectural Submission: Preparations and Submissions 10 20-Mar-16 31-Mar-16
MMU-AA-A1070 Final Architectural: Review and Approval by Municipality 20 03-Apr-16 28-Apr-16
MMU-AA-A1280 Structural Submission: Preparation and Submission 20 03-Apr-16 28-Apr-16
MMU-AA-A1290 Structural Approval by Municipality 20 01-May-16 26-May-16
Enabling Work Permit 30 28-Feb-16 07-Apr-16
MMU-DS-P081 Enabling works Design and permit 30 28-Feb-16 07-Apr-16
Building Permit NOC's 11 12-May-16 26-May-16
MMU-AA-BP100 Building Permit NOC - SEC (Suadi ELectric Company) 1 26-May-16 26-May-16
MMU-AA-BP110 Building Permit NOC - NWC (National Water Company) 1 22-May-16 22-May-16
MMU-AA-BP120 Building Permit NOC - Civil Defense 1 26-May-16 26-May-16
MMU-AA-BP130 Building Permit NOC - Gas 1 22-May-16 22-May-16
MMU-AA-BP150 Building Permit NOC - Telecommunicat ions 1 26-May-16 26-May-16
MMU-AA-BP160 Building Permit NOC - Civil Aviation / Airports 1 26-May-16 26-May-16
MMU-AA-BP170 Building Permit NOC - Roads 1 12-May-16 12-May-16
MMU-AA-BP180 Building Permit NOC - Sewrage 1 26-May-16 26-May-16
Secure Building Permit 10 29-May-16 09-Jun-16
MMU-AA-BP500 Submit All NOC's to RIyadh Municipality 2 29-May-16 30-May-16
MMU-AA-BP510 Secure Building Permit 8 31-May-16 09-Jun-16
Riyadh Civil Defense 50 20-Mar-16 26-May-16
MMU-AA-A1080 Preparations and Submissions 20 20-Mar-16 14-Apr-16
MMU-AA-A1090 Review and Approval 30 17-Apr-16 26-May-16
Saudi Electric Company 50 20-Mar-16 26-May-16
MMU-AA-A1100 Service Provider (Design NOC) for SEC - Preparation & Submission 20 20-Mar-16 14-Apr-16
MMU-AA-A1110 Approval of Service Provider (Design NOC) 30 17-Apr-16 26-May-16
National Water Company 45 20-Mar-16 19-May-16
MMU-AA-A1120 Preparations and Submissions 20 20-Mar-16 14-Apr-16
MMU-AA-A1130 Review and Approval 25 17-Apr-16 19-May-16
Sewrage Authority - Riyadh 50 20-Mar-16 26-May-16
MMU-AA-A1140 Preparations and Submissions 20 20-Mar-16 14-Apr-16
MMU-AA-A1150 Review and Approval 30 17-Apr-16 26-May-16
Telecommunication Authority - Riyadh 50 20-Mar-16 26-May-16
MMU-AA-A1160 Preparations and Submissions 20 20-Mar-16 14-Apr-16
MMU-AA-A1170 Review and Approval 30 17-Apr-16 26-May-16
Airports Authority / Civi l Aviation - Riyadh 50 20-Mar-16 26-May-16
MMU-AA-A1180 Preparations and Submissions 20 20-Mar-16 14-Apr-16
MMU-AA-A1190 Review and Approval 30 17-Apr-16 26-May-16