## Sheet1
Activity ID | Activity Name | Original Duration | Start | Finish | Actual Start | Actual Finish | % of Complete
A1000 | Receiving IFC drawings | 0 | 2010-07-07
A1010 | Receiving advance payement | 0 | 2010-07-07
A1020 | start construction phase | 0 | 2010-07-17
A1030 | finish construction | 0 |  | 2011-04-03
engineering |  | 32 | 2010-07-07 | 2010-08-12
A1990 | submit ground floor's shop drawings for approval | 1 | 2010-07-07 | 2010-07-07
A2010 | submit 1st floor shop drawings for approval | 1 | 2010-07-12 | 2010-07-12
A2000 | ground floor's shop drawings approval | 0 |  | 2010-07-15
A2030 | submit 2nd floor shop drawings for approval | 1 | 2010-07-17 | 2010-07-17
A2020 | 1st floor shop drawings approval | 0 |  | 2010-07-20
A2050 | submit 3rd floor shop drawings for approval | 1 | 2010-07-21 | 2010-07-21
A2040 | 2nd floor shop drawings approval | 0 |  | 2010-07-25
A2070 | submit 4th floor shop drawings for approval | 1 | 2010-07-26 | 2010-07-26
A2060 | 3rd floor shop drawings approval | 0 |  | 2010-07-29
A2090 | submit 5th floor shop drawings for approval | 1 | 2010-07-31 | 2010-07-31
A2080 | 4th floor shop drawings approval | 0 |  | 2010-08-03
A2110 | submit 6th floor shop drawings for approval | 1 | 2010-08-04 | 2010-08-04
A2100 | 5th floor shop drawings approval | 0 |  | 2010-08-08
A2120 | 6th floor shop drawings approval | 0 |  | 2010-08-12
skeleton |  | 220 | 2010-07-17 | 2011-04-03
ground floor |  | 22 | 2010-07-17 | 2010-08-10
A1330 | columns Formwork & Rft. Part 2 | 8 | 2010-07-17 | 2010-07-25
A1350 | Slab Formwork & Rft. Part1 | 10 | 2010-07-17 | 2010-07-27
A1340 | Columns Pouring Part2 | 1 | 2010-07-26 | 2010-07-26
A1370 | Slab Formwork & Rft. Part2 | 10 | 2010-07-29 | 2010-08-09
A1380 | Slab Pouring | 1 | 2010-08-10 | 2010-08-10
1st floor |  | 30 | 2010-08-12 | 2010-09-16
A1390 | columns Formwork & Rft. Part1 | 8 | 2010-08-12 | 2010-08-21
A1400 | Columns Pouring Part1 | 1 | 2010-08-22 | 2010-08-22
A1410 | columns Formwork & Rft. Part 2 | 8 | 2010-08-22 | 2010-08-30
A1420 | Slab Formwork & Rft. Part1 | 10 | 2010-08-24 | 2010-09-04
A1440 | Columns Pouring Part2 | 1 | 2010-08-31 | 2010-08-31
A1460 | Slab Formwork & Rft. Part2 | 10 | 2010-09-04 | 2010-09-15
A1480 | Slab Pouring | 1 | 2010-09-16 | 2010-09-16
2nd floor |  | 30 | 2010-09-19 | 2010-10-23
A1490 | columns Formwork & Rft. Part1 | 8 | 2010-09-19 | 2010-09-27
A1500 | Columns Pouring Part1 | 1 | 2010-09-28 | 2010-09-28
A1510 | columns Formwork & Rft. Part 2 | 8 | 2010-09-28 | 2010-10-06
A1520 | Slab Formwork & Rft. Part1 | 10 | 2010-09-30 | 2010-10-11
A1540 | Columns Pouring Part2 | 1 | 2010-10-07 | 2010-10-07
A1560 | Slab Formwork & Rft. Part2 | 10 | 2010-10-11 | 2010-10-21
A1580 | Slab Pouring | 1 | 2010-10-23 | 2010-10-23
3rd floor |  | 29 | 2010-10-25 | 2010-11-30
A1590 | columns Formwork & Rft. Part1 | 8 | 2010-10-25 | 2010-11-02
A1610 | columns Formwork & Rft. Part 2 | 8 | 2010-11-02 | 2010-11-10
A1600 | Columns Pouring Part1 | 1 | 2010-11-03 | 2010-11-03
A1620 | Slab Formwork & Rft. Part1 | 10 | 2010-11-06 | 2010-11-20
A1640 | Columns Pouring Part2 | 1 | 2010-11-11 | 2010-11-11
A1660 | Slab Formwork & Rft. Part2 | 10 | 2010-11-15 | 2010-11-29
A1680 | Slab Pouring | 1 | 2010-11-30 | 2010-11-30
4th floor |  | 29 | 2010-12-02 | 2011-01-04
A1690 | columns Formwork & Rft. Part1 | 8 | 2010-12-02 | 2010-12-11
A1710 | columns Formwork & Rft. Part 2 | 8 | 2010-12-11 | 2010-12-19
A1700 | Columns Pouring Part1 | 1 | 2010-12-12 | 2010-12-12
A1720 | Slab Formwork & Rft. Part1 | 10 | 2010-12-14 | 2010-12-25
A1740 | Columns Pouring Part2 | 1 | 2010-12-20 | 2010-12-20
A1760 | Slab Formwork & Rft. Part2 | 10 | 2010-12-23 | 2011-01-03
A1780 | Slab Pouring | 1 | 2011-01-04 | 2011-01-04
5th floor |  | 29 | 2011-01-06 | 2011-02-08
A1790 | columns Formwork & Rft. Part1 | 8 | 2011-01-06 | 2011-01-15
A1810 | columns Formwork & Rft. Part 2 | 8 | 2011-01-15 | 2011-01-23
A1800 | Columns Pouring Part1 | 1 | 2011-01-16 | 2011-01-16
A1820 | Slab Formwork & Rft. Part1 | 10 | 2011-01-18 | 2011-01-29
A1840 | Columns Pouring Part2 | 1 | 2011-01-24 | 2011-01-24
A1860 | Slab Formwork & Rft. Part2 | 10 | 2011-01-27 | 2011-02-07
A1880 | Slab Pouring | 1 | 2011-02-08 | 2011-02-08
6th floor |  | 29 | 2011-02-10 | 2011-03-15
A1890 | columns Formwork & Rft. Part1 | 8 | 2011-02-10 | 2011-02-19
A1910 | columns Formwork & Rft. Part 2 | 8 | 2011-02-19 | 2011-02-27
A1900 | Columns Pouring Part1 | 1 | 2011-02-20 | 2011-02-20
A1920 | Slab Formwork & Rft. Part1 | 10 | 2011-02-22 | 2011-03-05
A1940 | Columns Pouring Part2 | 1 | 2011-02-28 | 2011-02-28
A1960 | Slab Formwork & Rft. Part2 | 10 | 2011-03-03 | 2011-03-14
A1980 | Slab Pouring | 1 | 2011-03-15 | 2011-03-15
Roof floor |  | 14 | 2011-03-19 | 2011-04-03
A2130 | columns Formwork & Rft. | 5 | 2011-03-19 | 2011-03-23
A2140 | Columns Pouring | 1 | 2011-03-24 | 2011-03-24
A2150 | Slab Formwork & Rft. | 7 | 2011-03-26 | 2011-04-02
A2160 | Slab Pouring | 1 | 2011-04-03 | 2011-04-03