## Sheet1
Key Dates No. (Mile stone) | Description of stage (Physical works to be completed) | Period from the date of issue of notice to proceed with the work (In days) | Source Page | Period from the date of issue of notice to proceed with the work | KD 6 | Partial access of section (for a minimum length of 4 km) to S&T and Electrical contractors for their respective works | 550
KD 1 | Completion of 1st working pile | 90 | 133
KD 2 | Start of casting of Box girder segments | 110 | 133
KD-3 | Casting of first pier after approval of mark up | 120 | 133
KD 4 | Start of Erection of box girder/ U girder | 190 | 133
KD 5 | Partial access of Viaduct (for a minimum length of 3 km) to track contractor for laying track | 400 | 133
KD 6 | Partial access of viaduct (for a minimum length of 3 km) to S&T and Electrical contractors for their respective works | 450 | 133
KD 7 | Access of viaduct in entire length to track contractor for laying track. | 630 | 133
KD 8 | Access of viaduct in entire length to S&T and Electrical contractors for their respective works. | 730 | 133
KD 9 (Taking over date) | Completion of Entire Work as per the contract | 825 Days (27 months) | 133
KD 1 | Start of earthwork in embankment /cutting |  | 133 | 60
KD 2 | Completion of 2 km of embankment /cutting |  | 133 | 130
KD-3 | Start of one minor bridge |  | 133 | 80
KD 4 | Completion of 15 minor bridges |  | 133 | 270
KD 5 | Partial access of section (for a minimum length of 4 km) to track contractor for laying track |  | 133 | 470
|  |  | 134 |  | KD 7 | Access of section in entire length to track contractor for laying track. | 630
|  |  | 134 |  | KD 8 | Access of section in entire length to S&T and Electrical contractors for their respective works. | 710
|  |  | 134 |  | KD 9 (Taking over | Completion of Entire Work as per the contract | 825 Days (27 Months)