## Sheet1
Category | Information to Extract | Planning Impact / Why It's Critical
I. Time & Completion (The Baseline)
Commencement Date | Exact definition: Is it NTP, Site Handover, or Contract Signing? | Sets Project Start Date.
Project Duration | Defined in Calendar Days or Working Days? | Defines Project Calendar Setup.
Key Milestones / Sectional Completion | Exact deadlines (KD 1, KD 2, "Envelope Complete," "Podium Handover"). | Hard Constraints & Interim Critical Paths.
Liquidated Damages (LDs) | LD Rate (e.g., $X per day) and the Milestone to which it applies. | Determines Schedule Priority & Risk.
Definition of "Substantial Completion" | Criteria for project handover (e.g., 95% complete, all systems certified). | Determines when LDs stop.
Defect Liability Period (DLP) | Duration (e.g., 1 Year) after completion. | Post-Completion Resource Allocation.
II. Schedule Specification & Deliverables (The Setup)
Required Software | Primavera P6 (version?), MS Project, or other. | Software setup & File compatibility.
Level of Detail | Required schedule level (Level 3/4) and minimum activity duration (e.g., 5 days). | Determines WBS/Activity count.
WBS / Activity Coding Mandate | Does the client require a specific coding structure for reporting? | P6 Administration Setup.
Resource & Cost Loading Requirement | Must the schedule be resource-loaded? If so, what is the required cost granularity? | Required effort for Baseline Submission.
Float Ownership | Does the contract state who owns the float (Client, Contractor, or Project)? | Crucial for EOT claims defense.
Submission & Review Cycle | Time allowed for Client/Engineer to review and approve the schedule (e.g., 14 days). | Must be built into the Mobilization schedule.
III. Logistics & Site Constraints (The Execution)
Site Access / Phased Handover | Specific drawings/chainage/dates for progressive Right of Way or site area release. | Defines Start/Finish Constraints on activities.
Site Working Hours / Days | Restrictions on work on weekends, public holidays, or beyond a specific hour (e.g., urban noise ordinance). | Defines Resource Calendars.
Utility Clearance Schedule (Client Scope) | Baseline schedule for client-provided utility diversions (essential for foundation work). | External critical path dependencies.
Hoisting & Vertical Access Plan | Requirements for crane/hoist installation, operation zones, and mandated removal dates. | Dictates floor-level sequencing and tower crane timeline.
Safety / Quality (Curing Time) | Contractual cure times for concrete or specialty materials. | Activity Lags and Durations.
IV. Risk, Claims, & Commercial (The Defense)
Time Bar (Notice Period) | The most CRITICAL item: How many days to notify of a delay event (e.g., 7 days, 28 days)? | Failure means loss of EOT rights.
EOT Qualification | Clear definition of Excusable (Time) vs. Compensable (Time + Money) delays. | Basis for all claim submissions.
RFI / Change Order Response Time | Contractual time limit for the Engineer to respond to Contractor queries. | Dictates allowance for documentation/design time.
Weather Days Baseline | The assumed historical weather data or specific criteria (e.g., "Non-working day if rainfall > 15mm"). | Defense against weather-related EOT claims.
Payment Milestone Definition | The exact, measurable criteria that trigger a payment release (e.g., completion of 5th floor slab, 100% pile caps). | Links Schedule Progress to Cash Flow.